## Sheet1
| PROJECT DETAILS | [5 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS |  |  |  | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
DEPARTMENT | S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June XXX (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
HEALTH | 1 | Contruction of Nyanadrua kmtc | Construction of classes and ablution block | To establish a kmtc at nyandarua county | 6 classes established | 3110202 | Olkalou | Rurii | 0.24'S,36.22E | Human Resource | 2014-07-01 | 2015-07-01 | 2016-07-04 | 30 million | 27.87 million | 0 | County Government of Nyandarua |  | 100% | 0% | 0 |  | 0 | 0 | 0 | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 2 | Contruction of Casualty at JM Kariuki Hospital | Construction of a unit to attend to emergencies | To create space for handling emergencies | The unit was contructed | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2016-05-01 | 2018-05-01 | 2018-05-01 | 35million | 27 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 3 | Construction of County health offices | Construction of office block | To create space for offices | Offices established | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2015-05-01 | 2016-02-01 | 2016-02-01 | 10 million | 9 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 4 | Construction of laboratory at Olkalou hospital | Construction of a laboratory unit | To create an adeqaute working space | Unit established | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2015-05-01 | 2016-04-01 | 2016-12-05 | 35 million | 10.4 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 5 | Construction of Mukindu maternity | Construction of a maternity unit | To create an adeqaute working space | Unit established | 3110202 | Olkalou | Rurii | 0.20'S,36.42E | Human Resource | 2015-05-01 | 2016-05-01 |  | 20 million | 21 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 6 | JM Kariuki hospital Maternity theatre | Construction of a theatre unit | To create an adequate working space | Unit established | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2015-05-01 | 2016-05-01 |  | 35 million | 21 milliion | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 7 | JM Kariuki hospital Gate, walling , sentry box and improvement of road works and boundaries | Construction and improvement of Jm hospital hospital entrance | To improve security and image of the hospital | Improvements done | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2015-03-01 | 2015-05-01 |  | 7 million | 4 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 8 | Construction and completion of JM Kariuki eco toilet | Construction of an ablution block | To improve on sanitation standards of the hospital | Unit established | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2016-03-01 | 2017-05-01 |  | 4 million | 4 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 9 | JM Kariuki flood mast | Intallation of a flood light | To improve security | flood light installed | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2016-03-01 | 2016-05-01 |  | 1 million | 1 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 10 | JM Kariuki Block B Renovations | Renovations of an existing unit and change of asbestos | To create an adequate working space | Unit established | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2016-03-01 | 2017-03-01 |  | 9 million | 6.5 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 11 | Construction of Engineer hospital mortuary | Establishment of a mortuary unit at engineer | To create an adequate working space | Unit established | 3110202 | Kinangop | Gathaara | 0.611S,36.59E | Human Resource | 2014-05-01 | 2015-05-01 |  | 35 million | 20 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 12 | Construction of engineer hospital laboratory | Construction of a laboratory unit | To create an adequate working space | Unit established | 3110202 | Kinangop | Gathaara | 0.611S,36.59E | Human Resource | 2014-05-01 | 2015-05-01 |  | 35 million | 17.6 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 13 | Construction of engineer hospital X ray department | Construction of an X ray unit | To create an adequate working space | Unit established | 3110202 | Kinangop | Gathaara | 0.611S,36.59E | Human Resource | 2014-05-01 | 2015-05-01 |  | 8 million | 10 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 14 | Construction of Engineer hospital maternity | Construction of a maternity unit | To create an adequate working space | Unit established | 3110202 | Kinangop | Gathaara | 0.611S,36.59E | Human Resource | 2014-05-01 | 2016-05-01 |  | 70 million | 47 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 15 | Renovations and completion of kihuho dispensary | Renovations of an existing unit and change structures | To bring services closer to the people | A dispensary established | 3110202 | Olkalou | Mirangine | 0.177S,36.23E | Human Resource | 2016-05-01 | 2018-05-01 |  | 8 million | 3 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 16 | Renovations and completion of kamuchege dispensary | Renovations of an existing unit and change structures | To bring services closer to the people | A dispensary established | 3110202 | Olkalou | Mirangine | 0.177S,36.23E | Human Resource | 2016-05-01 | 2018-05-01 |  | 8 million | 3 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 17 | Construction of vip pit latrine at mirangine | Construction of a toilet unit | To improve sanitation facilities of the facility | Unit established | 3110202 | Olkalou | Mirangine | 0.177S,36.24E | Human Resource | 2016-05-01 | 2016-07-01 |  | 1 million | 0.4 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 18 | Construction and completion of shalom dispensary(kanyiriri Disp | Construction of a new dispensary | To bring services closer to the people | A dispensary established | 3110202 | Olkalou | Karau | 0.358S,36.32E | Human Resource | 2016-05-01 | 2017-05-01 |  | 12 million | 11 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 19 | Construction and completion of a kanyiriri public toilet | Construction of a toilet unit | To improve sanitation facilities of the facility | Unit established | 3110202 | Olkalou | Karau | 0.358S,36.32E | Human Resource | 2016-05-01 | 2016-07-01 |  | 1 million | 0.5 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 20 | Construction and completion of kanjuiri maternity | Construction of a maternity unit | To bring services closer to the people | Unit established | 3110202 | Olkalou | Kanjuiri Ridge | 0.362S,36.28E | Human Resource | 2014-05-01 | 2015-05-01 |  | 20 million | 9.46 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 21 | Construction of kanjuiri public toilet | Construction of a toilet unit | To improve sanitation facilities of the township | Unit established | 3110202 | Olkalou | Kanjuiri Ridge | 0.362S,36.28E | Human Resource | 2015-05-01 | 2015-07-01 |  | 1 million | 0.5 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 22 | Construction of Vip Public Toilet Nyamanu | Construction of a toilet unit | To improve sanitation facilities of the township | Unit established | 3110202 | Kinangop | Nyakio | 0.456S,36.57E | Human Resource | 2016-05-01 | 2017-05-01 |  | 1 million | 0.4 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 23 | Renovations and completion of pesi maternity | Renovations and completion of an existing cdf unit | To bring services closer to the people | Unit established | 3110202 | Ndaragwa | Shamata | 0.122S,36.53E | Human Resource | 2017-05-01 | 2018-05-01 |  | 5 million | 3.5million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 24 | Conversion of ngano disability friendly toilet | Construction of a toilet unit | To improve sanitation facilities of the facility | Unit established | 3110202 | Oljororok | Charagita | 0.109S,36.27E | Human Resource | 2016-05-01 | 2017-07-01 |  | 400000 | 0.4million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 25 | Construction and completion of Ruiru dispensary(Charagita) | Construction of a new dispensary | To bring services closer to the people | A dispensary established | 3110202 | Oljororok | Charagita | 0.146S,36.26E | Human Resource | 2015-05-01 | 2016-05-01 |  | 12 million | 4 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 26 | Construction and completion of Kiambogo maternity | Extension construction and completion of the existing unit | To create an adequate working space | Unit established | 3110202 | Kipipiri | kipipiri | 0.335S,36.51E | Human Resource | 2015-05-01 | 2016-05-01 |  | 8 million | 9.6 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 27 | Construction and completion of Kiambogo public toilet | Construction of a toilet unit | To improve sanitation facilities of the township | Unit established | 3110202 | Kipipiri | kipipiri | 0.335S,36.51E | Human Resource | 2015-05-01 | 2015-07-01 |  | 500000 | 0.4 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 28 | Construction of Mumui dispensary | Construction of a new dispensary | To bring services closer to the people | A dispensary established | 3110202 | Kipipiri | Githioro | 0.520S,36.49E | Human Resource | 2015-05-01 | 2016-05-01 | 2016-02-06 | 12 million | 9.5 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 29 | Construction of Gathiriga dispensary | Construction of a new dispensary | To bring services closer to the people | A dispensary was established | 3110202 | Kipipiri | Githioro | 0.479S,36.47E | Human Resource | 3rd April 2017 | 2rd April 2018 | 23rd july 2021 | 17 million | 16407512 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 30 | Construction of Munoru dispensary | Construction of a new dispensary | To bring services closer to the people | A dispensary was established | 3110202 | Kipipiri | Githioro | 0.521S, 36.422E | Human Resource | 3rd May 2016 | 2rd May 2017 |  | 17 million | 11615126.4 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 31 | Construction of a vip pit latrine and refuse burning chamber at mikeu dispensary | Construction of a toilet unit | To improve sanitation facilities of the facility | Unit established | 3110202 | Kipipiri | Geta | 0.381S,36.56E | Human Resource | 2016-05-01 | 2017-05-01 |  | 3 million | 3 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 32 | Construction of a VIP pit latrine at Magumu trading centre | Construction of a toilet unit | To improve sanitation facilities of the township | Unit established | 3110202 | Kinangop | Magumu | 0.863S,36.566E | Human Resource | 2016-05-01 | 2016-06-01 |  | 500000 | 0.4 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 33 | Construction of a VIP public toilet at Karangatha | Construction of a toilet unit | To improve sanitation facilities of the township | Unit established | 3110202 | Kinangop | Nyakio | 0.802S,36.63E | Human Resource | 2016-05-01 | 2016-05-01 |  | 500000 | 0.4 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 34 | Completion of Koinange dispensary and three door VIP latrine | Renovations and completion of an existing cdf unit | To create an adequate working space | a dispensary was established | 3110202 | Kinangop | Githabai | 0.749S,36.58E | Human Resource | 2016-05-01 | 2018-05-01 |  | 7 million | 3million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 35 | Completion of New Tumaini maternity | Construction of a maternity unit | To create an adequate working space | A maternity unit was established | 3110202 | Olkalou | Kanjuiri Ridge | 0.253S,36.29E | Human Resource | 2017-05-01 | 2018-05-01 |  | 30 million | 30million | 0 | County Government of Nyandarua/Government of Finland | finland agency | 0% | 100% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 36 | Renovatios Fencing and water reticulation of Rurii dispensary | Renovations and completion of an existing cdf unit | To create an adequate working space | A dispensary was established | 3110202 | Olkalou | Rurii | 0.243S,36.35E | Human Resource | 2015-05-01 | 2016-05-01 |  | 3 million | 2 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 37 | Completion of Kahuru dispensary and water connection | Renovations and completion of an existing cdf unit | To create an adequate working space | A dispensary was established | 3110202 | Kinangop | Engineer | 0.611S,36.59E | Human Resource | 2015-05-01 | 2016-03-01 |  | 3 million | 1.5 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 38 | Kahuho dispensary(mikaro) – maternity tiling | Renovations and completion of an existing cdf unit | To create an adequate working space | A maternity unit was established | 3110202 | Kinangop | North Kinangop | 0.506S,36.57E | Human Resource | 2014-05-01 | 2014-06-01 |  | 700000 | 0.6 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 39 | Water reticulation and sinking of borehole at Engineer hospital | installation of a water tower and sinking of a borehole, piping and water connection | To provide adeqaute water for facility use | The unit was established | 3110202 | Kinangop | Gathaara | 0.611S,36.59E | Human Resource | 2017-05-01 | 2017-06-01 | 2017-06-01 | 5 million | 5 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 40 | Fencing of Kahuru dumpsites | fencing of a purchased land | To secure the land | The fence was constructed | 3110202 | Kinangop | Engineer | 0.611S,36.59E | Human Resource | 2016-05-01 | 2017-05-01 |  | 3 million | 2599920 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 41 | Fencing of Tulaga dumpsite | fencing of a purchased land | To secure the land | The fence was constructed | 3110202 | Kinangop | Njabini/kiburu | 0.576S,36.59E | Human Resource | 2016-05-01 | 2017-05-01 |  | 3 million | 3405354 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 42 | Fencing of Mbuyu dumpsite | fencing of a purchased land | To secure the land | The fence was constructed | 3110202 | Ndaragwa | Ndaragwa central | 0.011N,36.48E | Human Resource | 2016-05-01 | 2017-05-01 |  | 2.5 million | 2499539 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 43 | Purchase of a back- up generator at Geta bush health centre | Purchase and installation of a backup generator | To provide power back up | The unit was installed | 3110202 | Kipipiri | Geta | 0.413S,36.58E | Human Resource | 2016-05-01 | 2016-06-01 |  | 1 million | 1 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 44 | Completion of a staff house at munyaka dispensary | Renovations and completion of an existing cdf unit | To provide accomodation for staff on night duty | The house was renovated | 3110202 | Kinangop | Gathaara | 0.687S,36.62E | Human Resource | 2016-05-01 | 2017-05-01 |  | 700000 | 700000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 45 | Construction and completion of Kiambogo ash pit, burning chamber and placenta pit | Construction of an ashpit burning chamber and placenta pit at kiambogo. | To improve sanitation standards of the facility | The units were constructed | 3110202 | Kipipiri | kipipiri | 0.335S,36.51E | Human Resource | 2015-05-01 | 2016-06-01 |  | 1 million | 1.1million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 46 | Renovation of Rwanyambo dispensary and water reticulation | Renovations of an existing cdf unit | To bring services closer to the people | A dispensary was established | 3110202 | Kinangop | Nyakio | 0.809S,36.62E | Human Resource | 2015-05-01 | 2016-06-01 |  | 700000 | 700000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 47 | Renovations of chamuka maternity and laboratory | Renovations of an existing cdf unit | To bring services closer to the people | A maternity unit was established | 3110202 | Oljororok | Weru | 0.075S,36.36E | Human Resource | 2015-05-01 | 2016-06-01 |  | 1 million | 1 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 48 | Construction and completion of Subuku dispensary toilet | Construction of a pit latrine at the facility | To improve sanitation standards of the facility | The unit was established | 3110202 | Ndaragwa | Ndaragwa central | 0.115S,36.455E | Human Resource | 2015-05-01 | 2015-07-01 |  | 650000 | 650000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 49 | Electrical works at kiambogo dispensary | Electricals works done to the existing cdf unit | To improve work environment | Works done | 3110202 | Kipipiri | kipipiri | 0.335S,36.51E | Human Resource | 2016-05-01 | 2016-06-01 |  | 450000 | 450000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 50 | Renovations at murungaru health centre and water reticulation | Renovations of an existing cdf unit | To bring services closer to the people | A maternity unit was established | 3110202 | Kinangop | Murungaru | 0.584S,36.549E | Human Resource | 2016-05-01 | 2017-06-01 |  | 700000 | 700000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 51 | Renovations at kahembe dispensary | Renovations and completion of an existing old unit | To bring services closer to the people | A maternity unit was established | 3110202 | Ndaragwa | Kiriita | 0.02N,36.45E | Human Resource | 2016-05-01 | 2017-06-01 |  | 1500000 | 1500000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 52 | Installation of power control panel at engineer hospital | Installation of power control unit | To regulate power usage at the facility | The unit was installed | 3110202 | Kinangop | Gathaara | 0.611S,36.59E | Human Resource | 2016-05-01 | 2016-06-01 |  | 1400000 | 1400000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 53 | Construction of a public pit latrine at mumui dispensary | Construction of a toilet unit | To improve sanitation standards of the facility | The unit was contructed | 3110202 | Kipipiri | Githioro | 0.521S, 36.492E | Human Resource | 2016-05-01 | 2016-07-01 | 30th November 2016 | 1 million | 1 million | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 54 | Purchase of Wanjohi health centre generator | Purchase and installation of a backup generator | To provide power back up | The unit was installed | 3110202 | Kipipiri | Wanjohi | 0.335S,36.52E | Human Resource | 2016-05-01 | 2016-06-01 |  | 1450000 | 1450000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 55 | Purchase of Murungaru health centre generator | Purchase and installation of a backup generator | To provide power back up | The unit was installed | 3110202 | Kinangop | Murungaru | 0.584S,36.549E | Human Resource | 2016-05-01 | 2016-06-01 |  | 1450000 | 1450000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 56 | Renovations for the facility and Water harvesting and reticulation at kibururti dispensary | Renovations of an existing cdf unit | To bring services closer to the people | A dispensary was established | 3110202 | Kipipiri | Wanjohi | 0.303S,36.44E | Human Resource | 2016-05-01 | 2017-06-01 |  | 500000 | 500000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 57 | Fencing and landscaping of kiburuti dispensary | Construction of a fence to secure the facility | To secure the land | The fence was constructed | 3110202 | Kipipiri | Wanjohi | 0.303S,36.44E | Human Resource | 2016-05-01 | 2017-06-01 |  | 1500000 | 1500000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 58 | Purchase installation and commissioning of Jm Kariuki incinerator | Construction of the housing unit and installation of an incinerator | To improve the waste management at the facility | The unit was installed | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2017-05-01 | 2019 |  | 10000000 | 10000000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 59 | Renovations of block A at JM Kariuki hospital | Carrying out renovations and change of asbestos for the facility | To provide adeqaute working space and removal of asbestos | The Unit was refurbished | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2017-05-01 | 2018-05-01 |  | 8500000 | 8500000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 60 | Cabro Works at JM olkalao hospital and internal fencing | Improvement of the accessibility to the mourtuary area and fencing to secure the facility | To improve accessibility and security | facilities put in place | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2018-05-01 | 2018-06-01 |  | 4000000 | 4000000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 61 | Construction of 3 door vip pit latrine at weru | Construction of a toilet unit | To improve sanitation standards of the township | The unit was established | 3110202 | Kinangop | Engineer | 0.635S,36.54E | Human Resource | 2015-05-01 | 2015-07-01 | 3rd feb 2017 | 4000000 | 4000000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 62 | Construction of 3 door vip pit latrine at kangui | Construction of a toilet unit | To improve sanitation standards of the township | The unit was established | 3110202 | Oljororok | Charagita | 0.075s,36.35E | Human Resource | 2016-05-01 | 2016-07-01 |  | 950000 | 950000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 63 | Construction of 3 door vip pit latrine at Koinange shopping centre | Construction of a toilet unit | To improve sanitation standards of the township | The unit was established | 3110202 | Kinangop | Githabai | 0.749S,36.58E | Human Resource | 2016-05-01 | 2016-07-01 |  | 950000 | 950000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 64 | Construction of 3 door vip pit latrine at kariamu shopping centre | Construction of a toilet unit | To improve sanitation standards of the township | The unit was established | 3110202 | Olkalou | Rurii | 0.275S,36.36E | Human Resource | 2016-05-01 | 2016-07-01 |  | 950000 | 950000 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 65 | Construction of a funeral home at JM kariuki hospital | Construction of a unit at jm for body preservations | To improve on body preservations | The unit was established | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 16th june 2019 | 16th june 2020 | 5th october 2022 | 50million | 64076595 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 66 | Construction and establishment of a CT scan at Jm kariuki | Construction of a unit and installation of the equipment | To improve service accessibility | The unit was established | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2018-05-01 | 2019-05-01 |  | 40million | 55million | 0 | County Government of Nyandarua/National Government | Ministry of health | 10% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 67 | Renovate and improve Jm kitchen | Carrying out renovations and change of asbestos for the facility | to improve sanitation standards | The facility is ongoing | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | May of 2019 | 2020-06-01 |  | 7 million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | 90% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project Ongoing
HEALTH | 68 | Construction of Mashujaa complex | Construction a Five storey inpatient unit | To bring services closer to the people | The facility is ongoing | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2023-01-01 | 2026-07-01 | Ongoing | 1.6 billion |  | 120000000 | County Government of Nyandarua/Development Partner | Worldbank | 90% | 10% | [5 empty] | Ongoing | 40% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project Ongoing
HEALTH | 69 | Construction of Kanguu dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Oljororok | Weru | 0.047S,36.40E | Human Resource | 4th June 2018 | 3rd June 2019 | 24th june 2020 | 15million | 14679982 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 70 | Construction of Kangubiri dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Ndaragwa | Ndaragwa central | 0.299S, 36.38E | Human Resource | 5th june 2020 | 18th dec 2021 | Ongoing | 15million | 12965697 | 2000000 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project Ongoing
HEALTH | 71 | Construction of Kihuha dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Ndaragwa | Shamata | 0.134S,36.50E | Human Resource | 2017-05-01 | 2019-06-01 |  | 15million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 72 | Construction of Kieni dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Olkalou | Kaimbaga | 0.308S,36.37E | Human Resource | 21st July 2019 | 30th june 2020 | 29th june 2021 | 15million | 16040364 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 73 | Construction of Muhakaini dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Ndaragwa | Shamata | 0.137S, 36.46E | Human Resource | 2017-05-01 | 2018-06-01 |  | 17million |  | 1001090 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project Ongoing
HEALTH | 74 | Construction of Matindiri dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Oljororok | Charagita | 0.177S,36.28E | Human Resource | 2017-05-01 | 2018-06-01 |  | 17million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 75 | Construction of Olaimutia dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Oljororok | Charagita | 0.110S,36.32E | Human Resource | 2018-05-01 | 2019-06-01 |  | 6million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 76 | Construction of Kiganjo dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Olkalou | Kaimbaga | 0.275S,36.35E | Human Resource | 25th september 2021 | 23rd april 2022 | Ongoing | 17million | 12837174.8 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | 70% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project Ongoing
HEALTH | 77 | Construction of Bamboo dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Kinangop | Magumu | 0.862S,36.56E | Human Resource | 2017-05-01 | 2018-05-01 | 7th November 2021 | 17million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 78 | Construction of Bamboo theatre | Construction of a Theatre block and it facilities | To bring services closer to the people | A unit was established | 3110202 | Kinangop | Magumu | 0.862S,36.56E | Human Resource | 7th june 2019 | 31st may 2020 |  | 35million | 25115942 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project Ongoing
HEALTH | 79 | Construction of Bamboo X ray | Construction of a x ray block and it facilities | To bring services closer to the people | A unit was established | 3110202 | Kinangop | Magumu | 0.862S,36.56E | Human Resource | 6th May 2024 | 6th May 2025 | Ongoing | 12million | 11496772 | 5000000 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | 10% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project ongoing
HEALTH | 80 | Construction of Manunga theatre | Construction of a Theatre block and it facilities | To bring services closer to the people | A unit was established | 3110202 | Kipipiri | kipipiri | 0.399S,36.49E | Human Resource | 2018-05-01 | 2019-05-01 |  | 35million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 81 | Construction of Manunga laboratory and pharmacy | Construction of a a pharmacy and laboratory block and it facilities | To bring services closer to the people | The works are ongoing | 3110202 | Kipipiri | kipipiri | 0.399S,36.49E | Human Resource | 6th May 2024 | 6th May 2025 | Ongoing | 10million | 8047615 | 5000000 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | 5% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project Ongoing
HEALTH | 82 | Construction of Ndaragwa health centre X ray | Construction an x ray unit | To bring services closer to the people | The works are ongoing | 3110202 | Ndaragwa | Ndaragwa central | 0.057S,36.53E | Human Resource | 3rd May 2024 | 2nd May 2025 | Ongoing | 12million | 11676183 | 3000000 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | 5% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project Ongoing
HEALTH | 83 | Construction of Kagaa dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Olkalou | Karau | 0.375S,36.32E | Human Resource | 2024-05-01 | 2024-12-01 | 2024-06-01 | 500000 | 499432 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 84 | Construction of Munyeki dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Olkalou | Karau | 0.355S,36.33E | Human Resource | 4th June 2024 | 4th june 2025 |  | 27million | 26500000 |  | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | 70% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project ongoing
HEALTH | 85 | Construction of Passenga dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Oljororok | Charagita | 0.206S, 36.32E | Human Resource | 2024-05-01 | 2024-12-01 |  | 15million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 86 | Construction of a maternity unit at Ndaragwa health centre | Construction of a maternity inpatient unit | To provide adeqauete working space | A unit was established | 3110202 | Ndaragwa | Ndaragwa central | 0.057S,36.53E | Human Resource | 2023-03-01 | 2024-10-01 | 2024-11-01 | 30million |  | 0 | County Government of Nyandarua/Government of Finland | finland agency | 0% | 100% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 87 | Constrcution of an inpatient complex at Engineer county Hospital | Construction an three storey inpatient complex | To bring services closer to the people | A unit was established | 3110202 | Kinangop | Gathaara | 0.611S,36.59E | Human Resource | 3rd march 2022 | 20th may 2023 | 20th may 2023 | 350million | 350million | 0 | National Government/County Government of Nyandarua | Ministry of health/Ministry of Defence | 0% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 88 | Establishment of fabricated dispensary at makara dispesary | Fabricatation and installation of a container | To bring services closer to the people | A dispensary was established | 3110202 | Olkalou | Mirangine | 0.156S,36.23E | Human Resource | 2020-05-01 | 2020-06-01 |  | 10million |  | 0 | National Government/County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 89 | Establishment of fabricated dispensary at kalampton dispesary | Fabricatation and installation of a container | To bring services closer to the people | A dispensary was established | 3110202 | Ndaragwa | Leshau pondo | 0.097N,36.17E | Human Resource | 2020-05-01 | 2020-06-01 |  | 10million |  | 0 | National Government/County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 90 | Purchase of ambulances for refferal | Purchase of 10 ambulaces | To assist in refferals | vehicles purchased | 3110707 | all | several | various stations | Human Resource | various | various | various | 100million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 91 | Renovations and completion of Kimathi dispensary | Renovations and completion of existing cdf facility | To bring services closer to the people | A dispensary was established | 3110202 | Kipipiri | kipipiri | 0.371S,36.45E | Human Resource | 2016-05-01 | 2018-05-01 |  | 7million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 92 | Renovations and completion of Kamiruri dispensary | Renovations and completion of existing cdf facility | To bring services closer to the people | A dispensary was established | 3110202 | Ndaragwa | Ndaragwa central | 0.161S,36.65E | Human Resource | 2016-05-01 | 2016-07-01 |  | 3million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 93 | Renovations and completion of Geta forest dispensary | Renovations and completion of existing cdf facility | To bring services closer to the people | A dispensary was established | 3110202 | Kipipiri | Geta | 0.423S,36.55E | Human Resource | 2015-05-01 | 2016-06-01 |  | 7million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 94 | Renovations and completion of Olmagogo dispensary | Renovations and completion of existing cdf facility | To bring services closer to the people | A dispensary was established | 3110202 | Kinangop | Murungaru | 0.52S, 36.44E | Human Resource | 2021-05-01 | 2022-05-01 |  | 7million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 95 | Construction of a maternity unit at chamuka health centre | Construction of a new maternity at the facility | To bring services closer to the people | The works are ongoing | 3110202 | Oljororok | Weru | 0.075S,36.36E | Human Resource | 29th May 2024 | 28th May 2025 | Ongoing | 35million | 28342801 | 10000000 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | 50% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project ongoing
HEALTH | 96 | Construction of a laundry unit at JM kariuki hsopital | Construction of a laundry unit at JM olkalou Hosp | To create adequate space for laundry | The works are ongoing | 3110202 | Olkalou | Rurii | 0.24'S,36.37E | Human Resource | 2021-05-01 | 2022-05-01 |  | 35million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | 70% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project ongoing
HEALTH | 97 | Construction of Matura dispensary | Construction of a dispensary block and it facilities | To bring services closer to the people | The dispensary has been operationalized | 3110202 | Olkalou | Rurii | 0.249S,36.37E | Human Resource | 2017-05-01 | 2018-05-01 |  | 17million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 98 | Construction of mirangine CDC unit | Construction of a unit for tests and research | To have a facility where research and investigations can be done | The unit is complete | 3110202 | Olkalou | Mirangine | 0.177S,36.24E | Human Resource | 2022-05-01 | 2024-06-01 |  | 120million | 135967873 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 99 | Renovations and completion of Nyairoko dispensary | Renovations and completion of a cdf facility | To bring services closer to the people | The dispensary has been operationalized | 3110202 | Oljororok | Charagita | 0.258S,36.17E | Human Resource | 2016-05-01 | 2017-05-01 |  | 5million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 100 | Renovations of Kaimbaga dispensary | Renovations and completion of a cdf facility | To improve accessibility and security | The dispensary has been operationalized | 3110202 | Olkalou | Kaimbaga | 0.386S,36.38E | Human Resource | 2017-05-01 | 2017-07-01 |  | 2million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 101 | Renovations and completion of kaimbaga health centre maternity | Renovations and completion of a cdf facility | To bring services closer to the people | The maternity is ongoing | 3110202 | Olkalou | Kaimbaga | 0.386S,36.38E | Human Resource | 23rd May 2022 | 23rd August 2022 | Ongoing | 8million | 6535741 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Ongoing | 90% | [5 empty] | Yes |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project Ongoing
HEALTH | 102 | Renovations and completion of captain dispensary | Renovations and completion of a cdf facility | To bring services closer to the people | The dispensary has been operationalized | 3110202 | Olkalou | Kaimbaga | 0.25'S, 36.39E | Human Resource | 14th June 2021 | 2022-06-13 |  | 5million | 2499962 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [6 empty] | NO |  | None | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project in use
HEALTH | 103 | Construction of a male ward at engineer Hospital | Construction of a male complex to establish the unit | To bring services closer to the people | The project stalled | 3110202 | Kinangop | Gathaara | 0.611S,36.59E | Human Resource | 2021-07-01 | 2023-07-01 | Stalled | 115million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Stalled | 5% | 5% | inadeqaute funds allocation | 2022 | 12months | 110million | No | Complete | Wastage of funds and can attract legal redress | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project stalled
HEALTH | 104 | Construction of Moset dispesary | Construction of a dispensary block and it facilities | To bring services closer to the people | A dispensary was established | 3110202 | Kinangop | North Kinangop | 0.523S, 36.64E | Human Resource | 25th september 2021 | 23rd april 2022 | Stalled | 17million | 12837175 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Stalled | 5% | 5% | funds not allocated for completion | 2023 | 5 months | 15 million | No | Complete | Wastage of funds and can attract legal redress | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project stalled
HEALTH | 105 | Construction of shamata twin ward | Construction of an Inpatient unit | To bring services closer to the people | Unit established | 3110202 | Ndaragwa | Shamata | 0.196S,36.50E | Human Resource | 14th April 2017 | 6th october 2017 | Stalled | 15 million | 8030525 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Stalled | 60% | 60% | inadeqaute funds allocation | 2022 | 4 months | 5 million | No | Complete | Wastage of funds and can attract legal redress | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Project stalled
HEALTH | 106 | Renovations and completion of Gichungo dispensary | Renovations of existing cdf block | To bring services closer to the people | Facilities put in place | 3110202 | Olkalou | Rurii | 0.275S,36.36E | Human Resource | 2016-05-01 | 2017-05-01 |  | 5 million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 107 | Construction of Ndaragwa health centre store | Construction of a commodity Store | To provide adeqaute storage facility | facilities put in place | 3110202 | Ndaragwa | Ndaragwa central | 0.057S,36.53E | Human Resource | 4th June 2018 | 3rd June 2019 | 29th May 2020 | 9million | 8765875 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 108 | Construction of Ndaragwa health Centre Theatre | Constrcution of a theatre unit | To bring services closer to the people | Unit established | 3110202 | Ndaragwa | Ndaragwa central | 0.057S,36.53E | Human Resource | 2015-05-01 | 2016-05-01 |  | 30million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 109 | renovations and completion of Githabai dipensary | Renovations of existing cdf block | To bring services closer to the people | Unit established | 3110202 | Kinangop | Githabai | 0.764S, 36.57E | Human Resource | 2015-05-01 | 2016-05-01 |  | 4 million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 110 | Renovations and completion of Huhoini Dispensary | Renovations of existing cdf block | To bring services closer to the people | Unit established | 3110202 | Oljororok | Gathanji | 0.001S,36.244E | Human Resource | 2017-05-01 | 2019-05-01 | Ongoing | 7 million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 111 | Renovations and completion of Geta forest dispensary toilet | Construction of a three door pit latrine | To improve sanitation standards | Facilities put in place | 3110202 | Kipipiri | Geta | 0.423S,36.55E | Human Resource | 2016-05-01 | 2017-05-01 |  | 7million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 112 | Renovations and Completion of Njabini health centre | Renovations of existing cdf block and the main facility | To bring services closer to the people | Facilities put in place | 3110202 | Kinangop | Njabini/kiburu | 0.725S,36.66E | Human Resource | 2016-05-01 | 2017-05-01 |  | 7 million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 113 | Renovations and completion of Heni health centre | Renovations of existing cdf block | To bring services closer to the people | Facilities put in place | 3110202 | Kinangop | Githabai | 0.783S,36.55E | Human Resource | 2018-05-01 | 2019-05-01 |  | 4 million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 114 | Renovations and completion of JM store | Improvement of the existing store and removal of asbestos | To create space for commodity store | unit established | 3110202 | Olkalou | Rurii | 0.246S, 36.37E | Human Resource | 2016-05-01 | 2017-05-01 |  | 7million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 115 | Renovations and completion of haraka dispensary | Renovations of existing cdf block and the main facility | To bring services closer to the people | Facilities put in place | 3110202 | Kinangop | Nyakio | 0.800S,36.62E | Human Resource | 14th June 2018 | 13th June 2020 | 18th Dec 2020 | 7million | 4494199 | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 116 | Renovations and completion of Munyaka dispensary | Renovations of existing cdf block and the main facility | To improve facility structures | Facilities put in place | 3110202 | Kinangop | Gathaara | 0.687S,36.62E | Human Resource | 2018-05-01 | 2019-05-01 |  | 5 million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 117 | Purchase of lands for use as Dumping sites | Purchase of private land to convert them into Public use | to Improve sanitation standards of towns | Facilities put in place | 3130101 | KInangop and ndaragwa | Gathara , Njabini and Leshau pondo | various stations | Human Resource | 2014-05-01 | 2015-05-01 |  | 11.5million |  |  | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 118 | Construction of eco Toilets | Construction of eco toilets in the major towns | facilitate sanitation standards of the townships | Facilities put in place | 3110202 | Kinangop kipipri ndaragwa and olkalou | Njabini/kiburu,kipipiri,Kaimbaga and ndaragwa central | various stations | Human Resource | 2014-05-01 | 2017-04-01 |  | 17.5million |  | 0 | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 119 | Purchase of Utility vehicles | Purchase of the landcruisers and double cabin pickups | TO facilitate movements | vehicles purchased | 3110701 | Olkalou | Rurii | 0.246S, 36.37E | Human Resource | various | various | various | 30 million |  |  | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Vehicles in use
HEALTH | 120 | Purchase of medical Equipment | Purchase of various medical equipment | To facilitate service delivery in various facilities | Various equipment purchased | 3111101 | Olkalou | Rurii | various stations | Human Resource | various | various | various | 250million |  |  | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Vehicles in use
HEALTH | 121 | Construction of a maternity unit at mikeu dispensary | constrcution of a maternity unit | To bring services closer to the people | facility constructed | 3110202 | Kipipiri | Wanjohi | 0.381S,36.56E | Human Resource | 2018-05-01 | 2019-05-01 |  | 30 million |  |  | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
HEALTH | 122 | Renovations at Ngano health centre and constrcution of a public toilet | renovations of an old block and construction of a vip latrine | To create space for outpatient department and isolation | the unit established | 3110201 | Oljororok | Charagita | 0.109S,36.27E | Human Resource | 2020-11-01 | 2021-02-01 |  | 3.5 million |  |  | County Government of Nyandarua |  | 100% | 0% | [5 empty] | Completed | [9 empty] | No | N/A | YES | Standards and Norms applied | YES | Found Useful and needed | Facility in use
WATER | 123 | Rurii Polytechnic borehole | Drilling of borehole | Enhanced water supply | 50 HH benefitting |  | Olkalou | Rurii |  |  | 2013-07-01 | 2014-06-30 |  | 975000 | 975000 | yes | CGN |  | 975000 |  | 975000 | 100% | 975000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 124 | Manunga dam | Repair of the dam | Ehnance water supply for both domestic and livestock use | 1000 livestock |  | Kipipiri | Kipipiri |  |  | 2013-07-01 | 2014-06-30 |  | 400000 | 400000 | yes | CGN |  | 400000 |  | 400000 | 100% | 400000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 125 | Kariko/Oljoroorok/Kangui | water distribution | Enhanced water supply | 1200 HH |  | Oljoroorok | Weru |  |  | 2013-07-01 | 2014-06-30 |  | 550000 | 550000 | YES | CGN |  | 550000 |  | 550000 | 100% | 550000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 126 | Kamwana water project | Water distribution | Enhanced water supply | 200HH |  | Oljoroorok | Gatimu |  |  | 2013-07-01 | 2014-06-30 |  | 600000 | 600000 | YES | CGN |  | 600000 |  | 600000 | 100% | 600000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 127 | Gwa Kiongo water project | water distribution | Enhanced water supply | 1200HH |  | Olkalou | Mirangine |  |  | 2013-07-01 | 2014-06-30 |  | 550000 | 550000 | YES | CGN |  | 550000 |  | 550000 | 100% | 550000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 128 | Gitirima water project | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2013-07-01 | 2014-06-30 |  | 450000 | 450000 |  | CGN |  | 450000 |  | 450000 | 100% | 450000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 129 | Raitha Kahuru water project | water distribution | Enhanced water supply | 60HH |  | Kinangop | Gathaara |  |  | 2013-07-01 | 2014-06-30 |  | 550000 | 550000 | YES | CGN |  | 550000 |  | 550000 | 100% | 550000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 130 | Kaimbaga water project | water distribution | Enhanced water supply |  |  | Olkalou | Kaimbaga |  |  | 2013-07-01 | 2014-06-30 |  | 600000 | 600000 | YES | CGN |  | 600000 |  | 600000 | 100% | 600000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 131 | Kagaa/Munyeki/Mawingo water project | water distribution | Enhanced water supply | 100HH |  | Olkalou | Karau |  |  | 2013-07-01 | 2014-06-30 |  | 555000 | 555000 | YES | CGN |  | 555000 |  | 555000 | 100% | 555000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 132 | Kirima water project | water distribution | Enhanced water supply | 2000HH |  | Olkalou | Karau, Kaimbaga and Rurii |  |  | 2013-07-01 | 2014-06-30 |  | 1900000 | 1900000 | YES | CGN |  | 1900000 |  | 1900000 | 100% | 1900000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 133 | Ngano water project | water distribution | Enhanced water supply | 100HH |  | Oljoroorok | Charangita |  |  | 2013-07-01 | 2014-06-30 |  | 555000 | 555000 | YES | CGN |  | 555000 |  | 555000 | 100% | 555000 |  | 0 | Complete | [13 empty] | YES | cost benefit analysis for long term economic value
WATER | 134 | Gitei/Karima water project | water distribution | Enhanced water supply | 112HH |  | Kipipiri | Wanjohi |  |  | 2013-07-01 | 2014-06-30 |  | 301000 | 301000 | YES | CGN |  |  |  | 301000 | 100% |  |  | 0 | Complete
WATER | 135 | Mihato water project | water distribution | Enhanced water supply | [6 empty] | 2013-07-01 | 2014-06-30 |  | 303000 | 303000 | YES | CGN |  |  |  | 303000 | 100% |  |  | 0 | Complete
WATER | 136 | Ngorika water project | water distribution | Enhanced water supply | 147HH |  | Olkalou | Kanjuiri |  |  | 2013-07-01 | 2014-06-30 |  | 561000 | 561000 | YES | CGN |  |  |  | 561000 | 100% |  |  | 0 | Complete
WATER | 137 | Leshau water project | water distribution | Enhanced water supply | 175HH |  | Ndaragwa |  |  |  | 2013-07-01 | 2014-06-30 |  | 559000 | 559000 | YES | CGN |  |  |  | 559000 | 100% |  |  | 0 | Complete
WATER | 138 | Shamata/Warukira/Simbara water project | water distribution | Enhanced water supply | 122HH |  | Ndaragwa | Shamata |  |  | 2013-07-01 | 2014-06-30 |  | 555000 | 555000 | YES | CGN |  |  |  | 555000 | 100% |  |  | 0 | Complete
WATER | 139 | Muhonia/Turasha water project | water distribution | Enhanced water supply | 312HH |  | Kinangop | Murungaru |  |  | 2013-07-01 | 2014-06-30 |  | 551000 | 551000 | YES | CGN |  |  |  | 551000 | 100% |  |  | 0 | Complete
WATER | 140 | Kenton water project | water distribution | Enhanced water supply | 60HH |  | Kinangop | Magumu |  |  | 2013-07-01 | 2014-06-30 |  | 559000 | 559000 |  | CGN |  |  |  | 559000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 141 | Turaga-Ngwataniro water project | water distribution | Enhanced water supply | 200HH |  | Kinangop | Gathaara |  |  | 2013-07-01 | 2014-06-30 |  | 552000 | 552000 |  | CGN |  |  |  | 552000 | 100% |  |  | 0 | Complete
WATER | 142 | Githabai water project | water distribution | Enhanced water supply | 181HH |  | Kinangop | Githabai |  |  | 2013-07-01 | 2014-06-30 |  | 720000 | 720000 |  | CGN |  |  |  | 720000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 143 | Mutanga and Mung'etho borehole | water distribution | Enhanced water supply | 165HH |  | Ndaragwa | Kiriita |  |  | 2013-07-01 | 2014-06-30 |  | 550000 | 550000 |  | CGN |  |  |  | 550000 | 100% |  |  | 0 | Complete
WATER | 144 | Cheese and Karangatha boreholes | water distribution | Enhanced water supply | 120HH |  | Kinangop | Nyakio |  |  | 2013-07-01 | 2014-06-30 |  | 555000 | 555000 |  | CGN |  |  |  | 555000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion.
WATER | 145 | Kiburu water project | water distribution | Enhanced water supply | 108HH |  | Kinangop | Njabini |  |  | 2013-07-01 | 2014-06-30 |  | 1470000 | 1470000 |  | CGN |  |  |  | 1470000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 146 | Tia Wira water project | water distribution | Enhanced water supply | 145HH |  | Kinangop | North Kinangop |  |  | 2013-07-01 | 2014-06-30 |  | 555000 | 555000 |  | CGN |  |  |  | 555000 | 100% |  |  | 0 | Complete
WATER | 147 | Gathanji water project | water distribution | Enhanced water supply | 123HH |  | Oljoroorok | Gathanji |  |  | 2013-07-01 | 2014-06-30 |  | 555000 | 555000 |  | CGN |  |  |  | 555000 | 100% |  |  | 0 | Complete
WATER | 148 | Murungaru water project | water distribution | Enhanced water supply | 130HH |  | Kinangop | Murungaru |  |  | 2013-07-01 | 2014-06-30 |  | 561000 | 561000 |  | CGN |  |  |  | 561000 | 100% |  |  | 0 | Complete
WATER | 149 | Leshau borehole | water distribution | Enhanced water supply | 110HH |  | Ndaragwa | Leshau Pondo |  |  | 2014-07-01 | 2015-06-30 |  | 672639 | 672639 |  | CGN |  |  |  | 672639 | 100% |  |  | 0 | Complete
WATER | 150 | Kaimbaga water project | water distribution | Enhanced water supply | 201HH |  | Olkalou | Kaimbaga |  |  | 2014-07-01 | 2015-06-30 |  | 983310 | 983310 |  | CGN |  |  |  | 983310 | 100% |  |  | 0 | Complete
WATER | 151 | Muiri water project | Supply of Pipes | Enhanced water supply | 106HH |  | Olkalou | Karau |  |  | 2014-07-01 | 2015-06-30 |  | 632125 | 632125 |  | CGN |  |  |  | 632125 | 100% |  |  | 0 | Complete
WATER | 152 | Raitha Kahuru water project | water distribution | Enhanced water supply | 60HH |  | Kinangop | Gathaara |  |  | 2014-07-01 | 2015-06-30 |  | 949550 | 949550 |  | CGN |  |  |  | 949550 | 100% |  |  | 0 | Complete
WATER | 153 | Mutamaiyu water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2014-07-01 | 2015-06-30 |  | 1130710 | 1130710 |  | CGN |  |  |  | 1130710 | 100% |  |  | 0 | Complete
WATER | 154 | Gatimu East water project | water distribution | Enhanced water supply | 150HH |  | OLJOROOROK | GATIMU |  |  | 2014-07-01 | 2015-06-30 |  | 590860 | 590860 |  | CGN |  |  |  | 590860 | 100% |  |  | 0 | Complete
WATER | 155 | Turaga-Muruaki water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2014-07-01 | 2015-06-30 |  | 1160220 | 1160220 |  | CGN |  |  |  | 1160220 | 100% |  |  | 0 | Complete
WATER | 156 | Mutamaiyu water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2014-07-01 | 2015-06-30 |  | 1130710 | 1130710 |  | CGN |  |  |  | 1130710 | 100% |  |  | 0 | Complete
WATER | 157 | Karangatha water project | water distribution | Enhanced water supply |  |  |  | Nyakio |  |  | 2014-07-01 | 2015-06-30 |  | 760000 | 760000 |  | CGN |  |  |  | 760000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 158 | Njoguini water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 1478750 | 1478750 |  | CGN |  |  |  | 1478750 | 100% |  |  | 0 | Complete
WATER | 159 | Gathima water project | water distribution | Enhanced water supply | 200HH |  | Olokalou | Mirangine |  |  | 2014-07-01 | 2015-06-30 |  | 645500 | 645500 |  | CGN |  |  |  | 645500 | 100% |  |  | 0 | Complete
WATER | 160 | Gwa Kiongo water project | water distribution | Enhanced water supply | 300HH |  | Olokalou | Mirangine |  |  | 2014-07-01 | 2015-06-30 |  | 460500 | 460500 |  | CGN |  |  |  | 460500 | 100% |  |  | 0 | Complete
WATER | 161 | 3Mwater project | water distribution | Enhanced water supply | 150HH |  | Kinangop | North Kinangop |  |  | 2014-07-01 | 2015-06-30 |  | 283800 | 283800 |  | CGN |  |  |  | 283800 | 100% |  |  | 0 | Complete
WATER | 162 | Muhonia Turasha water project | water distribution | Enhanced water supply |  |  | Kinangop | Murungaru |  |  | 2014-07-01 | 2015-06-30 |  | 282550 | 282550 |  | CGN |  |  |  | 282550 | 100% |  |  | 0 | Complete
WATER | 163 | Ruiru borehole | water distribution | Enhanced water supply | 130HH |  | OLJOROOROK | CHARAGITA |  |  | 2014-07-01 | 2015-06-30 |  | 649950 | 649950 |  | CGN |  |  |  | 649950 | 100% |  |  | 0 | Complete
WATER | 164 | Kirima water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 4957400 | 4957400 |  | CGN |  |  |  | 4957400 | 100% |  |  | 0 | Complete
WATER | 165 | Kianjogu water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 2272000 | 2272000 |  | CGN |  |  |  | 2272000 | 100% |  |  | 0 | Complete
WATER | 166 | Uhuru secondary school | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 100500 | 100500 |  | CGN |  |  |  | 100500 | 100% |  |  | 0 | Complete
WATER | 167 | Kio dam | water distribution | Enhanced water supply |  |  | Olokaluo | Mirangine |  |  | 2014-07-01 | 2015-06-30 |  | 88100 | 88100 |  | CGN |  |  |  | 88100 | 100% |  |  | 0 | Complete
WATER | 168 | Ndemi borehole | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 509900 | 509900 |  | CGN |  |  |  | 509900 | 100% |  |  | 0 | Complete
WATER | 169 | Gatondo dispensary | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 194380 | 194380 |  | CGN |  |  |  | 194380 | 100% |  |  | 0 | Complete
WATER | 170 | Kiburu water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2014-07-01 | 2015-06-30 |  | 122000 | 122000 |  | CGN |  |  |  | 122000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 171 | Olkalou water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 89410 | 89410 |  | CGN |  |  |  | 89410 | 100% |  |  | 0 | Complete
WATER | 172 | Mugathika water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 770000 | 770000 |  | CGN |  |  |  | 770000 | 100% |  |  | 0 | Complete
WATER | 173 | Ruiru borehole | water distribution | Enhanced water supply | 50HH |  | OLJOROOROK | CHARAGITA |  |  | 2014-07-01 | 2015-06-30 |  | 958850 | 958850 |  | CGN |  |  |  | 958850 | 100% |  |  | 0 | Complete
WATER | 174 | Kariko borehole | water distribution | Enhanced water supply | 350HH |  | OLJOROOROK | WERU |  |  | 2014-07-01 | 2015-06-30 |  | 1143760 | 1143760 |  | CGN |  |  |  | 1143760 | 100% |  |  | 0 | Complete
WATER | 175 | Muhonia Turasha | water distribution | Enhanced water supply | 150HH |  | Kinangop | Murungaru |  |  | 2014-07-01 | 2015-06-30 |  | 360325 | 360325 |  | CGN |  |  |  | 360325 | 100% |  |  | 0 | Complete
WATER | 176 | Wahome dam | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 153800 | 153800 |  | CGN |  |  |  | 153800 | 100% |  |  | 0 | Complete
WATER | 177 | Upper chania water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2014-07-01 | 2015-06-30 |  | 994000 | 994000 |  | CGN |  |  |  | 994000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 178 | Kirima water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 998300 | 998300 |  | CGN |  |  |  | 998300 | 100% |  |  | 0 | Complete
WATER | 179 | Kianjogu water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 987000 | 987000 |  | CGN |  |  |  | 987000 | 100% |  |  | 0 | Complete
WATER | 180 | Raitha Kahuru water project | water distribution | Enhanced water supply | 60HH |  | Kinangop | Gathaara |  |  | 2014-07-01 | 2015-06-30 |  | 695000 | 695000 |  | CGN |  |  |  | 695000 | 100% |  |  | 0 | Complete
WATER | 181 | Kirima water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 649980 | 649980 |  | CGN |  |  |  | 649980 | 100% |  |  | 0 | Complete
WATER | 182 | Weru water project | water distribution | Enhanced water supply | 250HH |  | OLJOROOROK | WERU |  |  | 2014-07-01 | 2015-06-30 |  | 999750 | 999750 |  | CGN |  |  |  | 999750 | 100% |  |  | 0 | Complete
WATER | 183 | Mutiini water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2014-07-01 | 2015-06-30 |  | 7161120 | 7161120 |  | CGN |  |  |  | 7161120 | 100% |  |  | 0 | Complete
WATER | 184 | Kenton/Karangatha | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2014-07-01 | 2015-06-30 |  | 1523000 | 1523000 |  | CGN |  |  |  | 1523000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 185 | Kirima welfare water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 428450 | 428450 |  | CGN |  |  |  | 428450 | 100% |  |  | 0 | Complete
WATER | 186 | Karangatha water project | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2014-07-01 | 2015-06-30 |  | 498600 | 498600 |  | CGN |  |  |  | 498600 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 187 | Muhonia water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2014-07-01 | 2015-06-30 |  | 1115500 | 1115500 |  | CGN |  |  |  | 1115500 | 100% |  |  | 0 | Complete
WATER | 188 | Kirima welfare | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 1037500 | 1037500 |  | CGN |  |  |  | 1037500 | 100% |  |  | 0 | Complete
WATER | 189 | Mawingu water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 68500 | 68500 |  | CGN |  |  |  | 68500 | 100% |  |  | 0 | Complete
WATER | 190 | Simbara Sibra | water distribution | Enhanced water supply | 100HH |  | NDARAGWA | SHAMATA |  |  | 2014-07-01 | 2015-06-30 |  | 2004890 | 2004890 |  | CGN |  |  |  | 2004890 | 100% |  |  | 0 | Complete
WATER | 191 | Ruiru borehole | water distribution | Enhanced water supply | 100HH |  | OLJOROOROK | CHARAGITA |  |  | 2014-07-01 | 2015-06-30 |  | 1903500 | 1903500 |  | CGN |  |  |  | 1903500 | 100% |  |  | 0 | Complete
WATER | 192 | Gwa Kiongo water project | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2014-07-01 | 2015-06-30 |  | 1492833 | 1492833 |  | CGN |  |  |  | 1492833 | 100% |  |  | 0 | Complete
WATER | 193 | Tia wira water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2014-07-01 | 2015-06-30 |  | 1101010 | 1101010 |  | CGN |  |  |  | 1101010 | 100% |  |  | 0 | Complete
WATER | 194 | Tulaga Muruaki | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2014-07-01 | 2015-06-30 |  | 1782630 | 1782630 |  | CGN |  |  |  | 1782630 | 100% |  |  | 0 | Complete
WATER | 195 | Uhuru borehole water project | water distribution | Enhanced water supply |  |  | Olkaluo | MIrangine |  |  | 2014-07-01 | 2015-06-30 |  | 360000 | 360000 |  | CGN |  |  |  | 360000 | 100% |  |  | 0 | Complete
WATER | 196 | Raitha Kahuru water project | water distribution | Enhanced water supply | 60HH |  | Kinangop | Gathaara |  |  | 2014-07-01 | 2015-06-30 |  | 751590 | 751590 |  | CGN |  |  |  | 751590 | 100% |  |  | 0 | Complete
WATER | 197 | Karurumo intake | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 1507977 | 1507977 |  | CGN |  |  |  | 1507977 | 100% |  |  | 0 | Complete
WATER | 198 | Mutamaiyu water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2014-07-01 | 2015-06-30 |  | 223335 | 223335 |  | CGN |  |  |  | 223335 | 100% |  |  | 0 | Complete
WATER | 199 | Kirima welfare | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 380000 | 380000 |  | CGN |  |  |  | 380000 | 100% |  |  | 0 | Complete
WATER | 200 | Malan borehole | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 579800 | 579800 |  | CGN |  |  |  | 579800 | 100% |  |  | 0 | Complete
WATER | 201 | Pesi river crossing | water distribution | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2014-07-01 | 2015-06-30 |  | 246415 | 246415 |  | CGN |  |  |  | 246415 | 100% |  |  | 0 | Complete
WATER | 202 | Gatimu water project | water distribution | Enhanced water supply | 1500HH |  | OLJOROOROK | GATIMU |  |  | 2014-07-01 | 2015-06-30 |  | 4616154 | 4616154 |  | CGN |  |  |  | 4616154 | 100% |  |  | 0 | Complete
WATER | 203 | Gatumbiro | water distribution | Enhanced water supply | 120HH |  | OLJOROOROK | WERU |  |  | 2014-07-01 | 2015-06-30 |  | 1098685 | 1098685 |  | CGN |  |  |  | 1098685 | 100% |  |  | 0 | Complete
WATER | 204 | Road C77 near Suera petrol station | water distribution | Enhanced water supply | 80HH |  | OLJOROOROK | GATIMU |  |  | 2014-07-01 | 2015-06-30 |  | 495230 | 495230 |  | CGN |  |  |  | 495230 | 100% |  |  | 0 | Complete
WATER | 205 | Gathima water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 178960 | 178960 |  | CGN |  |  |  | 178960 | 100% |  |  | 0 | Complete
WATER | 206 | Gatimu East W/P | water distribution | Enhanced water supply | 100HH |  | OLJOROOROK | GATIMU |  |  | 2014-07-01 | 2015-06-30 |  | 477700 | 477700 |  | CGN |  |  |  | 477700 | 100% |  |  | 0 | Complete
WATER | 207 | Inooro | water distribution | Enhanced water supply | 100HH |  | OLJOROOROK | WERU |  |  | 2014-07-01 | 2015-06-30 |  | 1081927 | 1081927 |  | CGN |  |  |  | 1081927 | 100% |  |  | 0 | Complete
WATER | 208 | Karurumo intake main line | water distribution | Enhanced water supply | 1000HH |  | NDARAGWA | SHAMATA |  |  | 2014-07-01 | 2015-06-30 |  | 2497312 | 2497312 |  | CGN |  |  |  | 2497312 | 100% |  |  | 0 | Complete
WATER | 209 | Karangatha water project | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2014-07-01 | 2015-06-30 |  | 521537 | 521537 |  | CGN |  |  |  | 521537 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 210 | Kagiiki water pan | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 889900 | 889900 |  | CGN |  |  |  | 889900 | 100% |  |  | 0 | Complete
WATER | 211 | Kianjogu water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 909277 | 909277 |  | CGN |  |  |  | 909277 | 100% |  |  | 0 | Complete
WATER | 212 | Gathanji springs | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 1442000 | 1442000 |  | CGN |  |  |  | 1442000 | 100% |  |  | 0 | Complete
WATER | 213 | Karangatha borehole | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2014-07-01 | 2015-06-30 |  | 708629 | 708629 |  | CGN |  |  |  | 708629 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 214 | Muti-ini water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2014-07-01 | 2015-06-30 |  | 195000 | 195000 |  | CGN |  |  |  | 195000 | 100% |  |  | 0 | Complete
WATER | 215 | Ngano water project | water distribution | Enhanced water supply | 20HH |  | OLJOROOROK | SHARAGITA |  |  | 2014-07-01 | 2015-06-30 |  | 199500 | 199500 |  | CGN |  |  |  | 199500 | 100% |  |  | 0 | Complete
WATER | 216 | Gwa Kiongo water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 149572 | 149572 |  | CGN |  |  |  | 149572 | 100% |  |  | 0 | Complete
WATER | 217 | Gitirima water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 245300 | 245300 |  | CGN |  |  |  | 245300 | 100% |  |  | 0 | Complete
WATER | 218 | Waithaka water pan | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 1487420 | 1487420 |  | CGN |  |  |  | 1487420 | 100% |  |  | 0 | Complete
WATER | 219 | Mumui water pan | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 1487420 | 1487420 |  | CGN |  |  |  | 1487420 | 100% |  |  | 0 | Complete
WATER | 220 | Mugathika water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 270000 | 270000 |  | CGN |  |  |  | 270000 | 100% |  |  | 0 | Complete
WATER | 221 | Kenton water project | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2014-07-01 | 2015-06-30 |  | 399500 | 399500 |  | CGN |  |  |  | 399500 | 100% |  |  | 0 | Complete
WATER | 222 | KKY water pan | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2014-07-01 | 2015-06-30 |  | 2883910 | 2883910 |  | CGN |  |  |  | 2883910 | 100% |  |  | 0 | Complete
WATER | 223 | Kenton water project | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2014-07-01 | 2015-06-30 |  | 2142014 | 2142014 |  | CGN |  |  |  | 2142014 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 224 | Mugathika water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 1782630 | 1782630 |  | CGN |  |  |  | 1782630 | 100% |  |  | 0 | Complete
WATER | 225 | Turaga Muruaki water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2014-07-01 | 2015-06-30 |  | 667690 | 667690 |  | CGN |  |  |  | 667690 | 100% |  |  | 0 | Complete
WATER | 226 | Mawingo Kagaa water project | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 264096 | 264096 |  | CGN |  |  |  | 264096 | 100% |  |  | 0 | Complete
WATER | 227 | Olkalou county commissioner main line | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 117000 | 117000 |  | CGN |  |  |  | 117000 | 100% |  |  | 0 | Complete
WATER | 228 | Mutu-ini water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2014-07-01 | 2015-06-30 |  | 2325000 | 2325000 |  | CGN |  |  |  | 2325000 | 100% |  |  | 0 | Complete
WATER | 229 | Kirima welfare | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 218400 | 218400 |  | CGN |  |  |  | 218400 | 100% |  |  | 0 | Complete
WATER | 230 | Rurii polytechnic borehole | water distribution | Enhanced water supply |  |  | Ol Kalou | Rurii |  |  | 2014-07-01 | 2015-06-30 |  | 114750 | 114750 |  | CGN |  |  |  | 114750 | 100% |  |  | 0 | Complete
WATER | 231 | Kisawel water supply | water distribution | Enhanced water supply | 400HH |  | OLJOROOROK | GATIMU |  |  | 2014-07-01 | 2015-06-30 |  | 466758 | 466758 |  | CGN |  |  |  | 466758 | 100% |  |  | 0 | Complete
WATER | 232 | Leshau pondo primary | water distribution | Enhanced water supply | 70HH |  | NDARAGWA | LESHAU PONDO |  |  | 2014-07-01 | 2015-06-30 |  | 56400 | 56400 |  | CGN |  |  |  | 56400 | 100% |  |  | 0 | Complete
WATER | 233 | Kiburuti dam | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 128300 | 128300 |  | CGN |  |  |  | 128300 | 100% |  |  | 0 | Complete
WATER | 234 | Gathara primary | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2014-07-01 | 2015-06-30 |  | 222755 | 222755 |  | CGN |  |  |  | 222755 | 100% |  |  | 0 | Complete
WATER | 235 | Mihato water supply | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 993500 | 993500 |  | CGN |  |  |  | 993500 | 100% |  |  | 0 | Complete
WATER | 236 | Raitha Kahuru | water distribution | Enhanced water supply | 60HH |  | Kinangop | Gathaara |  |  | 2014-07-01 | 2015-06-30 |  | 998185 | 998185 |  | CGN |  |  |  | 998185 | 100% |  |  | 0 | Complete
WATER | 237 | Leshau Karagoini | water distribution | Enhanced water supply | 2000HH |  | NDARAGWA | LESHAUPONDO/KIRIITA |  |  | 2014-07-01 | 2015-06-30 |  | 390450 | 390450 |  | CGN |  |  |  | 390450 | 100% |  |  | 0 | Complete
WATER | 238 | Mawingo Kagaa | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 160580 | 160580 |  | CGN |  |  |  | 160580 | 100% |  |  | 0 | Complete
WATER | 239 | Olkalou sewerage | water distribution | Enhanced water supply | [6 empty] | 2014-07-01 | 2015-06-30 |  | 50000000 | 50000000 |  | CGN |  |  |  | 50000000 | 100% |  |  | 0 | Complete
WATER | 240 | Wanjohi -100m3 masonry tank at Muthangira water project | Construction of water storage tank | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1797426 | 1797426 |  | CGN |  |  |  | 1797426 | 100% |  |  | 0 | Complete
WATER | 241 | Wanjohi -50m3 masonry tank at Mahigaini water project | Construction of water storage tank | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1207155 | 1207155 |  | CGN |  |  |  | 1207155 | 100% |  |  | 0 | Complete
WATER | 242 | Wanjohi -Construction of 6m high steel tank tower at Kahoro (Ndemi) borehole | Construction of water storage tank | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 545000 | 545000 |  | CGN |  |  |  | 545000 | 100% |  |  | 0 | Complete
WATER | 243 | Wanjohi -Supply of 2No 10m3 plastic tanks to Kahoro ( Ndemi )borehole | Construction of water storage tank | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 210000 | 210000 |  | CGN |  |  |  | 210000 | 100% |  |  | 0 | Complete
WATER | 244 | Wanjohi -Supply of 1No 10m3 plastic tank to Michore primary school | Construction of water storage tank | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 107500 | 107500 |  | CGN |  |  |  | 107500 | 100% |  |  | 0 | Complete
WATER | 245 | Wanjohi -Supply of pipes and fittings to Mahigaini water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 226500 | 226500 |  | CGN |  |  |  | 226500 | 100% |  |  | 0 | Complete
WATER | 246 | Wanjohi -Supply of pipes to Kinungu water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 670816 | 670816 |  | CGN |  |  |  | 670816 | 100% |  |  | 0 | Complete
WATER | 247 | Wanjohi -Supply of pipes to Kega water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 653500 | 653500 |  | CGN |  |  |  | 653500 | 100% |  |  | 0 | Complete
WATER | 248 | Kipipiri - Repair of 2No 100m3 storage tanks at Muthangira water project | Construction of water storage tank | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1825050 | 1825050 |  | CGN |  |  |  | 1825050 | 100% |  |  | 0 | Complete
WATER | 249 | Kipipiri -Rehabilitation of Forest One Hydram pump | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 585350 | 585350 |  | CGN |  |  |  | 585350 | 100% |  |  | 0 | Complete
WATER | 250 | Kipipiri -Construction of Kamuhu intake | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1569635 | 1569635 |  | CGN |  |  |  | 1569635 | 100% |  |  | 0 | Complete
WATER | 251 | Kipipiri -Supply and laying of pipes at Kamuhu water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1045867 | 1045867 |  | CGN |  |  |  | 1045867 | 100% |  |  | 0 | Complete
WATER | 252 | Kipipiri -Supply and laying of pipes at Forest One Hydram water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 990000 | 990000 |  | CGN |  |  |  | 990000 | 100% |  |  | 0 | Complete
WATER | 253 | Kipipiri -Supply and laying of pipes at Kianjogu/Miji Kenda water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 797250 | 797250 |  | CGN |  |  |  | 797250 | 100% |  |  | 0 | Complete
WATER | 254 | Kipipiri -Supply and laying of pipes from intake to Kaborithi tank | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 554875 | 554875 |  | CGN |  |  |  | 554875 | 100% |  |  | 0 | Complete
WATER | 255 | Gatimu - 225m3 masonry tank at Kianjata for Njunu water project | Construction of water storage tank | Enhanced water supply | 250HH |  | OLJOROOROK | GATIMU |  |  | 2015-07-01 | 2016-06-30 |  | 3419735 | 3419735 |  | CGN |  |  |  | 3419735 | 100% |  |  | 0 | Complete
WATER | 256 | Gatimu -Supplying and laying of pipes at Njunu water project | water distribution | Enhanced water supply | 150HH |  | OLJOROOROK | GATIMU |  |  | 2015-07-01 | 2016-06-30 |  | 8855716 | 8855716 |  | CGN |  |  |  | 8855716 | 100% |  |  | 0 | Complete
WATER | 257 | Gatimu -Supply and laying of pipes and construction of valve chambers at Gikingi water project | water distribution | Enhanced water supply | 500HH |  | OLJOROOROK | GATIMU |  |  | 2015-07-01 | 2016-06-30 |  | 11238869 | 11238869 |  | CGN |  |  |  | 11238869 | 100% |  |  | 0 | Complete
WATER | 258 | Weru - Rain water roof harvesting for Githima ECD primary school | Roof water harvesting | Enhanced water supply | 300PUPIL |  | OLJOROOROK | WERU |  |  | 2015-07-01 | 2016-06-30 |  | 226378 | 226378 |  | CGN |  |  |  | 226378 | 100% |  |  | 0 | Complete
WATER | 259 | Weru - Rain water roof harvesting for Inooro primary school | Roof water harvesting | Enhanced water supply | 280PUPILS |  | OLJOROOROK | WERU |  |  | 2015-07-01 | 2016-06-30 |  | 299805 | 299805 |  | CGN |  |  |  | 299805 | 100% |  |  | 0 | Complete
WATER | 260 | Weru - Rain water roof harvesting for Mandaraka primary school | Roof water harvesting | Enhanced water supply | 400PUPILS |  | OLJOROOROK | WERU |  |  | 2015-07-01 | 2016-06-30 |  | 299862 | 299862 |  | CGN |  |  |  | 299862 | 100% |  |  | 0 | Complete
WATER | 261 | Weru - Supply of 10No - 3m310m3 and 1No – 6m3 plastic tanks to Wendani water group and Oljoro Orok secondary school | Water storage tanks | Enhanced water supply | 50HH |  | OLJOROOROK | WERU |  |  | 2015-07-01 | 2016-06-30 |  | 303800 | 303800 |  | CGN |  |  |  | 303800 | 100% |  |  | 0 | Complete
WATER | 262 | Weru - Supply of submersible pump and control panel to Weru borehole | Pump installation | Enhanced water supply | 300HH |  | OLJOROOROK | WERU |  |  | 2015-07-01 | 2016-06-30 |  | 1075000 | 1075000 |  | CGN |  |  |  | 1075000 | 100% |  |  | 0 | Complete
WATER | 263 | Weru - Supply of pipes to Gatumbiro water project | water distribution | Enhanced water supply | 70HH |  | OLJOROOROK | WERU |  |  | 2015-07-01 | 2016-06-30 |  | 625000 | 625000 |  | CGN |  |  |  | 625000 | 100% |  |  | 0 | Complete
WATER | 264 | Weru - Supply and laying of pipes at Matura borehole water project | water distribution | Enhanced water supply | 108 |  | OLJOROOROK | WERU |  |  | 2015-07-01 | 2016-06-30 |  | 358800 | 358800 |  | CGN |  |  |  | 358800 | 100% |  |  | 0 | Complete
WATER | 265 | Weru - Supply of submersible cable and phase failure rely for Matura borehole | water distribution | Enhanced water supply | 300HH |  | OLJOROOROK | WERU |  |  | 2015-07-01 | 2016-06-30 |  | 172170 | 172170 |  | CGN |  |  |  | 172170 | 100% |  |  | 0 | Complete
WATER | 266 | Gathanje - Supply of pipes to Kirathimo water project | water distribution | Enhanced water supply | 75HH |  | OLJOROOROK | GATHANJE |  |  | 2015-07-01 | 2016-06-30 |  | 1076200 | 1076200 |  | CGN |  |  |  | 1076200 | 100% |  |  | 0 | Complete
WATER | 267 | Gathanje -Supply of pipes to Kambaa water project | water distribution | Enhanced water supply | 50HH |  | OLJOROOROK | GATHANJE |  |  | 2015-07-01 | 2016-06-30 |  | 1064550 | 1064550 |  | CGN |  |  |  | 1064550 | 100% |  |  | 0 | Complete
WATER | 268 | Gathanje -Supply of pipes to Ngano dispensary water project | water distribution | Enhanced water supply | 75HH |  | OLJOROOROK | GATHANJE |  |  | 2015-07-01 | 2016-06-30 |  | 231665 | 231665 |  | CGN |  |  |  | 231665 | 100% |  |  | 0 | Complete
WATER | 269 | Gathanje -Supply and laying of pipes at Boiman water project | water distribution | Enhanced water supply | 190HH |  | OLJOROOROK | GATHANJE |  |  | 2015-07-01 | 2016-06-30 |  | 722832 | 722832 |  | CGN |  |  |  | 722832 | 100% |  |  | 0 | Complete
WATER | 270 | Gathanje -Supply and laying of pipes at Ngufa water project | water distribution | Enhanced water supply | 130HH |  | OLJOROOROK | GATHANJE |  |  | 2015-07-01 | 2016-06-30 |  | 625025 | 625025 |  | CGN |  |  |  | 625025 | 100% |  |  | 0 | Complete
WATER | 271 | Gathanje -Supply of pipes to Gituamba water project | water distribution | Enhanced water supply | 120HH |  | OLJOROOROK | GATHANJE |  |  | 2015-07-01 | 2016-06-30 |  | 858340 | 858340 |  | CGN |  |  |  | 858340 | 100% |  |  | 0 | Complete
WATER | 272 | Gathanje -Test pumping of Boiman borehole | Borehole testpumping | Enhanced water supply | 300HH |  | OLJOROOROK | GATHANJE |  |  | 2015-07-01 | 2016-06-30 |  | 237405 | 237405 |  | CGN |  |  |  | 237405 | 100% |  |  | 0 | Complete
WATER | 273 | Charagita - 50m3 masonry tank at Ruiru borehole water project | Water storage tank | Enhanced water supply | 250HH |  | OLJOROOROK | CHARAGITA |  |  | 2015-07-01 | 2016-06-30 |  | 1180992 | 1180992 |  | CGN |  |  |  | 1180992 | 100% |  |  | 0 | Complete
WATER | 274 | Charagita -Supply of 4No 10m3 plastic tank to Ngano water project | Water Storage tank | Enhanced water supply | 500HH |  | OLJOROOROK | CHARAGITA |  |  | 2015-07-01 | 2016-06-30 |  | 415200 | 415200 |  | CGN |  |  |  | 415200 | 100% |  |  | 0 | Complete
WATER | 275 | Charagita -Design of Oraimutia water project | water distribution | Enhanced water supply | 250HH |  | OLJOROOROK | CHARAGITA |  |  | 2015-07-01 | 2016-06-30 |  | 365000 | 365000 |  | CGN |  |  |  | 365000 | 100% |  |  | 0 | Complete
WATER | 276 | Charagita -Supply and laying of pipes at Ruiru water project | water distribution | Enhanced water supply | 100HH |  | OLJOROOROK | CHARAGITA |  |  | 2015-07-01 | 2016-06-30 |  | 3652655 | 3652655 |  | CGN |  |  |  | 3652655 | 100% |  |  | 0 | Complete
WATER | 277 | Charagita -Drilling of production borehole at Kwa Lord | Borehole drilling | Enhanced water supply | 150HH |  | OLJOROOROK | CHARAGITA |  |  | 2015-07-01 | 2016-06-30 |  | 1964235 | 1964235 |  | CGN |  |  |  | 1964235 | 100% |  |  | 0 | Complete
WATER | 278 | Charagita -Installation of submersible pump at Ruiru borehole | Pump installation | Enhanced water supply | 250HH |  | OLJOROOROK | CHARAGITA |  |  | 2015-07-01 | 2016-06-30 |  | 154280 | 154280 |  | CGN |  |  |  | 154280 | 100% |  |  | 0 | Complete
WATER | 279 | Charagita -Construction of control panel pump house | Borehole works | Enhanced water supply | 250HH |  | OLJOROOROK | CHARAGITA |  |  | 2015-07-01 | 2016-06-30 |  | 500000 | 500000 |  | CGN |  |  |  | 500000 | 100% |  |  | 0 | Complete
WATER | 280 | Charagita -Supply of submersible pump and control panel for Ruiru borehole | Borehole works | Enhanced water supply | 250HH |  | OLJOROOROK | CHARAGITA |  |  | 2015-07-01 | 2016-06-30 |  | 963000 | 963000 |  | CGN |  |  |  | 963000 | 100% |  |  | 0 | Complete
WATER | 281 | Rurii - Supply and laying of pipes at Meja borehole water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 230222 | 230222 |  | CGN |  |  |  | 230222 | 100% |  |  | 0 | Complete
WATER | 282 | Rurii -Installation of submersible pump at Meja borehole | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 574080 | 574080 |  | CGN |  |  |  | 574080 | 100% |  |  | 0 | Complete
WATER | 283 | Rurii -Installation of submersible pump at Rurii borehole | Borehole works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 220000 | 220000 |  | CGN |  |  |  | 220000 | 100% |  |  | 0 | Complete
WATER | 284 | Rurii -Drilling of production borehole at Matuiku | Borehole works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1936200 | 1936200 |  | CGN |  |  |  | 1936200 | 100% |  |  | 0 | Complete
WATER | 285 | Rurii -Supply and laying of pipes at Kahonge water project ( Malan) | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1610805 | 1610805 |  | CGN |  |  |  | 1610805 | 100% |  |  | 0 | Complete
WATER | 286 | Rurii -Installation of submersible pump at Matura borehole | Borehole works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 290000 | 290000 |  | CGN |  |  |  | 290000 | 100% |  |  | 0 | Complete
WATER | 287 | Rurii -Supply and laying of pipes and fittings for Mugathika water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1910090 | 1910090 |  | CGN |  |  |  | 1910090 | 100% |  |  | 0 | Complete
WATER | 288 | Rurii -Supply and laying of pipes and fittings at Olkalou water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1363935 | 1363935 |  | CGN |  |  |  | 1363935 | 100% |  |  | 0 | Complete
WATER | 289 | Rurii -Supply of Matura borehole submersible pump motor | Borehole works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 189476 | 189476 |  | CGN |  |  |  | 189476 | 100% |  |  | 0 | Complete
WATER | 290 | Rurii -Supply of Matura borehole surface pump | Borehole works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 867250 | 867250 |  | CGN |  |  |  | 867250 | 100% |  |  | 0 | Complete
WATER | 291 | Rurii -Installation of submersible pump at Malan borehole | Borehole works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 142680 | 142680 |  | CGN |  |  |  | 142680 | 100% |  |  | 0 | Complete
WATER | 292 | Rurii -Supply of Malan water project surface pump | Pump installation | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 926550 | 926550 |  | CGN |  |  |  | 926550 | 100% |  |  | 0 | Complete
WATER | 293 | Rurii -Laying of pipes and installation of fittings at Kirima self help water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 194796 | 194796 |  | CGN |  |  |  | 194796 | 100% |  |  | 0 | Complete
WATER | 294 | Rurii -Supply of 1No 5m3 plastic tank to Huhoini primary school | Water storage tank | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 55000 | 55000 |  | CGN |  |  |  | 55000 | 100% |  |  | 0 | Complete
WATER | 295 | Rurii -Laying of pipes and installation of fittings at Olkalou (Thita) water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 302680 | 302680 |  | CGN |  |  |  | 302680 | 100% |  |  | 0 | Complete
WATER | 296 | Rurii -Supply of 1No 10m3 plastic tank to Rurii polytechnic borehole | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 92000 | 92000 |  | CGN |  |  |  | 92000 | 100% |  |  | 0 | Complete
WATER | 297 | Rurii -Construction of 6m high steel tank tower at Malan borehole | water storage tank | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 822421 | 822421 |  | CGN |  |  |  | 822421 | 100% |  |  | 0 | Complete
WATER | 298 | Karau - Servicing and testing of pump and accessories at Mawingu water project | Borehole works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 204527 | 204527 |  | CGN |  |  |  | 204527 | 100% |  |  | 0 | Complete
WATER | 299 | Karau - Supply of 230 No 0.1m3 plastic tanks to ward water groups | Water storage works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 225400 | 225400 |  | CGN |  |  |  | 225400 | 100% |  |  | 0 | Complete
WATER | 300 | Karau - Kwa Njane water tank repair | Water storage tanks | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 419750 | 419750 |  | CGN |  |  |  | 419750 | 100% |  |  | 0 | Complete
WATER | 301 | Karau - Hydrogeological survey for Kiburuti borehole | Borehole works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 72000 | 72000 |  | CGN |  |  |  | 72000 | 100% |  |  | 0 | Complete
WATER | 302 | Karau - Drilling of production borehole at Kiburuti | Borehole drilling | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 2298122 | 2298122 |  | CGN |  |  |  | 2298122 | 100% |  |  | 0 | Complete
WATER | 303 | Karau - Supply of pipes and fittings to Munyeki water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 2100000 | 2100000 |  | CGN |  |  |  | 2100000 | 100% |  |  | 0 | Complete
WATER | 304 | Karau - Supply of 700 No 230 litre capacity plastic tanks to ward water groups | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 2100000 | 2100000 |  | CGN |  |  |  | 2100000 | 100% |  |  | 0 | Complete
WATER | 305 | Karau - Hydrogeological surveys for boreholes in Olkalou subcounty | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 375000 | 375000 |  | CGN |  |  |  | 375000 | 100% |  |  | 0 | Complete
WATER | 306 | Karau - Storm water drainage in Olkalou town | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 29335000 | 29335000 |  | CGN |  |  |  | 29335000 | 100% |  |  | 0 | Complete
WATER | 307 | Karau - Drilling of production borehole at Kiandeto | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1725885 | 1725885 |  | CGN |  |  |  | 1725885 | 100% |  |  | 0 | Complete
WATER | 308 | Karau - Drilling of production borehole at Kianda | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 2254822 | 2254822 |  | CGN |  |  |  | 2254822 | 100% |  |  | 0 | Complete
WATER | 309 | Kaimbaga - Rehabilitation of pump house, installation of control panel, pump and accessories and testing of Kaimbaga water project | Borehole works | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 315210 | 315210 |  | CGN |  |  |  | 315210 | 100% |  |  | 0 | Complete
WATER | 310 | Kaimbaga - Rehabilitation of Mihuti dam | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 428072 | 428072 |  | CGN |  |  |  | 428072 | 100% |  |  | 0 | Complete
WATER | 311 | Kaimbaga - Trenching and pipelaying at Mathathi water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1094800 | 1094800 |  | CGN |  |  |  | 1094800 | 100% |  |  | 0 | Complete
WATER | 312 | Kaimbaga - Supply of pipes and fittings for Kaimbaga water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1946250 | 1946250 |  | CGN |  |  |  | 1946250 | 100% |  |  | 0 | Complete
WATER | 313 | Kaimbaga - Supply of 1No 10m3 plastic tank to Nyakinyua water group | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 94000 | 94000 |  | CGN |  |  |  | 94000 | 100% |  |  | 0 | Complete
WATER | 314 | Kaimbaga - Supply of 1No 10m3 plastic tank to Kamande primary school | Roof water harvesting | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 95000 | 95000 |  | CGN |  |  |  | 95000 | 100% |  |  | 0 | Complete
WATER | 315 | Kaimbaga - Drilling of production borehole at Mathathi | Borehole drilling | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 2425290 | 2425290 |  | CGN |  |  |  | 2425290 | 100% |  |  | 0 | Complete
WATER | 316 | Mirangine - Roof harvesting for Gituamba primary school | Roof water harvesting | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2015-07-01 | 2016-06-30 |  | 299989 | 299989 |  | CGN |  |  |  | 299989 | 100% |  |  | 0 | Complete
WATER | 317 | Mirangine -Roof harvesting for Mathakwa primary school | Roof water harvesting | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2015-07-01 | 2016-06-30 |  | 301955 | 301955 |  | CGN |  |  |  | 301955 | 100% |  |  | 0 | Complete
WATER | 318 | Mirangine -Roof harvesting for Mirangine primary school | Roof water harvesting | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2015-07-01 | 2016-06-30 |  | 299994 | 299994 |  | CGN |  |  |  | 299994 | 100% |  |  | 0 | Complete
WATER | 319 | Mirangine -Drilling of production borehole at Micharage | Borehole drilling | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2015-07-01 | 2016-06-30 |  | 2084145 | 2084145 |  | CGN |  |  |  | 2084145 | 100% |  |  | 0 | Complete
WATER | 320 | Mirangine -Gwa Kiongo composite filtration unit | Water treatment works | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2015-07-01 | 2016-06-30 |  | 1192230 | 1192230 |  | CGN |  |  |  | 1192230 | 100% |  |  | 0 | Complete
WATER | 321 | Mirangine -50m3 masonry tank at Micharage water project | Water storage tanks | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2015-07-01 | 2016-06-30 |  | 1254893 | 1254893 |  | CGN |  |  |  | 1254893 | 100% |  |  | 0 | Complete
WATER | 322 | Mirangine -Supply and laying of pipes at Gitirima water project | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2015-07-01 | 2016-06-30 |  | 521515 | 521515 |  | CGN |  |  |  | 521515 | 100% |  |  | 0 | Complete
WATER | 323 | Kanjuiri - 50m3 masonry tank at Nyaituga water project | Water storage tanks | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2015-07-01 | 2016-06-30 |  | 1197182 | 1197182 |  | CGN |  |  |  | 1197182 | 100% |  |  | 0 | Complete
WATER | 324 | Kanjuiri - Supply and laying of pipes at Uhuru water project | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2015-07-01 | 2016-06-30 |  | 896195 | 896195 |  | CGN |  |  |  | 896195 | 100% |  |  | 0 | Complete
WATER | 325 | Kanjuiri - Supply of submersible pump and control panel for Nyaituga borehole | Pump installation | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2015-07-01 | 2016-06-30 |  | 907657 | 907657 |  | CGN |  |  |  | 907657 | 100% |  |  | 0 | Complete
WATER | 326 | Kanjuiri - Drilling of production borehole at Nyaituga | Borehole drilling works | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2015-07-01 | 2016-06-30 |  | 2204996 | 2204996 |  | CGN |  |  |  | 2204996 | 100% |  |  | 0 | Complete
WATER | 327 | Kiriita - Rehabilitation of Njimbiri well | Well Works | Enhanced water supply | 50HH |  | NDARAGWA | KIRIITA |  |  | 2015-07-01 | 2016-06-30 |  | 253092 | 253092 |  | CGN |  |  |  | 253092 | 100% |  |  | 0 | Complete
WATER | 328 | Kiriita - 50m3 masonry tank at Karagoine water project | Water storage tank | Enhanced water supply | 100HH |  | NDARAGWA | KIRIITA |  |  | 2015-07-01 | 2016-06-30 |  | 1197558 | 1197558 |  | CGN |  |  |  | 1197558 | 100% |  |  | 0 | Complete
WATER | 329 | Kiriita - Kanjuiri - Test pumping of Leshau borehole | Borehole works | Enhanced water supply | 100HH |  | NDARAGWA | KIRIITA |  |  | 2015-07-01 | 2016-06-30 |  | 244650 | 244650 |  | CGN |  |  |  | 244650 | 100% |  |  | 0 | Complete
WATER | 330 | Kiriita - 50m3 masonry tank at Mung’etho water project | Water Storage tank | Enhanced water supply | 100HH |  | NDARAGWA | KIRIITA |  |  | 2015-07-01 | 2016-06-30 |  | 1197967 | 1197967 |  | CGN |  |  |  | 1197967 | 100% |  |  | 0 | Complete
WATER | 331 | Kiriita - Supply and laying of pipes at Mung’etho water project | water distribution | Enhanced water supply | 80HH |  | NDARAGWA | KIRIITA |  |  | 2015-07-01 | 2016-06-30 |  | 736575 | 736575 |  | CGN |  |  |  | 736575 | 100% |  |  | 0 | Complete
WATER | 332 | Leshau - Supply and laying of pipes at Shauri Kianda borehole water project | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | LESHAU PONDO |  |  | 2015-07-01 | 2016-06-30 |  | 1008233 | 1008233 |  | CGN |  |  |  | 1008233 | 100% |  |  | 0 | Complete
WATER | 333 | Leshau - Construction of 3m x 3m pump house at Shauri Kianda borehole | Borehole works | Enhanced water supply | 50HH |  | NDARAGWA | LESHAU PONDO |  |  | 2015-07-01 | 2016-06-30 |  | 697268 | 697268 |  | CGN |  |  |  | 697268 | 100% |  |  | 0 | Complete
WATER | 334 | Leshau - Supply and laying of pipes at Nyakinyua water project | water distribution | Enhanced water supply | 75HH |  | NDARAGWA | LESHAU PONDO |  |  | 2015-07-01 | 2016-06-30 |  | 369638 | 369638 |  | CGN |  |  |  | 369638 | 100% |  |  | 0 | Complete
WATER | 335 | Leshau - Supply of surface pump to Shauri Kianda borehole water project | Borehole works | Enhanced water supply | 50HH |  | NDARAGWA | LESHAU PONDO |  |  | 2015-07-01 | 2016-06-30 |  | 1420000 | 1420000 |  | CGN |  |  |  | 1420000 | 100% |  |  | 0 | Complete
WATER | 336 | Leshau - Installation of Shauri Kianda borehole surface pump | Borehole works | Enhanced water supply | 50HH |  | NDARAGWA | LESHAU PONDO |  |  | 2015-07-01 | 2016-06-30 |  | 82000 | 82000 |  | CGN |  |  |  | 82000 | 100% |  |  | 0 | Complete
WATER | 337 | Leshau - Supply of 2No 10m3 plastic tanks to Nyakinyua borehole water project | Water storage tanks | Enhanced water supply | 75HH |  | NDARAGWA | LESHAU PONDO |  |  | 2015-07-01 | 2016-06-30 |  | 210000 | 210000 |  | CGN |  |  |  | 210000 | 100% |  |  | 0 | Complete
WATER | 338 | Leshau - Supply of 4No 10m3 plastic tanks to water groups | Water storage tanks | Enhanced water supply | 100HH |  | NDARAGWA | LESHAU PONDO |  |  | 2015-07-01 | 2016-06-30 |  | 420000 | 420000 |  | CGN |  |  |  | 420000 | 100% |  |  | 0 | Complete
WATER | 339 | Leshau - Supply of pipes for Leshau Karagoine water project | water distribution | Enhanced water supply | 85HH |  | NDARAGWA | LESHAU PONDO |  |  | 2015-07-01 | 2016-06-30 |  | 2451000 | 2451000 |  | CGN |  |  |  | 2451000 | 100% |  |  | 0 | Complete
WATER | 340 | Leshau - Supply of pipes for Mathingira Girls pipeline project | water distribution | Enhanced water supply | 65HH |  | NDARAGWA | LESHAU PONDO |  |  | 2015-07-01 | 2016-06-30 |  | 174300 | 174300 |  | CGN |  |  |  | 174300 | 100% |  |  | 0 | Complete
WATER | 341 | Shamata - 50m3 masonry tank at Canary for Kirima water project | WATER STORAGE TANK | Enhanced water supply | 100HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 1199967 | 1199967 |  | CGN |  |  |  | 1199967 | 100% |  |  | 0 | Complete
WATER | 342 | Shamata -Pipe laying at Kirima water project | water distribution | Enhanced water supply | 120HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 2115707 | 2115707 |  | CGN |  |  |  | 2115707 | 100% |  |  | 0 | Complete
WATER | 343 | Shamata -Supply of pipes and fittings for Kirima water project | water distribution | Enhanced water supply | 110HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 640000 | 640000 |  | CGN |  |  |  | 640000 | 100% |  |  | 0 | Complete
WATER | 344 | Shamata -50m3 masonry tank at Kihuha borehole water project | STORAGE TANK | Enhanced water supply | 85HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 1203568 | 1203568 |  | CGN |  |  |  | 1203568 | 100% |  |  | 0 | Complete
WATER | 345 | Shamata -50m3 masonry tank at Kiambogo for Kirima water project | STORAGE TANK | Enhanced water supply | 108HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 1197403 | 1197403 |  | CGN |  |  |  | 1197403 | 100% |  |  | 0 | Complete
WATER | 346 | Shamata -Construction of Pesi II intake | WATER INTAKE | Enhanced water supply | 200HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 1511951 | 1511951 |  | CGN |  |  |  | 1511951 | 100% |  |  | 0 | Complete
WATER | 347 | Shamata -Supply of pipes and laying at Kaheho (Kirima) water project | water distribution | Enhanced water supply | 150HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 1050410 | 1050410 |  | CGN |  |  |  | 1050410 | 100% |  |  | 0 | Complete
WATER | 348 | Shamata -Supply of pipes to Ndararua water project | water distribution | Enhanced water supply | 120HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 783000 | 783000 |  | CGN |  |  |  | 783000 | 100% |  |  | 0 | Complete
WATER | 349 | Shamata -Roofing of Wihote 225m3 tank | WATER STORAGE | Enhanced water supply | 100HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 1398285 | 1398285 |  | CGN |  |  |  | 1398285 | 100% |  |  | 0 | Complete
WATER | 350 | Shamata -Rehabilitation of Ndararua water project | WATER INTAKE/SPRING | Enhanced water supply | 120HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 1548791 | 1548791 |  | CGN |  |  |  | 1548791 | 100% |  |  | 0 | Complete
WATER | 351 | Shamata -Supply of pipes and laying at Kirima water project | water distribution | Enhanced water supply | 106HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 868250 | 868250 |  | CGN |  |  |  | 868250 | 100% |  |  | 0 | Complete
WATER | 352 | Shamata -Supply of pipes to Subuku Self Help water project | water distribution | Enhanced water supply | 88HH |  | NDARAGWA | CENTRAL |  |  | 2015-07-01 | 2016-06-30 |  | 1144200 | 1144200 |  | CGN |  |  |  | 1144200 | 100% |  |  | 0 | Complete
WATER | 353 | Shamata -Supply of pipes to Githima Mwihoko water project | water distribution | Enhanced water supply | 100HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 222000 | 222000 |  | CGN |  |  |  | 222000 | 100% |  |  | 0 | Complete
WATER | 354 | Shamata -Pipe laying and installation of fittings at Kirima water project | water distribution | Enhanced water supply | 80HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 1894667 | 1894667 |  | CGN |  |  |  | 1894667 | 100% |  |  | 0 | Complete
WATER | 355 | Shamata -50m3 masonry tank at Waking'ethua for Kirima water project | STORAGE TANK | Enhanced water supply | 105HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 1288920 | 1288920 |  | CGN |  |  |  | 1288920 | 100% |  |  | 0 | Complete
WATER | 356 | Shamata -Supply of pipes and fittings to Kirima water project | water distribution | Enhanced water supply | 100HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 841600 | 841600 |  | CGN |  |  |  | 841600 | 100% |  |  | 0 | Complete
WATER | 357 | Shamata -Supply of Bamboo tree seedlings to Ndararua water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 420000 | 420000 |  | CGN |  |  |  | 420000 | 100% |  |  | 0 | Complete
WATER | 358 | Central - Supply of pipes and fittings to Simbara Sabra water project | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | CENTRAL |  |  | 2015-07-01 | 2016-06-30 |  | 174000 | 174000 |  | CGN |  |  |  | 174000 | 100% |  |  | 0 | Complete
WATER | 359 | Central -Supply of pipes and fittings for Mutara irrigation project | water distribution | Enhanced water supply | 90HH |  | NDARAGWA | CENTRAL |  |  | 2015-07-01 | 2016-06-30 |  | 1549050 | 1549050 |  | CGN |  |  |  | 1549050 | 100% |  |  | 0 | Complete
WATER | 360 | SHAMATA -Pipe laying and installation of fittings at Kilimanjaro water project | water distribution | Enhanced water supply | 65HH |  | NDARAGWA | SHAMATA |  |  | 2015-07-01 | 2016-06-30 |  | 2025726 | 2025726 |  | CGN |  |  |  | 2025726 | 100% |  |  | 0 | Complete
WATER | 361 | Central -Construction of Gathimaki intake | WATER INTAKE | Enhanced water supply | 250HH |  | NDARAGWA | CENTRAL |  |  | 2015-07-01 | 2016-06-30 |  | 2098175 | 2098175 |  | CGN |  |  |  | 2098175 | 100% |  |  | 0 | Complete
WATER | 362 | Central -Pipe laying and installation of fittings at Kihara Lowdor water project | water distribution | Enhanced water supply | 110HH |  | NDARAGWA | CENTRAL |  |  | 2015-07-01 | 2016-06-30 |  | 1377078 | 1377078 |  | CGN |  |  |  | 1377078 | 100% |  |  | 0 | Complete
WATER | 363 | Central -50m3 masonry tank at Subuku | STORAGE TANK | Enhanced water supply | 100HH |  | NDARAGWA | CENTRAL |  |  | 2015-07-01 | 2016-06-30 |  | 1292830 | 1292830 |  | CGN |  |  |  | 1292830 | 100% |  |  | 0 | Complete
WATER | 364 | Central -50m3 masonry tank at Kanyagia | STORAGE TANK | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2015-07-01 | 2016-06-30 |  | 1293566 | 1293566 |  | CGN |  |  |  | 1293566 | 100% |  |  | 0 | Complete
WATER | 365 | Geta - Supply of pipes and fittings to Kangurunga water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 426970 | 426970 |  | CGN |  |  |  | 426970 | 100% |  |  | 0 | Complete
WATER | 366 | Geta -Supply of pipes and laying and installation of fitting at Kirima water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 749960 | 749960 |  | CGN |  |  |  | 749960 | 100% |  |  | 0 | Complete
WATER | 367 | Geta -Supply of pipes and fittings to Michukia water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 652560 | 652560 |  | CGN |  |  |  | 652560 | 100% |  |  | 0 | Complete
WATER | 368 | Geta -Supply of pipes and laying and installation of fitting at Makianyo water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 272840 | 272840 |  | CGN |  |  |  | 272840 | 100% |  |  | 0 | Complete
WATER | 369 | Geta -Supply of pipes and laying and installation of fitting at Mbiriti water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 433220 | 433220 |  | CGN |  |  |  | 433220 | 100% |  |  | 0 | Complete
WATER | 370 | Geta -Supply of pipes and laying and installation of fitting at Marimu water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 541700 | 541700 |  | CGN |  |  |  | 541700 | 100% |  |  | 0 | Complete
WATER | 371 | Geta -Supply of pipes and laying and installation of fitting at Kagongo water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 408350 | 408350 |  | CGN |  |  |  | 408350 | 100% |  |  | 0 | Complete
WATER | 372 | Geta -Supply of pipes and fittings to Mikeu water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 444400 | 444400 |  | CGN |  |  |  | 444400 | 100% |  |  | 0 | Complete
WATER | 373 | Geta -50m3 masonry tank at Kiambogo | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1197055 | 1197055 |  | CGN |  |  |  | 1197055 | 100% |  |  | 0 | Complete
WATER | 374 | Geta -100m3 masonry tank at Geta town | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1799299 | 1799299 |  | CGN |  |  |  | 1799299 | 100% |  |  | 0 | Complete
WATER | 375 | Geta -50m3 masonry tank at Rutumba | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1185256 | 1185256 |  | CGN |  |  |  | 1185256 | 100% |  |  | 0 | Complete
WATER | 376 | Geta -50m3 masonry tank at Makumbi | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1292623 | 1292623 |  | CGN |  |  |  | 1292623 | 100% |  |  | 0 | Complete
WATER | 377 | Geta -100m3 masonry tank at Kiambogo | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1799820 | 1799820 |  | CGN |  |  |  | 1799820 | 100% |  |  | 0 | Complete
WATER | 378 | Githioro - Supply of pipes and fittings for Muhonia Turasha water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1450700 | 1450700 |  | CGN |  |  |  | 1450700 | 100% |  |  | 0 | Complete
WATER | 379 | Githioro - Construction of Githioro intake | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1468757 | 1468757 |  | CGN |  |  |  | 1468757 | 100% |  |  | 0
WATER | 380 | Githioro - Supply of pipes and laying and installation of fitting at Mawingu water project | water distribution | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 1720000 | 1720000 |  | CGN |  |  |  | 1720000 | 100% |  |  | 0 | Complete
WATER | 381 | North Kinangop - 50m3 masonry tank at Gatamaiyu | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2015-07-01 | 2016-06-30 |  | 1197099 | 1197099 |  | CGN |  |  |  | 1197099 | 100% |  |  | 0 | Complete
WATER | 382 | North Kinangop - Supply and construction of 2No. tank towers at Kikanamuku water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2015-07-01 | 2016-06-30 |  | 1700000 | 1700000 |  | CGN |  |  |  | 1700000 | 100% |  |  | 0 | Complete
WATER | 383 | North Kinangop - Supply of pipes to (KRM) Kwambekenya water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2015-07-01 | 2016-06-30 |  | 994460 | 994460 |  | CGN |  |  |  | 994460 | 100% |  |  | 0 | Complete
WATER | 384 | North Kinangop - Supply of 4No 10m3 plastic tanks to Kikanamuku water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2015-07-01 | 2016-06-30 |  | 420000 | 420000 |  | CGN |  |  |  | 420000 | 100% |  |  | 0 | Complete
WATER | 385 | North Kinangop - Supply of pipes and fittings for Karima 410 bridge water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2015-07-01 | 2016-06-30 |  | 560150 | 560150 |  | CGN |  |  |  | 560150 | 100% |  |  | 0 | Complete
WATER | 386 | North Kinangop - 100m3 masonry tank at Tia Wira water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2015-07-01 | 2016-06-30 |  | 1799805 | 1799805 |  | CGN |  |  |  | 1799805 | 100% |  |  | 0 | Complete
WATER | 387 | North Kinangop - 50m3 masonry tank at Tia Wira water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2015-07-01 | 2016-06-30 |  | 1197558 | 1197558 |  | CGN |  |  |  | 1197558 | 100% |  |  | 0 | Complete
WATER | 388 | North Kinangop - Supply of pipes and fittings for Tia Wira water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2015-07-01 | 2016-06-30 |  | 940520 | 940520 |  | CGN |  |  |  | 940520 | 100% |  |  | 0 | Complete
WATER | 389 | North Kinangop - Supply of 1No 10m3 plastic tank to Karima water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2015-07-01 | 2016-06-30 |  | 105000 | 105000 |  | CGN |  |  |  | 105000 | 100% |  |  | 0 | Complete
WATER | 390 | Murungaru - Supply of pipes and fittings for Muhonia Turasha water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2015-07-01 | 2016-06-30 |  | 1495000 | 1495000 |  | CGN |  |  |  | 1495000 | 100% |  |  | 0 | Complete
WATER | 391 | Murungaru - Supply of pipes and fittings to Mumui, Mikaro, Mukungi water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2015-07-01 | 2016-06-30 |  | 1817500 | 1817500 |  | CGN |  |  |  | 1817500 | 100% |  |  | 0 | Complete
WATER | 392 | Engineer - Desilting of Kinja intake | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 544180 | 544180 |  | CGN |  |  |  | 544180 | 100% |  |  | 0 | Complete
WATER | 393 | Engineer -Supply of 48m3 steel tank on a 12m high tower at Faru borehole water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 1800000 | 1800000 |  | CGN |  |  |  | 1800000 | 100% |  |  | 0 | Complete
WATER | 394 | Engineer -Drilling of production borehole at Weru primary school | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 2049915 | 2049915 |  | CGN |  |  |  | 2049915 | 100% |  |  | 0 | Complete
WATER | 395 | Engineer -Supply and laying of pipes at Itomboya water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 2086960 | 2086960 |  | CGN |  |  |  | 2086960 | 100% |  |  | 0 | Complete
WATER | 396 | Engineer -100m3 masonry tank at Itomboya water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 1795964 | 1795964 |  | CGN |  |  |  | 1795964 | 100% |  |  | 0 | Complete
WATER | 397 | Engineer -100m3 masonry tank at Kaimba hill | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 1797781 | 1797781 |  | CGN |  |  |  | 1797781 | 100% |  |  | 0 | Complete
WATER | 398 | Engineer -100m3 masonry tank at Gachichio water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 1799348 | 1799348 |  | CGN |  |  |  | 1799348 | 100% |  |  | 0 | Complete
WATER | 399 | Engineer -Supply of 48m3 steel tank on a 12m high tower at Manyatta borehole water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 1811150 | 1811150 |  | CGN |  |  |  | 1811150 | 100% |  |  | 0 | Complete
WATER | 400 | Engineer -Supply and laying of pipes at Raitha Kahuru water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 2730020 | 2730020 |  | CGN |  |  |  | 2730020 | 100% |  |  | 0 | Complete
WATER | 401 | Engineer -Hydrogeological survey for Faru borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 80000 | 80000 |  | CGN |  |  |  | 80000 | 100% |  |  | 0 | Complete
WATER | 402 | Engineer -Supply of10m3 plastic water tank and roof harvesting for Kamunyaka primary school | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2015-07-01 | 2016-06-30 |  | 357937 | 357937 |  | CGN |  |  |  | 357937 | 100% |  |  | 0 | Complete
WATER | 403 | Gathara - Supply of 6No 10m3 plastic tanks to water groups | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2015-07-01 | 2016-06-30 |  | 630000 | 630000 |  | CGN |  |  |  | 630000 | 100% |  |  | 0 | Complete
WATER | 404 | Gathara -Supply of pipes and fittings for Kinja water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2015-07-01 | 2016-06-30 |  | 1316000 | 1316000 |  | CGN |  |  |  | 1316000 | 100% |  |  | 0 | Complete
WATER | 405 | Gathara -Supply of pipes and fittings to Mutamaiyu water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2015-07-01 | 2016-06-30 |  | 952000 | 952000 |  | CGN |  |  |  | 952000 | 100% |  |  | 0 | Complete
WATER | 406 | Githabai - Drilling of production borehole at Koinange area | water distribution |  |  |  | Njabini | Githabai |  |  | 2015-07-01 | 2016-06-30 |  | 2096745 | 2096745 |  | CGN |  |  |  | 2096745 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 407 | Githabai - Drilling of production borehole at Roof House area | water distribution |  |  |  | Njabini | Githabai |  |  | 2015-07-01 | 2016-06-30 |  | 1676808 | 1676808 |  | CGN |  |  |  | 1676808 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 408 | Githabai - Supply and laying pipes and installation of fittings at Heni borehole water project | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2015-07-01 | 2016-06-30 |  | 3541350 | 3541350 |  | CGN |  |  |  | 3541350 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, care is being taken to prevent soil erosion and contamination during trenching and pipe laying. Socially, public consultations were held to ensure community involvement and acceptance. Occupational health and safety are being addressed through the provision of personal protective equipment (PPE), safety training for workers, and clear site signage. Gender concerns are being mitigated by ensuring women participate in decision-making processes and benefit equally from the project outcomes. A grievance redress mechanism is in place to handle any emerging concerns.
WATER | 409 | Githabai - Supply and laying pipes and installation of fittings at Koinange borehole water project | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2015-07-01 | 2016-06-30 |  | 1478400 | 1478400 |  | CGN |  |  |  | 1478400 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 410 | Githabai - Supply of pipes and fittings to Kagiiki water project | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2015-07-01 | 2016-06-30 |  | 117600 | 117600 |  | CGN |  |  |  | 117600 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 411 | Githabai - Hydrogeological survey for Koinange borehole | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2015-07-01 | 2016-06-30 |  | 95000 | 95000 |  | CGN |  |  |  | 95000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include minimizing environmental disturbance during survey activities, ensuring occupational health and safety through provision of personal protective equipment (PPE), involving the local community to address social concerns, promoting gender inclusion in consultations, and establishing a grievance redress mechanism to manage complaints promptly and fairly.
WATER | 412 | Githabai - Hydrogeological survey for Heni borehole |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2015-07-01 | 2016-06-30 |  | 75000 | 75000 |  | CGN |  |  |  | 75000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include minimizing environmental disturbance during survey activities, ensuring occupational health and safety through provision of personal protective equipment (PPE), involving the local community to address social concerns, promoting gender inclusion in consultations, and establishing a grievance redress mechanism to manage complaints promptly and fairly.
WATER | 413 | Nyakio - Drilling of production borehole at Ndongonye (Kwa Haraka) |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2015-07-01 | 2016-06-30 |  | 1579725 | 1579725 |  | CGN |  |  |  | 1579725 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 414 | Nyakio -Supply of 6No 5m3 plastic tanks to institutions |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2015-07-01 | 2016-06-30 |  | 300000 | 300000 |  | CGN |  |  |  | 300000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include ensuring environmentally sound transport and installation practices to avoid site contamination, engaging beneficiary institutions to address social and gender inclusion concerns, using appropriate lifting and handling procedures to safeguard workers' health and safety, and applying a transparent and inclusive process in tank allocation to promote equity and community trust.
WATER | 415 | Nyakio -Supply of 2No 10m3 plastic tanks to institutions |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2015-07-01 | 2016-06-30 |  | 210000 | 210000 |  | CGN |  |  |  | 210000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include ensuring environmentally sound transport and installation practices to avoid site contamination, engaging beneficiary institutions to address social and gender inclusion concerns, using appropriate lifting and handling procedures to safeguard workers' health and safety, and applying a transparent and inclusive process in tank allocation to promote equity and community trust.
WATER | 416 | Nyakio -100m3 masonry tank for Wachira water project |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2015-07-01 | 2016-06-30 |  | 1797767 | 1797767 |  | CGN |  |  |  | 1797767 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures taken include proper siting and construction to minimize environmental degradation, community sensitization and engagement to promote inclusivity and address social and gender equity, enforcement of occupational health and safety protocols at the construction site (such as provision of PPE and trained personnel), and ensuring that the project benefits are equitably distributed among all community members, including women and vulnerable groups.
WATER | 417 | Nyakio -Supply and laying pipes and installation of fittings at Wachira water project | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2015-07-01 | 2016-06-30 |  | 3731910 | 3731910 |  | CGN |  |  |  | 3731910 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, the project has ensured minimal disruption through proper waste disposal, prevention of soil erosion, and protection of surrounding vegetation. Socially, community sensitization and stakeholder engagement have been undertaken to promote transparency and resolve any emerging conflicts. To address occupational health and safety, workers have been equipped with personal protective equipment, trained on safe practices, and supervised throughout the construction phase, with first aid support readily available. On gender, the project promotes inclusivity by encouraging the participation of women and ensuring that the benefits of the project reach all members of the community, including vulnerable and marginalized groups.
WATER | 418 | Njabini - Supply and laying pipes and installation of fittings at Soilo Ngwataniro water project | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2015-07-01 | 2016-06-30 |  | 9438700 | 9438700 |  | CGN |  |  |  | 9438700 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, the project has ensured minimal disruption through proper waste disposal, prevention of soil erosion, and protection of surrounding vegetation. Socially, community sensitization and stakeholder engagement have been undertaken to promote transparency and resolve any emerging conflicts. To address occupational health and safety, workers have been equipped with personal protective equipment, trained on safe practices, and supervised throughout the construction phase, with first aid support readily available. On gender, the project promotes inclusivity by encouraging the participation of women and ensuring that the benefits of the project reach all members of the community, including vulnerable and marginalized groups.
WATER | 419 | Njabini -Supply and laying pipes and installation of fittings at Kiburu water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2015-07-01 | 2016-06-30 |  | 2511844 | 2511844 |  | CGN |  |  |  | 2511844 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, the project has ensured minimal disruption through proper waste disposal, prevention of soil erosion, and protection of surrounding vegetation. Socially, community sensitization and stakeholder engagement have been undertaken to promote transparency and resolve any emerging conflicts. To address occupational health and safety, workers have been equipped with personal protective equipment, trained on safe practices, and supervised throughout the construction phase, with first aid support readily available. On gender, the project promotes inclusivity by encouraging the participation of women and ensuring that the benefits of the project reach all members of the community, including vulnerable and marginalized groups.
WATER | 420 | Njabini -100m3 masonry tank for Kiburu water project |  | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2015-07-01 | 2016-06-30 |  | 1799628 | 1799628 |  | CGN |  |  |  | 1799628 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures taken include proper siting and construction to minimize environmental degradation, community sensitization and engagement to promote inclusivity and address social and gender equity, enforcement of occupational health and safety protocols at the construction site (such as provision of PPE and trained personnel), and ensuring that the project benefits are equitably distributed among all community members, including women and vulnerable groups.
WATER | 421 | Njabini -Supply and laying pipes and installation of fittings at Karuang'i water project |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2015-07-01 | 2016-06-30 |  | 1045580 | 1045580 |  | CGN |  |  |  | 1045580 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, the project has ensured minimal disruption through proper waste disposal, prevention of soil erosion, and protection of surrounding vegetation. Socially, community sensitization and stakeholder engagement have been undertaken to promote transparency and resolve any emerging conflicts. To address occupational health and safety, workers have been equipped with personal protective equipment, trained on safe practices, and supervised throughout the construction phase, with first aid support readily available. On gender, the project promotes inclusivity by encouraging the participation of women and ensuring that the benefits of the project reach all members of the community, including vulnerable and marginalized groups.
WATER | 422 | Njabini -Hydrogeological survey for Gitwe borehole |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2015-07-01 | 2016-06-30 |  | 75000 | 75000 |  | CGN |  |  |  | 75000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include minimizing environmental disturbance during survey activities, ensuring occupational health and safety through provision of personal protective equipment (PPE), involving the local community to address social concerns, promoting gender inclusion in consultations, and establishing a grievance redress mechanism to manage complaints promptly and fairly.
WATER | 423 | Njabini -Construction Chania river intake |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2015-07-01 | 2016-06-30 |  | 1873907 | 1873907 |  | CGN |  |  |  | 1873907 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, protective measures such as controlled excavation, stabilization of riverbanks, and proper waste disposal have been applied to prevent degradation and preserve aquatic ecosystems. Socially, local community engagement and consultation were conducted to foster inclusivity, minimize conflicts, and ensure shared project ownership. On occupational health and safety, the workforce has been provided with appropriate personal protective equipment (PPE), safety training, and medical support to reduce risks during construction. Gender considerations were addressed by promoting equitable participation of women in project benefits and activities, and safeguarding the rights and safety of vulnerable groups throughout the project lifecycle.
WATER | 424 | Magumu - Supply of submersible pump and control panel for Mutonyora 'C' borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 1985000 | 1985000 |  | CGN |  |  |  | 1985000 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental risks, measures such as appropriate siting of equipment, waste management, and protection of water sources have been enforced. Social mitigation involved community sensitization and engagement to enhance local participation and address potential concerns. Occupational health and safety risks have been mitigated by ensuring the use of personal protective equipment (PPE), adherence to safe installation procedures, and provision of safety training to workers. Gender considerations included promoting inclusivity in project participation, ensuring that women and vulnerable groups benefit from improved water access, and safeguarding against any form of discrimination or gender-based violence during implementation.
WATER | 425 | Magumu -Supply of submersible pump and control panel for Mutonyora 'B' borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 1965000 | 1965000 |  | CGN |  |  |  | 1965000 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental risks, measures such as appropriate siting of equipment, waste management, and protection of water sources have been enforced. Social mitigation involved community sensitization and engagement to enhance local participation and address potential concerns. Occupational health and safety risks have been mitigated by ensuring the use of personal protective equipment (PPE), adherence to safe installation procedures, and provision of safety training to workers. Gender considerations included promoting inclusivity in project participation, ensuring that women and vulnerable groups benefit from improved water access, and safeguarding against any form of discrimination or gender-based violence during implementation.
WATER | 426 | Magumu -Supply and construction of tank tower at Mutonyora 'C' borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 710000 | 710000 |  | CGN |  |  |  | 710000 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental impacts, proper waste disposal practices, noise and dust suppression, and site restoration measures were adopted. Social safeguards included community consultations, securing land use consent, and ensuring local involvement to promote ownership. Occupational health and safety risks were addressed by enforcing the use of personal protective equipment (PPE), ensuring secure scaffolding and safe construction practices, and training workers on emergency response. Gender-sensitive strategies were applied to ensure equitable benefit-sharing, participation of women in project-related activities, and protection against gender-based discrimination and exploitation throughout implementation.
WATER | 427 | Magumu -Supply and construction of tank tower at Mutonyora 'B' borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 710000 | 710000 |  | CGN |  |  |  | 710000 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental impacts, proper waste disposal practices, noise and dust suppression, and site restoration measures were adopted. Social safeguards included community consultations, securing land use consent, and ensuring local involvement to promote ownership. Occupational health and safety risks were addressed by enforcing the use of personal protective equipment (PPE), ensuring secure scaffolding and safe construction practices, and training workers on emergency response. Gender-sensitive strategies were applied to ensure equitable benefit-sharing, participation of women in project-related activities, and protection against gender-based discrimination and exploitation throughout implementation
WATER | 428 | Magumu -Supply of 2No 10m3 plastic tanks to Mutonyora 'B' and 'C' boreholes |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 210000 | 210000 |  | CGN |  |  |  | 210000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include ensuring environmentally sound transport and installation practices to avoid site contamination, engaging beneficiary institutions to address social and gender inclusion concerns, using appropriate lifting and handling procedures to safeguard workers' health and safety, and applying a transparent and inclusive process in tank allocation to promote equity and community trust.
WATER | 429 | Magumu -Installation of submersible pump at Mutonyora 'C' borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 144900 | 144900 |  | CGN |  |  |  | 144900 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental risks, measures such as appropriate siting of equipment, waste management, and protection of water sources have been enforced. Social mitigation involved community sensitization and engagement to enhance local participation and address potential concerns. Occupational health and safety risks have been mitigated by ensuring the use of personal protective equipment (PPE), adherence to safe installation procedures, and provision of safety training to workers. Gender considerations included promoting inclusivity in project participation, ensuring that women and vulnerable groups benefit from improved water access, and safeguarding against any form of discrimination or gender-based violence during implementation.
WATER | 430 | Magumu -Installation of submersible pump at Mutonyora 'B' borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 144375 | 144375 |  | CGN |  |  |  | 144375 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental risks, measures such as appropriate siting of equipment, waste management, and protection of water sources have been enforced. Social mitigation involved community sensitization and engagement to enhance local participation and address potential concerns. Occupational health and safety risks have been mitigated by ensuring the use of personal protective equipment (PPE), adherence to safe installation procedures, and provision of safety training to workers. Gender considerations included promoting inclusivity in project participation, ensuring that women and vulnerable groups benefit from improved water access, and safeguarding against any form of discrimination or gender-based violence during implementation.
WATER | 431 | Magumu -Construction of borehole control panel house at Mutonyora 'C' borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 479000 | 479000 |  | CGN |  |  |  | 479000 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental risks, site clearing was done responsibly, construction waste was properly managed, and water conservation practices were emphasized. Socially, stakeholder engagement was conducted to secure local support and minimize potential conflict. On occupational health and safety, workers were provided with appropriate PPE, trained on site safety procedures, and supervised to ensure compliance with safety standards. Gender considerations were addressed by promoting inclusive participation, safeguarding against harassment, and ensuring that both women and men benefit equally from the project.
WATER | 432 | Magumu -Construction of borehole control panel house at Mutonyora 'B' borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 479500 | 479500 |  | CGN |  |  |  | 479500 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental risks, site clearing was done responsibly, construction waste was properly managed, and water conservation practices were emphasized. Socially, stakeholder engagement was conducted to secure local support and minimize potential conflict. On occupational health and safety, workers were provided with appropriate PPE, trained on site safety procedures, and supervised to ensure compliance with safety standards. Gender considerations were addressed by promoting inclusive participation, safeguarding against harassment, and ensuring that both women and men benefit equally from the project.
WATER | 433 | Magumu -Construction of water kiosk Mutonyora 'B' borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 529320 | 529320 |  | CGN |  |  |  | 529320 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental risks, measures were taken to manage construction waste, avoid water pollution, and minimize land disturbance. Social safeguards included community engagement, sensitization on project benefits, and grievance redress mechanisms. Occupational health and safety was addressed through provision of personal protective equipment (PPE), safety briefings, and site supervision. Gender aspects were integrated by promoting equitable access to water services, ensuring safe spaces around the kiosk, and encouraging participation of women in water user committees.
WATER | 434 | Magumu -Supply of pipes and fittings to Mutonyora 'B' and 'C' boreholes | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 742200 | 742200 |  | CGN |  |  |  | 742200 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, the project has ensured minimal disruption through proper waste disposal, prevention of soil erosion, and protection of surrounding vegetation. Socially, community sensitization and stakeholder engagement have been undertaken to promote transparency and resolve any emerging conflicts. To address occupational health and safety, workers have been equipped with personal protective equipment, trained on safe practices, and supervised throughout the construction phase, with first aid support readily available. On gender, the project promotes inclusivity by encouraging the participation of women and ensuring that the benefits of the project reach all members of the community, including vulnerable and marginalized groups.
WATER | 435 | Magumu -Drilling of production borehole at Magumu Junction |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 2925877 | 2925877 |  | CGN |  |  |  | 2925877 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 436 | Magumu -Supply and laying pipes and installation of fittings at Kenton water project |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 2047367 | 2047367 |  | CGN |  |  |  | 2047367 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, the project has ensured minimal disruption through proper waste disposal, prevention of soil erosion, and protection of surrounding vegetation. Socially, community sensitization and stakeholder engagement have been undertaken to promote transparency and resolve any emerging conflicts. To address occupational health and safety, workers have been equipped with personal protective equipment, trained on safe practices, and supervised throughout the construction phase, with first aid support readily available. On gender, the project promotes inclusivity by encouraging the participation of women and ensuring that the benefits of the project reach all members of the community, including vulnerable and marginalized groups.
WATER | 437 | Magumu -Drilling of production borehole at Mutonyora ‘C’ |  | Enhanced water supply |  |  |  | Magumu |  |  | 2015-07-01 | 2016-06-30 |  | 2207940 | 2207940 |  | CGN |  |  |  | 2207940 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 438 | Karau - Storm water drainage for Olkalou town |  | Enhanced water supply | [6 empty] | 2015-07-01 | 2016-06-30 |  | 20000000 | 20000000 |  | CGN |  |  |  | 20000000 | 100% |  |  | 0 | Ongoing
WATER | 439 | Central - Kanyagia borehole | BOREHOLE | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 85000 | 85000 |  | CGN |  |  |  | 85000 | 100% |  |  | 0 | Complete
WATER | 440 | Central -Ndaragwa Banda pipeline | water distribution | Enhanced water supply | 75HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 135000 | 135000 |  | CGN |  |  |  | 135000 | 100% |  |  | 0 | Complete
WATER | 441 | Central -Simbara Sabra water project | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 185750 | 185750 |  | CGN |  |  |  | 185750 | 100% |  |  | 0 | Complete
WATER | 442 | Central -Gathamaki water project | water distribution | Enhanced water supply | 250HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 519970 | 519970 |  | CGN |  |  |  | 519970 | 100% |  |  | 0 | Complete
WATER | 443 | Central -50m3 masonry storage tank at Subego | STORAGE TANK | Enhanced water supply | 75HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 1241450 | 1241450 |  | CGN |  |  |  | 1241450 | 100% |  |  | 0 | Complete
WATER | 444 | Central -Suguroi water project | INTAKE AND WATER DISTRIBUTION | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 1284800 | 1284800 |  | CGN |  |  |  | 1284800 | 100% |  |  | 0 | Complete
WATER | 445 | Central -Kihara Lodwar water project | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 1298250 | 1298250 |  | CGN |  |  |  | 1298250 | 100% |  |  | 0 | Complete
WATER | 446 | Central -Ndaragwa Banda water project | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 1843030 | 1843030 |  | CGN |  |  |  | 1843030 | 100% |  |  | 0 | Complete
WATER | 447 | Central -Suguroi water project | water distribution | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 2283171 | 2283171 |  | CGN |  |  |  | 2283171 | 100% |  |  | 0 | Complete
WATER | 448 | Central -Gathamaki water project | water distribution | Enhanced water supply | 250HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 2528860 | 2528860 |  | CGN |  |  |  | 2528860 | 100% |  |  | 0 | Complete
WATER | 449 | Central -Kanyagia borehole | BOREHOLE | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 2797316 | 2797316 |  | CGN |  |  |  | 2797316 | 100% |  |  | 0 | Complete
WATER | 450 | Central -Thuku Dam | WATER STORAGE | Enhanced water supply | 50HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 3499267 | 3499267 |  | CGN |  |  |  | 3499267 | 100% |  |  | 0 | Complete
WATER | 451 | Central -Suguroi water project | water distribution | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 3846000 | 3846000 |  | CGN |  |  |  | 3846000 | 100% |  |  | 0 | Complete
WATER | 452 | Central -Supply of 230 litres capacity plastic water tanks to public institutions | WATER STORAGE | Enhanced water supply | 10 INSTITUTIONS |  | NDARAGWA | CENTRAL |  |  | 2016-07-01 | 2017-06-30 |  | 3959100 | 3959100 |  | CGN |  |  |  | 3959100 | 100% |  |  | 0 | Complete
WATER | 453 | Charagita - Supply of 10m3 plastic water tanks to Matindiri and Munga primary schools | WATER HARVESTING | Enhanced water supply | 2 INSTITUTIONS |  | OLJOROOROK | CHARAGITA |  |  | 2016-07-01 | 2017-06-30 |  | 105000 | 105000 |  | CGN |  |  |  | 105000 | 100% |  |  | 0 | Complete
WATER | 454 | Charagita - Oraimutia water project surface pump | WATER INTAKE | Enhanced water supply | 150HH |  | OLJOROOROK | CHARAGITA |  |  | 2016-07-01 | 2017-06-30 |  | 105000 | 105000 |  | CGN |  |  |  | 105000 | 100% |  |  | 0 | Complete
WATER | 455 | Charagita - Supply of 10m3 plastic water tanks to Matindiri and Kagema primary schools | RAIN WATER HARVESTING- STORAGE | Enhanced water supply | 2 PRIMARYS SCHOOL |  | OLJOROOROK | CHARAGITA |  |  | 2016-07-01 | 2017-06-30 |  | 210000 | 210000 |  | CGN |  |  |  | 210000 | 100% |  |  | 0 | Complete
WATER | 456 | Charagita - Nyairoko - Matindiri water project | water distribution | Enhanced water supply | 100HH |  | OLJOROOROK | CHARAGITA |  |  | 2016-07-01 | 2017-06-30 |  | 385000 | 385000 |  | CGN |  |  |  | 385000 | 100% |  |  | 0 | Complete
WATER | 457 | Charagita - Gichaka spring protection | SPRING | Enhanced water supply | 50HH |  | OLJOROOROK | CHARAGITA |  |  | 2016-07-01 | 2017-06-30 |  | 2371705 | 2371705 |  | CGN |  |  |  | 2371705 | 100% |  |  | 0 | Complete
WATER | 458 | Charagita - Ruiru water project |  | Enhanced water supply | 150HH |  | OLJOROOROK | CHARAGITA |  |  | 2016-07-01 | 2017-06-30 |  | 2446345 | 2446345 |  | CGN |  |  |  | 2446345 | 100% |  |  | 0 | Complete
WATER | 459 | Charagita - Supply of a 210 litre capacity plastic tanks to public institutions | HAND WASHING | Enhanced water supply | 5 SCHOOLS |  | OLJOROOROK | CHARAGITA |  |  | 2016-07-01 | 2017-06-30 |  | 2850700 | 2850700 |  | CGN |  |  |  | 2850700 | 100% |  |  | 0 | Complete
WATER | 460 | Engineer - Itomboya borehole | water distribution | Enhanced water supply | 100HH | [5 empty] | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 461 | Engineer -Raitha Kahuru water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 190300 | 190300 |  | CGN |  |  |  | 190300 | 100% |  |  | 0 | Complete
WATER | 462 | Engineer -Weru (Central) primary school borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 213527 | 213527 |  | CGN |  |  |  | 213527 | 100% |  |  | 0 | Complete
WATER | 463 | Engineer -Itomboya borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 219028 | 219028 |  | CGN |  |  |  | 219028 | 100% |  |  | 0 | Complete
WATER | 464 | Engineer -Supply of 10m3 Plastic water tanks to Matundura primary school, Thindi, Kangutu, Highstar secondary school, Muti-ini secondary school and Kanyugi primary school | sanitation | Enhanced water supply | 4 SCHOOLS |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 525000 | 525000 |  | CGN |  |  |  | 525000 | 100% |  |  | 0 | Complete
WATER | 465 | Engineer -Small scale projects | water distribution | Enhanced water supply |  |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 773443 | 773443 |  | CGN |  |  |  | 773443 | 100% |  |  | 0 | Complete
WATER | 466 | Engineer -Faru Wandorokathi pipeline | water distribution | Enhanced water supply |  |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 1291400 | 1291400 |  | CGN |  |  |  | 1291400 | 100% |  |  | 0 | Complete
WATER | 467 | Engineer -Supply, installation of gutters and construction of 5 No. 10m3 plastic tank concrete platforms at Matundura Primary school,Thindi Highstar secondary school,Muti-ini secondary school,Kanyugi Primary school and Kangutu primary school | Roof harvesting | Enhanced water supply | 5 Schools |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 1319594 | 1319594 |  | CGN |  |  |  | 1319594 | 100% |  |  | 0 | Complete
WATER | 468 | Engineer -Supply and delivery of 300 No. 500Lts plastic water tanks to Weru women empowernet rain water harvesting | Roof harvesting | Enhanced water supply | 300HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 1650000 | 1650000 |  | CGN |  |  |  | 1650000 | 100% |  |  | 0 | Complete
WATER | 469 | Engineer -Engineer Level 4 Hospital and Law Courts / Kitiri water project | water storage tank | Enhanced water supply |  |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 1690469 | 1690469 |  | CGN |  |  |  | 1690469 | 100% |  |  | 0 | Complete
WATER | 470 | Engineer -100m3 masonry storage tank at Matura | water storage tank | Enhanced water supply |  |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 1852483 | 1852483 |  | CGN |  |  |  | 1852483 | 100% |  |  | 0 | Complete
WATER | 471 | Engineer -Landscaping and tree planting in schools in Muruaki/Kahuru | Landscaping and tree planting | Enhanced water supply | various schools |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 1975470 | 1975470 |  | CGN |  |  |  | 1975470 | 100% |  |  | 0 | Complete
WATER | 472 | Engineer -Elevated 48m3 pressed steel water tank on 12m high steel tower at Faru (Githima) borehole | water storage tank | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 2120010 | 2120010 |  | CGN |  |  |  | 2120010 | 100% |  |  | 0 | Complete
WATER | 473 | Engineer -Itomboya borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 2299994 | 2299994 |  | CGN |  |  |  | 2299994 | 100% |  |  | 0 | Complete
WATER | 474 | Engineer -Supply and delivery of 500 litre capacity plastic water tanks to Aged women empowerment rain water harvesting | Roof harvesting | Enhanced water supply | 500HH | [5 empty] | 2016-07-01 | 2017-06-30 |  | 2400000 | 2400000 |  | CGN |  |  |  | 2400000 | 100% |  |  | 0 | Complete
WATER | 475 | Engineer -Matundura water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 2719134 | 2719134 |  | CGN |  |  |  | 2719134 | 100% |  |  | 0 | Complete
WATER | 476 | Engineer -Gachichio Weru water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 2826010 | 2826010 |  | CGN |  |  |  | 2826010 | 100% |  |  | 0 | Complete
WATER | 477 | Engineer -Weru (Centre primary) borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 3031904 | 3031904 |  | CGN |  |  |  | 3031904 | 100% |  |  | 0 | Complete
WATER | 478 | Engineer -Muti-ini pipeline | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 3487429 | 3487429 |  | CGN |  |  |  | 3487429 | 100% |  |  | 0 | Complete
WATER | 479 | Engineer -Itomboya borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 3770000 | 3770000 |  | CGN |  |  |  | 3770000 | 100% |  |  | 0 | Complete
WATER | 480 | Engineer -Engineer Level 4 Hospital and Law Courts / Kitiri water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 3821500 | 3821500 |  | CGN |  |  |  | 3821500 | 100% |  |  | 0 | Complete
WATER | 481 | Gathanje - Ngengi borehole | BOREHOLE | Enhanced water supply | 50HH |  | OLJOROOROK | GATHANJE |  |  | 2016-07-01 | 2017-06-30 |  | 80000 | 80000 |  | CGN |  |  |  | 80000 | 100% |  |  | 0 | Complete
WATER | 482 | Gathanje -Boiman borehole | BOREHOLE | Enhanced water supply | 50HH |  | OLJOROOROK | GATHANJE |  |  | 2016-07-01 | 2017-06-30 |  | 253844 | 253844 |  | CGN |  |  |  | 253844 | 100% |  |  | 0 | Complete
WATER | 483 | Gathanje -Njoro borehole | BOREHOLE | Enhanced water supply | 50HH |  | OLJOROOROK | GATHANJE |  |  | 2016-07-01 | 2017-06-30 |  | 281400 | 281400 |  | CGN |  |  |  | 281400 | 100% |  |  | 0 | Complete
WATER | 484 | Gathanje -Madaraka borehole | BOREHOLE | Enhanced water supply | 50HH |  | OLJOROOROK | GATHANJE |  |  | 2016-07-01 | 2017-06-30 |  | 289013 | 289013 |  | CGN |  |  |  | 289013 | 100% |  |  | 0 | Complete
WATER | 485 | Gathanje -Boiman borehole | BOREHOLE | Enhanced water supply | 250HH |  | OLJOROOROK | GATHANJE |  |  | 2016-07-01 | 2017-06-30 |  | 374640 | 374640 |  | CGN |  |  |  | 374640 | 100% |  |  | 0 | Complete
WATER | 486 | Gathanje -Kambaa water project | BOREHOLE | Enhanced water supply | 50HH |  | OLJOROOROK | GATHANJE |  |  | 2016-07-01 | 2017-06-30 |  | 630000 | 630000 |  | CGN |  |  |  | 630000 | 100% |  |  | 0 | Complete
WATER | 487 | Gathanje -Boiman borehole | BOREHOLE | Enhanced water supply | 250HH |  | OLJOROOROK | GATHANJE |  |  | 2016-07-01 | 2017-06-30 |  | 925000 | 925000 |  | CGN |  |  |  | 925000 | 100% |  |  | 0 | Complete
WATER | 488 | Gathanje -Supply of Solar panels and accessories (Bosihu) | BOREHOLE | Enhanced water supply | 50HH |  | OLJOROOROK | GATHANJE |  |  | 2016-07-01 | 2017-06-30 |  | 1300500 | 1300500 |  | CGN |  |  |  | 1300500 | 100% |  |  | 0 | Complete
WATER | 489 | Gathanje -Huhoini borehole | BOREHOLE | Enhanced water supply | 100HH |  | OLJOROOROK | GATHANJE |  |  | 2016-07-01 | 2017-06-30 |  | 3136455 | 3136455 |  | CGN |  |  |  | 3136455 | 100% |  |  | 0 | Complete
WATER | 490 | Gathara -Haraka water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2016-07-01 | 2017-06-30 |  | 648175 | 648175 |  | CGN |  |  |  | 648175 | 100% |  |  | 0 | Complete
WATER | 491 | Gathara -Mbaruku water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2016-07-01 | 2017-06-30 |  | 749000 | 749000 |  | CGN |  |  |  | 749000 | 100% |  |  | 0 | Complete
WATER | 492 | Gathara -Mutamaiyu water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2016-07-01 | 2017-06-30 |  | 889125 | 889125 |  | CGN |  |  |  | 889125 | 100% |  |  | 0 | Complete
WATER | 493 | Gathara -Laigiri Water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2016-07-01 | 2017-06-30 |  | 996250 | 996250 |  | CGN |  |  |  | 996250 | 100% |  |  | 0 | Complete
WATER | 494 | Gathara -Supply and delivery of 10m3 plastic water tanks to public institutions | Sanitation | Enhanced water supply | Various schools |  | Kinangop | Gathaara |  |  | 2016-07-01 | 2017-06-30 |  | 1155000 | 1155000 |  | CGN |  |  |  | 1155000 | 100% |  |  | 0 | Complete
WATER | 495 | Gathara -Gathara water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2016-07-01 | 2017-06-30 |  | 1221950 | 1221950 |  | CGN |  |  |  | 1221950 | 100% |  |  | 0 | Complete
WATER | 496 | Gathara -Wendani water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2016-07-01 | 2017-06-30 |  | 1520400 | 1520400 |  | CGN |  |  |  | 1520400 | 100% |  |  | 0 | Complete
WATER | 497 | Gathara -100m3 masonry storage tank at Kinja water project | storage | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2016-07-01 | 2017-06-30 |  | 1792605 | 1792605 |  | CGN |  |  |  | 1792605 | 100% |  |  | 0 | Complete
WATER | 498 | Gatimu -Gatimu/Gikingi water project | water distribution | Enhanced water supply | 100HH |  | OLJOROOROK | GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 621060 | 621060 |  | CGN |  |  |  | 621060 | 100% |  |  | 0 | Complete
WATER | 499 | Gatimu -Njunu Hawa Ndunye line water project | water distribution | Enhanced water supply | 30HH |  | OLJOROOROK | GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 691493 | 691493 |  | CGN |  |  |  | 691493 | 100% |  |  | 0 | Complete
WATER | 500 | Gatimu -Njunu water project | water distribution | Enhanced water supply | 30HH |  | OLJOROOROK | GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 850000 | 850000 |  | CGN |  |  |  | 850000 | 100% |  |  | 0 | Complete
WATER | 501 | Gatimu -Njunu Hawa line water project | water distribution | Enhanced water supply | 25HH |  | OLJOROOROK | GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 867823 | 867823 |  | CGN |  |  |  | 867823 | 100% |  |  | 0 | Complete
WATER | 502 | Gatimu -Jericho line water project | water distribution | Enhanced water supply | 50HH |  | OLJOROOROK | GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 924935 | 924935 |  | CGN |  |  |  | 924935 | 100% |  |  | 0 | Complete
WATER | 503 | Gatimu -Kibathi water project | water distribution | Enhanced water supply | 75HH |  | OLJOROOROK | GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 1131372 | 1131372 |  | CGN |  |  |  | 1131372 | 100% |  |  | 0 | Complete
WATER | 504 | Gatimu -Kibathi Muhindi pipeline extensions | water distribution | Enhanced water supply | 50HH |  | OLJOROOROK | GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 1589203 | 1589203 |  | CGN |  |  |  | 1589203 | 100% |  |  | 0 | Complete
WATER | 505 | Gatimu -Njunu water project | water distribution | Enhanced water supply | 30HH |  | OLJOROOROK | GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 1782462 | 1782462 |  | CGN |  |  |  | 1782462 | 100% |  |  | 0 | Complete
WATER | 506 | Gatimu -Supply of pipes, fittings and 10m3 plastic water tank for Njunu, Gikingi and Matura water projects | water Storage distribution | Enhanced water supply | 50HH |  | OLJOROOROK | WERU/GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 280650 | 280650 |  | CGN |  |  |  | 280650 | 100% |  |  | 0 | Complete
WATER | 507 | Geta - Mihato borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 80000 | 80000 |  | CGN |  |  |  | 80000 | 100% |  |  | 0 | Complete
WATER | 508 | Geta - Kariua water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 207000 | 207000 |  | CGN |  |  |  | 207000 | 100% |  |  | 0 | Complete
WATER | 509 | Geta - Supply and delivery of 3 No. 10m3 plastic water tanks to public institutions |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 315000 | 315000 |  | CGN |  |  |  | 315000 | 100% |  |  | 0 | Complete
WATER | 510 | Geta - Kariani water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 340800 | 340800 |  | CGN |  |  |  | 340800 | 100% |  |  | 0 | Complete
WATER | 511 | Geta - Marimu water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 539250 | 539250 |  | CGN |  |  |  | 539250 | 100% |  |  | 0 | Complete
WATER | 512 | Geta - Gatondu water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 667274 | 667274 |  | CGN |  |  |  | 667274 | 100% |  |  | 0 | Complete
WATER | 513 | Geta - Rotuba water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 735700 | 735700 |  | CGN |  |  |  | 735700 | 100% |  |  | 0 | Complete
WATER | 514 | Geta - Mikeu, Kiriti and Geta town water projects | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1128390 | 1128390 |  | CGN |  |  |  | 1128390 | 100% |  |  | 0 | Complete
WATER | 515 | Geta - 50m3 masonry storage tank at Kiamugu water project |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1199996 | 1199996 |  | CGN |  |  |  | 1199996 | 100% |  |  | 0 | Complete
WATER | 516 | Geta - 50m3 masonry storage tank at Kagongo water project |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1292905 | 1292905 |  | CGN |  |  |  | 1292905 | 100% |  |  | 0 | Complete
WATER | 517 | Geta - Mihato borehole |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2789745 | 2789745 |  | CGN |  |  |  | 2789745 | 100% |  |  | 0 | Complete
WATER | 518 | Geta - Supply and delivery of 1000 No. 230 litre capacity plastic water tanks to public institutions |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 3500000 | 3500000 |  | CGN |  |  |  | 3500000 | 100% |  |  | 0 | Complete
WATER | 519 | Githabai - Koinange borehole | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2016-07-01 | 2017-06-30 |  | 274176 | 274176 |  | CGN |  |  |  | 274176 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 520 | Githabai -Koinange borehole | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2016-07-01 | 2017-06-30 |  | 857325 | 857325 |  | CGN |  |  |  | 857325 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 521 | Githabai -Koinange borehole | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2016-07-01 | 2017-06-30 |  | 1570000 | 1570000 |  | CGN |  |  |  | 1570000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 522 | Githabai -Elevated 30m3 pressed steel water tank on 12m high steel tower at Koinange borehole water project |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2016-07-01 | 2017-06-30 |  | 2398500 | 2398500 |  | CGN |  |  |  | 2398500 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental impacts, proper waste disposal practices, noise and dust suppression, and site restoration measures were adopted. Social safeguards included community consultations, securing land use consent, and ensuring local involvement to promote ownership. Occupational health and safety risks were addressed by enforcing the use of personal protective equipment (PPE), ensuring secure scaffolding and safe construction practices, and training workers on emergency response. Gender-sensitive strategies were applied to ensure equitable benefit-sharing, participation of women in project-related activities, and protection against gender-based discrimination and exploitation throughout implementation.
WATER | 523 | Githabai -Heni borehole | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2016-07-01 | 2017-06-30 |  | 3359974 | 3359974 |  | CGN |  |  |  | 3359974 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 524 | Githioro -Githioro water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 105000 | 105000 |  | CGN |  |  |  | 105000 | 100% |  |  | 0 | Complete
WATER | 525 | Githioro -Mawingo water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 375500 | 375500 |  | CGN |  |  |  | 375500 | 100% |  |  | 0 | Complete
WATER | 526 | Githioro -Muhonia Turasha water project sub mains | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2405755 | 2405755 |  | CGN |  |  |  | 2405755 | 100% |  |  | 0 | Complete
WATER | 527 | Githioro -Mawingo water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 3309603 | 3309603 |  | CGN |  |  |  | 3309603 | 100% |  |  | 0 | Complete
WATER | 528 | Kaimbaga - Bahati borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 529 | Kaimbaga - Mugathika Borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 530 | Kaimbaga - Kaimbaga water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 918800 | 918800 |  | CGN |  |  |  | 918800 | 100% |  |  | 0 | Complete
WATER | 531 | Kaimbaga - Kieni water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 999381 | 999381 |  | CGN |  |  |  | 999381 | 100% |  |  | 0 | Complete
WATER | 532 | Kaimbaga - Mugathika borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2410275 | 2410275 |  | CGN |  |  |  | 2410275 | 100% |  |  | 0 | Complete
WATER | 533 | Kaimbaga - Bahati borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2500890 | 2500890 |  | CGN |  |  |  | 2500890 | 100% |  |  | 0 | Complete
WATER | 534 | Kaimbaga - Kaimbaga water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 114312 | 114312 |  | CGN |  |  |  | 114312 | 100% |  |  | 0 | Complete
WATER | 535 | Kanjuiri - Uhuru water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 136510 | 136510 |  | CGN |  |  |  | 136510 | 100% |  |  | 0 | Complete
WATER | 536 | Kanjuiri -Roof harvesting for Harambe Primary school |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 303082 | 303082 |  | CGN |  |  |  | 303082 | 100% |  |  | 0 | Complete
WATER | 537 | Kanjuiri -Roof harvesting for Rutara Primary school |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 303082 | 303082 |  | CGN |  |  |  | 303082 | 100% |  |  | 0 | Complete
WATER | 538 | Kanjuiri -Roof harvesting for Wiyumiririe primary school |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 309150 | 309150 |  | CGN |  |  |  | 309150 | 100% |  |  | 0 | Complete
WATER | 539 | Kanjuiri -Roof harvesting for Kio primary school |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2016-07-01 | 2017-06-30 |  | 309150 | 309150 |  | CGN |  |  |  | 309150 | 100% |  |  | 0 | Complete
WATER | 540 | Kanjuiri -Kunyotoka springs |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2016-07-01 | 2017-06-30 |  | 599995 | 599995 |  | CGN |  |  |  | 599995 | 100% |  |  | 0
WATER | 541 | Kanjuiri -Uhuru water project |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2016-07-01 | 2017-06-30 |  | 896195 | 896195 |  | CGN |  |  |  | 896195 | 100% |  |  | 0 | Complete
WATER | 542 | Kanjuiri -Ngorika water project |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2016-07-01 | 2017-06-30 |  | 1574088 | 1574088 |  | CGN |  |  |  | 1574088 | 100% |  |  | 0 | Complete
WATER | 543 | Kanjuiri -Kihoto (Mutaro) earth dam | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2016-07-01 | 2017-06-30 |  | 2062060 | 2062060 |  | CGN |  |  |  | 2062060 | 100% |  |  | 0 | Complete
WATER | 544 | Karau - Munyeki secondary school borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 545 | Karau -Kianda borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 250000 | 250000 |  | CGN |  |  |  | 250000 | 100% |  |  | 0 | Complete
WATER | 546 | Karau -Gachwe borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 298683 | 298683 |  | CGN |  |  |  | 298683 | 100% |  |  | 0 | Complete
WATER | 547 | Karau -Gachwe borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 760000 | 760000 |  | CGN |  |  |  | 760000 | 100% |  |  | 0 | Complete
WATER | 548 | Karau -Gachwe Borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1298500 | 1298500 |  | CGN |  |  |  | 1298500 | 100% |  |  | 0 | Complete
WATER | 549 | Karau -Supply and deliver LPG gas cookers |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1540500 | 1540500 |  | CGN |  |  |  | 1540500 | 100% |  |  | 0 | Complete
WATER | 550 | Karau -Munyeki water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1875588 | 1875588 |  | CGN |  |  |  | 1875588 | 100% |  |  | 0 | Complete
WATER | 551 | Karau -Supply and delivery of 230 Litre capacity plastic water tanks |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2191000 | 2191000 |  | CGN |  |  |  | 2191000 | 100% |  |  | 0 | Complete
WATER | 552 | Karau -Munyeki secondary school | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2307900 | 2307900 |  | CGN |  |  |  | 2307900 | 100% |  |  | 0 | Complete
WATER | 553 | Karau -Gachwe primary school borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 3497183 | 3497183 |  | CGN |  |  |  | 3497183 | 100% |  |  | 0 | Complete
WATER | 554 | Kipipiri - Miji Kenda water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 375000 | 375000 |  | CGN |  |  |  | 375000 | 100% |  |  | 0 | Complete
WATER | 555 | Kipipiri -Thing'oru water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1060389 | 1060389 |  | CGN |  |  |  | 1060389 | 100% |  |  | 0 | Complete
WATER | 556 | Kipipiri -Miji Kenda water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1461962 | 1461962 |  | CGN |  |  |  | 1461962 | 100% |  |  | 0 | Complete
WATER | 557 | Kipipiri -Kahuruko dam | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1511400 | 1511400 |  | CGN |  |  |  | 1511400 | 100% |  |  | 0 | Complete
WATER | 558 | Kipipiri -Manunga dam | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2043800 | 2043800 |  | CGN |  |  |  | 2043800 | 100% |  |  | 0 | Complete
WATER | 559 | Kipipiri -Miji Kenda project distribution lines | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2842521 | 2842521 |  | CGN |  |  |  | 2842521 | 100% |  |  | 0 | Complete
WATER | 560 | Kipipiri -Kianjogu water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 103500 | 103500 |  | CGN |  |  |  | 103500 | 100% |  |  | 0 | Complete
WATER | 561 | Kipipiri -Miji Kenda water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 3007280 | 3007280 |  | CGN |  |  |  | 3007280 | 100% |  |  | 0 | Complete
WATER | 562 | Kiriita - Karagoini Mung’etho borehole | water distribution | Enhanced water supply | 30HH |  | NDARAGWA | KIRIITA |  |  | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 563 | Kiriita -Kwa Njora water project | water distribution | Enhanced water supply | 35HH |  | NDARAGWA | KIRIITA |  |  | 2016-07-01 | 2017-06-30 |  | 770100 | 770100 |  | CGN |  |  |  | 770100 | 100% |  |  | 0 | Complete
WATER | 564 | Kiriita -50m3 masonry storage tank at Karagoini Mung’etho | STORAGE TANK | Enhanced water supply | 50HH |  | NDARAGWA | KIRIITA |  |  | 2016-07-01 | 2017-06-30 |  | 1291620 | 1291620 |  | CGN |  |  |  | 1291620 | 100% |  |  | 0 | Complete
WATER | 565 | Kiriita -Supply and delivery of plastic water tanks to public institutions | ROOF HARVESTING STORAGE TANK | Enhanced water supply | 4 INSTITUTIONS |  | NDARAGWA | KIRIITA |  |  | 2016-07-01 | 2017-06-30 |  | 2199955 | 2199955 |  | CGN |  |  |  | 2199955 | 100% |  |  | 0 | Complete
WATER | 566 | Kiriita -Karagoini Mung’etho borehole | BOREHOLE | Enhanced water supply | 50HH |  | NDARAGWA | KIRIITA |  |  | 2016-07-01 | 2017-06-30 |  | 2624475 | 2624475 |  | CGN |  |  |  | 2624475 | 100% |  |  | 0 | Complete
WATER | 567 | Leshau pondo - Ebenezer borehole | water distribution | Enhanced water supply | 75HH |  | NDARAGWA | LESHAU PONDO |  |  | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 568 | Leshau pondo - Supply and Deliver 2 No. 10m3 plastic water tanks to Nyakinyua borehole water project | STORAGE TANKS | Enhanced water supply | 50HH |  | NDARAGWA | LESHAU PONDO |  |  | 2016-07-01 | 2017-06-30 |  | 210000 | 210000 |  | CGN |  |  |  | 210000 | 100% |  |  | 0 | Complete
WATER | 569 | Leshau pondo - Supply of 4 No. 10m3 plastic water tanks to Kandoro, Pondo and Nyakinyua boreholes and Karagoine primary school | STORAGE TANKS | Enhanced water supply | 4 INSTITUTIONS |  | NDARAGWA | LESHAU PONDO |  |  | 2016-07-01 | 2017-06-30 |  | 315000 | 315000 |  | CGN |  |  |  | 315000 | 100% |  |  | 0 | Complete
WATER | 570 | Leshau pondo - Leshau Pondo water project | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | LESHAU PONDO |  |  | 2016-07-01 | 2017-06-30 |  | 338900 | 338900 |  | CGN |  |  |  | 338900 | 100% |  |  | 0 | Complete
WATER | 571 | Leshau pondo - Supply, installation of gutters and construction of 4 No. 10m3 plastic water tanks concrete platforms | STORAGE TANKS | Enhanced water supply | 4 INSTITUTIONS |  | NDARAGWA | LESHAU PONDO |  |  | 2016-07-01 | 2017-06-30 |  | 751977 | 751977 |  | CGN |  |  |  | 751977 | 100% |  |  | 0 | Complete
WATER | 572 | Leshau pondo - Leshau Karogoini water project | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | LESHAU PONDO |  |  | 2016-07-01 | 2017-06-30 |  | 953200 | 953200 |  | CGN |  |  |  | 953200 | 100% |  |  | 0 | Complete
WATER | 573 | Leshau pondo - Shauri Kianda borehole | water distribution | Enhanced water supply | 25HH |  | NDARAGWA | LESHAU PONDO |  |  | 2016-07-01 | 2017-06-30 |  | 1994663 | 1994663 |  | CGN |  |  |  | 1994663 | 100% |  |  | 0 | Complete
WATER | 574 | Leshau pondo - Umoja Mbuyu borehole | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | LESHAU PONDO |  |  | 2016-07-01 | 2017-06-30 |  | 2663850 | 2663850 |  | CGN |  |  |  | 2663850 | 100% |  |  | 0 | Complete
WATER | 575 | Magumu - Mutonyora ‘B’ borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2016-07-01 | 2017-06-30 |  | 144375 | 144375 |  | CGN |  |  |  | 144375 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 576 | Magumu - Elevated tanks at Mutonyora ‘B’ and ‘C’ water projects |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2016-07-01 | 2017-06-30 |  | 181300 | 181300 |  | CGN |  |  |  | 181300 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental impacts, proper waste disposal practices, noise and dust suppression, and site restoration measures were adopted. Social safeguards included community consultations, securing land use consent, and ensuring local involvement to promote ownership. Occupational health and safety risks were addressed by enforcing the use of personal protective equipment (PPE), ensuring secure scaffolding and safe construction practices, and training workers on emergency response. Gender-sensitive strategies were applied to ensure equitable benefit-sharing, participation of women in project-related activities, and protection against gender-based discrimination and exploitation throughout implementation.
WATER | 577 | Magumu - Supply and delivery of 2 No. 10m3 plastic water tank to Mutonyora ‘B’ and ‘C’ boreholes |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2016-07-01 | 2017-06-30 |  | 210000 | 210000 |  | CGN |  |  |  | 210000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include ensuring environmentally sound transport and installation practices to avoid site contamination, engaging beneficiary institutions to address social and gender inclusion concerns, using appropriate lifting and handling procedures to safeguard workers' health and safety, and applying a transparent and inclusive process in tank allocation to promote equity and community trust.
WATER | 578 | Magumu - Kibuyu water project | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2016-07-01 | 2017-06-30 |  | 242130 | 242130 |  | CGN |  |  |  | 242130 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 579 | Magumu - Gitwe borehole | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2016-07-01 | 2017-06-30 |  | 298683 | 298683 |  | CGN |  |  |  | 298683 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 580 | Magumu - Kenton water project | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2016-07-01 | 2017-06-30 |  | 526450 | 526450 |  | CGN |  |  |  | 526450 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 581 | Magumu - Mutonyora ‘B’ water project | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2016-07-01 | 2017-06-30 |  | 1240000 | 1240000 |  | CGN |  |  |  | 1240000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 582 | Magumu - Gitwe borehole | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2016-07-01 | 2017-06-30 |  | 2510445 | 2510445 |  | CGN |  |  |  | 2510445 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 583 | Magumu - Mutonyora ‘C’ water project | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2016-07-01 | 2017-06-30 |  | 2623100 | 2623100 |  | CGN |  |  |  | 2623100 | 100% |  |  | 0 | Complete | [12 empty] | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 584 | Mirangine - Kamichege dispensary borehole | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 585 | Mirangine -Kihuho dispensary borehole | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 586 | Mirangine -Gwa Kiongo water project | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2016-07-01 | 2017-06-30 |  | 190600 | 190600 |  | CGN |  |  |  | 190600 | 100% |  |  | 0 | Complete
WATER | 587 | Mirangine -50m3 masonry storage tank at Micharage |  | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2016-07-01 | 2017-06-30 |  | 1245394 | 1245394 |  | CGN |  |  |  | 1245394 | 100% |  |  | 0 | Complete
WATER | 588 | Mirangine -Kurungu borehole | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2016-07-01 | 2017-06-30 |  | 1528888 | 1528888 |  | CGN |  |  |  | 1528888 | 100% |  |  | 0 | Complete
WATER | 589 | Mirangine -Kihuho borehole | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2016-07-01 | 2017-06-30 |  | 1802012 | 1802012 |  | CGN |  |  |  | 1802012 | 100% |  |  | 0 | Complete
WATER | 590 | Mirangine -Kamichege borehole | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2016-07-01 | 2017-06-30 |  | 1894830 | 1894830 |  | CGN |  |  |  | 1894830 | 100% |  |  | 0 | Complete
WATER | 591 | Murungaru - 3M water project | water distribution | Enhanced water supply | 100HH | [5 empty] | 2016-07-01 | 2017-06-30 |  | 1488200 | 1488200 |  | CGN |  |  |  | 1488200 | 100% |  |  | 0 | Complete
WATER | 592 | Murungaru -Muhonia Turasha water project | water distribution | Enhanced water supply | 100HH | [5 empty] | 2016-07-01 | 2017-06-30 |  | 1793900 | 1793900 |  | CGN |  |  |  | 1793900 | 100% |  |  | 0 | Complete
WATER | 593 | Murungaru -3M water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2016-07-01 | 2017-06-30 |  | 1451000 | 1451000 |  | CGN |  |  |  | 1451000 | 100% |  |  | 0 | Complete
WATER | 594 | Murungaru -100m3 masonry storage tank in Githunguri area- Muhonia Turasha water project | storage | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2016-07-01 | 2017-06-30 |  | 1798833 | 1798833 |  | CGN |  |  |  | 1798833 | 100% |  |  | 0 | Complete
WATER | 595 | North Kinangop - Kamiigua water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2016-07-01 | 2017-06-30 |  | 41475 | 41475 |  | CGN |  |  |  | 41475 | 100% |  |  | 0 | Complete
WATER | 596 | North Kinangop - Kamiigua intake weir | source | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2016-07-01 | 2017-06-30 |  | 1198901 | 1198901 |  | CGN |  |  |  | 1198901 | 100% |  |  | 0 | Complete
WATER | 597 | North Kinangop - Kikanamku water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2016-07-01 | 2017-06-30 |  | 1260710 | 1260710 |  | CGN |  |  |  | 1260710 | 100% |  |  | 0 | Complete
WATER | 598 | North Kinangop - Elevated 30m3 pressed steel water tank on 12m high steel tower at Kitiri water project | storage | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2016-07-01 | 2017-06-30 |  | 2350000 | 2350000 |  | CGN |  |  |  | 2350000 | 100% |  |  | 0 | Complete
WATER | 599 | North Kinangop - Elevated 48m3 pressed steel water tank on 12m high steel tower at Nandarasi for Kikanamku water project | storage | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2016-07-01 | 2017-06-30 |  | 2498980 | 2498980 |  | CGN |  |  |  | 2498980 | 100% |  |  | 0 | Complete
WATER | 600 | Wanjohi - Ndemi water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 59200 | 59200 |  | CGN |  |  |  | 59200 | 100% |  |  | 0 | Complete
WATER | 601 | Njabini - Soilo Ngwataniro borehole | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 602 | Njabini - Kiburu water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2016-07-01 | 2017-06-30 |  | 192400 | 192400 |  | CGN |  |  |  | 192400 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 603 | Njabini - Kiburu water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2016-07-01 | 2017-06-30 |  | 251250 | 251250 |  | CGN |  |  |  | 251250 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 604 | Njabini - Njabini water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2016-07-01 | 2017-06-30 |  | 361800 | 361800 |  | CGN |  |  |  | 361800 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 605 | Njabini - Kiburu water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2016-07-01 | 2017-06-30 |  | 563500 | 563500 |  | CGN |  |  |  | 563500 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 606 | Njabini - Soilo Ngwataniro water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2016-07-01 | 2017-06-30 |  | 1643198 | 1643198 |  | CGN |  |  |  | 1643198 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 607 | Njabini - Storm/ Waste water drain cleaning, lining and construction of road crossing culverts at Njabini town | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2016-07-01 | 2017-06-30 |  | 2949100 | 2949100 |  | CGN |  |  |  | 2949100 | 100% |  |  | 0 | Complete | [11 empty] | yes | Advised on usage of PPEs and incorporation of both gender during labour distribution
WATER | 608 | Njabini - Soilo Ngwatanero borehole | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2016-07-01 | 2017-06-30 |  | 2988825 | 2988825 |  | CGN |  |  |  | 2988825 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 609 | Njabini - Supply and delivery of pipes and fittings for water projects | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2016-07-01 | 2017-06-30 |  | 1140900 | 1140900 |  | CGN |  |  |  | 1140900 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, the project has ensured minimal disruption through proper waste disposal, prevention of soil erosion, and protection of surrounding vegetation. Socially, community sensitization and stakeholder engagement have been undertaken to promote transparency and resolve any emerging conflicts. To address occupational health and safety, workers have been equipped with personal protective equipment, trained on safe practices, and supervised throughout the construction phase, with first aid support readily available. On gender, the project promotes inclusivity by encouraging the participation of women and ensuring that the benefits of the project reach all members of the community, including vulnerable and marginalized groups.
WATER | 610 | North Kinangop - Supply and delivery of 10m3 plastic water tank to Muhuti primary school | Roof harvesting | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2016-07-01 | 2017-06-30 |  | 105000 | 105000 |  | CGN |  |  |  | 105000 | 100% |  |  | 0 | Complete
WATER | 611 | North Kinangop - 50m3 masonry water tank at Githae water project | storage | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2016-07-01 | 2017-06-30 |  | 1202889 | 1202889 |  | CGN |  |  |  | 1202889 | 100% |  |  | 0 | Complete
WATER | 612 | North Kinangop - Kairia Gitite water project | water distribution | Enhanced water supply | 100hh |  | Kinangop | North Kinangop |  |  | 2016-07-01 | 2017-06-30 |  | 1662450 | 1662450 |  | CGN |  |  |  | 1662450 | 100% |  |  | 0 | Complete
WATER | 613 | North Kinangop - Kamiigua water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2016-07-01 | 2017-06-30 |  | 2999970 | 2999970 |  | CGN |  |  |  | 2999970 | 100% |  |  | 0 | Complete
WATER | 614 | Nyakio - Ndongonye borehole | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 615 | Nyakio -Supply and delivery a 10m3 plastic water tank to Nyakio secondary school | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2016-07-01 | 2017-06-30 |  | 105000 | 105000 |  | CGN |  |  |  | 105000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include ensuring environmentally sound transport and installation practices to avoid site contamination, engaging beneficiary institutions to address social and gender inclusion concerns, using appropriate lifting and handling procedures to safeguard workers' health and safety, and applying a transparent and inclusive process in tank allocation to promote equity and community trust.
WATER | 616 | Nyakio -Supply of 1,000 litres plastic water tanks to public institutions |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2016-07-01 | 2017-06-30 |  | 126000 | 126000 |  | CGN |  |  |  | 126000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include ensuring environmentally sound transport and installation practices to avoid site contamination, engaging beneficiary institutions to address social and gender inclusion concerns, using appropriate lifting and handling procedures to safeguard workers' health and safety, and applying a transparent and inclusive process in tank allocation to promote equity and community trust.
WATER | 617 | Nyakio -Supply of 10m3 plastic water tanks to public institutions |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2016-07-01 | 2017-06-30 |  | 210000 | 210000 |  | CGN |  |  |  | 210000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include ensuring environmentally sound transport and installation practices to avoid site contamination, engaging beneficiary institutions to address social and gender inclusion concerns, using appropriate lifting and handling procedures to safeguard workers' health and safety, and applying a transparent and inclusive process in tank allocation to promote equity and community trust.
WATER | 618 | Nyakio -Supply and installation of hot water system in South Kinangop Co-operative society |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2016-07-01 | 2017-06-30 |  | 499000 | 499000 |  | CGN |  |  |  | 499000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | Advised on usage of PPEs and incorporation of both gender during labour distribution
WATER | 619 | Nyakio -Supply of 5m3 plastic water tanks to public institutions |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2016-07-01 | 2017-06-30 |  | 900000 | 900000 |  | CGN |  |  |  | 900000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include ensuring environmentally sound transport and installation practices to avoid site contamination, engaging beneficiary institutions to address social and gender inclusion concerns, using appropriate lifting and handling procedures to safeguard workers' health and safety, and applying a transparent and inclusive process in tank allocation to promote equity and community trust.
WATER | 620 | Nyakio -Wachira Kagera water project | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2016-07-01 | 2017-06-30 |  | 2212870 | 2212870 |  | CGN |  |  |  | 2212870 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 621 | Nyakio -Ndongonye borehole | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2016-07-01 | 2017-06-30 |  | 2624738 | 2624738 |  | CGN |  |  |  | 2624738 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 622 | Rurii borehole (Health Centre) | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 247819 | 247819 |  | CGN |  |  |  | 247819 | 100% |  |  | 0 | Complete
WATER | 623 | Rurii - Malan Kahonge water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 304000 | 304000 |  | CGN |  |  |  | 304000 | 100% |  |  | 0 | Complete
WATER | 624 | Rurii - Githunguri water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 383050 | 383050 |  | CGN |  |  |  | 383050 | 100% |  |  | 0 | Complete
WATER | 625 | Rurii - Malan-Kahonge borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 550000 | 550000 |  | CGN |  |  |  | 550000 | 100% |  |  | 0 | Complete
WATER | 626 | Rurii - Supply of 10,000 litre plastic water tanks to public institutions |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 630000 | 630000 |  | CGN |  |  |  | 630000 | 100% |  |  | 0 | Complete
WATER | 627 | Shamata - Warukira borehole | BOREHOLE | Enhanced water supply | 50HH |  | NDARAGWA | SHAMATA |  |  | 2016-07-01 | 2017-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 628 | Shamata -Supply of 10m3 plastic water tank to Ol’borossat secondary school | water distribution | Enhanced water supply | 200PUPILS |  | NDARAGWA | SHAMATA |  |  | 2016-07-01 | 2017-06-30 |  | 105000 | 105000 |  | CGN |  |  |  | 105000 | 100% |  |  | 0 | Complete
WATER | 629 | Shamata -Warukira borehole | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | SHAMATA |  |  | 2016-07-01 | 2017-06-30 |  | 274996 | 274996 |  | CGN |  |  |  | 274996 | 100% |  |  | 0 | Complete
WATER | 630 | Shamata -Macharia King’ethua and Wihote water projects | water distribution | Enhanced water supply | 150HH |  | NDARAGWA | SHAMATA |  |  | 2016-07-01 | 2017-06-30 |  | 1070720 | 1070720 |  | CGN |  |  |  | 1070720 | 100% |  |  | 0 | Complete
WATER | 631 | Shamata -Warukira borehole tanks tower |  | Enhanced water supply | 50HH |  | NDARAGWA | SHAMATA |  |  | 2016-07-01 | 2017-06-30 |  | 1185000 | 1185000 |  | CGN |  |  |  | 1185000 | 100% |  |  | 0 | Complete
WATER | 632 | Shamata -Warukira borehole |  | Enhanced water supply | 50HH |  | NDARAGWA | SHAMATA |  |  | 2016-07-01 | 2017-06-30 |  | 2237970 | 2237970 |  | CGN |  |  |  | 2237970 | 100% |  |  | 0 | Complete
WATER | 633 | Shamata -Kambaa springs and cattle trough | water distribution | Enhanced water supply | 75HH |  | NDARAGWA | SHAMATA |  |  | 2016-07-01 | 2017-06-30 |  | 2446090 | 2446090 |  | CGN |  |  |  | 2446090 | 100% |  |  | 0 | Complete
WATER | 634 | Shamata -Warukira borehole | water distribution | Enhanced water supply | 50HH |  | NDARAGWA | SHAMATA |  |  | 2016-07-01 | 2017-06-30 |  | 2967668 | 2967668 |  | CGN |  |  |  | 2967668 | 100% |  |  | 0 | Complete
WATER | 635 | Shamata -Kiambogo water project | water distribution | Enhanced water supply | 75HH |  | NDARAGWA | SHAMATA |  |  | 2016-07-01 | 2017-06-30 |  | 3002000 | 3002000 |  | CGN |  |  |  | 3002000 | 100% |  |  | 0 | Complete
WATER | 636 | Kipipiri - Supply of pipes, fittings and10m3 plastic water tank for Mugitiri, Malan and Githae water projects |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 397950 | 397950 |  | CGN |  |  |  | 397950 | 100% |  |  | 0 | Complete
WATER | 637 | Wanjohi - Kiamboga borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 80000 | 80000 |  | CGN |  |  |  | 80000 | 100% |  |  | 0 | Complete
WATER | 638 | Wanjohi -Kega water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1704075 | 1704075 |  | CGN |  |  |  | 1704075 | 100% |  |  | 0 | Complete
WATER | 639 | Wanjohi -100m3 masonry water tank at Nyagathuru water project |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 1798876 | 1798876 |  | CGN |  |  |  | 1798876 | 100% |  |  | 0 | Complete
WATER | 640 | Wanjohi -Kega water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2298758 | 2298758 |  | CGN |  |  |  | 2298758 | 100% |  |  | 0 | Complete
WATER | 641 | Wanjohi -Kiamboga borehole | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 2304750 | 2304750 |  | CGN |  |  |  | 2304750 | 100% |  |  | 0 | Complete
WATER | 642 | Wanjohi -Magomano water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 3001042 | 3001042 |  | CGN |  |  |  | 3001042 | 100% |  |  | 0 | Complete
WATER | 643 | Wanjohi -Magomano water project | water distribution | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 3137590 | 3137590 |  | CGN |  |  |  | 3137590 | 100% |  |  | 0 | Complete
WATER | 644 | Supply of tools to county Water office |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 158000 | 158000 |  | CGN |  |  |  | 158000 | 100% |  |  | 0 | Complete
WATER | 645 | Weru - Supply of a 10m3 plastic water tank to Gatumbiro primary school | WATER STORAGE | Enhanced water supply | 250PUPILS |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 105000 | 105000 |  | CGN |  |  |  | 105000 | 100% |  |  | 0 | Complete
WATER | 646 | Weru - Madaraka borehole water project | water distribution | Enhanced water supply | 50HH |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 332700 | 332700 |  | CGN |  |  |  | 332700 | 100% |  |  | 0 | Complete
WATER | 647 | Weru - Ol’jororok water project | water distribution | Enhanced water supply | 95HH |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 332900 | 332900 |  | CGN |  |  |  | 332900 | 100% |  |  | 0 | Complete
WATER | 648 | Weru - Supply of 10No 3m3 and 1No 6m3 plastic water tanks to Wendani water group and Ol’ joro Orok secondary school | WATER STORAGE | Enhanced water supply | 30HH AND 1No INSTITUTION |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 335000 | 335000 |  | CGN |  |  |  | 335000 | 100% |  |  | 0 | Complete
WATER | 649 | Weru - Kasuku water project | water distribution | Enhanced water supply | 25hh |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 379258 | 379258 |  | CGN |  |  |  | 379258 | 100% |  |  | 0 | Complete
WATER | 650 | Weru - Micro tunneling and provision of 150mm diameter GI medium grade sleeve across C77 at Suera petrol station | water distribution | Enhanced water supply | 100HH |  | OLJOROOROK | GATIMU |  |  | 2016-07-01 | 2017-06-30 |  | 507000 | 507000 |  | CGN |  |  |  | 507000 | 100% |  |  | 0 | Complete
WATER | 651 | Weru - Supply of pipes, fittings, trenching, pipelaying and construction of a tank platform at Gatumbiro primary school | water distribution | Enhanced water supply | 75HH AND 200PUPILS |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 649576 | 649576 |  | CGN |  |  |  | 649576 | 100% |  |  | 0 | Complete
WATER | 652 | Weru - Weru water project | water distribution | Enhanced water supply | 150HH |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 654540 | 654540 |  | CGN |  |  |  | 654540 | 100% |  |  | 0 | Complete
WATER | 653 | Weru - Matura water project | water distribution | Enhanced water supply | 110HH |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 654900 | 654900 |  | CGN |  |  |  | 654900 | 100% |  |  | 0 | Complete
WATER | 654 | Weru - Kirimangai water project | water distribution | Enhanced water supply | 85HH |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 913000 | 913000 |  | CGN |  |  |  | 913000 | 100% |  |  | 0 | Complete
WATER | 655 | Weru - Kanyiriri, Karandi and Ol’ bolossat water projects | water distribution | Enhanced water supply | 45HH |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 1410680 | 1410680 |  | CGN |  |  |  | 1410680 | 100% |  |  | 0 | Complete
WATER | 656 | Weru - Gatumbiro water project | water distribution | Enhanced water supply | 30HH |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 1729150 | 1729150 |  | CGN |  |  |  | 1729150 | 100% |  |  | 0 | Complete
WATER | 657 | Weru - Supply of 5m3 plastic water tanks to public institutions | water distribution | Enhanced water supply | 4 INSTITUTIONS |  | OLJOROOROK | WERU |  |  | 2016-07-01 | 2017-06-30 |  | 3300000 | 3300000 |  | CGN |  |  |  | 3300000 | 100% |  |  | 0 | Complete
WATER | 658 | Karau - Storm water drainage for Olkalou town |  | Enhanced water supply | [6 empty] | 2016-07-01 | 2017-06-30 |  | 10000000 | 8800500 |  | CGN |  |  |  | 8800500 | 100% |  |  | 0 | Complete
WATER | 659 | Leshau Pondo - supply and install roof water harvesting and 2 no 100m3 tanks in Kagondo Pry School | STORAGE TANKS | Enhanced water supply | 180PUPILS |  | NDARAGWA | LESHAU PONDO |  |  | 2017-07-01 | 2018-06-30 |  | 400000 | 399211 |  | CGN |  |  |  | 399211 | 100% |  |  | 0 | Complete
WATER | 660 | Leshau Pondo - Extension of water supply in Kamukunji Kieni Divai area | water distribution | Enhanced water supply | 20HH |  | NDARAGWA | LESHAU PONDO |  |  | 2017-07-01 | 2018-06-30 |  | 1200000 | 1164260 |  | CGN |  |  |  | 1164260 | 100% |  |  | 0 | Complete
WATER | 661 | Leshau Pondo - Extension of water supply in Shauri, Kiandege and Ndogino area | water distribution | Enhanced water supply | 35HH |  | NDARAGWA | LESHAU PONDO |  |  | 2017-07-01 | 2018-06-30 |  | 1200000 | 1198220 |  | CGN |  |  |  | 1198220 | 100% |  |  | 0 | Complete
WATER | 662 | Leshau Pondo - Extension of water supply in Raicheri and Karampton area | water distribution | Enhanced water supply | 15HH |  | NDARAGWA | LESHAU PONDO |  |  | 2017-07-01 | 2018-06-30 |  | 1000000 | 999940 |  | CGN |  |  |  | 999940 | 100% |  |  | 0 | Complete
WATER | 663 | Leshau Pondo - Extension of water supply in Nyakinyua Muthiga area | water distribution | Enhanced water supply | 20HH |  | NDARAGWA | LESHAU PONDO |  |  | 2017-07-01 | 2018-06-30 |  | 1200000 | 1198432 |  | CGN |  |  |  | 1198432 | 100% |  |  | 0 | Complete
WATER | 664 | Leshau Pondo - Extension of water supply in Mithuuri, Buyu and gwakungu area | water distribution | Enhanced water supply | 35HH |  | NDARAGWA | LESHAU PONDO |  |  | 2017-07-01 | 2018-06-30 |  | 3000000 | 2999800 |  | CGN |  |  |  | 2999800 | 100% |  |  | 0 | Complete
WATER | 665 | Central - Supply & Install Solar Powered pump in Mailo kumi borehole | BOREHOLE | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2017-07-01 | 2018-06-30 |  | 3400000 | 3398000 |  | CGN |  |  |  | 3398000 | 100% |  |  | 0 | Complete
WATER | 666 | Test pumping in Mailo kumi borehole | BOREHOLE | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2017-07-01 | 2018-06-30 |  | 100000 |  |  | CGN | [7 empty] | 0 | Complete
WATER | 667 | Central - Construct a 1,5m*1.5m*2.3m high façade and 2.15m high back elevated control panel house in Mairo ikumi borehole | POWER HOUSE | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2017-07-01 | 2018-06-30 |  | 225000 | 224144 |  | CGN |  |  |  | 224144 | 100% |  |  | 0 | Complete
WATER | 668 | Central - Procure & lay distribution mains In Mairo ikumi borehole | water distribution | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2017-07-01 | 2018-06-30 |  | 1600000 | 1596040 |  | CGN |  |  |  | 1596040 | 100% |  |  | 0 | Complete
WATER | 669 | Central - Erect Tank Platform & fix Intake & Outlet pipes and supply 2no. 10m3 plastic tanks in Mairo ikumi borehole | WATER STORAGE | Enhanced water supply | 150HH |  | NDARAGWA | CENTRAL |  |  | 2017-07-01 | 2018-06-30 |  | 1325000 | 1300000 |  | CGN |  |  |  | 1300000 | 100% |  |  | 0 | Complete
WATER | 670 | supply & laying of pipes in ngurumo -Githunguchu | water distribution | Enhanced water supply | 30HH |  | NDARAGWA | CENTRAL |  |  | 2017-07-01 | 2018-06-30 |  | 2350000 | 2347840 |  | CGN |  |  |  | 2347840 | 100% |  |  | 0 | Complete
WATER | 671 | Shamata - Supply & Install Solar Powered submersible pump, solar panels, panel support structure and solar controller for Muhakaini borehole | BOREHOLE | Enhanced water supply | 50HH |  | NDARAGWA | SHAMATA |  |  | 2017-07-01 | 2018-06-30 |  | 3500000 | 3495700 |  | CGN |  |  |  | 3495700 | 100% |  |  | 0 | Complete
WATER | 672 | Shamata - Construct a power house & Erect Tank Platform, supply 2No 10m3 plastic water tank & fix Intake & Outlet pipes in Muhakaini borehole | WATER STORAGE | Enhanced water supply | 50HH |  | NDARAGWA | SHAMATA |  |  | 2017-07-01 | 2018-06-30 |  | 1450000 | 1450000 |  | CGN |  |  |  | 1450000 | 100% |  |  | 0 | Complete
WATER | 673 | Shamata - Supply & Install Solar Powered pump in Warukira borehole |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 3850000 | 3848400 |  | CGN |  |  |  | 3848400 | 100% |  |  | 0 | Complete
WATER | 674 | Shamata - Test pumping in Warukira borehole |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 100000 | 100000 |  | CGN |  |  |  | 100000 | 100% |  |  | 0 | Complete
WATER | 675 | Shamata – Procure, supply and lay pipes and fittings for warukira bohelhole | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 400000 | 398460 |  | CGN |  |  |  | 398460 | 100% |  |  | 0 | Complete
WATER | 676 | Kiriita - Extension of water supply in Mutanga area | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1200000 | 1197140 |  | CGN |  |  |  | 1197140 | 100% |  |  | 0 | Complete
WATER | 677 | Kiriita - Extension of water supply in Mairo Inya | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 4000000 | 2399320 |  | CGN |  |  |  | 2399320 | 100% |  |  | 0 | Complete
WATER | 678 | Kiriita - Extension of water supply in Mungetho area | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1200000 | 1174450 |  | CGN |  |  |  | 1174450 | 100% |  |  | 0 | Complete
WATER | 679 | Kiriita - Extension of water supply in Karagoine | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1300000 | 1292840 |  | CGN |  |  |  | 1292840 | 100% |  |  | 0 | Complete
WATER | 680 | Kiriita - supply and install roof water harvesting and 2 no 10m3 tanks in Michinda Pry School |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 450000 | 449200 |  | CGN |  |  |  | 449200 | 100% |  |  | 0 | Complete
WATER | 681 | Supply and deliver pipes and fittings, trenchin and laying at mairo inya – police pipeline | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 4000000 | 1601680 |  | CGN |  |  |  | 1601680 | 100% |  |  | 0 | Complete
WATER | 682 | Micharage Borehole water project in Mirangine Ward | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2017-07-01 | 2018-06-30 |  | 4000000 | 1200000 |  | CGN |  |  |  | 1200000 | 100% |  |  | 0 | Complete
WATER | 683 | Kihuho Borehole Water project in Mirangine Ward | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2017-07-01 | 2018-06-30 |  | 8000000 | 6100000 |  | CGN |  |  |  | 6100000 | 100% |  |  | 0 | Complete
WATER | 684 | Wiyumiririe Borehole Water Project | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2017-07-01 | 2018-06-30 |  | 13000000 | 7700000 |  | CGN |  |  |  | 7700000 | 100% |  |  | 0 | Complete
WATER | 685 | Mawingu soweto water project 100m³tank Githioro ward |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1800000 |  |  | CGN | [7 empty] | 0 | Complete
WATER | 686 | Mawingu water project Canadian intake dredging and pipelines in Githioro ward | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1500000 | 1485500 |  | CGN |  |  |  | 1485500 | 100% |  |  | 0 | Complete
WATER | 687 | Kangiri water project 100m³tank wanjohi ward | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1800000 | 1782705 |  | CGN |  |  |  | 1782705 | 100% |  |  | 0 | Complete
WATER | 688 | Muthangira water project wanjohi ward | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 900000 | 799050 |  | CGN |  |  |  | 799050 | 100% |  |  | 0 | Complete
WATER | 689 | Muhonia turasha water project 225m³tank Githioro ward |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 3300000 | 3291950 |  | CGN |  |  |  | 3291950 | 100% |  |  | 0 | Complete
WATER | 690 | Mawingu water project gathiriga line Githioro ward | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 700000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 691 | Karima water project 100m³tank wanjohi ward |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1800000 | 1967283 |  | CGN |  |  |  | 1967283 | 100% |  |  | 0 | Complete
WATER | 692 | mikeu water project 100m³tank Geta ward |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1800000 | 1799199 |  | CGN |  |  |  | 1799199 | 100% |  |  | 0 | Complete
WATER | 693 | Kiambogo water project 100m³tank Geta ward |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1800000 | 1799999 |  | CGN |  |  |  | 1799999 | 100% |  |  | 0 | Complete
WATER | 694 | Witeithie water project intake Geta ward |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 500000 | 499000 |  | CGN |  |  |  | 499000 | 100% |  |  | 0 | Complete
WATER | 695 | China b/orehole development in kipipri ward |  | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1000000 | 998409 |  | CGN |  |  |  | 998409 | 100% |  |  | 0 | Complete
WATER | 696 | Konoike offtake points for kamahia and corner lereshwa in kipipri ward | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 1500000 | 1494938 |  | CGN |  |  |  | 1494938 | 100% |  |  | 0 | Complete
WATER | 697 | Construction of 100m3 Masonry Storage tank for Kinja WP | Storage | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2017-07-01 | 2018-06-30 |  | 2000000 | 1982081 |  | CGN |  |  |  | 1982081 | 100% |  |  | 0 | Complete
WATER | 698 | Construction of 100m3 Masonry Storage tank for Laigiri WP | Storage | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2017-07-01 | 2018-06-30 |  | 2000000 | 1784500 |  | CGN |  |  |  | 1784500 | 100% |  |  | 0 | Complete
WATER | 699 | Supply and lying of pipes and fittings for Tulaga Ngwataniro WP | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2017-07-01 | 2018-06-30 |  | 1000000 | ----- |  | CGN |  |  |  | ----- |  |  |  |  | Complete
WATER | 700 | Matundura WP Supply, Deliver & Install solar panels and inverters | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2017-07-01 | 2018-06-30 |  | 2400000 | 2398500 |  | CGN |  |  |  | 2398500 | 100% |  |  | 0 | Complete
WATER | 701 | Matundura WP fencing 1/2 acre | Security | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2017-07-01 | 2018-06-30 |  | 500000 | ------- |  | CGN |  |  |  | ------- |  |  |  |  | Complete
WATER | 702 | Muti-ini WP erection of an elevated platform and supply of 2no.10m3 plastic tanks | Storage | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2017-07-01 | 2018-06-30 |  | 1500000 | 1497200 |  | CGN |  |  |  | 1497200 | 100% |  |  | 0 | Complete
WATER | 703 | Muti-ini WP supply and laying of pipes and fittings | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2017-07-01 | 2018-06-30 |  | 1250000 | 1198330 |  | CGN |  |  |  | 1198330 | 100% |  |  | 0 | Complete
WATER | 704 | Purchase and installation of submersible pump for Faru Borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2017-07-01 | 2018-06-30 |  | 1200000 | ----- |  | CGN |  |  |  | ----- |  |  |  |  | Complete
WATER | 705 | Supply and laying of pipes and fittings for Faru Borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2017-07-01 | 2018-06-30 |  | 450000 | 438400 |  | CGN |  |  |  | 438400 | 100% |  |  | 0 | Complete
WATER | 706 | Muhonia Turasha supply of pipes and lying | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2017-07-01 | 2018-06-30 |  | 2650000 | 2644920 |  | CGN |  |  |  | 2644920 | 100% |  |  | 0 | Complete
WATER | 707 | 3M Water tank and supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2017-07-01 | 2018-06-30 |  | 3000000 | 2994963 |  | CGN |  |  |  | 2994963 | 100% |  |  | 0 | Complete
WATER | 708 | Kagongo/Njurui water pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2017-07-01 | 2018-06-30 |  | 1650000 | 1647990 |  | CGN |  |  |  | 1647990 | 100% |  |  | 0 | Complete
WATER | 709 | Supply of borehole casings and gravel pack materials for North Kinangop Boreholes | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2017-07-01 | 2018-06-30 |  | 4800000 | 4800000 |  | CGN |  |  |  | 4800000 | 100% |  |  | 0 | Complete
WATER | 710 | Kamigwa water project purchase and laying of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2017-07-01 | 2018-06-30 |  | 600000 | 599900 |  | CGN |  |  |  | 599900 | 100% |  |  | 0 | Complete
WATER | 711 | Gitamaiyu water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2017-07-01 | 2018-06-30 |  | 1600000 | 1599920 |  | CGN |  |  |  | 1599920 | 100% |  |  | 0 | Complete
WATER | 712 | Highland water project plot acquisition &installation of pipes | water distribution | Enhanced water supply | [6 empty] | 2017-07-01 | 2018-06-30 |  | 300000 | 299900 |  | CGN |  |  |  | 299900 | 100% |  |  | 0 | Complete
WATER | 713 | Gitwe borehole in Magumu ward | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2017-07-01 | 2018-06-30 |  | 500000 | 500000 |  | CGN |  |  |  | 500000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 714 | Our Lady of Mercy Catholic borehole in Magumu ward | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2017-07-01 | 2018-06-30 |  | 403120 | 403120 |  | CGN |  |  |  | 403120 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 715 | Mwenda Andu borehole in Magumu ward | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2017-07-01 | 2018-06-30 |  | 6300000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 716 | Koinange borehole in Githabai ward | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2017-07-01 | 2018-06-30 |  | 800000 | 3436123 |  | CGN |  |  |  | 3436123 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 717 | Heni borehole in Githabai ward | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2017-07-01 | 2018-06-30 |  | 2900000 | 1896720 |  | CGN |  |  |  | 1896720 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 718 | Miti iri cattle dip borehole in Githabai ward | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2017-07-01 | 2018-06-30 |  | 3600000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 719 | Wacira-Kageraini borehole in Nyakio ward | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2017-07-01 | 2018-06-30 |  | 500000 | 449990 |  | CGN |  |  |  | 449990 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 720 | Ndogonye borehole in Nyakio ward | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2017-07-01 | 2018-06-30 |  | 500000 | 5639836 |  | CGN |  |  |  | 5639836 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 721 | Rwanyambo Primary borehole in Nyakio ward | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2017-07-01 | 2018-06-30 |  | 6300000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 722 | Soilo borehole in Njabini/Kiburu ward | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2017-07-01 | 2018-06-30 |  | 3073560 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 723 | Soilo Ngwataniro W/P in Njabini/Kiburu ward | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2017-07-01 | 2018-06-30 |  | 1226440 | 5467083 |  | CGN |  |  |  | 5467083 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 724 | Kiburu WP in Njabini/Kiburu ward | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2017-07-01 | 2018-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 725 | Sasumua primary Borehole in Njabini/Kiburu ward | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2017-07-01 | 2018-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 726 | Kanyawa borehole in Njabini/Kiburu ward | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2017-07-01 | 2018-06-30 |  | - | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 727 | Mwenda andu borehole water project | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2018-07-01 | 2019-06-30 |  | 5300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 728 | Gitwe and Mutonyara B Water Projects | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2018-07-01 | 2019-06-30 |  | 1600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 729 | Bamboo dispensary | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2018-07-01 | 2019-06-30 |  | 400000 | 399905 |  | CGN |  |  |  | 399905 | 100% |  |  | 0 | complete | [11 empty] | yes | Advised on usage of PPEs and incorporation of both gender during labour distribution
WATER | 730 | Yaang'a Water Project | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2018-07-01 | 2019-06-30 |  | 430000 | 429440 |  | CGN |  |  |  | 429440 | 100% |  |  | 0 | complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 731 | Rwanyambo borehole water project | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2018-07-01 | 2019-06-30 |  | 6370000 | 4097550 |  | CGN |  |  |  | 4097550 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 732 | Ndogonye kwa haraka water project | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2018-07-01 | 2019-06-30 |  | 500000 | 723315 |  | CGN |  |  |  | 723315 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 733 | Miti iri borehole water project- | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2018-07-01 | 2019-06-30 |  | 5000000 | 827120 |  | CGN |  |  |  | 827120 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 734 | Koinange borehole | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2018-07-01 | 2019-06-30 |  | 800000 | 1994000 |  | CGN |  |  |  | 1994000 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 735 | Koinange dispensary | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2018-07-01 | 2019-06-30 |  | 180000 |  |  | CGN | [7 empty] | 0 | complete | [11 empty] | yes | Advised on usage of PPEs and incorporation of both gender during labour distribution
WATER | 736 | Heni Borehole water project | water distribution | Enhanced water supply |  |  | Nabini | Nyakio |  |  | 2018-07-01 | 2019-06-30 |  | 1150000 | 798430 |  | CGN |  |  |  | 798430 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 737 | Ndothua borehole Water Project | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2018-07-01 | 2019-06-30 |  | 170000 | 98100 |  | CGN |  |  |  | 98100 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 738 | Soilo gwataniro Water Project | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2018-07-01 | 2019-06-30 |  | 300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 739 | Kiburu water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2018-07-01 | 2019-06-30 |  | 1000000 | 986179 |  | CGN |  |  |  | 986179 | 100% |  |  | 0 | complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 740 | Sasumua Secondary ECD borehole water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini/Kiburu |  |  | 2018-07-01 | 2019-06-30 |  | 1000000 | 138500 |  | CGN |  |  |  | 138500 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 741 | Soilo Ngwataniro borehole water project | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2018-07-01 | 2019-06-30 |  | 3000000 | 1999830 |  | CGN |  |  |  | 1999830 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 742 | Upper Chania Water Project-Kinamba Water | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2018-07-01 | 2019-06-30 |  | 2000000 | 1995033 |  | CGN |  |  |  | 1995033 | 100% |  |  | 0 | complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 743 | Nyondo weir | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2018-07-01 | 2019-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 744 | Mbirithi water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2018-07-01 | 2019-06-30 |  | 300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 745 | Engineer water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2018-07-01 | 2019-06-30 |  | 3800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 746 | Engineer water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2018-07-01 | 2019-06-30 |  | 1800000 | 1798125 |  | CGN |  |  |  | 1798125 | 100% |  |  | 0 | complete
WATER | 747 | Raitha Kahuru water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2018-07-01 | 2019-06-30 |  | 1900000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 748 | Tulaga Ngwataniro water project/Mutamaiyo water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2018-07-01 | 2019-06-30 |  | 3300000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | complete
WATER | 749 | Tulaga Ngwataniro water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2018-07-01 | 2019-06-30 |  | 2000000 | 1967306 |  | CGN |  |  |  | 1967306 | 100% |  |  | 0 | complete
WATER | 750 | Kwa Njugi/ Kirima intake | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2018-07-01 | 2019-06-30 |  | 2000000 | 1980000 |  | CGN |  |  |  | 1980000 | 100% |  |  | 0 | complete
WATER | 751 | Githae Umoja water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2018-07-01 | 2019-06-30 |  | 3900000 | 2449936 |  | CGN |  |  |  | 2449936 | 100% |  |  | 0 | complete
WATER | 752 | Gatamaiyo water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2018-07-01 | 2019-06-30 |  | 1400000 | 1398288 |  | CGN |  |  |  | 1398288 | 100% |  |  | 0 | complete
WATER | 753 | Kirimire water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2018-07-01 | 2019-06-30 |  | 400000 | 399995 |  | CGN |  |  |  | 399995 | 100% |  |  | 0 | complete
WATER | 754 | Tia Wira water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2018-07-01 | 2019-06-30 |  | 3250000 | 3250000 |  | CGN |  |  |  | 3250000 | 100% |  |  | 0 | complete
WATER | 755 | 3M water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2018-07-01 | 2019-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 756 | Kagongo Njuruini borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2018-07-01 | 2019-06-30 |  | 700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 757 | Muhonia Turasha water project | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2018-07-01 | 2019-06-30 |  | 1800000 | 1799950 |  | CGN |  |  |  | 1799950 | 100% |  |  | 0 | complete
WATER | 758 | Aurthur Dam | Desilting | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2018-07-01 | 2019-06-30 |  | 2000000 | 1728389 |  | CGN |  |  |  | 1728389 | 100% |  |  | 0 | complete
WATER | 759 | St. Mary’s borehole Matundura | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2018-07-01 | 2019-06-30 |  | 500000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 760 | Faru borehole | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2018-07-01 | 2019-06-30 |  | 438400 |  |  | CGN | [7 empty] | 0 | complete
WATER | 761 | Makumbi water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1900000 | 1896588 |  | CGN |  |  |  | 1896588 | 100% |  |  | 0 | complete
WATER | 762 | Waiyego | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1200000 | 1186107 |  | CGN |  |  |  | 1186107 | 100% |  |  | 0 | complete
WATER | 763 | witeithie, mibiriti, kona and geta lower town | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 800000 | 798347 |  | CGN |  |  |  | 798347 | 100% |  |  | 0 | complete
WATER | 764 | Cooking gas cylinders | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3000000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 765 | Kariua water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 766 | Mawingo Water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1000000 | 992208 |  | CGN |  |  |  | 992208 | 100% |  |  | 0 | complete
WATER | 767 | karuri. Water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 768 | 3M water project, mumui . | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2250000 | 2235912 |  | CGN |  |  |  | 2235912 | 100% |  |  | 0 | complete
WATER | 769 | Gathiriga borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1250000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 770 | Another WP Projects in Githioro kimbo pipeline | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 771 | Kirima water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 772 | Ndemi borehole water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 773 | Magomano | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2500000 | 2498685 |  | CGN |  |  |  | 2498685 | 100% |  |  | 0 | complete
WATER | 774 | Gaturufari water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 500000 | 500519 |  | CGN |  |  |  | 500519 | 100% |  |  | 0 | complete
WATER | 775 | Kega Irrigation project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 776 | Muthangira water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1500000 | 1499605 |  | CGN |  |  |  | 1499605 | 100% |  |  | 0 | complete
WATER | 777 | Kabati Water tank | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 778 | Manunga borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3830000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 779 | Manunga borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 780 | Manunga borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1900000 | 1899593 |  | CGN |  |  |  | 1899593 | 100% |  |  | 0 | complete
WATER | 781 | Manunga borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 600000 | 599810 |  | CGN |  |  |  | 599810 | 100% |  |  | 0 | complete
WATER | 782 | Wiyumiririe Borehole water project | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2018-07-01 | 2019-06-30 |  | 7300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 783 | Micharage Borehole water project | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2018-07-01 | 2019-06-30 |  | 1800000 | 1799472 |  | CGN |  |  |  | 1799472 | 100% |  |  | 0 | complete
WATER | 784 | Kihuho Borehole water project | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2018-07-01 | 2019-06-30 |  | 6100000 | 2100000 |  | CGN |  |  |  | 2100000 | 100% |  |  | 0 | complete
WATER | 785 | Makara water project | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2018-07-01 | 2019-06-30 |  | 1800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 786 | GwaKiongo dam | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2018-07-01 | 2019-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 787 | Leshau Karagoini | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 96000000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 788 | Kiriko-Kahembe dispensary. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3590000 | 3581.34 |  | CGN |  |  |  | 3581.34 | 100% |  |  | 0 | complete
WATER | 789 | Githunguchu borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1600000 | 1600000 |  | CGN |  |  |  | 1600000 | 100% |  |  | 0 | complete
WATER | 790 | Karagoini Primary and Secondary pipeline | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1200000 | 1200000 |  | CGN |  |  |  | 1200000 | 100% |  |  | 0 | complete
WATER | 791 | Kwanjora borehole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | complete
WATER | 792 | Kwanjora borehole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 793 | Baari borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | complete
WATER | 794 | Baari borehole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 90000 | 78500 |  | CGN |  |  |  | 78500 | 100% |  |  | 0 | complete
WATER | 795 | Baari borehole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 100000 | 98100 |  | CGN |  |  |  | 98100 | 100% |  |  | 0 | complete
WATER | 796 | Baari pipeline | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 500000 | 92840 |  | CGN |  |  |  | 92840 | 100% |  |  | 0 | complete
WATER | 797 | Kagondo water supply community. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 600000 | 599193 |  | CGN |  |  |  | 599193 | 100% |  |  | 0 | complete
WATER | 798 | Raichiri community Group. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 400000 | 398129 |  | CGN |  |  |  | 398129 | 100% |  |  | 0 | complete
WATER | 799 | Ndivai ECD school. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 500000 | 499250 |  | CGN |  |  |  | 499250 | 100% |  |  | 0 | complete
WATER | 800 | Ngaindeithia ECD school. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 400000 | 399752 |  | CGN |  |  |  | 399752 | 100% |  |  | 0 | complete
WATER | 801 | Ndogino pipeline | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 700000 | 699950 |  | CGN |  |  |  | 699950 | 100% |  |  | 0 | complete
WATER | 802 | Kiandege pipeline | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 803 | Kiboya borehole water project. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 700000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 804 | Kiandege dam. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1100000 | 498030 |  | CGN |  |  |  | 498030 | 100% |  |  | 0 | complete
WATER | 805 | Kwanjora community group | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 300000 | 299499 |  | CGN |  |  |  | 299499 | 100% |  |  | 0 | complete
WATER | 806 | Kingi dam water project. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1500000 | 1499411 |  | CGN |  |  |  | 1499411 | 100% |  |  | 0 | complete
WATER | 807 | Kandoro borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 808 | Mairo Kumi borehole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 300000 | 299950 |  | CGN |  |  |  | 299950 | 100% |  |  | 0 | complete
WATER | 809 | Githunguchu borehole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 700000 | 629813 |  | CGN |  |  |  | 629813 | 100% |  |  | 0 | complete
WATER | 810 | Subuku borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | complete
WATER | 811 | Subuku borehole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 100000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 812 | Subuku borehole water. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 813 | Subuku borehole water project. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3850000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 814 | Subuku borehole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 815 | Nduthi irrigation project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 816 | Muhakaini bole hole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 4000000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 817 | Warukira borehole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 350000 | 349871 |  | CGN |  |  |  | 349871 | 100% |  |  | 0 | complete
WATER | 818 | Karandi B borehole W/P. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 70000 | 70000 |  | CGN |  |  |  | 70000 | 100% |  |  | 0 | complete
WATER | 819 | Karandi B borehole Water Project. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 100000 | 98100 |  | CGN |  |  |  | 98100 | 100% |  |  | 0 | complete
WATER | 820 | Karandi B borehole water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3834866 | 3815000 |  | CGN |  |  |  | 3815000 | 100% |  |  | 0 | complete
WATER | 821 | Karandi B borehole water project. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 822 | Karandi B borehole water project. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 400000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 823 | Karandi B borehole water project. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 824 | Kirimanjaro bore hole. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1797495 |  |  | CGN | [7 empty] | 0 | complete
WATER | 825 | kirimanjaro borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2020000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 826 | Kangocho irrigation project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 827 | kaheho township. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 828 | Shamata tanks | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 829 | Ex-daya | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2500000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 830 | Kaheho Dispensary. | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1940000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 831 | Kirima Weir | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1980000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 832 | Nyakanja water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1797020 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 833 | Nyakanja water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 834 | Gikingi water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 835 | Nyakanja water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 836 | Njoro borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 296000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 837 | Boiman water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1100000 | 1099900 |  | CGN |  |  |  | 1099900 | 100% |  |  | 0 | complete
WATER | 838 | Huho-ini water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 700000 | 698000 |  | CGN |  |  |  | 698000 | 100% |  |  | 0 | complete
WATER | 839 | Huho-ini water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 4000000 | 3986820 |  | CGN |  |  |  | 3986820 | 100% |  |  | 0 | complete
WATER | 840 | Huho-ini water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1400000 | 1399020 |  | CGN |  |  |  | 1399020 | 100% |  |  | 0 | complete
WATER | 841 | Ruiru water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1900000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 842 | Oraimutia water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2600000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 843 | Matindiri water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 844 | Matindiri water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3830000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 845 | Weru water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2500000 | 2490600 |  | CGN |  |  |  | 2490600 | 100% |  |  | 0 | complete
WATER | 846 | Gatumbiro irrigation project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1000000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 847 | Gathundia water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 848 | Karandi water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 849 | Madaraka borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2300000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 850 | Matindiri water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 851 | Matindiri water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 90000 | 78500 |  | CGN |  |  |  | 78500 | 100% |  |  | 0 | complete
WATER | 852 | Bosnia borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | complete
WATER | 853 | Githunguri borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1840000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 854 | Githunguri borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 100000 | 98100 |  | CGN |  |  |  | 98100 | 100% |  |  | 0 | complete
WATER | 855 | Githunguri borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | complete
WATER | 856 | Githunguri borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 857 | Githunguri borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1500000 | 248800 |  | CGN |  |  |  | 248800 | 100% |  |  | 0 | complete
WATER | 858 | Munyeki borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 859 | Munyeki borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 860 | munyeki borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 100000 | 98100 |  | CGN |  |  |  | 98100 | 100% |  |  | 0 | complete
WATER | 861 | Munyeki B/H | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 90000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | complete
WATER | 862 | Munyeki borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 60000 | 78500 |  | CGN |  |  |  | 78500 | 100% |  |  | 0 | complete
WATER | 863 | Munyeki borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1650000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 864 | Kihurire borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1500000 | 1488543 |  | CGN |  |  |  | 1488543 | 100% |  |  | 0 | complete
WATER | 865 | Kihurire borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3750000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 866 | Kihurire borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 100000 | 98100 |  | CGN |  |  |  | 98100 | 100% |  |  | 0 | complete
WATER | 867 | Kihurire borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 90000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | complete
WATER | 868 | Kihurire | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 60000 | 78500 |  | CGN |  |  |  | 78500 | 100% |  |  | 0 | complete
WATER | 869 | Kihurire borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 870 | Gichungo water tower | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 871 | Rumathi borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 872 | Rumathi B/H | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 873 | Mumbi borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 350000 | 349650 |  | CGN |  |  |  | 349650 | 100% |  |  | 0 | complete
WATER | 874 | Kieni borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 875 | Kieni borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3750000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 876 | kieni borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 100000 | 98100 |  | CGN |  |  |  | 98100 | 100% |  |  | 0 | complete
WATER | 877 | Kieni borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 90000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | complete
WATER | 878 | Kieni borehole | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 250000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 879 | Civil works |  | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2000000 | 1990990 |  | CGN |  |  |  | 1990990 | 100% |  |  | 0 | complete
WATER | 880 | Tree planting |  | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1800000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 881 | Gwa kiongo dam |  | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2800000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 882 | Gas cylinder |  | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2000000 | 2000000 |  | CGN |  |  |  | 2000000 | 100% |  |  | 0 | complete
WATER | 883 | Gas cylinder |  | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1000000 | 998800 |  | CGN |  |  |  | 998800 | 100% |  |  | 0 | complete
WATER | 884 | Nyakanja community forest |  | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2400000 | 1996644 |  | CGN |  |  |  | 1996644 | 100% |  |  | 0 | complete
WATER | 885 | Civil works (others) |  | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 886 | Nduthi irrigation project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 887 | Kanjauu dam | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 4000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 888 | Gatumbero irrigation project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | complete
WATER | 889 | Land acquisition |  | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 890 | Kega Irrigation project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 2000000 | 1999991 |  | CGN |  |  |  | 1999991 | 100% |  |  | 0 | complete
WATER | 891 | Kangocho irrigation project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 892 | Njabini water project | water distribution | Enhanced water supply | 100HH |  | Njabini | Njabini |  |  | 2018-07-01 | 2019-06-30 |  | 250000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | yes | Environmental: Controlled erosion, minimized vegetation loss, and ensured proper waste and water quality management. Social: Engaged local stakeholders, addressed land access issues, and established a grievance redress mechanism. Occupational Health & Safety: Provided PPE, safety training, and emergency response plans for workers. Gender: Promoted women and youth participation, created inclusive job opportunities, and implemented GBV/SEA prevention measures.
WATER | 893 | Gatahara water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 250000 | 250000 |  | CGN |  |  |  | 250000 | 100% |  |  | 0 | complete
WATER | 894 | Kasuku borehole water project | water distribution | Enhanced water supply | [6 empty] | 2018-07-01 | 2019-06-30 |  | 350000 | 249800 |  | CGN |  |  |  | 249800 | 100% |  |  | 0 | Complete
WATER | 895 | Line Moja Water tank | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3000000 | 2993669 |  | CGN |  |  |  | 2993669 | 100% |  |  | 0 | Complete
WATER | 896 | Supply of tanks | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2019-07-01 | 2020-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 897 | Tulaga- Muruaki- Ngwataniro intake expansion | desilting | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2019-07-01 | 2020-06-30 |  | 1800000 | 1502632 |  | CGN |  |  |  | 1502632 | 100% |  |  | 0 | Complete
WATER | 898 | KIKANAMUKU water supply A | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2019-07-01 | 2020-06-30 |  | 3000000 | 2999325 |  | CGN |  |  |  | 2999325 | 100% |  |  | 0 | Complete
WATER | 899 | KIKANAMUKU water supply B | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2019-07-01 | 2020-06-30 |  | 2000000 | 1999720 |  | CGN |  |  |  | 1999720 | 100% |  |  | 0 | Complete
WATER | 900 | Githae/Umoja Water project Intake construction | Intake construction | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2019-07-01 | 2020-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 901 | N. Kinangop water Tanks supply | water tanks supply | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2019-07-01 | 2020-06-30 |  | 1300000 | 1300000 |  | CGN |  |  |  | 1300000 | 100% |  |  | 0 | Complete
WATER | 902 | Faru borehole solar panels installation | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  | 2500000 | 2498475 |  | CGN |  |  |  | 2498475 | 100% |  |  | 0 | Complete
WATER | 903 | Supply of pipes and fittings | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  | 350000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 904 | Engineer ward-other water works | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  | 1300000 | 1300000 |  | CGN |  |  |  | 1300000 | 100% |  |  | 0 | Complete
WATER | 905 | Engineer ward - Lower Munyaka | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | Complete
WATER | 906 | borehole EIA | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  |  |  |  | CGN | [7 empty] | 0 | Complete
WATER | 907 | Engineer ward - Lower Munyaka | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 908 | borehole hydrologeological survey and WRA | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  |  |  |  | CGN | [7 empty] | 0 | Complete
WATER | 909 | Lower Munyaka borehole drilling | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  | 1200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 910 | Lower Munyaka borehole Pump testing | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  | 100000 | 100000 |  | CGN |  |  |  | 100000 | 100% |  |  | 0 | Complete
WATER | 911 | Manyatta borehole water tower | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2019-07-01 | 2020-06-30 |  | 2200000 | 2199944 |  | CGN |  |  |  | 2199944 | 100% |  |  | 0 | Complete
WATER | 912 | Muhonia Turasha | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2019-07-01 | 2020-06-30 |  | 2700000 | 2699424 |  | CGN |  |  |  | 2699424 | 100% |  |  | 0 | Complete
WATER | 913 | Muhonia Turasha WP emergency works * | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2019-07-01 | 2020-06-30 |  | 600000 | 599970 |  | CGN |  |  |  | 599970 | 100% |  |  | 0 | Complete
WATER | 914 | 3M water Project construction of 100m3 masonry tank | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2019-07-01 | 2020-06-30 |  | 1800000 | 1800000 |  | CGN |  |  |  | 1800000 | 100% |  |  | 0 | Complete
WATER | 915 | 3 M water project - Distribution of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2019-07-01 | 2020-06-30 |  | 1300000 | 1299219 |  | CGN |  |  |  | 1299219 | 100% |  |  | 0 | Complete
WATER | 916 | Kagongo water project Elevation of tank | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2019-07-01 | 2020-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 917 | Micharage Water project- Supply of pipes | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2019-07-01 | 2020-06-30 |  | 1000000 | 998235 |  | CGN |  |  |  | 998235 | 100% |  |  | 0 | Complete
WATER | 918 | Mwarangu Dam Desilting | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2019-07-01 | 2020-06-30 |  | 2500000 | 2497950 |  | CGN |  |  |  | 2497950 | 100% |  |  | 0 | Complete
WATER | 919 | Kihuho borehole water project Distribution pf pipes | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2019-07-01 | 2020-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 920 | Gwa- kiongo water project Purchase and laying pipes for distribution network | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2019-07-01 | 2020-06-30 |  | 2000000 | 1997457 |  | CGN |  |  |  | 1997457 | 100% |  |  | 0 | Complete
WATER | 921 | Kamichege water project distribution pipes and fencing | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3000000 | 2998170 |  | CGN |  |  |  | 2998170 | 100% |  |  | 0 | Complete
WATER | 922 | Plastic tanks Supply of tanks | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 800000 | 800000 |  | CGN |  |  |  | 800000 | 100% |  |  | 0 | Complete
WATER | 923 | Wiyumiririe borehole - supply of pipes and construction of water kiosk | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 924 | Kanjuiri borehole- EIA | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2019-07-01 | 2020-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | Complete
WATER | 925 | Kanjuiri borehole - Drilling | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2019-07-01 | 2020-06-30 |  | 1200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 926 | Kanjuiri borehole- pump testing | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2019-07-01 | 2020-06-30 |  | 100000 | 100000 |  | CGN |  |  |  | 100000 | 100% |  |  | 0 | Complete
WATER | 927 | Kanjuiri borehole- Installation of solar panels and construction of power house | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2019-07-01 | 2020-06-30 |  | 2800000 | 2800000 |  | CGN |  |  |  | 2800000 | 100% |  |  | 0 | Complete
WATER | 928 | Uhuru water project - fittings and laying of pipe to Tumaini | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2019-07-01 | 2020-06-30 |  | 1500000 | 1499400 |  | CGN |  |  |  | 1499400 | 100% |  |  | 0 | Complete
WATER | 929 | Uhuru Water Project - supply of Pipes network to Tumaini Town | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2019-07-01 | 2020-06-30 |  | 2000000 | 2000000 |  | CGN |  |  |  | 2000000 | 100% |  |  | 0 | Complete
WATER | 930 | Nyaituga Water Project - Pipe supply | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2019-07-01 | 2020-06-30 |  | 1640000 | 1639575 |  | CGN |  |  |  | 1639575 | 100% |  |  | 0 | Complete
WATER | 931 | Leshau karagoini extension of water distribution network Baari, Mungetho and Mutanga area | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3870000 | 3870000 |  | CGN |  |  |  | 3870000 | 100% |  |  | 0 | Complete
WATER | 932 | Leshau karagoini extension of water distribution network Kimaru, Ritaya and Mairo Inya town | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2500000 | 2500000 |  | CGN |  |  |  | 2500000 | 100% |  |  | 0 | Complete
WATER | 933 | Water Tanks for the elderly |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 980000 | 979947 |  | CGN |  |  |  | 979947 | 100% |  |  | 0 | Complete
WATER | 934 | 5,000Ltr Tanks for Nairobi ECD and Maguna ECD including guttering |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 935 | Mung'etho water project supply and installation of 2No. 10,000Ltr Tanks |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 250000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 936 | Karagoini Laying of pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 937 | Kiandege Pry School Laying of pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 200000 | 199999 |  | CGN |  |  |  | 199999 | 100% |  |  | 0 | Complete
WATER | 938 | Gwakung'u market water tank and guttering |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 200000 | 199038 |  | CGN |  |  |  | 199038 | 100% |  |  | 0 | Complete
WATER | 939 | ECDE (Kihingo, Kwa Njora, Ndogino, Kirera, Mithuri, Mayuu, Muthomi, Karai, Ngawa, Kahuho, Pondo Pry, Muthiga,Githima, Raicheri, Mbuyu Primary and Kware |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3400000 | 3394960 |  | CGN |  |  |  | 3394960 | 100% |  |  | 0 | Complete
WATER | 940 | Kirera Welfare | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 200000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Complete
WATER | 941 | Nyakinyua village piping | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 942 | Kagondo village piping | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 400000 | 399735 |  | CGN |  |  |  | 399735 | 100% |  |  | 0 | Complete
WATER | 943 | Nyakinyua welfare | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 944 | DM dam supply and intallation of pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2000000 | 1998446 |  | CGN |  |  |  | 1998446 | 100% |  |  | 0 | Complete
WATER | 945 | DM dam- Construction of 225m3 masonry tank |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3300000 | 2959648 |  | CGN |  |  |  | 2959648 | 100% |  |  | 0 | Complete
WATER | 946 | DM dam- Supply and installation of solar panels |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1746000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 947 | DM dam- Supply and installation of booster pump |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1104000 | 1103306 |  | CGN |  |  |  | 1103306 | 100% |  |  | 0 | Complete
WATER | 948 | Water distribution works- piping | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2300000 | 2299174 |  | CGN |  |  |  | 2299174 | 100% |  |  | 0 | Complete
WATER | 949 | Mithuri Water Project piping | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 950 | Madaraka Borehole Shamata Extension and laying of pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2300000 | 2299080 |  | CGN |  |  |  | 2299080 | 100% |  |  | 0 | Complete
WATER | 951 | Upper Shamata borehole Drilling |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1800000 | 1619417 |  | CGN |  |  |  | 1619417 | 100% |  |  | 0 | Complete
WATER | 952 | Simbara pipe laying |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1400000 | 1400000 |  | CGN |  |  |  | 1400000 | 100% |  |  | 0 | Complete
WATER | 953 | Shamata village- Pipe laying | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 800000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Complete
WATER | 954 | Pesi township borehole Drilling |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1200000 | 1200000 |  | CGN |  |  |  | 1200000 | 100% |  |  | 0 | Complete
WATER | 955 | Pesi township borehole pump testing |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 100000 | 100000 |  | CGN |  |  |  | 100000 | 100% |  |  | 0 | Complete
WATER | 956 | Pesi township borehole fencing, construction of panel house and water tower |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2200000 | 2199945 |  | CGN |  |  |  | 2199945 | 100% |  |  | 0 | Complete
WATER | 957 | Pesi township borehole installation of pump and solar system |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 4000000 | 3999450 |  | CGN |  |  |  | 3999450 | 100% |  |  | 0 | Complete
WATER | 958 | Shamata - Aberdare borehole EIA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 60000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 959 | Shamata - Aberdare borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 900000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 960 | Shamata - Aberdare borehole pump |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 961 | Aberdare borehole fencing, construction of panel house and water tower |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2200000 | 2199945 |  | CGN |  |  |  | 2199945 | 100% |  |  | 0 | Complete
WATER | 962 | Shamata Township Supply of pipes |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2000000 | 1999904 |  | CGN |  |  |  | 1999904 | 100% |  |  | 0 | Complete
WATER | 963 | Kirimanjaro Supply of Pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 964 | Guthunguri bore hole | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 965 | Bosinia Borehole | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 400000 | 400000 |  | CGN |  |  |  | 400000 | 100% |  |  | 0 | Complete
WATER | 966 | Maran Water project | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3400000 | 3396810 |  | CGN |  |  |  | 3396810 | 100% |  |  | 0 | Complete
WATER | 967 | Rurii- Maran Water |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 968 | Rurii-Kimende borehole EIA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | Complete
WATER | 969 | Rurii-Kimende borehole- Hydrological |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 970 | Kimende borehole pump testing |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 971 | Rurii-Matara borehole EIA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | Complete
WATER | 972 | Rurii- Matara borehole- Hydrological |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 973 | Matara borehole drilling and pump testing |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2400000 | 400000 |  | CGN |  |  |  | 400000 | 100% |  |  | 0 | Complete
WATER | 974 | Githungurig borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 600000 | 600000 |  | CGN |  |  |  | 600000 | 100% |  |  | 0 | Complete
WATER | 975 | Karau ward-Kahuho borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1300000 | 198815 |  | CGN |  |  |  | 198815 | 100% |  |  | 0 | Complete
WATER | 976 | Karau- Kianda borehole- drilling, Submersible pump and solar panels |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 4000000 | 3999975 |  | CGN |  |  |  | 3999975 | 100% |  |  | 0 | Complete
WATER | 977 | Muiri Water Project solar and supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2200000 | 2199047 |  | CGN |  |  |  | 2199047 | 100% |  |  | 0 | Complete
WATER | 978 | Karau- Muiri Borehole distribution | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1600000 | 1600000 |  | CGN |  |  |  | 1600000 | 100% |  |  | 0 | Complete
WATER | 979 | Kaimbaga- Kamande borehole EIA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 60000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 980 | Kaimbaga- Kamande borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 90000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 981 | Kaimbaga - Kamande borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3800000 | 3799950 |  | CGN |  |  |  | 3799950 | 100% |  |  | 0 | Complete
WATER | 982 | Kaimbaga - Kamande borehole power |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 250000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 983 | Kaimbaga - Kamande borehole pump |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 100000 | 100000 |  | CGN |  |  |  | 100000 | 100% |  |  | 0 | Complete
WATER | 984 | Kaimbaga- Gichungo borehole EIA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 60000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 985 | Kaimbaga- Gichungo borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 90000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 986 | Kaimbaga- Gichungo borehole pump |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 987 | Kaimbaga- Mwireri borehole EIA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 60000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 988 | Kaimbaga- Mwireri borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 90000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 989 | Kaimbaga - Gichungo and Mwireri Boreholes drilling |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 4000000 | 3999966 |  | CGN |  |  |  | 3999966 | 100% |  |  | 0 | Complete
WATER | 990 | Kaimbaga - Canaan IDP water distribution |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | Complete
WATER | 991 | Kaimbaga- Drilling of Kamande, Kieni |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 4000000 | 3999910 |  | CGN |  |  |  | 3999910 | 100% |  |  | 0 | Complete
WATER | 992 | Kaimbaga- Mwireri borehole power |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 250000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 993 | Kaimbaga- Mwireri borehole pump |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 994 | Geta - Kiaibabu intake EIA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 60000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 995 | Kiaibabu common intake construction and water networks extension |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 996 | Supply of 6 tanks to ECDE schools |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 400000 | 399966 |  | CGN |  |  |  | 399966 | 100% |  |  | 0 | Complete
WATER | 997 | Iganjo water project Pipes laying | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 150000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 998 | Mihato water project – supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 999 | Kanyiriri WP pipes and extension of water works | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 500000 | 499905 |  | CGN |  |  |  | 499905 | 100% |  |  | 0 | Complete
WATER | 1000 | Marimu WP pipes and extension of water works | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 400000 | 398999 |  | CGN |  |  |  | 398999 | 100% |  |  | 0 | Complete
WATER | 1001 | Kariua Water project pipes and extension of water works | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 450000 | 449995 |  | CGN |  |  |  | 449995 | 100% |  |  | 0 | Complete
WATER | 1002 | Kagongo WP installation of pipe |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1400000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1003 | Canadian Water Project Rehabilitation and Expansion | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2500000 | 2499600 |  | CGN |  |  |  | 2499600 | 100% |  |  | 0 | Complete
WATER | 1004 | Mawingu water | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1005 | Gathiriga pipeline pipingS | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 1006 | Muhonia water project piping | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2000000 | 2000000 |  | CGN |  |  |  | 2000000 | 100% |  |  | 0 | Complete
WATER | 1007 | Water tanks for the elderly and vulnerable Distribution network |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1008 | Supply of water tanks to ECDEs |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 300000 | 299808 |  | CGN |  |  |  | 299808 | 100% |  |  | 0 | Complete
WATER | 1009 | Bondeni water project Construction of 50M3 storage |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1200000 | 1200000 |  | CGN |  |  |  | 1200000 | 100% |  |  | 0 | Complete
WATER | 1010 | Kipipiri Water Project - Supply and Delivery of pipes for distribution | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 300000 | 299250 |  | CGN |  |  |  | 299250 | 100% |  |  | 0 | Complete
WATER | 1011 | Kipipiri Lereshwa Water Project - Raising main and distribution of water pipes (system) | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2000000 | 1998276 |  | CGN |  |  |  | 1998276 | 100% |  |  | 0 | Complete
WATER | 1012 | Machinery Lereshwa line rehabilitation | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete
WATER | 1013 | Supply and Delivery of 500L Water Tanks |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1300000 | 1299375 |  | CGN |  |  |  | 1299375 | 100% |  |  | 0 | Complete
WATER | 1014 | Rironi Borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3000000 | 2992500 |  | CGN |  |  |  | 2992500 | 100% |  |  | 0 | Complete
WATER | 1015 | Gatondo Water Project Tank construction, raising amin, testing and power connection |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1016 | Gaturufari water in-take project develoment |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 300000 | 300000 |  | CGN |  |  |  | 300000 | 100% |  |  | 0 | Complete
WATER | 1017 | Kipipiri water project integrated piping | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 1499498 |  | CGN |  |  |  | 1499498 | 100% |  |  | 0 | Complete
WATER | 1018 | Wanjohi-Gatei Water pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1000000 | 999820 |  | CGN |  |  |  | 999820 | 100% |  |  | 0 | Complete
WATER | 1019 | Ol'Joro'Orok Secondary School Water supply and erection of tanks |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 1020 | Madaraka Water project solar installation |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2500000 | 2494747 |  | CGN |  |  |  | 2494747 | 100% |  |  | 0 | Complete
WATER | 1021 | Karandi water project- solar installation |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2500000 | 2499000 |  | CGN |  |  |  | 2499000 | 100% |  |  | 0 | Complete
WATER | 1022 | Karandi water project- pump installation |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1023 | kariko water project solar system installation |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2500000 | 2493750 |  | CGN |  |  |  | 2493750 | 100% |  |  | 0 | Complete
WATER | 1024 | Gathanji - Kwa Ngara borehole EIA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | Complete
WATER | 1025 | Gathanji - Kwa Ngara borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 1026 | Kwa Ngara dam borehole- Supply and laying of pipes |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1450000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1027 | Kwa Ngara borehole pump testing |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 100000 | 100000 |  | CGN |  |  |  | 100000 | 100% |  |  | 0 | Complete
WATER | 1028 | Kwa Ngara borehole equipping |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1029 | Gathanji - Njoro borehole pipe extension to Boiman Township | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1250000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1030 | Mung'etho Township- Supply and laying of pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1031 | Kagema borehole (EIA, hydro-geological survey and WRA and drilling) |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2550000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1032 | Charagita - Nyairoko water borehole Hydrological Survey and WARA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 30000 | 30000 |  | CGN |  |  |  | 30000 | 100% |  |  | 0 | Complete
WATER | 1033 | Nyairoko water borehole drilling and test pumping |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2400000 | 2399145 |  | CGN |  |  |  | 2399145 | 100% |  |  | 0 | Complete
WATER | 1034 | Supply and laying of pipes- Charagita | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2020000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1035 | Nyakanja 300m3 Concrete construction of water tanks |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 5500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1036 | Kanguu water tank- Supply | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2000000 | 1999935 |  | CGN |  |  |  | 1999935 | 100% |  |  | 0 | Complete
WATER | 1037 | of 6-inch supply pipes | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  |  |  |  | CGN | [7 empty] | 0 | Complete
WATER | 1038 | Gikingi Water Project- piping | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3000000 | 3000000 |  | CGN |  |  |  | 3000000 | 100% |  |  | 0 | Complete
WATER | 1039 | Magumu-Mwenda-adu Hydrological |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions taken include minimizing environmental disturbance during survey activities, ensuring occupational health and safety through provision of personal protective equipment (PPE), involving the local community to address social concerns, promoting gender inclusion in consultations, and establishing a grievance redress mechanism to manage complaints promptly and fairly.
WATER | 1040 | Survey and WRA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  |  |  |  | CGN | [7 empty] | 0 | Complete
WATER | 1041 | Mwenda-adu Construction of Water Tower |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 1610000 | 1610000 |  | CGN |  |  |  | 1610000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included erosion control, community engagement, safety training and PPE use for workers, and promotion of gender inclusion to ensure fair participation and benefit-sharing.
WATER | 1042 | Mwenda-adu Pump Testing |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 100000 | 100000 |  | CGN |  |  |  | 100000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included proper wastewater management, use of protective gear, enforcement of safety protocols, and inclusive stakeholder engagement to promote gender equity and environmental protection.
WATER | 1043 | Magumu- Upper Gitwe borehole EIA |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 1044 | Magumu- Upper Gitwe borehole |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 1045 | Upper Gitwe borehole pump testing |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 100000 | 100000 |  | CGN |  |  |  | 100000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included proper wastewater management, use of protective gear, enforcement of safety protocols, and inclusive stakeholder engagement to promote gender equity and environmental protection.
WATER | 1046 | Upper Gitwe borehole drilling |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 2000000 | 1139424 |  | CGN |  |  |  | 1139424 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included proper wastewater management, use of protective gear, enforcement of safety protocols, and inclusive stakeholder engagement to promote gender equity and environmental protection.
WATER | 1047 | Gitwe borehole supply of pipes | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 360000 | 360000 |  | CGN |  |  |  | 360000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included safe excavation and backfilling, provision of PPE to workers, community sensitization, inclusive stakeholder engagement, and proper waste management to minimize health, safety, environmental, and gender-related risks.
WATER | 1048 | Nyakio Ward- Haraka Borehole EIA |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | Complete | [11 empty] | yes | key mitigation measures included safe waste disposal, use of protective gear, community sensitization, inclusive consultations, promotion of fair labor practices, and control of dust, noise, and water use to safeguard people and the environment.
WATER | 1049 | Nyakio Ward- Haraka Borehole |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 1050 | Haraka Borehole- drilling |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 1200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 1051 | Haraka Borehole Construction of Water Tower and Installation of Tanks, Power house and Fencing and Kiosk |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 2500000 | 639300 |  | CGN |  |  |  | 639300 | 100% |  |  | 0 | Complete | [11 empty] | yes | The screening for the Haraka Borehole project in Nyakio Ward led to actions such as proper waste management, use of PPE, safety signage, community engagement, gender inclusion, and environmental protection to ensure health, safety, and social safeguards during construction.
WATER | 1052 | Haraka Borehole-Installation of Submersible Pump and solar panels |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 3450000 | 3450000 |  | CGN |  |  |  | 3450000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures, included proper waste disposal, dust and noise control, stakeholder engagement with gender inclusivity, provision of PPE to workers, safety signage, and adherence to national occupational health standards to ensure environmental protection, social equity, and worker safety.
WATER | 1053 | Haraka Borehole - Supply and laying of pipes |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 500000 | 500000 |  | CGN |  |  |  | 500000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Potential impacts and implemented mitigation measures included ensuring proper waste management and disposal, minimizing dust and noise pollution during trenching and laying activities, using appropriate signage and personal protective equipment (PPE) for workers, conducting public awareness and stakeholder consultations with gender inclusivity, restoring affected sites post-installation, and ensuring occupational safety standards were observed throughout the project.
WATER | 1054 | phase 2 EIA, hydrogeological survey and WRA, borehole drilling and test pumping |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 2650000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | Identified key risks and implemented targeted mitigation measures included adherence to EIA recommendations, ensuring licensed and environmentally compliant borehole drilling practices, provision of personal protective equipment (PPE) for workers, management of drilling waste to avoid contamination, engagement with local communities (with attention to gender inclusion), and compliance with WRA regulations to safeguard water sustainability and equitable access.
WATER | 1055 | Phase 2 WP - Supply and installation of submersible pump |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 1900000 | 1794311 |  | CGN |  |  |  | 1794311 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental risks, measures such as appropriate siting of equipment, waste management, and protection of water sources have been enforced. Social mitigation involved community sensitization and engagement to enhance local participation and address potential concerns. Occupational health and safety risks have been mitigated by ensuring the use of personal protective equipment (PPE), adherence to safe installation procedures, and provision of safety training to workers. Gender considerations included promoting inclusivity in project participation, ensuring that women and vulnerable groups benefit from improved water access, and safeguarding against any form of discrimination or gender-based violence during implementation.
WATER | 1056 | Phase 2 WP Fencing, construction of water kiosk and power house |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | The screening for the Haraka Borehole project in Nyakio Ward led to actions such as proper waste management, use of PPE, safety signage, community engagement, gender inclusion, and environmental protection to ensure health, safety, and social safeguards during construction.
WATER | 1057 | Phase 2- Construction of water tower and supply of 2No. 10,000Ltrs tanks |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 1600000 | 1572165 |  | CGN |  |  |  | 1572165 | 100% |  |  | 0 | Complete | [11 empty] | yes | Identified potential risks and instituted mitigation measures included ensuring the structural safety of the elevated tank through approved engineering designs, provision of personal protective equipment (PPE) to workers, secure fencing of the site to prevent accidents, enforcement of gender-inclusive hiring practices, and regular stakeholder engagement to ensure community needs and environmental concerns were addressed throughout the project implementation.
WATER | 1058 | Ndothua WP - Supply and installation of submersible pump |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 1900000 | 1899450 |  | CGN |  |  |  | 1899450 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures, included proper waste disposal, dust and noise control, stakeholder engagement with gender inclusivity, provision of PPE to workers, safety signage, and adherence to national occupational health standards to ensure environmental protection, social equity, and worker safety.
WATER | 1059 | Ndothua Fencing, construction of water kiosk and power house |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 800000 | 794688 |  | CGN |  |  |  | 794688 | 100% |  |  | 0 | Complete | [11 empty] | yes | The screening led to actions such as proper waste management, use of PPE, safety signage, community engagement, gender inclusion, and environmental protection to ensure health, safety, and social safeguards during construction.
WATER | 1060 | Ndothua Construction of water tower and supply of 2No. 10,000Ltrs tanks |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 1600000 | 1600000 |  | CGN |  |  |  | 1600000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Identified potential risks and instituted mitigation measures included ensuring the structural safety of the elevated tank through approved engineering designs, provision of personal protective equipment (PPE) to workers, secure fencing of the site to prevent accidents, enforcement of gender-inclusive hiring practices, and regular stakeholder engagement to ensure community needs and environmental concerns were addressed throughout the project implementation.
WATER | 1061 | Gwa Senior WP - Installation of submersible pump |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 800000 | 791800 |  | CGN |  |  |  | 791800 | 100% |  |  | 0 | Complete
WATER | 1062 | Gwa Senior WP constructionVof 2No. water kiosks and power house |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 800000 | 800000 |  | CGN |  |  |  | 800000 | 100% |  |  | 0 | Complete
WATER | 1063 | Gwa Senior WP Construction of water tower and supply of 1No. 10,000Ltrs tanks |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete
WATER | 1064 | Gwa Senior WP- Installation of solar panels |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1900000 | 1898320 |  | CGN |  |  |  | 1898320 | 100% |  |  | 0 | Complete
WATER | 1065 | Gwa Senior WP pipe laying | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 200000 | 200000 |  | CGN |  |  |  | 200000 | 100% |  |  | 0 | Complete
WATER | 1066 | Heni Borehole drilling and test pumping |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 1900000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 1067 | Heni WP Construction of water tower and supply of 2No. 10,000Ltrs tanks |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 1600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | The screening led to actions such as proper waste management, use of PPE, safety signage, community engagement, gender inclusion, and environmental protection to ensure health, safety, and social safeguards during construction.
WATER | 1068 | Karuang'i water project extension of water networks distribution | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | yes | several mitigation actions were implemented. These include safe excavation practices to prevent soil erosion and protect existing ecosystems, provision of personal protective equipment (PPE) for all workers to ensure occupational safety, engagement of both men and women in project activities to promote gender equity, and community sensitization meetings to address social concerns and promote project ownership. Additionally, clear signage and traffic control measures were put in place to safeguard public safety during pipe laying.
WATER | 1069 | Korobois borehole drilling and test pumping |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 2150000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 1070 | Korobois borehole installation of submersible pump and solar panels |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 3450000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures, included proper waste disposal, dust and noise control, stakeholder engagement with gender inclusivity, provision of PPE to workers, safety signage, and adherence to national occupational health standards to ensure environmental protection, social equity, and worker safety.
WATER | 1071 | Korobois construction of control panel house, fencing and plastic tank |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 1100000 | 1100000 |  | CGN |  |  |  | 1100000 | 100% |  |  | 0 | Complete | [11 empty] | yes | various mitigation measures were undertaken. These included ensuring the use of personal protective equipment (PPE) for all workers to uphold occupational safety standards, incorporating proper waste disposal and dust suppression methods to minimize environmental impacts, engaging both men and women equitably in the project to promote gender inclusion, and fencing the site to prevent accidents and unauthorized access. Public awareness and community consultations were also conducted to address social concerns and ensure local support.
WATER | 1072 | Kanyawa Borehole Test Pumping |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 100000 | 84800 |  | CGN |  |  |  | 84800 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included proper wastewater management, use of protective gear, enforcement of safety protocols, and inclusive stakeholder engagement to promote gender equity and environmental protection.
WATER | 1073 | Gitundu borehole Rehabilitation |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1200000 | 1190000 |  | CGN |  |  |  | 1190000 | 100% |  |  | 0 | Complete
WATER | 1074 | Tia Wira water pump | Water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2019-07-01 | 2020-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1075 | Tia wira solar structures and panels | Water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2019-07-01 | 2020-06-30 |  | 1700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1076 | Tia wira water towers and plastic tanks | Water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2019-07-01 | 2020-06-30 |  | 1200000 | 1197000 |  | CGN |  |  |  | 1197000 | 100% |  |  | 0 | Complete
WATER | 1077 | Wanjohi Secondary School Borehole |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2000000 | 2000000 |  | CGN |  |  |  | 2000000 | 100% |  |  | 0 | Complete
WATER | 1078 | Solar Power Installation and Equiping of Kanyawa Borehole |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 3000000 | 3000000 |  | CGN |  |  |  | 3000000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included proper wastewater management, use of protective gear, enforcement of safety protocols, and inclusive stakeholder engagement to promote gender equity and environmental protection.
WATER | 1079 | Rwanyambo Bore hole Pipes | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Potential impacts and implemented mitigation measures included ensuring proper waste management and disposal, minimizing dust and noise pollution during trenching and laying activities, using appropriate signage and personal protective equipment (PPE) for workers, conducting public awareness and stakeholder consultations with gender inclusivity, restoring affected sites post-installation, and ensuring occupational safety standards were observed throughout the project. Potential impacts and implemented mitigation measures included ensuring proper waste management and disposal, minimizing dust and noise pollution during trenching and laying activities, using appropriate signage and personal protective equipment (PPE) for workers, conducting public awareness and stakeholder consultations with gender inclusivity, restoring affected sites post-installation, and ensuring occupational safety standards were observed throughout the project.
WATER | 1080 | Soko mpya water supply | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2019-07-01 | 2020-06-30 |  | 3000000 | 2992489 |  | CGN |  |  |  | 2992489 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation actions were undertaken including ensuring environmentally sound water distribution by preventing leakages and soil erosion, enforcing the use of personal protective equipment (PPE) by workers to enhance occupational safety, and conducting community sensitization on safe water use. The project also incorporated measures to promote gender equity by engaging women and vulnerable groups in decision-making processes. Additionally, proper waste disposal methods were implemented during installation to minimize pollution and maintain public health standards.
WATER | 1081 | Rumathi borehole fencing, control panel house and tank connections |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 1499991 |  | CGN |  |  |  | 1499991 | 100% |  |  | 0 | Complete
WATER | 1082 | kandutura borehole water tower |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1800000 | 1799928 |  | CGN |  |  |  | 1799928 | 100% |  |  | 0 | Complete
WATER | 1083 | Purchase of Water Tanks for the vulnerable communities |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2000000 | 2000000 |  | CGN |  |  |  | 2000000 | 100% |  |  | 0 | Complete
WATER | 1084 | Cleaning of drains in Sub County Headquaters (Ndaragwa,Ol,joro,orok, Ol,kalou, Miharati and Engineer) |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1920000 | 1920000 |  | CGN |  |  |  | 1920000 | 100% |  |  | 0 | Complete
WATER | 1085 | Extension of Kamutharaba line | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 500000 | 499634 |  | CGN |  |  |  | 499634 | 100% |  |  | 0 | Complete
WATER | 1086 | ol'Kalou arboretum Tree planting |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete
WATER | 1087 | Desilting of dams |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2600000 |  |  | CGN | [7 empty] | 0 | Complete
WATER | 1088 | Establishment of green houses for Bamboo propagation and tree nurseries in Njabini ATC, Ol,joro,orok ATC and Ol,kalou Polytechnic EIA |  | Enhanced water supply |  |  | Njabini | Magumu,Njabini |  |  | 2019-07-01 | 2020-06-30 |  | 50000 |  |  | CGN | [7 empty] | 0 | Complete | [11 empty] | yes | Several mitigation measures were implemented. These included careful site selection to prevent ecological disruption, construction of appropriate drainage to manage water runoff, and the use of organic materials to reduce chemical exposure. Occupational safety was enhanced through the training of workers and provision of personal protective equipment (PPE). Gender equity and inclusion were promoted by involving youth, women, and marginalized groups in the project. Additionally, proper waste disposal protocols were put in place to ensure environmental cleanliness and safety.
WATER | 1089 | Ol'Kalou arboretum Environment and Social Impact Assessment - ESIA |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 300000 | 300000 |  | CGN |  |  |  | 300000 | 100% |  |  | 0 | Complete
WATER | 1090 | Kianjogu Water project - | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1800000 | 1800000 |  | CGN |  |  |  | 1800000 | 100% |  |  | 0 | Complete
WATER | 1091 | Mumui spring water | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2500000 |  |  | CGN | [7 empty] | 0 | Complete
WATER | 1092 | College/Kianjata irrigation project | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 2500000 | 2500000 |  | CGN |  |  |  | 2500000 | 100% |  |  | 0 | Complete
WATER | 1093 | Jerusalem irrigation water project | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete
WATER | 1094 | Kega irrigation WP | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 1499400 |  | CGN |  |  |  | 1499400 | 100% |  |  | 0 | Complete
WATER | 1095 | Kanjangiri project Construction of 50 m3 masonry tank |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1200000 | 1199577 |  | CGN |  |  |  | 1199577 | 100% |  |  | 0 | Complete
WATER | 1096 | JM Weir in Aberdare Forest |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3680000 | 3679935 |  | CGN |  |  |  | 3679935 | 100% |  |  | 0 | Complete
WATER | 1097 | Kanjangiri Water project- | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 300000 | 299670 |  | CGN |  |  |  | 299670 | 100% |  |  | 0 | Complete
WATER | 1098 | Mubiriti Common intake | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1300000 | 1299270 |  | CGN |  |  |  | 1299270 | 100% |  |  | 0 | Complete
WATER | 1099 | Pesi WP water tanks | water distribution | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 1500000 | 1499925 |  | CGN |  |  |  | 1499925 | 100% |  |  | 0 | Complete
WATER | 1100 | Ol’Kalou arboretum |  | Enhanced water supply | [6 empty] | 2019-07-01 | 2020-06-30 |  | 3278000 |  |  | CGN | [7 empty] | 0 | Complete
WATER | 1101 | Gathaara-Assorted Supply and laying of pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 3000000 | 2999910 |  | CGN |  |  |  | 2999910 | 100% |  |  | 0 | Complete
WATER | 1102 | Gathaara- Supply of 500litre water tanks | roof harvesting | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2000000 | 1993575 |  | CGN |  |  |  | 1993575 | 100% |  |  | 0 | Complete
WATER | 1103 | Gathaara- Construction of 100m³ masonry tank- Gaitha | storage facility | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 3000000 | 2998904 |  | CGN |  |  |  | 2998904 | 100% |  |  | 0 | Complete
WATER | 1104 | North Kinangop - Tia Wira Borehole-Installation of water pump and test pumping | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2020-07-01 | 2021-06-30 |  | 400000 | 300000 |  | CGN |  |  |  | 300000 | 100% |  |  | 0 | Complete
WATER | 1105 | North Kinangop - Githae water project supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2020-07-01 | 2021-06-30 |  | 3000000 | 2998400 |  | CGN |  |  |  | 2998400 | 100% |  |  | 0 | Complete
WATER | 1106 | North kinangop - Kirimire water project Construction of Water tower and installation of tanks | Enhanced water storage | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2020-07-01 | 2021-06-30 |  | 1500000 | 1492220 |  | CGN |  |  |  | 1492220 | 100% |  |  | 0 | Complete
WATER | 1107 | North kinangop - Gatamaiyu water project Construction of Water tower and installation of tanks | Enhanced water storage | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2020-07-01 | 2021-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1108 | North Kinangop- Supply of 500litres water tanks | roof harvesting | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2020-07-01 | 2021-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1109 | North Kinangop- Tia wira control panel house | enhanced solar powered system | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2020-07-01 | 2021-06-30 |  | 300000 | 300000 |  | CGN |  |  |  | 300000 | 100% |  |  | 0 | Complete
WATER | 1110 | North Kinangop- Kikana Muku supply of water pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2020-07-01 | 2021-06-30 |  | 1800000 | 1798920 |  | CGN |  |  |  | 1798920 | 100% |  |  | 0 | Complete
WATER | 1111 | Nyakio Ward- Assorted pipes, Tank and 2No. Water kiosks |  | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2020-07-01 | 2021-06-30 |  | 2000000 | 1349518 |  | CGN |  |  |  | 1349518 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation measures have been undertaken. These include ensuring safe pipe laying to minimize environmental disruption, enforcing occupational safety protocols through the use of PPE and site supervision, and sensitizing the community on project benefits and safety. Inclusive stakeholder engagement was conducted to ensure gender considerations and community ownership. Additionally, proper siting of kiosks was done to enhance accessibility while maintaining environmental integrity.
WATER | 1112 | Nyakio ward - Rwanyambo community borehole piping | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | yes | key mitigation actions were implemented. These included safe excavation and pipe laying practices to prevent environmental degradation, use of personal protective equipment (PPE) by workers to ensure occupational health and safety, and regular supervision to enforce safety standards. Gender-sensitive consultations were conducted to ensure inclusive participation, and community awareness was raised to foster cooperation and minimize social disruptions.
WATER | 1113 | Engineer ward - Thindi borehole equipping with solar system | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2020-07-01 | 2021-06-30 |  | 2500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1114 | Engineer ward - Lower Munyaka borehole drilling | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2020-07-01 | 2021-06-30 |  | 2200000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1115 | Engineer ward - Lower Munyaka borehole supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2020-07-01 | 2021-06-30 |  | 300000 | 298600 |  | CGN |  |  |  | 298600 | 100% |  |  | 0 | Complete
WATER | 1116 | Engineer Ward - Kang'utu borehole supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2020-07-01 | 2021-06-30 |  | 1200000 | 1053449 |  | CGN |  |  |  | 1053449 | 100% |  |  | 0 | Complete
WATER | 1117 | Engineer Ward - Thayu water project supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 1118 | Engineer Ward - Raitha Kahuru water project supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2020-07-01 | 2021-06-30 |  | 800000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1119 | Murungaru ward - Muhonia Turasha WP - Kagongo borehole drilling | Water source | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2020-07-01 | 2021-06-30 |  | 2300000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1120 | Murungaru ward - 3M water project construction of 100m3 masonry storage tank | storage facility | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2020-07-01 | 2021-06-30 |  | 1800000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1121 | Murungaru ward - Supply of 210 litre capacity water tanks | Roof harvesting | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2020-07-01 | 2021-06-30 |  | 2500000 | 2499200 |  | CGN |  |  |  | 2499200 | 100% |  |  | 0 | Complete
WATER | 1122 | Mirangine - Highwood borehole installation of the borehole with draw pipes , submersible pump, solar panels and support structure |  | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2020-07-01 | 2021-06-30 |  | 3850000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1123 | Mirangine - Highwood borehole drilling and supply of pipe for rising main and distribution network |  | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2020-07-01 | 2021-06-30 |  | 3700000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1124 | Mirangine- other water work | water distribution | Enhanced water supply |  |  | Olkalou | MIirangine |  |  | 2020-07-01 | 2021-06-30 |  | 1193800 | 1193000 |  | CGN |  |  |  | 1193000 | 100% |  |  | 0 | Complete
WATER | 1125 | Mirangine - kamuchege supply and laying of pipe for the rising main and distribution network | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2020-07-01 | 2021-06-30 |  | 3250000 | 3249385 |  | CGN |  |  |  | 3249385 | 100% |  |  | 0 | Complete
WATER | 1126 | Kanjuiri-Wiyumiririe WP-Supply of pipes | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2020-07-01 | 2021-06-30 |  | 2800000 | 2496500 |  | CGN |  |  |  | 2496500 | 100% |  |  | 0 | Complete
WATER | 1127 | Kanjuiri-Kirathimo Borehole- EIA |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2020-07-01 | 2021-06-30 |  | 60000 | - |  | CGN |  |  |  | - |  |  |  |  | Done
WATER | 1128 | Kanjuirii-Kirathimo Borehole- Drilling and casing and test pumping |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2020-07-01 | 2021-06-30 |  | 2400000 | - |  | CGN |  |  |  | - |  |  |  |  | Drilling done-Dry borehole
WATER | 1129 | Kanjuiri-Kirathimo Borehole-Supply and installation of submersible pump |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2020-07-01 | 2021-06-30 |  | 1900000 | - |  | CGN |  |  |  | - |  |  |  |  | Not done-Dry borehole
WATER | 1130 | Kanjuiri-Kirathimo Borehole-Construction of water tower and erection of 2No. 10m3 tanks |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2020-07-01 | 2021-06-30 |  | 1700000 | - |  | CGN |  |  |  | - |  |  |  |  | Not done-Dry borehole
WATER | 1131 | Kanjuiri-Kirathimo Borehole-Fencing and construction power house |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2020-07-01 | 2021-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | Not done-Dry borehole
WATER | 1132 | Kanjuiri-Kirathimo Borehole-Supply and installation of solar panels |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2020-07-01 | 2021-06-30 |  | 2500000 | - |  | CGN |  |  |  | - |  |  |  |  | Not Done( Borehole Dry)
WATER | 1133 | Kanjuiri-Wiyumiririe WP-Supply and laying of pipes and construction of water kiosk | water distribution | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 |  |  |  | 0 | Complete
WATER | 1134 | Kiriita- Starehe Kwa Njora WP Extension of Leshau Karagoini WP- Supply and laying of pipes | water distribution | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2020-07-01 | 2021-06-30 |  | 3000000 | 2999200 |  | CGN |  |  |  | 2999200 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR
WATER | 1135 | Leshau pondo-Supply of pipes | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2020-07-01 | 2021-06-30 |  | 2000000 | 1999950 |  | CGN |  |  |  | 1999950 | 100% |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1136 | Leshau pondo-Fencing of Muguruki dam |  | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | Yes | SPR recommended but project not implemented
WATER | 1137 | Leshau Pondo-Supply of 10000 litres water tank-Kanyagia Ecde |  | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2020-07-01 | 2021-06-30 |  | 250000 | 249900 |  | CGN |  |  |  | 249900 | 100% |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1138 | Leshau Pondo- Kandoro Borehole pump repair, pipes and KPLC Bills |  | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2020-07-01 | 2021-06-30 |  | 400000 | 400000 |  | CGN |  |  |  | 400000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1139 | Leshau Pondo- Kingi Dam Hydram and pipes |  | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2020-07-01 | 2021-06-30 |  | 300000 | 300000 |  | CGN |  |  |  | 300000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1140 | Ndaragwa Central- Muti-umwe Pry water project piping | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2020-07-01 | 2021-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | Yes | SPR recommended but project not implemented
WATER | 1141 | Central - supply and laying of pipes for the distribution network at kanyagia | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2020-07-01 | 2021-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | Yes | SPR
WATER | 1142 | Central - supply and laying of pipes for the distribution network at muruai | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2020-07-01 | 2021-06-30 |  | 3000000 | 2997006 |  | CGN |  |  |  | 2997006 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR
WATER | 1143 | Central - supply and laying of pipes for the distribution network at Mairo Kumi | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2020-07-01 | 2021-06-30 |  | 3000000 | 3000000 |  | CGN |  |  |  | 3000000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR
WATER | 1144 | Water tanks for the elderly- Shamata |  | Enhanced water supply |  |  | Ndaragwa | Shamata |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1145 | Shamata- Supply of water tanks to the vulnerable |  | Enhanced water supply |  |  | Ndaragwa | Shamata |  |  | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1146 | Shamata-Pesi -Supply and laying of pipes | water distribution | Enhanced water supply |  |  | Ndaragwa | Shamata |  |  | 2020-07-01 | 2021-06-30 |  | 4000000 | 4000000 |  | CGN |  |  |  | 4000000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR
WATER | 1147 | Shamata ward -Supply and laying of pipes-Shamata | water distribution | Enhanced water supply |  |  | Ndaragwa | Shamata |  |  | 2020-07-01 | 2021-06-30 |  | 4000000 | 4000000 |  | CGN |  |  |  | 4000000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR
WATER | 1148 | Rurii - Githunguri water project -Fencing and supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1600000 | 1600000 |  | CGN |  |  |  | 1600000 | 100% |  |  | 0 | Complete
WATER | 1149 | Kaheho- Plot 10 borehole EIA |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 60000 | 60000 |  | CGN |  |  |  | 60000 | 100% |  |  | 0 | Complete
WATER | 1150 | Kaheho borehole hydrogeological survey and WRA |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 90000 | 90000 |  | CGN |  |  |  | 90000 | 100% |  |  | 0 | Complete
WATER | 1151 | Kaheho- Plot 10 borehole Drilling, casing and test pumping |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2300000 | 2300000 |  | CGN |  |  |  | 2300000 | 100% |  |  | 0 | Complete
WATER | 1152 | Rurii-Kimende Borehole-Drilling, Casing and pump testing |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1153 | Rurii-Maran Borehole- Supply of pipes |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 600000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1154 | Rurii- Kahonge -Supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 600000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1155 | Rurii- Mugathika Borehole- Supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 600000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1156 | Rurii- Matara Borehole- Construction of water kiosk and installation of submersible pump | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1205000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1157 | Rurii- Supply of 5000litre tanks to ECDE Centres |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 500000 | 499992 |  | CGN |  |  |  | 499992 | 100% |  |  | 0 | Complete
WATER | 1158 | Rurii- Green slopes distribution pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 300000 | 299850 |  | CGN |  |  |  | 299850 | 100% |  |  | 0 | Complete
WATER | 1159 | Rurii- Kareko Wasquary piping | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1160 | Karau- Gachwe- Glad force borehole- Supply and installation of solar panels | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 450000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1161 | Karau- borehole- Renovation and repair of Muiri borehole | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 150000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1162 | Karau- Karugutu water spring- supply and installation of water pump and 10000litres water tank | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 300000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1163 | Karau- Supply and distribution of pipes for Ol'Kalou Township-Vatican AC Borehole | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 400000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1164 | Karau - Kirimaini water project supply and installation of submersible pump and solar panel. | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 4000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1165 | Karau- Kirimaini Borehole test pumping |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 94000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1166 | Karau - Kirimaini water project fencing and construction of a power house |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1167 | Karau - Munyeki secondary borehole water project- Supply and laying of distribution pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 500000 | 498500 |  | CGN |  |  |  | 498500 | 100% |  |  | 0 | Complete
WATER | 1168 | Karau- Kianda borehole- Supply and laying of distribution pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1169 | Karau ward- Kianda borehole- Fencing and construction of security house |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 756000 | 756000 |  | CGN |  |  |  | 756000 | 100% |  |  | 0 | Complete
WATER | 1170 | Kaimbaga - Supply and laying of distribution pipes in Bahati water project | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1171 | Kaimbaga - Supply of distribution pipes for Kaimbaga dispensary borehole water project | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1172 | Geta - construction of 50m³tank at kirima water project |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1200000 | 1199240 |  | CGN |  |  |  | 1199240 | 100% |  |  | 0 | Complete
WATER | 1173 | Geta - construction of 225m³tank at mihato water project |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 3800000 | 3797540 |  | CGN |  |  |  | 3797540 | 100% |  |  | 0 | Complete
WATER | 1174 | Geta - construction of 50m³tank at Kariahu water project |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1200000 | 1198064 |  | CGN |  |  |  | 1198064 | 100% |  |  | 0 | Complete
WATER | 1175 | Geta- Construction of Mibiriti intake |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 400000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1176 | Geta- Mibiriti water project supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 400000 | 400000 |  | CGN |  |  |  | 400000 | 100% |  |  | 0 | Complete
WATER | 1177 | Githioro Muhonia WP -Supply of pipes and fittings | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2600000 | 2600000 |  | CGN |  |  |  | 2600000 | 100% |  |  | 0 | Complete
WATER | 1178 | Githioro Karuri WP- Assorted pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 700000 | 699900 |  | CGN |  |  |  | 699900 | 100% |  |  | 0 | Complete
WATER | 1179 | Githioro 3M WP-Kwa Joshua: Construction of 50 M3 Masory tank |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1200000 | 1199120 |  | CGN |  |  |  | 1199120 | 100% |  |  | 0 | Complete
WATER | 1180 | Githioro Kimbo WP Supply of Pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 1181 | Githioro Mawingu WP- Pillars to Gathiriga | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 500000 | 499500 |  | CGN |  |  |  | 499500 | 100% |  |  | 0 | Complete
WATER | 1182 | Githioro-Mawingu WP- Githima ECDE-Construction of 50M3 masonry tank |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1200000 | 1196060 |  | CGN |  |  |  | 1196060 | 100% |  |  | 0 | Complete
WATER | 1183 | Githioro Aberdare-Tigoni -Extension of distribution line and pillars | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 800000 | 800000 |  | CGN |  |  |  | 800000 | 100% |  |  | 0 | Complete
WATER | 1184 | Kipipiri- Renovation and repair of Kahiga water tank |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 1185 | Kipipiri - supply and delivery of pipes -Kamahia WP | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1186 | Kipipiri- Construction of 50m³ masonry tank - Munyuini |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1200000 | 1192622 |  | CGN |  |  |  | 1192622 | 100% |  |  | 0 | Complete
WATER | 1187 | Kipipiri- Supply of pipes for Malewa and Munyuini Water projects | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 999100 |  | CGN |  |  |  | 999100 | 100% |  |  | 0 | Complete
WATER | 1188 | Kipipiri - supply and delivery of pipes -Leleshwa serving line | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 3000000 | 2999000 |  | CGN |  |  |  | 2999000 | 100% |  |  | 0 | Complete
WATER | 1189 | Wanjohi - Gatondo WP- Supply and laying of pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 3300000 | 3298000 |  | CGN |  |  |  | 3298000 | 100% |  |  | 0 | Complete
WATER | 1190 | Wanjohi - Rironi borehole solar system and supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2500000 | 2497500 |  | CGN |  |  |  | 2497500 | 100% |  |  | 0 | Complete
WATER | 1191 | Wanjohi- Supply of pipes to water groups (Munanda, Kairi, Chabuthwa) | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 999500 |  | CGN |  |  |  | 999500 | 100% |  |  | 0 | Complete
WATER | 1192 | Ndemi and Mirangi WPs- Supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 999912 |  | CGN |  |  |  | 999912 | 100% |  |  | 0 | Complete
WATER | 1193 | Wanjohi- Karima and Ndiara Water Project- Supply and laying of pipes | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2000000 | 1999710 |  | CGN |  |  |  | 1999710 | 100% |  |  | 0 | Complete
WATER | 1194 | Weru- Kariko water project- Additional solar panels | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1195 | Weru - Gathundia WP distribution extension | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | 999100 |  | CGN |  |  |  | 999100 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR
WATER | 1196 | Weru- Karandi WP -Distribution mains | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2020-07-01 | 2021-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1197 | Gathanji- Ex Smith Dam repair work and fencing | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR
WATER | 1198 | Gathanji -Kamukunji Water project EIA | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2020-07-01 | 2021-06-30 |  | 60000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1199 | Gathanji -Kamukunji Water project borehole drilling and casing |  | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2020-07-01 | 2021-06-30 |  | 2490000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1200 | Gathanji -Kamukunji Water project -Submersible pump |  | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2020-07-01 | 2021-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1201 | Gathanji -Kamukunji Water project- Water tower |  | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2020-07-01 | 2021-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1202 | Gathanji -Kamukunji Water project- construction of power house |  | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2020-07-01 | 2021-06-30 |  | 400000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1203 | Gathanji -Kamukunji Water project- Installation of solar system |  | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2020-07-01 | 2021-06-30 |  | 2500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1204 | Charagita-Assorted water works | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2020-07-01 | 2021-06-30 |  | 4000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1205 | Charagita -Olaimutia water project-Rerouting KPLC power lines | water distribution | Enhanced water supply |  |  | Oljororok | Charagita |  |  | 2020-07-01 | 2021-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1206 | Gatimu - Gakingi/Kamwana WP- Nyandarua water solar system including all accessories (152 solar panels for 380 sq. metres) |  | Enhanced water supply |  |  | Oljororok | Gatimu |  |  | 2020-07-01 | 2021-06-30 |  | 10200000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1207 | Gatimu - Nyakanja WP-solar system including all accessories (128 solar panels for 320 sq. metres) |  | Enhanced water supply |  |  | Oljororok | Gatimu |  |  | 2020-07-01 | 2021-06-30 |  | 9800000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1208 | Magumu - Other water works | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2020-07-01 | 2021-06-30 |  | 1350000 | 1314597 |  | CGN |  |  |  | 1314597 | 100% |  |  | 0 | Complete | [11 empty] | yes | key mitigation measures were implemented. These included ensuring proper waste disposal to protect the environment, enforcing the use of personal protective equipment (PPE) for worker safety, and conducting health and safety briefings. Social safeguards were addressed through community engagement and minimizing disruptions during construction. Gender considerations were integrated by promoting inclusive participation and ensuring equal access to project benefits.
WATER | 1209 | Magumu-St. Marys WP-Supply of pipes | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2020-07-01 | 2021-06-30 |  | 1500000 | 1498560 |  | CGN |  |  |  | 1498560 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included safe excavation and backfilling, provision of PPE to workers, community sensitization, inclusive stakeholder engagement, and proper waste management to minimize health, safety, environmental, and gender-related risks.
WATER | 1210 | Magumu-Motonyora B-Supply and installation of solar panels |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2020-07-01 | 2021-06-30 |  | 2500000 | 2500000 |  | CGN |  |  |  | 2500000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation measures were implemented. These included adherence to safe installation practices to prevent electrical and occupational hazards, use of appropriate personal protective equipment (PPE), community sensitization to enhance awareness and cooperation, and ensuring gender inclusion during project planning and implementation. Environmental considerations were addressed through proper disposal of installation waste and minimizing vegetation disturbance.
WATER | 1211 | Magumu- Magumu Borehole- Supply and laying of pipes | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Potential impacts and implemented mitigation measures included ensuring proper waste management and disposal, minimizing dust and noise pollution during trenching and laying activities, using appropriate signage and personal protective equipment (PPE) for workers, conducting public awareness and stakeholder consultations with gender inclusivity, restoring affected sites post-installation, and ensuring occupational safety standards were observed throughout the project.
WATER | 1212 | Magumu-Mutonyora C WP-Supply of pipes | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2020-07-01 | 2021-06-30 |  | 500000 | 500000 |  | CGN |  |  |  | 500000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Potential impacts and implemented mitigation measures included ensuring proper waste management and disposal, minimizing dust and noise pollution during trenching and laying activities, using appropriate signage and personal protective equipment (PPE) for workers, conducting public awareness and stakeholder consultations with gender inclusivity, restoring affected sites post-installation, and ensuring occupational safety standards were observed throughout the project.
WATER | 1213 | Githabai-Junction Joma Borehole- Hydrogeological survey and WRA |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 90000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | mitigation actions were undertaken. These included ensuring proper siting of the borehole to avoid environmental degradation, promoting safe working conditions during field investigations, engaging the local community to foster social acceptance and ownership, and integrating gender considerations by involving both men and women in consultations. Additionally, measures were taken to comply with water resource regulations and minimize potential conflicts over water use.
WATER | 1214 | Githabai- Phase 2 Water Project- Supply and installation of solar panels | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 1950000 | 1596720 |  | CGN |  |  |  | 1596720 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation measures were undertaken. These included ensuring the safe handling and installation of solar equipment to prevent electrical hazards, use of personal protective equipment (PPE) for all workers to promote occupational safety, proper waste disposal practices to minimize environmental harm, and engagement of local community members in a gender-inclusive manner. Additionally, awareness sessions were conducted to enhance community understanding and acceptance of the project, and site security measures were implemented to prevent accidents and unauthorized access.
WATER | 1215 | Githabai-Junction Joma Borehole- EIA |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 60000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | key mitigation measures included safe waste disposal, use of protective gear, community sensitization, inclusive consultations, promotion of fair labor practices, and control of dust, noise, and water use to safeguard people and the environment.
WATER | 1216 | Githabai-Junction Joma Borehole- Drilling, casing and test pumping |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 2400000 | 2400000 |  | CGN |  |  |  | 2400000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation measures were undertaken. These included ensuring minimal disturbance to the environment by managing drill cuttings and wastewater appropriately, enforcing health and safety protocols for workers including provision of PPE, sensitizing the community on the project’s benefits and impacts, engaging both women and men in public participation forums to ensure inclusivity, and complying with legal and regulatory requirements from the Water Resources Authority (WRA) and environmental agencies.
WATER | 1217 | Githabai-Junction Joma Borehole-Supply and installation of submersible pump |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 1900000 | 1900000 |  | CGN |  |  |  | 1900000 | 100% |  |  | 0 | Complete | [11 empty] | yes | To mitigate environmental risks, measures such as appropriate siting of equipment, waste management, and protection of water sources have been enforced. Social mitigation involved community sensitization and engagement to enhance local participation and address potential concerns. Occupational health and safety risks have been mitigated by ensuring the use of personal protective equipment (PPE), adherence to safe installation procedures, and provision of safety training to workers. Gender considerations included promoting inclusivity in project participation, ensuring that women and vulnerable groups benefit from improved water access, and safeguarding against any form of discrimination or gender-based violence during implementation.
WATER | 1218 | Githabai-Junction Joma Borehole-Construction of water tower and erection of 2No. 10m3 tanks |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 1600000 | 1600000 |  | CGN |  |  |  | 1600000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation measures have been implemented. These include enforcing occupational health and safety procedures at the construction site such as the use of personal protective equipment (PPE) and first aid kits, minimizing environmental degradation through proper waste management and erosion control, ensuring inclusive community engagement with consideration for gender representation, and providing safety signage and restricted access to hazardous areas to protect both workers and the public.
WATER | 1219 | Githabai-Junction Joma Borehole-Fencing, construction of water kiosk and power house |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 800000 | 799575 |  | CGN |  |  |  | 799575 | 100% |  |  | 0 | Complete | [11 empty] | yes | Appropriate mitigation actions were implemented included enforcing safety protocols at the site such as the use of personal protective equipment (PPE), clear signage and fencing to restrict unauthorized access, proper waste disposal to prevent environmental pollution, and ensuring community involvement and gender inclusion in decision-making and labour opportunities. Additionally, structures were designed and constructed to be safe, accessible, and inclusive, promoting health, safety, and equity for all users.
WATER | 1220 | Githabai-Junction Joma Borehole-Solar power supply |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 1950000 | 1950000 |  | CGN |  |  |  | 1950000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures implemented included ensuring safe installation practices for solar components to prevent electrical hazards, using certified technicians, and providing adequate training on system operation and maintenance. Environmental safeguards such as managing electronic waste, proper battery storage, and minimizing land disturbance were observed. Socially, the project promoted inclusion by engaging local stakeholders and encouraging women's participation in decision-making, while occupational health and safety protocols—like PPE usage and safety briefings—were enforced to protect all workers involved.
WATER | 1221 | Githabai-Nyakio pry Borehole- Hydrogeological survey and WRA |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 90000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Mitigation measures were taken to ensure environmental integrity, social inclusion, and safety. These included minimizing land disturbance during the survey, proper disposal of non-hazardous waste, and strict adherence to guidelines provided by WRA. Socially, the project engaged the local school and community, promoting participation and awareness. Safety protocols were observed for all workers, including the use of personal protective equipment (PPE), and gender considerations were integrated by ensuring inclusivity in consultations and decision-making.
WATER | 1222 | Githabai-Nyakio pry borehole - EIA |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 60000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Key mitigation measures included safe waste disposal, use of protective gear, community sensitization, inclusive consultations, promotion of fair labor practices, and control of dust, noise, and water use to safeguard people and the environment.
WATER | 1223 | Githabai-Nyakio pry borehole - Drilling, casing and test pumping |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 2400000 | 799996 |  | CGN |  |  |  | 799996 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation measures were implemented. These included proper siting of the borehole to avoid environmentally sensitive areas, use of licensed drillers adhering to NEMA and WRA guidelines, and safe disposal of drilling fluids and waste. Occupational safety was ensured through provision of personal protective equipment (PPE), adherence to safety protocols, and worker briefings. Community engagement was carried out to inform and involve stakeholders, while gender considerations included equitable participation and efforts to minimize potential negative impacts on women and vulnerable groups.
WATER | 1224 | Githabai-Nyakio pry borehole-Supply and installation of submersible pump |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 1900000 | 1900000 |  | CGN |  |  |  | 1900000 | 100% |  |  | 0 | Complete | [11 empty] | yes | key mitigation actions were implemented. These included ensuring the pump was installed by trained personnel following safety standards, providing personal protective equipment (PPE) to workers, and observing occupational safety measures to prevent injuries. Environmentally, the pump installation was done in a way that minimized disturbance to surrounding areas. Socially, community members were informed in advance and their concerns addressed. Gender inclusion was promoted through community engagement efforts that encouraged participation from women and vulnerable groups, while ensuring that installation activities did not disproportionately affect them.
WATER | 1225 | Githabai-Nyakio pry borehole -Construction of water tower and erection of 2No. 10m3 tanks |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 1600000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Mitigation measures included erosion control, community engagement, safety training and PPE use for workers, and promotion of gender inclusion to ensure fair participation and benefit-sharing.
WATER | 1226 | Githabai-Nyakio pry borehole-Fencing, construction of water kiosk and power house |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 800000 | 648300 |  | CGN |  |  |  | 648300 | 100% |  |  | 0 | Complete | [11 empty] | yes | The screening led to actions such as proper waste management, use of PPE, safety signage, community engagement, gender inclusion, and environmental protection to ensure health, safety, and social safeguards during construction.
WATER | 1227 | Githabai -Supply and laying of pipes and accessories | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2020-07-01 | 2021-06-30 |  | 3600000 | 3599970 |  | CGN |  |  |  | 3599970 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, care is being taken to prevent soil erosion and contamination during trenching and pipe laying. Socially, public consultations were held to ensure community involvement and acceptance. Occupational health and safety are being addressed through the provision of personal protective equipment (PPE), safety training for workers, and clear site signage. Gender concerns are being mitigated by ensuring women participate in decision-making processes and benefit equally from the project outcomes. A grievance redress mechanism is in place to handle any emerging concerns.
WATER | 1228 | Njabini-Soilo WP-supply and installation of solar panels |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2020-07-01 | 2021-06-30 |  | 2000000 | 1999520 |  | CGN |  |  |  | 1999520 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation measures were undertaken. These included ensuring the safe handling and installation of solar equipment to prevent electrical hazards, use of personal protective equipment (PPE) for all workers to promote occupational safety, proper waste disposal practices to minimize environmental harm, and engagement of local community members in a gender-inclusive manner. Additionally, awareness sessions were conducted to enhance community understanding and acceptance of the project, and site security measures were implemented to prevent accidents and unauthorized access.
WATER | 1229 | Njabini- Coloboise WP- Construction of water tower |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2020-07-01 | 2021-06-30 |  | 1600000 | 1600000 |  | CGN |  |  |  | 1600000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included erosion control, community engagement, safety training and PPE use for workers, and promotion of gender inclusion to ensure fair participation and benefit-sharing.
WATER | 1230 | Njabini- Kanyawa WP- Construction of water tower |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2020-07-01 | 2021-06-30 |  | 1600000 | 1589200 |  | CGN |  |  |  | 1589200 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included erosion control, community engagement, safety training and PPE use for workers, and promotion of gender inclusion to ensure fair participation and benefit-sharing.
WATER | 1231 | Njabini- Kiburu WP- Kiburu water project extension of water networks distribution (supply of pipes) | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2020-07-01 | 2021-06-30 |  | 1000000 | 998940 |  | CGN |  |  |  | 998940 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation actions were implemented. These include safe excavation practices to prevent soil erosion and protect existing ecosystems, provision of personal protective equipment (PPE) for all workers to ensure occupational safety, engagement of both men and women in project activities to promote gender equity, and community sensitization meetings to address social concerns and promote project ownership. Additionally, clear signage and traffic control measures were put in place to safeguard public safety during pipe laying.
WATER | 1232 | Njabini-Sasumwa borehole EIA, hydrogeological survey & WRA and drilling |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2020-07-01 | 2021-06-30 |  | 2300000 | 2300000 |  | CGN |  |  |  | 2300000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Identified key risks and implemented targeted mitigation measures included adherence to EIA recommendations, ensuring licensed and environmentally compliant borehole drilling practices, provision of personal protective equipment (PPE) for workers, management of drilling waste to avoid contamination, engagement with local communities (with attention to gender inclusion), and compliance with WRA regulations to safeguard water sustainability and equitable access.
WATER | 1233 | Njabini- Water tanks for Canaan Self Help Group |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2020-07-01 | 2021-06-30 |  | 1200000 | 1199000 |  | CGN |  |  |  | 1199000 | 100% |  |  | 0 | Done | [11 empty] | yes | Several mitigation actions were undertaken. The site was assessed for minimal environmental impact and proper siting of the tanks to avoid interference with water catchment or ecologically sensitive areas. Workers were provided with personal protective equipment (PPE) during delivery and installation, and standard occupational safety measures were observed. The project also ensured local community engagement, particularly involving women and vulnerable groups in decision-making. Social safeguards were implemented to avoid disruption to livelihoods or access to land, while promoting gender equity and inclusion throughout project implementation.
WATER | 1234 | Njabini-Assorted pipes and fittings | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2020-07-01 | 2021-06-30 |  | 400000 | 399950 |  | CGN |  |  |  | 399950 | 100% |  |  | 0 | Complete | [11 empty] | yes | key mitigation actions were undertaken. These included ensuring environmentally sound storage and transportation of the pipes to prevent soil or water contamination. Workers handling the materials were equipped with appropriate personal protective equipment (PPE), and occupational safety protocols were enforced throughout the delivery and installation phases. Social safeguards were addressed by involving local community members in planning and ensuring minimal disruption to public access and movement. Additionally, the project promoted gender inclusion by encouraging participation of both men and women in community engagement forums and ensuring equitable access to project benefits.
WATER | 1235 | Sasumwa Primary borehole rehabilitation | water distribution | Enhanced water supply |  |  | NJabini | Njabini |  |  | 2020-07-01 | 2021-06-30 |  | 1500000 | 1351474 |  | CGN |  |  |  | 1351474 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation actions have been implemented. These include proper handling and disposal of waste materials generated during rehabilitation works to prevent environmental pollution, enforcing occupational health and safety standards by providing workers with personal protective equipment (PPE), and training on safe work practices. Social safeguards involved informing and engaging the school and local community to ensure minimal disruption to learning activities and community access. Gender inclusion was promoted through equitable community involvement and prioritization of access to water for both boys and girls within the school.
WATER | 1236 | Wanjohi Girls Borehole Watertower | water distribution | Enhanced water supply |  |  | NJabini | Njabini |  |  | 2020-07-01 | 2021-06-30 |  | 1800000 | 1799500 |  | CGN |  |  |  | 1799500 | 100% |  |  | 0 | Complete
WATER | 1237 | kurungu borehole water project drilling and pump testing |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2200000 | 2089921 |  | CGN |  |  |  | 2089921 | 100% |  |  | 0 | Complete
WATER | 1238 | kurungu borehole EIA |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 60000 | - |  | CGN | [8 empty] | Done
WATER | 1239 | kurungu borehole water Project equipping |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 3800000 | 3065252 |  | CGN |  |  |  | 3065252 | 100% |  |  | 0 | Complete
WATER | 1240 | Karau - supply of LPG gas cylinders 6Kg, Gas and burner |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 1241 | North kinangop - supply of LPG gas cylinders 6Kg, Gas and burner |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 3000000 | 3000000 |  | CGN |  |  |  | 3000000 | 100% |  |  | 0 | Complete
WATER | 1242 | North kinangop - supply of LPG gas cylinders 6Kg, Gas and burner |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 1243 | Rurii - supply of LPG gas cylinders 6Kg, Gas and burner |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete
WATER | 1244 | Geta (Geta and Makumbi) - supply of LPG gas cylinders 6Kg, Gas and burner |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 4500000 | 4500000 |  | CGN |  |  |  | 4500000 | 100% |  |  | 0 | Complete
WATER | 1245 | Githioro - supply of LPG gas cylinders 6Kg, Gas and burner |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2250000 | 2250000 |  | CGN |  |  |  | 2250000 | 100% |  |  | 0 | Complete
WATER | 1246 | Kiriita - supply of LPG gas cylinders 6Kg, Gas and burner |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 3000000 | 3000000 |  | CGN |  |  |  | 3000000 | 100% |  |  | 0 | Complete
WATER | 1247 | Kiriita - supply of LPG gas cylinders 6Kg, Gas and burner - Kiriita Forest |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete
WATER | 1248 | Shamata -Supply of LPG gas cylinders 6Kg, Gas and burner-Simbara |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2000000 | 2000000 |  | CGN |  |  |  | 2000000 | 100% |  |  | 0 | Complete
WATER | 1249 | Shamata-Supply of LPG gas cylinders 6Kg, Gas and burner-Pesi |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2000000 | 2000000 |  | CGN |  |  |  | 2000000 | 100% |  |  | 0 | Complete
WATER | 1250 | Shamata-Supply of LPG gas cylinders 6Kg, Gas and burner-Kangocho |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 1251 | Supply of LPG gas cylinders 6Kg, Gas and burner- Mirangine |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2500000 | 2500000 |  | CGN |  |  |  | 2500000 | 100% |  |  | 0 | Complete
WATER | 1252 | Supply of LPG gas cylinders 6Kg, Gas and burner- Magumu |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Several mitigation actions have been undertaken. These include ensuring that the supplied LPG cylinders and burners meet the Kenya Bureau of Standards (KEBS) quality and safety standards to prevent accidents and leaks. Users were sensitized on safe handling, storage, and usage practices to minimize health and fire hazards. Socially, the project considered equitable distribution, with special attention given to vulnerable households. Gender aspects were addressed by prioritizing women-headed households to promote clean energy access and reduce reliance on harmful biomass fuels. Occupational safety during transport and delivery was ensured through appropriate loading and protective handling practices.
WATER | 1253 | Supply of LPG gas cylinders 6Kg, Gas and burner- Gatimu |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete
WATER | 1254 | Supply of tree seedlings and planting |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1255 | Establishment of tree Nurseries |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 700000 | 700000 |  | CGN |  |  |  | 700000 | 100% |  |  | 0 | Complete
WATER | 1256 | Tree seedlings |  | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete
WATER | 1257 | Mastoo Irrigation project- Shamata | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1258 | Karandi Irrigation Project Weru Ward | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1259 | Mataara Irrigation project- Lower Mataara Ndaragwa Central | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1260 | Mirangine-Kurungu Borehole Completion - Pipes Distribution | water distribution | Enhanced water supply | [6 empty] | 2020-07-01 | 2021-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Supply of pipes done.
WATER | 1261 | Soko mpya water project- supply of pipes | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2021-07-01 | 2022-06-30 |  | 2000000 | 1999890 |  | CGN |  |  |  | 1999890 | 100% |  |  | 0 | Project work completed. | [11 empty] | yes | Several mitigation measures have been implemented. Environmentally, pipe materials were selected based on their durability and minimal ecological impact, with proper storage to avoid pollution. Socially, community consultations were carried out to ensure inclusion, transparency, and minimal disruption during transportation and delivery. Occupational health and safety measures included the use of proper lifting gear and personal protective equipment (PPE) for handlers to avoid injuries. Gender considerations ensured that women and vulnerable groups were involved in the project process, particularly in community sensitization and benefit-sharing activities.
WATER | 1262 | Heni borehole- construction of kiosk, power house, supply and installation of submersible pump | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2021-07-01 | 2022-06-30 |  | 3000000 | 3000000 |  | CGN |  |  |  | 3000000 | 100% |  |  | 0 | complete | [11 empty] | yes | Several mitigation actions were undertaken. To address environmental concerns, proper waste management practices were adopted, and construction was scheduled to minimize land and water pollution. Socially, local community engagement ensured inclusive participation and minimized conflicts. For occupational health and safety, workers were provided with personal protective equipment (PPE), trained on safe handling of equipment, and a safety supervisor was designated on-site. Gender-sensitive measures were also implemented, ensuring equal opportunities for both men and women in project activities and prioritizing women’s needs in the design and location of the water kiosk.
WATER | 1263 | Nyakio borehole power connection | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2021-07-01 | 2022-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | yes | Several mitigation measures have been undertaken. These include ensuring safe installation procedures in line with electrical safety standards, providing protective gear and training for workers handling electrical components, and establishing clear signage and restricted access zones to protect the public. Social safeguards involved community engagement and notification to reduce disruption, while gender considerations ensured the participation of both men and women in planning and implementation phases.
WATER | 1264 | Yaanga community borehole- construction of water tower and power house, erection of 2no. 10m3 tanks, supply and installation of submersible pump | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2021-07-01 | 2022-06-30 |  | 3500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | yes | mitigation actions have been undertaken. These include enforcing the use of personal protective equipment (PPE) for all workers, implementing site safety protocols to prevent accidents, and ensuring proper handling and disposal of construction materials to protect the environment. Community engagement was carried out to promote inclusion and transparency, and both women and men were encouraged to participate in project activities. Additionally, gender-sensitive approaches were applied in site selection and access to water points to ensure equitable benefit across the community.
WATER | 1265 | Kageraini community borehole- eia and drilling and casing |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1266 | Sasumu dam water project-installation of solar panels and construction of water tower |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2021-07-01 | 2022-06-30 |  | 4000000 | 3999500 |  | CGN |  |  |  | 3999500 | 100% |  |  | 0 | complete | [11 empty] | yes | Several mitigation measures have been implemented. These include enforcing occupational safety protocols through the mandatory use of personal protective equipment (PPE) by workers, ensuring structural integrity and secure installation of solar components, and minimizing environmental disruption during construction. The project also integrated gender-responsive approaches by promoting equal opportunities for men and women in labor participation and ensuring safe and accessible water facilities for all community members. Community sensitization sessions were conducted to enhance awareness of safety practices and foster local support for the project.
WATER | 1267 | Coloboise water project- supply of pipes | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2021-07-01 | 2022-06-30 |  | 2000000 | 1999300 |  | CGN |  |  |  | 1999300 | 100% |  |  | 0 | complete | [11 empty] | yes | Potential impacts and implemented mitigation measures included ensuring proper waste management and disposal, minimizing dust and noise pollution during trenching and laying activities, using appropriate signage and personal protective equipment (PPE) for workers, conducting public awareness and stakeholder consultations with gender inclusivity, restoring affected sites post-installation, and ensuring occupational safety standards were observed throughout the project.
WATER | 1268 | Churiri borehole- eia, hydrogeological survey and wra permit, drilling |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2021-07-01 | 2022-06-30 |  | 2200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | yes | Several mitigation measures have been undertaken. These include ensuring safe drilling practices, enforcing the use of personal protective equipment (PPE) for all workers, managing noise and dust emissions, and proper waste disposal to minimize environmental harm. Social safeguards were addressed through community engagement and awareness sessions. Gender inclusion was promoted by encouraging equal participation and ensuring that the project benefits all, including women and vulnerable groups.
WATER | 1269 | Construction of mugo kihiko 100m3 water tank |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1800000 | 1799641 |  | CGN |  |  |  | 1799641 | 100% |  |  | 0 | complete
WATER | 1270 | Supply of assorted water pipes | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1000000 | 995450 |  | CGN |  |  |  | 995450 | 100% |  |  | 0 | complete
WATER | 1271 | Thindi borehole- suppply and installation of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1272 | Itomboya water project construction of a water tower and installation of 2no. 10,000litres water tanks | Storage facility | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 1800000 | 1799975 |  | CGN |  |  |  | 1799975 | 100% |  |  | 0 | complete | [11 empty] | Yes | Provision of PPEs,recyle of construction debris where possible and safe disposal to authorized sites and prevent runoff from contaminating nearby areas
WATER | 1273 | Lower munyaka supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water
WATER | 1274 | Upper weru borehole drilling | Water source | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 2200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and harzardous materials and maintain machineries to reduce noise emmision
WATER | 1275 | Raitha supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 900000 | 900000 |  | CGN |  |  |  | 900000 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water
WATER | 1276 | Thayu supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 900000 | 900000 |  | CGN |  |  |  | 900000 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water
WATER | 1277 | Faru supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 900000 | 892000 |  | CGN |  |  |  | 892000 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water
WATER | 1278 | Kikanamuku supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water
WATER | 1279 | Muhuti pry sch borehole-drilling and test pumping | Water source | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2021-07-01 | 2022-06-30 |  | 2500000 | 2499400 |  | CGN |  |  |  | 2499400 | 100% |  |  | 0 | complete | [11 empty] | Yes | Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and harzardous materials and maintain machineries to reduce noise emmision
WATER | 1280 | Gitite kairia water project- construction of water tower | Storage facility | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2021-07-01 | 2022-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | Provision of PPEs,recyle of construction debris where possible and safe disposal to authorized sites and prevent runoff from contaminating nearby areas
WATER | 1281 | Supply of pipes for umoja-githae wp-north kinangop | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water
WATER | 1282 | Kagogo water project-equipping of the borehole with solar powered submersible pump and solar panels | solar powered water pumping | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | Securing solar panels agaisnt theft and weather,ensure abstraction rate does not exceed yield of the aquifer and dispose wastes properly
WATER | 1283 | Kagogo water project-tank tower | Water storage | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1500000 | 1498000 |  | CGN |  |  |  | 1498000 | 100% |  |  | 0 | complete | [11 empty] | Yes | Provision of PPEs,recyle of construction debris where possible and safe disposal to authorized sites and prevent runoff from contaminating nearby areas
WATER | 1284 | Kagogo water project-power house and fencing | Security | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | Ensure fence is secure and allow proper water flow to avoid stagnation,power house to have adequate ventilation and drainage,proper waste management,dust and noise control
WATER | 1285 | Supply of 3,000ltr tanks |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | Provision of high quality duable tanks that are recyclable,safe transportation and handling and ensure tanks places have community consent and are on a public land with proper authorization
WATER | 1286 | Supply of assorted water pipes | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water
WATER | 1287 | 3m borehole equiping of borehole with submersible pump and solar panel |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | Securing solar panels agaisnt theft and weather,ensure abstraction rate does not exceed yield of the aquifer and dispose wastes properly
WATER | 1288 | 3m borehole drilling and test pumping |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and harzardous materials and maintain machineries to reduce noise emission
WATER | 1289 | Mawingu company borehole drilling and test pumping (mahiga meeri) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1290 | Mawingu water company equipping of the borehole with solar powered submersible pump and solar panels (githioro secondary) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 4000000 | 3999298 |  | CGN |  |  |  | 3999298 | 100% |  |  | 0 | complete
WATER | 1291 | Mawingu water company borehole- construction of a water tower and installation of 2no. 10,000 litres plastic water tanks - (githioro secondary) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1292 | Supply of assorted water pipes- dry area karuri | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1293 | Muhonia water distribution mains | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1800000 | 1799550 |  | CGN |  |  |  | 1799550 | 100% |  |  | 0 | complete | [11 empty] | Yes | Minimize disturbance to natural terrain and existing infrastructure,avoid fuel and oil leaks from machinery
WATER | 1294 | Muhonia turasha- equipping of borehole with solar powered submersible pump and solar panel |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete | [11 empty] | Yes | Securing solar panels agaisnt theft and weather,ensure abstraction rate does not exceed yield of the aquifer and dispose wastes properly
WATER | 1295 | Mawingu-gathiriga line repairs (pillars) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1296 | Gatondo borehole- equipping of the borehole with solar panels |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2500000 | 2500000 |  | CGN |  |  |  | 2500000 | 100% |  |  | 0 | complete
WATER | 1297 | Gatondo borehole -supply and laying of pipes | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2000000 | 1999506 |  | CGN |  |  |  | 1999506 | 100% |  |  | 0 | complete
WATER | 1298 | Rironi borehole distribution mains | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | complete
WATER | 1299 | Muthangira borehole hydrogeological survey and wra permit |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1300 | Ndinda b- supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1200000 | 1200000 |  | CGN |  |  |  | 1200000 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1301 | Kiamboga water project- borehole drilling |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1302 | Ndiara water project- supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1000000 | 998300 |  | CGN |  |  |  | 998300 | 100% |  |  | 0 | complete
WATER | 1303 | Ndemi/mrefu/ngano- supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1700000 | 1698010 |  | CGN |  |  |  | 1698010 | 100% |  |  | 0 | complete
WATER | 1304 | Munyuini borehole solar system | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1305 | Machinery water storage 50m3 tank | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1306 | Supply of water pipes for nairobi range malewa | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1307 | Assorted water pipes | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 900000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1308 | Kagongo borehole | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | complete
WATER | 1309 | Mwiyumia borehole equipping of the borehole with solar powered submersible pump and solar panels | Solarization & Equipping | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done | [11 empty] | YES | Monitor ESMP
WATER | 1310 | Muthaiti borehole equipping of the borehole with solar powered submersible pump and solar panels | Solarization & Equipping | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1311 | Ririchwa borehole equipping of the borehole with solar panels | Solarization & Equipping | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1312 | Canaan borehole equipping of the borehole with solar powered submersible pump and solar panels | Solarization & Equipping | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1313 | Canaan borehole water tower | Storage | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1314 | Mwiyumia and canaan boreholes power houses | Solarization & Equipping | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1315 | Kamande borehole distribution pipes | Water Distribution | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Done
WATER | 1316 | Mumbi borehole distribution pipes | Water Distribution | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Done
WATER | 1317 | Supply of water tanks -kaimbaga | Roof Harvesting and Storage | Enhanced water supply | 368HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Done
WATER | 1318 | Fencing of bahati borehole | Fencing | Enhanced water supply |  |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1319 | Mihuti and simba water projects -supply and laying of pipes | Water Distribution | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Done | [11 empty] | yes | community capacity building
WATER | 1320 | Borehole steel pipes |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 800000 | 779800 |  | CGN |  |  |  | 779800 | 100% |  |  | 0 | Done
WATER | 1321 | Githugo(zyon) borehole repair and rehabilitation and distribution pipework | water distribution | Enhanced water supply | 80HH |  | Ol Kalou | Karau |  |  | 2021-07-01 | 2022-06-30 |  | 2500000 | 2499550 |  | CGN |  |  |  | 2499550 | 100% |  |  | 0 | Done
WATER | 1322 | Assorted pipes and accessories | water distribution | Enhanced water supply | 100HH |  | Ol Kalou | Karau |  |  | 2021-07-01 | 2022-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not done
WATER | 1323 | Munyeki borehole pipe extension | water distribution | Enhanced water supply | 200HH |  | Ol Kalou | Karau |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Done | [11 empty] | yes | community sensitization
WATER | 1324 | Kianda borehole distribution pipeline | water distribution | Enhanced water supply | 150HH |  | Ol Kalou | Karau |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Done
WATER | 1325 | Rurii-matura community borehole- eia, hydrogeological survey and drilling | Drilling and casing | Enhanced water supply | 70HH |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 2200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Done | [11 empty] | yes | Adhererance to ESMP
WATER | 1326 | Mwana-mwende pipe distribution | water distribution | Enhanced water supply | 50 HH |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done | [11 empty] | yes | community capacity building
WATER | 1327 | Plot 10 borehole- submersible pump and solar pannels | Solarization and Equiping | Enhanced water supply | - |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done | [11 empty] | yes | Adhererance to ESMP
WATER | 1328 | Plot 10 borehole equipping- water tower | Water Tower | Enhanced water supply | - |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 1600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done | [11 empty] | yes | Adhererance to ESMP
WATER | 1329 | Itangi-ini water project piping to serve thitai, and umoja villages | water distribution | Enhanced water supply | 100HH |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 2000000 | 1999780 |  | CGN |  |  |  | 1999780 | 100% |  |  | 0 | Done | [11 empty] | yes | community capacity building
WATER | 1330 | Rurii-manyatta community borehole- eia, hydrogeological survey and drilling | Drilling and casing | Enhanced water supply |  |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 2200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1331 | Rurii- matara borehole wp -installation of solar panels and construction of water kiosk | Solarization, Equiping & Water Kiosk | Enhanced water supply | 100HH |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Done | [11 empty] | YES | adhere to ESMP
WATER | 1332 | Mugumo water project -repair and installation of pump and settlement of electricity pending bills | Repair and installation of pump and settlement of electricity pending bills | Enhanced water supply | 200HH |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1333 | Assorted pipes and accessories | Water Distribution | Enhanced water supply | 100HH |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1334 | Rurii- supply of pipes for colonial village | Water Distribution | Enhanced water supply | 100HH |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1335 | Rurii- supply of pipes for 22 village | Water Distribution | Enhanced water supply | 120HH |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1336 | Uhuru water project-supply and laying of distribution pipes |  | Enhanced water supply |  |  | Olkalou | kanjuiri |  |  | 2021-07-01 | 2022-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Complete
WATER | 1337 | Wiyumiririe water project-supply and laying of distribution pipes |  | Enhanced water supply |  |  | Olkalou | kanjuiri |  |  | 2021-07-01 | 2022-06-30 |  | 1500000 | 1499750 |  | CGN |  |  |  | 1499750 | 100% |  |  | 0 | Complete | [11 empty] | yes | community sensitization
WATER | 1338 | Supply of water pipes (compensation for kirathimo borehole)- kio b/h water project | water distribution | Enhanced water supply |  |  | Olkalou | kanjuiri |  |  | 2021-07-01 | 2022-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1339 | Kunyutoka water tank repair | water distribution | Enhanced water supply |  |  | Olkalou | kanjuiri |  |  | 2021-07-01 | 2022-06-30 |  | 300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1340 | Matunda borehole-drilling and test pumping |  | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 2600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | adhereance to ESMP
WATER | 1341 | Matunda borehole-equipping of the bh with solar panels, submersible pump and construction of power house) |  | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 4000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | YES | adhereance to ESMP
WATER | 1342 | Gituamba water project- bore hole drilling and casing |  | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 2600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | YES | Adhere to ESMP
WATER | 1343 | Makara water project-extension of the gravity mains | water distribution | Enhanced water supply |  |  | Olkalou |  |  |  | 2021-07-01 | 2022-06-30 |  | 2400000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1344 | Kurungu water project-extension of distribution mains | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | community capacity building
WATER | 1345 | Charagita- assorted pipes and fittings | water distribution | Enhanced water supply |  |  | Oljororok | Charagita |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 999995 |  | CGN |  |  |  | 999995 | 100% |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1346 | Weru-inooro commuinity borehole -eia, hydrological survey, drilling, casing and test pumping |  | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2021-07-01 | 2022-06-30 |  | 2700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | SPR+ ESMP Monitoring
WATER | 1347 | Weru-uiguano community borehole -eia, hydrological survey, drilling, casing and test pumping |  | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2021-07-01 | 2022-06-30 |  | 2700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1348 | Weru-ka-maina community borehole -eia, hydrological survey, drilling, casing and test pumping |  | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2021-07-01 | 2022-06-30 |  | 2700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1349 | Karandi water project inverter and gatumbiro wp solar repair |  | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2021-07-01 | 2022-06-30 |  | 900000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1350 | Kibathi water project- solar panels |  | Enhanced water supply |  |  | Oljororok | Gatimu |  |  | 2021-07-01 | 2022-06-30 |  | 9300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1351 | Drilling of mungetho borehole |  | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2021-07-01 | 2022-06-30 |  | 2200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1352 | Mungetho borehole water tower and installation of 2x10m3 plastic tanks |  | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2021-07-01 | 2022-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1353 | Mungetho borehole equipping of the borehole with solar powered submersible pump and solar panels |  | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2021-07-01 | 2022-06-30 |  | 3800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1354 | Mungetho borehole powerhouse and tower |  | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2021-07-01 | 2022-06-30 |  | 1700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1355 | Supply and installation of assorted pipes | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 3500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1356 | Assorted supply of pipes and accessories | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 2700000 | 2696680 |  | CGN |  |  |  | 2696680 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR to follow when pipe laying wil be budgeted.
WATER | 1357 | Supply of pipes - mutufa line | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1358 | Supply of pipes - pcea line karai | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2021-07-01 | 2022-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1359 | Supply of pipes - ndogino line reedemed | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR to follow when pipe laying wil be budgeted.
WATER | 1360 | Supply of pipes - ndivai line | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR to follow when pipe laying wil be budgeted.
WATER | 1361 | Supply of pipes - raichiri line | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR to follow when pipe laying wil be budgeted.
WATER | 1362 | Supply of pipes - kanyagia line | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1363 | Supply of pipes- nyakinyua line | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2021-07-01 | 2022-06-30 |  | 625000 | 625000 |  | CGN |  |  |  | 625000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR to follow when pipe laying wil be budgeted.
WATER | 1364 | Nyakinyua borehole | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 |  | CGN |  |  |  | 500000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR+ ESMP Monitoring
WATER | 1365 | Supply of water pipes | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2021-07-01 | 2022-06-30 |  | 1500000 | 1498150 |  | CGN |  |  |  | 1498150 | 100% |  |  | 0 | Complete | [11 empty] | Yes | SPR+ ESMP Monitoring
WATER | 1366 | Desilting of joseph dam | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 5000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | CPR+ ESMP monitoring
WATER | 1367 | Baari bolehole water project - kiriita | water distribution | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2021-07-01 | 2022-06-30 |  | 2200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | SPR + ESMP monitoring
WATER | 1368 | Nyandarua water and sanitation company - assorted pipes and fittings | water distribution | Enhanced water supply |  |  | Ndaragwa |  |  |  | 2021-07-01 | 2022-06-30 |  | 2000000 | 1999500 |  | CGN |  |  |  | 1999500 | 100% |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1369 | Rurii- ol'kalou water and sanitation - assorted pipes and fittings | water distribution | Enhanced water supply | 110HH |  | Kaimbaga | Ol Kalou |  |  | 2021-07-01 | 2022-06-30 |  | 2000000 | 1999970 |  | CGN |  |  |  | 1999970 | 100% |  |  | 0 | Complete | [11 empty] | yes | community capacity building
WATER | 1370 | Office generator and power house |  | Enhanced water supply |  |  | Kaimbaga | Ol Kalou |  |  | 2021-07-01 | 2022-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1371 | Umoja mbuyu- supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1372 | Supply of lpg cylinders in north kinangop ward |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3000000 | 3000000 |  | CGN |  |  |  | 3000000 | 100% |  |  | 0 | Complete | [11 empty] | Yes | Ensure supply of sealed LPG,properly labled with clear safety instructions,transport the LPG in well ventilated vehicles and away from heat sources,equity issuance to vulnearble groops
WATER | 1373 | Supply of lpg cylinders in mirangine |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3000000 | 2601279 |  | CGN |  |  |  | 2601279 | 100% |  |  | 0 | Complete
WATER | 1374 | Supply of lpg cylinder to the elderly- lower shamata |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2500000 | 877430 |  | CGN |  |  |  | 877430 | 100% |  |  | 0 | Complete
WATER | 1375 | Supply of lpg cylinder to the elderly- olbolosat shamata |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3000000 | 3000000 |  | CGN |  |  |  | 3000000 | 100% |  |  | 0 | Complete
WATER | 1376 | Supply of lpg cylinder to the elderly-kirimanjaro and canary shamata |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1954900 | 1537624 |  | CGN |  |  |  | 1537624 | 100% |  |  | 0 | Complete
WATER | 1377 | Supply of lpg cylinders- magumu ward |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2021-07-01 | 2022-06-30 |  | 4000000 | 4000000 |  | CGN |  |  |  | 4000000 | 100% |  |  | 0 | Lpg supplied and is be distributed to the community. | [11 empty] | yes | Several mitigation measures were put in place. These include conducting safety sensitization and training for beneficiaries on the safe handling, storage, and use of LPG cylinders to prevent accidents and fire hazards. Social safeguards were implemented by ensuring fair and inclusive distribution, prioritizing vulnerable households. To address occupational health and safety, suppliers adhered to proper transportation and handling protocols. Gender considerations were mainstreamed by involving both men and women in awareness campaigns and ensuring equal access to the LPG kits.
WATER | 1378 | Rehabilitation of degraded sites.-western escarpment of aberdare along riparian land |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 800000 | 800000 |  | CGN |  |  |  | 800000 | 100% |  |  | 0 | Seedlings delivered and distributed | [11 empty] | Yes | SPR+ ESMP Monitoring
WATER | 1379 | Seedlings propagation for high value treees |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 500000 | 495617 |  | CGN |  |  |  | 495617 | 100% |  |  | 0 | Seedlings delivered and distributed | [11 empty] | Yes | ESMP Monitoring
WATER | 1380 | Increase trees cover and forest cover program:adopt and nurture a tree(anat) programme support community based tree nurseries- 5 sub catchments, one in each ward |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 5000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1381 | Catchment and ecosystem management -review of 2 wruas and cfa management plans |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1382 | Integrated institutions programme and green hubs programme -1 in every subcounty |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1383 | Floods and disaster control-disilting 1 water pan |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1384 | Kwa moa irrigation project borehole-mirangine | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 2200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1385 | Youth empowerment in irrigation- leshau pondo:supply of 3 water tanks | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1386 | Mirangine- makara irrigation project | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1387 | Githima water project- supply and laying of pipes mirangine | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done | [11 empty] | yes | monitor ESMP
WATER | 1388 | Bamboo seedling (implementation of kefri mou on bamboo propogation to rehabilitate graded areas) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1389 | Support to youth group hikers with assorted hiking gear for economic empowerment (shamata gate) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 250000 | 250000 |  | CGN |  |  |  | 250000 | 100% |  |  | 0 | done
WATER | 1390 | Support to youth group hikers with assorted for economic empowerment ( njabini gate) |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2021-07-01 | 2022-06-30 |  | 250000 | 250000 |  | CGN |  |  |  | 250000 | 100% |  |  | 0 | done | [11 empty] | yes | Several mitigation measures have been implemented. These include offering entrepreneurship training and safety awareness to ensure proper use and management of the items provided. Social safeguards were observed by ensuring inclusive and equitable participation of both male and female youth. Occupational health and safety measures were incorporated by sensitizing beneficiaries on safe handling and usage of equipment or materials supplied. Gender considerations were addressed by promoting equal opportunities in access, participation, and leadership roles within the youth group.
WATER | 1391 | Support to youth group hikers with assorted for economic empowerment (ndunyu-njeru gate) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 250000 | 250000 |  | CGN |  |  |  | 250000 | 100% |  |  | 0 | done
WATER | 1392 | Support to youth group hikers with assorted for economic empowerment (geta gate) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 250000 | 250000 |  | CGN |  |  |  | 250000 | 100% |  |  | 0 | done
WATER | 1393 | Support to youth group hikers with assorted for economic empowerment (wanjohi gate) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 250000 | 250000 |  | CGN |  |  |  | 250000 | 100% |  |  | 0 | done
WATER | 1394 | Ol' kalou arboretum maintenance of the events ground and perimeter live fence |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 200000 | 200000 |  | CGN |  |  |  | 200000 | 100% |  |  | 0 | done
WATER | 1395 | Conservation of lake ol'bolosat construction marketing bill board at kasuku |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 300000 | 250000 |  | CGN |  |  |  | 250000 | 100% |  |  | 0 | done
WATER | 1396 | Conservation of lake ol'bolosat construction of a pit latrine for health & sanitation |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1397 | Conservation of lake ol'bolosat construction of a gate, cubicle and a barrier for revenue collection |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1398 | Conservation of lake ol'bolosat purchase and delivery one boat for local community conservation groups (loccog) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 750000 | 750000 |  | CGN |  |  |  | 750000 | 100% |  |  | 0 | done
WATER | 1399 | Conservation of lake ol' bollosat - construction of boat docking jetty at the lake |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1400 | Conservation of lake ol'bolosat water distribution network from karandi b/hole to the lake |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1401 | Ol'kalou arboretum- phase 2 completion of solar heated swimming pool and septic tank -kaimbaga |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 20600000 | 16525302 |  | CGN |  |  |  | 16525302 | 100% |  |  | 0 | done | [11 empty] | YES | Monitor ESMP
WATER | 1402 | Ol'kalou arboretum- water distribution and electricity installation and transmission |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 400000 | 400000 |  | CGN |  |  |  | 400000 | 100% |  |  | 0 | done | [11 empty] | YES | Community sensitization
WATER | 1403 | Ol'kalou arboretum- mount eco-sitting benches |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 250000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1404 | Ol'kalou arboretum-signage -kaimbaga |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1405 | Ol' kalou arboretum installation of eco-bins |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1406 | Murungaru - muhonia turasha water project - kagongo borehole drilling | Water source | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2021-07-01 | 2022-06-30 |  | 2300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done | [11 empty] | Yes | - Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and harzardous materials and maintain machineries to reduce noise emission
WATER | 1407 | Rurii- plot 10 borehole drilling, casing and test pumping | Drilling, casing and test pumping | Enhanced water supply | 100HH |  | Ol Kalou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done | [11 empty] | yes | Monitor ESMP
WATER | 1408 | Plastic tanks for the elderly & vulnerable group- shamata |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1794303 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1409 | Kanjuiri - wiyumiririe borehole water project construction of water tower and installation of 2 x 10m3 plastic tanks |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1599150 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done
WATER | 1410 | Engineer - lower munyaka borehole drilling and thindi borehole equipping | Water source | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | done | [11 empty] | Yes | - Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and harzardous materials and maintain machineries to reduce noise emission
WATER | 1411 | Rurii - githunguri water project fencing and supply of pipes | fencing and supply of pipes | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1599995 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1412 | Rurii - supply of lpg gas cylinders 6kg, gas and burner |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1413 | Gathanji-kamukuji water project borehole drilling, casing,hydrological survey and wra |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2449530 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1414 | Rurii - kimende borehole - drilling casing and pump testing | drilling casing and pump testing | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1999990 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1415 | Kanjuiri - kirathimo borehole eia-hydrogeological survey and wiyumiririe wp supply of pipes |  | Enhanced water supply |  |  | Olkalou | Kanjuiri |  |  | 2021-07-01 | 2022-06-30 |  | 4049844 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | YES | monitor ESMP
WATER | 1416 | Mirangine- highwood borehole drilling and supply of pipes | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 3699775 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1417 | Karau- gachwe- glad force borehole supply and installation of solar panel and renovation and repair of muiri borehole | water distribution | Enhanced water supply |  |  | Olkalou | Karau |  |  | 2021-07-01 | 2022-06-30 |  | 599627 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1418 | Gatimu- gikingi water project piping | water distribution | Enhanced water supply |  |  | Oljororok | Gatimu |  |  | 2021-07-01 | 2022-06-30 |  | 2998700 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1419 | Gatimu- supply and installation of solar power panels and construction of 6m high solar panels support structures facilities at gatimu and nyakanja water project |  | Enhanced water supply |  |  | Oljororok | Gatimu |  |  | 2021-07-01 | 2022-06-30 |  | 19990842 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | solars supplied but not installed | [11 empty] | Yes | _
WATER | 1420 | Karandi irrigation project weru | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2021-07-01 | 2022-06-30 |  | 2999800 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1421 | Mataara irrigation project- lower mataara ndaragwa central | water distribution | Enhanced water supply |  |  | Oljororok | Central |  |  | 2021-07-01 | 2022-06-30 |  | 1999980 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1422 | Construction of solar heated swimming pool and support facilities ol-kalou arboretum in kaimbaga |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 4404135 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1423 | Githabai- phase 2 water project- supply and installation of solar panels |  | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2021-07-01 | 2022-06-30 |  | 1950000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | key mitigation actions were implemented. These included ensuring the pump was installed by trained personnel following safety standards, providing personal protective equipment (PPE) to workers, and observing occupational safety measures to prevent injuries. Environmentally, the pump installation was done in a way that minimized disturbance to surrounding areas. Socially, community members were informed in advance and their concerns addressed. Gender inclusion was promoted through community engagement efforts that encouraged participation from women and vulnerable groups, while ensuring that installation activities did not disproportionately affect them.
WATER | 1424 | Kaimbaga- drilling of canaan and mwiyumia boreholes |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 5000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done | [11 empty] | YES | Monitor ESMP
WATER | 1425 | Githioro- supply & laying of pipes- shecago ventures |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1426 | Rurii matara b/h- installation of submersible pump | Solarization and Equipping | Enhanced water supply | 100HH | [5 empty] | 2021-07-01 | 2022-06-30 |  | 1205000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | YES | Community capacity building
WATER | 1427 | Githabai- supply & laying of pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3520000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1428 | Mirangine- shoreport ltd-high wood borehole equipping |  | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 3849600 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1429 | Mirangine- kurungu borehole water project eia, drilling and pump testing |  | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 2258900 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | monitor ESMP
WATER | 1430 | Mwireri water tower & rumathi control panel and fencing -kaimbaga | Tower Construction and erection of Fence | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 2999983 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1431 | Kipipiri supply of pipes |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1432 | Geta- kariahu construction of a tank |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1433 | Gichungo b/h equiping | Solarization and Equipping | Enhanced water supply |  |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 3799976 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1434 | Gathanji kamukunji water tower & installation of solar system |  | Enhanced water supply |  |  | Oljororok | Gathaji |  |  | 2021-07-01 | 2022-06-30 |  | 3999999 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1435 | Gathanji kamukunji construction of power house & submersible pump |  | Enhanced water supply |  |  | Oljororok | Gathaji |  |  | 2021-07-01 | 2022-06-30 |  | 1900000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1436 | Kieni bh supply and installation of solar powered pumps and solar system. | Solarization and Equipping | Enhanced water supply | 100HH |  | Olkalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 3749000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1437 | Gichungo & mwireri bh drilling | Drilling and Casing | Enhanced water supply | 100HH |  | Olkalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 3999966 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1438 | Kiganjo primary sch water point | Construction of a water point | Enhanced water supply | 100HH |  | Olkalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 1499991 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1439 | Mirangine- kurungu bore hole equipping |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3798950 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1440 | Mwireri bh equiping | Solarization and Equipping | Enhanced water supply | 100HH |  | Olkalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 3899910 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1441 | Construction of kandutura and kieni water towers | Solarization and Equipping | Enhanced water supply | 100HH |  | Olkalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 3298908 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1442 | Construction of arboretum ground in olkalou |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3278000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1443 | Makara spring weir |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1998800 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1444 | Supply & laying of pipes and accessories@ muhonia turasha water project | enhanced water supply | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2021-07-01 | 2022-06-30 |  | 2405755 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1445 | Construction of kianjogu water tank - murungaru ward | water storage | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2021-07-01 | 2022-06-30 |  | 2200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | Reuse of excavated materials,storage of cement and sand in covered areas to prevent runoff,public participation before implementation,workers to be provided with PPEs
WATER | 1446 | Kamande bh equipping, pump, solar power installation | Solarization and Equipping | Enhanced water supply | 100HH |  | Olkalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 3799950 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1447 | Supply of lpg cylinders - geta(gerek) |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1448 | Supply of water to various hand washing points | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 420000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1449 | Kiriita ward-supply and installation of 5000 litre tanks for nairobi ecde and maguna ecde including guttering |  | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2021-07-01 | 2022-06-30 |  | 200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1450 | Central ward- mithuri water project |  | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 1499909 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1451 | Ndaragwa central-dm dam supply and installation of solar pump |  | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 1746000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1452 | Assorted water works- charagita ward | water distribution | Enhanced water supply |  |  | Oljororok | Charagita |  |  | 2021-07-01 | 2022-06-30 |  | 3998900 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1453 | Charagita - completion of oleimutia water project | water distribution | Enhanced water supply |  |  | Oljororok | Charagita |  |  | 2021-07-01 | 2022-06-30 |  | 1500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1454 | Njabini- borehole drilling and testing pumping |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2021-07-01 | 2022-06-30 |  | 2150000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included proper wastewater management, use of protective gear, enforcement of safety protocols, and inclusive stakeholder engagement to promote gender equity and environmental protection.
WATER | 1455 | Karau- munyeki borehole fencing and construction of power house supply and installation of distribution mains | Fencing,onstruction of power house supply and installation of distribution mains | Enhanced water supply | 100HH |  | Ol Kalou | Karau |  |  | 2021-07-01 | 2022-06-30 |  | 1649557 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | YES | Adhere to ESMP
WATER | 1456 | Gathanji- kwa ngara borehole equipping |  | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2021-07-01 | 2022-06-30 |  | 3798165 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1457 | Gathanji- kwa ngara borehole - construction of powerhouse |  | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2021-07-01 | 2022-06-30 |  | 200000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1458 | Mirangine- kihuho distribution of pipes | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 1999830 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1459 | Ndaragwa central- muti-umwe pry water project piping | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1460 | Ndaragwa central - supply and laying of pipes for the distribution network at kanyagia | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1461 | Central - supply and laying of pipes for the distribution network at muruai and supply and installation of dm water pump for the distribution network at muruai | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2021-07-01 | 2022-06-30 |  | 3000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | _
WATER | 1462 | Karau - muiri water project solar and supply of pipes | water distribution | Enhanced water supply | 100 HH |  | Ol Kalou | Karau |  |  | 2021-07-01 | 2022-06-30 |  | 1600000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1463 | Geta - kagongo water project- supply and installation of pipes | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 1400000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1464 | Kaimbaga -2no. Power house ( kamande and kieni) and painting works in mumbi and bahati boreholes | Construction 2no. Power house ( kamande and kieni) and painting works in mumbi and bahati boreholes | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1465 | Magumu -mwenda-andu pump testing |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2021-07-01 | 2022-06-30 |  | 100000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1466 | Engineer ward - raitha kahuru water project supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 800000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1467 | Charagita- supply and installation of submersible pump for oleimutia borehole |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2599380 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1468 | Kihurure supply and laying of pipes | water distribution | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 2002000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done | [11 empty] | YES | community capacity building
WATER | 1469 | Distribution pipes for mwiyumia boreholes, gituamba water point and bluecity point | water distribution | Enhanced water supply |  |  | Ol Kalou | Kaimbaga |  |  | 2021-07-01 | 2022-06-30 |  | 1505968 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1470 | North kinangop- supply and delivery of tia wira water pump. | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2021-07-01 | 2022-06-30 |  | 999442 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | Ensure abstraction rate does not exceed yield of the aquifer and dispose wastes properly
WATER | 1471 | Drilling of kagondo borehole muhonia turasha water project |  | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2300000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | Yes | Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and harzardous materials and maintain machineries to reduce noise emission
WATER | 1472 | Mirangine- installation of bore hole withdrawal pipes, submersiblle pump,solar pannels and support structure for gituamba bore hole | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2021-07-01 | 2022-06-30 |  | 3849600 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | community capacity building
WATER | 1473 | Shamata -supply of lpg gas cylinders 6kg, gas and burner-simbara |  | Enhanced water supply |  |  | Ndaragwa | Shamata |  |  | 2021-07-01 | 2022-06-30 |  | 1999500 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | _ | _
WATER | 1474 | North kinangop- construction of elevated steel tank tower at umoja githae water project | storage facility | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2021-07-01 | 2022-06-30 |  | 1458185 |  |  | CGN | [7 empty] | 0 | Complete | [11 empty] | Yes | Provision of PPEs,recyle of construction debris where possible and safe disposal to authorized sites and prevent runoff from contaminating nearby areas
WATER | 1475 | Gathanji- kamukunji water project borehole drilling and casing, hydrological survey and acquire wra permit |  | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2021-07-01 | 2022-06-30 |  | 2449530 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not started-repeated project | [11 empty] | Yes | _
WATER | 1476 | Kanjuiri-wiyumiririe wp-supply and laying of pipes and construction of water kiosk | water distribution | Enhanced water supply |  |  | Olkaluo | Kanjuiri |  |  | 2021-07-01 | 2022-06-30 |  | 1000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete | [11 empty] | yes | community capacity building
WATER | 1477 | Rurii -supply of pipes to maran borehole,kahonge and mugathika borehole | water distribution | Enhanced water supply | 100HH |  | Ol Klaou | Rurii |  |  | 2021-07-01 | 2022-06-30 |  | 700000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Not Done
WATER | 1478 | Enginer ward - thindi borhole equipping with solar system | water pumping | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2021-07-01 | 2022-06-30 |  | 2500000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Thindi borehole is a dry borehole. | [11 empty] | Yes | Securing solar panels against theft and weather,ensure abstraction rate does not exceed yield of the aquifer and dispose wastes properly
WATER | 1479 | Kipipiri - supply and delivery of pipes -kamahia wp | water distribution | Enhanced water supply | [6 empty] | 2021-07-01 | 2022-06-30 |  | 2000000 | 0 |  | CGN |  |  |  | 0 |  |  |  | 0 | Complete
WATER | 1480 | Magumu borehole EIA |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2022-07-01 | 2023-06-30 |  | 60000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | key mitigation measures included safe waste disposal, use of protective gear, community sensitization, inclusive consultations, promotion of fair labor practices, and control of dust, noise, and water use to safeguard people and the environment.
WATER | 1481 | Magumu borehole Hydrogeological survey and WRA |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2022-07-01 | 2023-06-30 |  | 90000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Several mitigation measures have been undertaken. These include adherence to environmental guidelines to prevent contamination and ecosystem disruption during survey activities, ensuring worker safety through the use of protective equipment and safety protocols, and promoting community engagement with special attention to gender inclusion. Local stakeholders were consulted, and measures to protect both male and female participants’ rights, access, and safety were incorporated throughout the process.
WATER | 1482 | Magumu borehole - Drilling and casing |  | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2022-07-01 | 2023-06-30 |  | 3125000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | Mitigation measures were implemented to address potential risks. Environmental safeguards included proper waste management during drilling, prevention of soil and water contamination, and minimal disturbance to the natural habitat. Social measures involved community engagement to ensure inclusive participation and awareness, with gender considerations integrated to promote equitable access and benefits. Occupational health and safety protocols were enforced by providing personal protective equipment (PPE), training on safety procedures, and establishing emergency response plans to ensure a safe working environment.
WATER | 1483 | Supply of assorted pipes and accesssories | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1484 | Supply of pipes and accessories - Koinange borehole WP | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2022-07-01 | 2023-06-30 |  | 1650000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | a range of mitigation actions were undertaken. Environmentally, care was taken to minimize land disturbance during transportation and storage of materials, and to ensure safe disposal of packaging waste. Socially, community consultations were conducted to ensure inclusion, with a particular focus on engaging marginalized and vulnerable groups. On occupational health and safety, all workers involved in the handling and installation of pipes were provided with appropriate personal protective equipment (PPE) and safety training. Gender considerations were mainstreamed by encouraging equal participation and ensuring that both women and men benefitted from the project through improved access to clean water and related opportunities.
WATER | 1485 | Supply of pipes and accessories - Ndothua borehole WP | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2022-07-01 | 2023-06-30 |  | 1650000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | several mitigation measures were implemented. Environmentally, materials were transported and stored in a manner that minimized soil disturbance and pollution. Social mitigation included community engagement and awareness to ensure project acceptability and support, with a focus on inclusion of vulnerable groups. Occupational health and safety measures involved provision of proper personal protective equipment (PPE) and safety instructions to all personnel handling the materials. Gender equity was promoted by ensuring participation of both men and women in project-related activities and fair access to project benefits.
WATER | 1486 | Repair/replace Koinange B/H Pump and repair of solar panels and replace Gwa Senior B/H pump motor |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2022-07-01 | 2023-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | yes | appropriate mitigation measures were taken. Environmentally, care was taken to prevent oil spills and manage waste from old parts. Social safeguards involved informing and engaging local community members to minimize disruptions and ensure inclusive access. Occupational health and safety measures included equipping technicians with proper PPE and enforcing safe repair procedures. Gender considerations ensured that women and vulnerable groups were consulted and their access to clean water maintained throughout the repair period.
WATER | 1487 | Nyakio-Assorted pipes and accessories | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2022-07-01 | 2023-06-30 |  | 2000000 | 1999927 |  | CGN |  |  |  | 1999927 | 100% |  |  | 0 | Complete | [11 empty] | yes | several mitigation measures were implemented. Environmentally, proper handling and storage of materials were ensured to avoid pollution and physical degradation of the site. Socially, community engagement was carried out to inform and involve stakeholders in the process. Occupational health and safety protocols, such as the use of personal protective equipment (PPE) and safe material handling, were observed by workers. Gender considerations were integrated by promoting inclusive participation and ensuring that women and vulnerable groups had access to project benefits without discrimination.
WATER | 1488 | Line Moja wp - Construction of water tower |  | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2022-07-01 | 2023-06-30 |  | 1600000 | 1600000 |  | CGN |  |  |  | 1600000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Mitigation measures included erosion control, community engagement, safety training and PPE use for workers, and promotion of gender inclusion to ensure fair participation and benefit-sharing.
WATER | 1489 | Line Moja wp- Supply and laying of pipes | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Complete | [11 empty] | yes | Environmentally, care is being taken to prevent soil erosion and contamination during trenching and pipe laying. Socially, public consultations were held to ensure community involvement and acceptance. Occupational health and safety are being addressed through the provision of personal protective equipment (PPE), safety training for workers, and clear site signage. Gender concerns are being mitigated by ensuring women participate in decision-making processes and benefit equally from the project outcomes. A grievance redress mechanism is in place to handle any emerging concerns.
WATER | 1490 | Supply and laying of distribution pipes for Coloboise | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 999948 |  | CGN |  |  |  | 999948 | 100% |  |  | 0 | Complete | [11 empty] | yes | Potential impacts and implemented mitigation measures included ensuring proper waste management and disposal, minimizing dust and noise pollution during trenching and laying activities, using appropriate signage and personal protective equipment (PPE) for workers, conducting public awareness and stakeholder consultations with gender inclusivity, restoring affected sites post-installation, and ensuring occupational safety standards were observed throughout the project.
WATER | 1491 | Supply and laying of distribution pipes for Kinamba Town/Shirikisho | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1000000 | 999550 |  | CGN |  |  |  | 999550 | 100% |  |  | 0 | Complete
WATER | 1492 | Gathaara- Raitha Kahuru water project - supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 999500 |  | CGN |  |  |  | 999500 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1493 | Tulaga Ngwataniro water tank and piping | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | Provision of high quality durable tanks that are recyclable,to ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1494 | Tulaga Muruaki Ngwataniro water tank and piping | water distribution | Enhanced water supply | 100HH |  | Kinangop | Gathaara |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1495 | Engineer- Gichigirira Chief Ndumia-solar powered submersible pump and solar panels | pumping | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2022-07-01 | 2023-06-30 |  | 3900000 | _ |  | CGN |  |  |  | _ |  |  |  |  | Project complete and in use. | [11 empty] | Yes | - Securing solar panels agaisnt theft and weather,ensure abstraction rate does not exceed yield of the aquifer and dispose wastes properly
WATER | 1496 | Assessment and Rehabilitation of Bidii Borehole | update of imformation of the borehole | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2022-07-01 | 2023-06-30 |  | 500000 | 499760 |  | CGN |  |  |  | 499760 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | Ensure borehole is drawing from a renewable and sustainable aquifer,avoid over abstraction,proper disposal of waste materilas and continued access of all users
WATER | 1497 | Upper Weru Borehole- Supply and installation of solar panels and solar-powered submissible pump | Pumping | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2022-07-01 | 2023-06-30 |  | 4500000 | 4499955 |  | CGN |  |  |  | 4499955 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | Securing solar panels against theft and weather,ensure abstraction rate does not exceed yield of the aquifer and dispose wastes properly
WATER | 1498 | Hydrogeological Survey, Drilling and casing of Upper Weru Borehole | borehole assessment and water source | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | 3000000 |  | CGN |  |  |  | 3000000 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | - Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and harzardous materials and maintain machineries to reduce noise emission
WATER | 1499 | Upper Weru Supply and laying of pipes ( Operization of wadorokathi masonry tank) | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2022-07-01 | 2023-06-30 |  | 2500000 | 2473550 |  | CGN |  |  |  | 2473550 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1500 | Maintenance of storm water drains (Cleaning)- Nguri, J-30 and Dick Estates | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1000000 | 999900 |  | CGN |  |  |  | 999900 | 100% |  |  | 0 | Project complete | [11 empty] | Yes | Collect and separate organic,plastic and harzadous waste durng cleaning,dispose silt and solid matter to authorized siteuse of PPEs during maintanance
WATER | 1501 | Manyatta borehole - supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 |  | CGN |  |  |  | 500000 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1502 | Engineer- Raitha Kahuru water project - supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Engineer |  |  | 2022-07-01 | 2023-06-30 |  | 500000 | 498800 |  | CGN |  |  |  | 498800 | 100% |  |  | 0 | Project complete and in use. | [12 empty] | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1503 | Kirimire water project supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 997870 |  | CGN |  |  |  | 997870 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1504 | Githae water project-Construction of water tower and erection of 2No. 10M3 plastic tanks | storage facility | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2022-07-01 | 2023-06-30 |  | 2000000 | 1998360 |  | CGN |  |  |  | 1998360 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | Provision of PPEs,recyle of construction debris where possible and safe disposal to authorized sites and prevent runoff from contaminating nearby areas
WATER | 1505 | Kikanamuku water project - Supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | North Kinangop |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1506 | Utugi water project - Supply of pipes | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 999200 |  | CGN |  |  |  | 999200 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1507 | Jugimo borehole drilling and casing | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | 2998660 |  | CGN |  |  |  | 2998660 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and hazardous materials and maintain machineries to reduce noise emission
WATER | 1508 | Jugimo borehole water project - Supply and laying of pipes and accessories | water distribution | Enhanced water supply | 100HH |  | Kinangop | Murungaru |  |  | 2022-07-01 | 2023-06-30 |  | 2500000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1509 | Construction of Mikeu water tank | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete and in use.
WATER | 1510 | Construction of Marimu B water tank | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 2000000 | 549610 |  | CGN |  |  |  | 549610 | 100% |  |  | 0 | Project complete and in use.
WATER | 1511 | Makumbi BH- EIA, hydrogeological survey and WRA permit, drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 3000000 | 2999900 |  | CGN |  |  |  | 2999900 | 100% |  |  | 0 | Project complete and in use.
WATER | 1512 | Makumbi BH Pump and Solar Equipping | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 3500000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete and in use.
WATER | 1513 | Umoja Githae - Supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1200000 | 1200000 |  | CGN |  |  |  | 1200000 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1514 | Kagongo intake | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1500000 | 1500000 |  | CGN |  |  |  | 1500000 | 100% |  |  | 0 | Project complete and in use.
WATER | 1515 | Githima and Gathiriga boreholes- Hydrogeological survey and WRA permit | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 300000 | 300000 |  | CGN |  |  |  | 300000 | 100% |  |  | 0 | Project complete and in use.
WATER | 1516 | Githima borehole drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 3050000 | 3046250 |  | CGN |  |  |  | 3046250 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and hazardous materials and maintain machineries to reduce noise emission
WATER | 1517 | Turasha Water Project- Supply of pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1000000 | 998798 |  | CGN |  |  |  | 998798 | 100% |  |  | 0 | Project complete and in use. | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1518 | Mawingu Water Company Mahiga Meeri Borehole WP- Supply of distribution pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1150000 | 1150000 |  | CGN |  |  |  | 1150000 | 100% |  |  | 0 | Project complete and in use.
WATER | 1519 | Dry area Karuri- Supply of 1No. 10M3 water tank | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 150000 | 147040 |  | CGN |  |  |  | 147040 | 100% |  |  | 0 | Project complete and in use.
WATER | 1520 | Supply of assorted pipes and accessories- Dry area Karuri | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 500000 | 499940 |  | CGN |  |  |  | 499940 | 100% |  |  | 0 | Project complete and in use.
WATER | 1521 | MawinguWP- Gathiriga line repairs (pillars) | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1200000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete and in use.
WATER | 1522 | Gathiriga Water Tank Repair |  | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 400000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete and in use.
WATER | 1523 | Mawingu WP- Supply and laying of pipes-Aberdare, Mawingu and Gathiriga | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete and in use.
WATER | 1524 | Supply of assorted pipes and accessories- Kimbo | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete and in use.
WATER | 1525 | Gatondo water project - supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 2000000 | 2000000 |  | CGN |  |  |  | 2000000 | 100% |  |  | 0 | Project complete and in use.
WATER | 1526 | Rironi borehole - Construction of water tower | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete and in use.
WATER | 1527 | Kipkwagary borehole hydrogeological survey | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 150000 | 149385 |  | CGN |  |  |  | 149385 | 100% |  |  | 0 | complete
WATER | 1528 | Kipkwagary borehole drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 2850000 | 2850000 |  | CGN |  |  |  | 2850000 | 100% |  |  | 0 | complete
WATER | 1529 | Kipkwagary borehole installation of pump and Solar panels | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 4000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1530 | Mahindu B/H Equipping with solar-powered submissible pump and solar panels | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 4000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1531 | Mahindu borehole drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 3200000 | 3198000 |  | CGN |  |  |  | 3198000 | 100% |  |  | 0 | complete
WATER | 1532 | Assorted pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1000000 | 999910 |  | CGN |  |  |  | 999910 | 100% |  |  | 0 | complete
WATER | 1533 | Thitai water project-supply and laying of distribution pipes | water distribution | Enhanced water supply | 80HH |  | Ol Kalou | Kaimbaga |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | yes | community capacity building
WATER | 1534 | Assorted pipes and accessories Kieni w/p | water distribution | Enhanced water supply | 70HH |  | Ol Kalou | Kaimbaga |  |  | 2022-07-01 | 2023-06-30 |  | 400000 | - |  | CGN |  |  |  | - |  |  |  |  | The project has issues with EACC. Borehole not equipped
WATER | 1535 | Kaimbaga ward- Water reticulation (laying of distribution mains) | water distribution | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2022-07-01 | 2023-06-30 |  | 1700000 | 1549610 |  | CGN |  |  |  | 1549610 | 100% |  |  | 0 | The project is complete and in use
WATER | 1536 | Rumathi water project-supply and laying of distribution pipes | water distribution | Enhanced water supply | 100HH |  | Ol Kalou | Kaimbaga |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 999550 |  | CGN |  |  |  | 999550 | 100% |  |  | 0 | The project is complete and in use
WATER | 1537 | Assorted pipes and accessories | water distribution | Enhanced water supply | 50HH |  | Ol Kalou | Karau |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 |  |  | CGN | [7 empty] | 0 | The project is complete and in use
WATER | 1538 | Karau- Supply and laying of pipes- Vatican, Mairo, Kianda and Canaan | water distribution | Enhanced water supply | 120HH |  | Ol Kalou | Karau |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | 2999244 |  | CGN |  |  |  | 2999244 | 100% |  |  | 0 | The project is complete and in use
WATER | 1539 | Karau- Assorted pipes and accessories | water distribution | Enhanced water supply | 1000HH |  | Ol Kalou | Karau |  |  | 2022-07-01 | 2023-06-30 |  | 2000000 | 1999145 |  | CGN |  |  |  | 1999145 | 100% |  |  | 0 | The project is complete and in use
WATER | 1540 | Matura borehole water project -EIA, Hydrogeological survey and WRA permit, Drilling and Casing | Drilling and Casing | Enhanced water supply | 110HH |  | Ol Kalou | Karau |  |  | 2022-07-01 | 2023-06-30 |  | 2800000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing | [11 empty] | yes | monitor ESMP
WATER | 1541 | Rurii Village Borehole piping to Primary Sch | water distribution | Enhanced water supply | 80HH |  | Ol Kalou | Rurii |  |  | 2022-07-01 | 2023-06-30 |  | 1200000 | 1200000 |  | CGN |  |  |  | 1200000 | 100% |  |  | 0 | The project is complete and in use
WATER | 1542 | Matura borehole water project - test pumping | water distribution | Enhanced water supply | 100HH |  | Ol Kalou | Rurii |  |  | 2022-07-01 | 2023-06-30 |  | 100000 | - |  | CGN |  |  |  | - |  |  |  |  | Not Done
WATER | 1543 | Rurii- Construction of power house | Construction of power house | Enhanced water supply | 65HH |  | Ol Kalou | Rurii |  |  | 2022-07-01 | 2023-06-30 |  | 300000 | - |  | CGN |  |  |  | - |  |  |  |  | The project is complete and in use
WATER | 1544 | Mugathika- Assorted pipes and accessories | water distribution | Enhanced water supply | 100HH |  | Ol Kalou | Rurii |  |  | 2022-07-01 | 2023-06-30 |  | 900000 | 899260 |  | CGN |  |  |  | 899260 | 100% |  |  | 0 | The project is complete and in use
WATER | 1545 | Rurii- Plot 10 borehole- EIA, Hydrogeological survey and WRA permit, drilling and casing | Drilling and Casing | Enhanced water supply | 110HH |  | Ol Kalou | Rurii |  |  | 2022-07-01 | 2023-06-30 |  | 2800000 | 2798500 |  | CGN |  |  |  | 2798500 | 100% |  |  | 0 | The project is complete and in use | [11 empty] | YES | Monitor ESMP
WATER | 1546 | Plot 10 water project -Construction of water tower and supply and installation of 2No. 10m3 plastic tanks | Construction of water tower and supply and installation of 2No. 10m3 plastic tanks | Enhanced water supply | 50HH |  | Ol Kalou | Rurii |  |  | 2022-07-01 | 2023-06-30 |  | 1700000 | - |  | CGN |  |  |  | - |  |  |  |  | The project is complete and in use | [11 empty] | YES | Community capacity building
WATER | 1547 | Upgrade of kirima water project | water distribution | Enhanced water supply | 70HH |  | Ol Kalou | Rurii |  |  | 2022-07-01 | 2023-06-30 |  | 450000 | - |  | CGN |  |  |  | - |  |  |  |  | Not Done
WATER | 1548 | Bosinia (Huhoini) Borehole- Drilling and casing FY 2018-19 reinstatement and supply and laying of pipes | Drilling and Casing | Enhanced water supply | 60HH |  | Ol Kalou | Rurii |  |  | 2022-07-01 | 2023-06-30 |  | 3500000 | 3499350 |  | CGN |  |  |  | 3499350 | 100% |  |  | 0 | The works are Complete
WATER | 1549 | Kanjuiri BH - Supply and installation of with solarpowered submersible pump and solar panels | water distribution | Enhanced water supply |  | Olkaluo | Kanjuiri |  |  |  | 2022-07-01 | 2023-06-30 |  | 2800000 | - |  | CGN |  |  |  | - |  |  |  |  | The works are Complete
WATER | 1550 | Rutara-Kanjau WP- Supply and laying of distribution pipes | water distribution | Enhanced water supply |  | Olkaluo | Kanjuiri |  |  |  | 2022-07-01 | 2023-06-30 |  | 750000 | - |  | CGN |  |  |  | - |  |  |  |  | The works are Complete
WATER | 1551 | Rutara Secondary School- Borehole- EIA, Hydrogeological WRA permit, Drilling and casing | water distribution | Enhanced water supply |  | Olkluo | Kanjuiri |  |  |  | 2022-07-01 | 2023-06-30 |  | 2750000 | 2749250 |  | CGN |  |  |  | 2749250 | 100% |  |  | 0 | The works are Complete
WATER | 1552 | Nyandundo water project-EIA and hydrogeological survey and WRA Permit | water distribution | Enhanced water supply |  | Olkaluo | Mirangine |  |  |  | 2022-07-01 | 2023-06-30 |  | 200000 | - |  | CGN |  |  |  | - |  |  |  |  | The works are Complete
WATER | 1553 | Nyandundo Borehole -drilling and casing | water distribution | Enhanced water supply |  | Olkaluo | Mirangine |  |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | The works are Complete
WATER | 1554 | Mirangine ward- Assorted pipes and accessories | water distribution | Enhanced water supply |  | Olkalou | Mirangine |  |  |  | 2022-07-01 | 2023-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | The works are Complete
WATER | 1555 | Kihuho Borehole -supply and installation of solar powered submersible pump and solar panels and construction of powerhouse | water distribution | Enhanced water supply |  | Olkalou | Mirangine |  |  |  | 2022-07-01 | 2023-06-30 |  | 4800000 | - |  | CGN |  |  |  | - |  |  |  |  | The works are Complete
WATER | 1556 | Gatimu-Supply and laying of distribution pipes | water distribution | Enhanced water supply |  |  | Oljororok | Gatimu |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | 2999250 |  | CGN |  |  |  | 2999250 | 100% |  |  | 0 | The works are Complete | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1557 | Gatimu -Supply and laying of distribution pipes for Kamwana Water Project | water distribution | Enhanced water supply |  |  | Oljororok | Gatimu |  |  | 2022-07-01 | 2023-06-30 |  | 2000000 | 1998500 |  | CGN |  |  |  | 1998500 | 100% |  |  | 0 | The works are Complete | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1558 | Gathanji- Njoro BH WP -Supply of pipes and accessories | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2022-07-01 | 2023-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | The works are Complete | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1559 | Huhoini- Supply of pipes and accessories | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2022-07-01 | 2023-06-30 |  | 2000000 | 1998050 |  | CGN |  |  |  | 1998050 | 100% |  |  | 0 | The works are Complete | [11 empty] | Yes | _
WATER | 1560 | Construction of water kiosk - Huhoini | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2022-07-01 | 2023-06-30 |  | 700000 |  |  | CGN | [7 empty] | 0 | The works are Complete | [11 empty] | Yes | _
WATER | 1561 | Muungano Water Project- Supply of pipes and accessories | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 |  | CGN |  |  |  | 1000000 | 100% |  |  | 0 | Project complete. | [11 empty] | Yes | _
WATER | 1562 | Gituamba water project - Supply of pipes and accessories | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 999000 |  | CGN |  |  |  | 999000 | 100% |  |  | 0 | Project complete. | [11 empty] | Yes | _
WATER | 1563 | Rehabilitation of Boiman water tank | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 | 955650 |  | CGN |  |  |  | 955650 | 100% |  |  | 0 | Project complete. | [11 empty] | Yes | _
WATER | 1564 | Boiman Borehole - Supply of pipes and accessories | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2022-07-01 | 2023-06-30 |  | 1000000 |  |  | CGN | [7 empty] | 0 | Project complete. | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1565 | Gathanji- Kwa Ngara BH WP -Supply of pipes and accessories | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2022-07-01 | 2023-06-30 |  | 2000000 | 1995100 |  | CGN |  |  |  | 1995100 | 100% |  |  | 0 | Project complete. | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1566 | Supply of assorted pipes and accessories | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | 2999160 |  | CGN |  |  |  | 2999160 | 100% |  |  | 0 | Project complete. | [11 empty] | Yes | SPR + ESMP Monitoring(Once laying is done)
WATER | 1567 | Supply of assorted pipes and accessories for Mutitu, Ndothua and Kwa Njora | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | 2998920 |  | CGN |  |  |  | 2998920 | 100% |  |  | 0 | Project complete. | [11 empty] | Yes | SPR + ESMP Monitoring(Once laying is done)
WATER | 1568 | Leshau/Karagoini Water Project Transformer (serving Kiriita, Leshau Pondo & Ndaragwa Central Wards) | water distribution | Enhanced water supply |  |  | Ndaragwa | Kiriita, Leshau Pondo & Ndaragwa Central |  |  | 2022-07-01 | 2023-06-30 |  | 2500000 | 2500000 |  | CGN |  |  |  | 2500000 | 100% |  |  | 0 | Project complete. | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1569 | Leshau Pondo- Supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1600000 |  |  | CGN | [7 empty] | 0 | Project complete. | [11 empty] | Yes | _
WATER | 1570 | Mutara WP intake | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 4000000 | 3979250 |  | CGN |  |  |  | 3979250 | 100% |  |  | 0 | Project complete. | [11 empty] | Yes | CPR+ ESMP Monitoring
WATER | 1571 | Shamata- Rehabilitation of Kilimanjaro water project storage tank | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 1000000 |  |  | CGN | [7 empty] | 0 | Project complete. | [11 empty] | Yes | _
WATER | 1572 | Desilting of Wambuku Dam- Shamata | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 3003176 | 2699748 |  | CGN |  |  |  | 2699748 | 100% |  |  | 0 | Project complete. | [11 empty] | Yes | CPR to be done + ESMP Monitoring
WATER | 1573 | Shamata- Wambuku Dam-Desilting, fencing and water troughs | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 2700000 |  |  | CGN | [7 empty] | 0 | Project complete. | [11 empty] | Yes | CPR to be done + ESMP Monitoring
WATER | 1574 | Engineer- Gichigirira Chief Ndumia- Borehole- EIA, Hydrogeogical survey, Drilling, Casing and construction of water tower and erecting 2No. 10xm3 water tanks | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 4500000 | 4497500 |  | CGN |  |  |  | 4497500 | 100% |  |  | 0 | Project complete.
WATER | 1575 | Mirangine- Makara water project-supply and installation of submersible pump,solar power installation, fencing and powerhouse | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2022-07-01 | 2023-06-30 |  | 4304525 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete. | [11 empty] | YES | adhere to ESMP
WATER | 1576 | Magumu borehole kenyatta road- magumu ward | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete. | [11 empty] | yes | Mitigation actions include managing drilling impacts, engaging the community, ensuring safety with proper PPE and training, and promoting gender inclusion. A grievance redress mechanism has been established, and efforts are ongoing to ensure the project is safe, inclusive, and environmentally sound.
WATER | 1577 | Githunguchu masonry tank- Kiriita ward | water distribution | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete. | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1578 | Shamata ward- Borehole drilling and casing - Shamata borehole | water distribution | Enhanced water supply |  |  | Ndaragwa | Shamata |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete. | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1579 | Ndaragwa Central-Purchase and supply of 500litres tanks- Kiandongoro, Kiriogo | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2022-07-01 | 2023-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete. | [11 empty] | Yes | _
WATER | 1580 | Kipipiri -Supply of 500litre capacity water storage tanks | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | Project complete.
WATER | 1581 | Cleaning urban storm water drains in Engineer Towns-Engineer | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete. | [11 empty] | Yes | Collect and separate organic,plastic and harzadous waste durng cleaning,dispose silt and solid matter to authorized siteuse of PPEs during maintenance
WATER | 1582 | Cleaning urban storm water drains in Njabini Towns-Njabini ward | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete. | [11 empty] | yes | Advised on usage of PPEs and incorporation of both gender during labour distribution
WATER | 1583 | Cleaning urban storm water drains in Maironya- Kiriita | water distribution | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete. | [11 empty] | Yes | Monitoring of functional storm water drains.
WATER | 1584 | Cleaning urban storm water drains in Ndaragwa towns-Central ward | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete. | [11 empty] | Yes | Monitoring of functional storm water drains.
WATER | 1585 | Cleaning urban storm water drains in Oljorok town-Gatimu | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete. | [11 empty] | Yes | Monitoring of functional storm water drains.
WATER | 1586 | Cleaning urban storm water drains in Kasuku towns-Weru | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete. | [11 empty] | Yes | Monitoring of functional storm water drains.
WATER | 1587 | Cleaning urban storm water drains in Miharati town-Kipipiri | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete.
WATER | 1588 | Cleaning urban storm water drains in wanjohi towns-Wanjohi | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete.
WATER | 1589 | Cleaning urban storm water drains in Gwa Kiongo town-Mirangine | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete.
WATER | 1590 | Cleaning urban storm water drains in Tumaini towns-Kanjuiri | water distribution | Enhanced water supply | [6 empty] | 2022-07-01 | 2023-06-30 |  | 150000 | 150000 |  | CGN |  |  |  | 150000 | 100% |  |  | 0 | Works complete.
WATER | 1591 | Kibuyu water project- installation of booster pump, additional solar panel and supply of pipes & fittings | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1592 | Mutonyora B borehole flushing, pump replacement and installation of sunverter | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2023-07-01 | 2024-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | yes | Several mitigation measures were undertaken. Environmentally, care was taken to manage wastewater and avoid contamination during flushing. Socially, the local community was engaged and informed about the scope and safety precautions of the project. In terms of occupational health and safety, workers were provided with appropriate personal protective equipment (PPE), and safe handling procedures were implemented during pump and equipment installation. Gender-sensitive approaches were integrated by ensuring that both men and women were considered in public consultations and benefit sharing.
WATER | 1593 | Supply and deliver assorted pipes for Heni and Phase 2 Boreholes | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2023-07-01 | 2024-06-30 |  | 3000000 | 2999769 |  | CGN |  |  |  | 2999769 | 100% |  |  | 0 | complete | [11 empty] | yes | several mitigation measures were undertaken. Environmentally, precautions were taken to minimize waste and avoid pollution during transportation and storage of the pipes. Socially, community awareness was raised to ensure smooth project implementation and inclusivity. For occupational health and safety, all handlers and workers were provided with appropriate personal protective equipment (PPE), and proper lifting and handling procedures were followed. Gender considerations included fair community engagement and ensuring that both men and women were involved and informed throughout the process.
WATER | 1594 | Repair phase 2 borehole and supply pipes and accessories to Bogani Pry sch | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2023-07-01 | 2024-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | yes | Several mitigation actions were implemented. Environmentally, measures were taken to control waste, avoid contamination, and ensure proper handling and disposal of repair materials. Social mitigation included sensitizing the school community to ensure inclusive participation and avoid disruption to learning activities. Occupational health and safety practices were upheld through provision of PPE, adherence to safe work procedures, and supervision during repair works. Gender aspects were considered by ensuring fair representation and benefit to both male and female students and community members. | Several mitigation actions were implemented. Environmentally, measures were taken to control waste, avoid contamination, and ensure proper handling and disposal of repair materials. Social mitigation included sensitizing the school community to ensure inclusive participation and avoid disruption to learning activities. Occupational health and safety practices were upheld through provision of PPE, adherence to safe work procedures, and supervision during repair works. Gender aspects were considered by ensuring fair representation and benefit to both male and female students and community members.
WATER | 1595 | Yaang'a Primary borehole- construction of water tower and powerhouse and equipping with submersible pump | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2023-07-01 | 2024-06-30 |  | 4000000 | 3999624 |  | CGN |  |  |  | 3999624 | 100% |  |  | 0 | complete | [11 empty] | yes | Several mitigation measures have been implemented. Environmentally, measures were taken to minimize soil disturbance and manage construction waste. Socially, community engagement was conducted to ensure local support and participation. On occupational health and safety, workers were provided with personal protective equipment (PPE), safe work procedures were followed, and regular supervision was ensured. Gender considerations were addressed through inclusive community participation and equitable access to project benefits for both boys and girls at the school and surrounding community.
WATER | 1596 | Churiri borehole- EIA, Hydrogeological survey, WRA, drilling and casing | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2023-07-01 | 2024-06-30 |  | 3200000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | yes | appropriate mitigation measures have been implemented. Environmentally, efforts were made to prevent contamination of groundwater, manage drilling waste, and restore vegetation cover. Socially, the project involved local community engagement and ensured that the borehole development would benefit all, including vulnerable groups. On occupational health and safety, all workers were equipped with appropriate PPE, trained on safe drilling operations, and supervised to prevent accidents. Gender inclusion was also emphasized, ensuring that both men and women were consulted and that the project promotes equitable access to clean water.
WATER | 1597 | Kioneki borehole- test pumping | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2023-07-01 | 2024-06-30 |  | 180882 |  |  | CGN | [7 empty] | 0 | ongoing | [11 empty] | yes | Mitigation measures included proper wastewater management, use of protective gear, enforcement of safety protocols, and inclusive stakeholder engagement to promote gender equity and environmental protection.
WATER | 1598 | Kanyawa borehole- supply and laying of pipes | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2023-07-01 | 2024-06-30 |  | 1000000 | 999573 |  | CGN |  |  |  | 999573 | 100% |  |  | 0 | complete | [11 empty] | yes | Potential impacts and implemented mitigation measures included ensuring proper waste management and disposal, minimizing dust and noise pollution during trenching and laying activities, using appropriate signage and personal protective equipment (PPE) for workers, conducting public awareness and stakeholder consultations with gender inclusivity, restoring affected sites post-installation, and ensuring occupational safety standards were observed throughout the project.
WATER | 1599 | Kiburu Water Project- supply and laying of pipes | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2023-07-01 | 2024-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | yes | Potential impacts and implemented mitigation measures included ensuring proper waste management and disposal, minimizing dust and noise pollution during trenching and laying activities, using appropriate signage and personal protective equipment (PPE) for workers, conducting public awareness and stakeholder consultations with gender inclusivity, restoring affected sites post-installation, and ensuring occupational safety standards were observed throughout the project.
WATER | 1600 | Desiliting Nyondo weir | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2023-07-01 | 2024-06-30 |  | 3000000 | 2999973 |  | CGN |  |  |  | 2999973 | 100% |  |  | 0 | complete | [11 empty] | yes | several mitigation measures have been implemented. Environmentally, measures were taken to control erosion and manage silt disposal without affecting nearby ecosystems. Socially, the local community was sensitized, and inclusive stakeholder engagement was conducted to ensure support and awareness. Occupational health and safety protocols were enforced, including provision of personal protective equipment (PPE), site supervision, and adherence to safe work procedures. Gender considerations were addressed by promoting the inclusion of women and marginalized groups in project benefits and consultation processes.
WATER | 1601 | Line Moja/Kindege Water project- supply and laying of pipes | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2023-07-01 | 2024-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | yes | Environmentally, the project has ensured minimal disruption through proper waste disposal, prevention of soil erosion, and protection of surrounding vegetation. Socially, community sensitization and stakeholder engagement have been undertaken to promote transparency and resolve any emerging conflicts. To address occupational health and safety, workers have been equipped with personal protective equipment, trained on safe practices, and supervised throughout the construction phase, with first aid support readily available. On gender, the project promotes inclusivity by encouraging the participation of women and ensuring that the benefits of the project reach all members of the community, including vulnerable and marginalized groups.
WATER | 1602 | Raitha kahuru water project- supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1603 | Ngwataniro water project - supply of pipes | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2023-07-01 | 2024-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | yes | Environmentally, the project has ensured minimal disruption through proper waste disposal, prevention of soil erosion, and protection of surrounding vegetation. Socially, community sensitization and stakeholder engagement have been undertaken to promote transparency and resolve any emerging conflicts. To address occupational health and safety, workers have been equipped with personal protective equipment, trained on safe practices, and supervised throughout the construction phase, with first aid support readily available. On gender, the project promotes inclusivity by encouraging the participation of women and ensuring that the benefits of the project reach all members of the community, including vulnerable and marginalized groups.
WATER | 1604 | Kinja water project - supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1605 | Mutamaiyu water project- supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 | 999688 |  | CGN |  |  |  | 999688 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1606 | Supply and laying of assorted pipes- Mbirithi, Manyatta and Kanyugi | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2300000 | 2298000 |  | CGN |  |  |  | 2298000 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1607 | Supply and laying of assorted pipes- Itomboya | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1200000 | 1199457 |  | CGN |  |  |  | 1199457 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1608 | Construction of itomboya borehole and weru centre borehole fences | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1200000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | Ensure fence is secure and allow proper water flow to avoid stagnation,proper waste management
WATER | 1609 | Excavation and laying of Muti-ini pipes along Muti-ini downstreams section | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2200000 | 2198487 |  | CGN |  |  |  | 2198487 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1610 | North Kinangop Ward- Supply and laying of assorted pipes | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1611 | Gatamaiyu Water Project- Supply and installation of submersible pump and solar panels | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 4000000 | 3999420 |  | CGN |  |  |  | 3999420 | 100% |  |  | 0 | complete | [11 empty] | Yes | Securing solar panels against theft and weather,ensure abstraction rate does not exceed yield of the aquifer and dispose wastes properly
WATER | 1612 | Gatamaiyu Water project- Construction of water tower and erection of 2No. 10M3 plastic water tanks | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1700000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | Provision of PPEs,recyle of construction debris where possible and safe disposal to authorized sites and prevent runoff from contaminating nearby areas
WATER | 1613 | Kwa Michinu borehole drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | 2999500 |  | CGN |  |  |  | 2999500 | 100% |  |  | 0 | complete | [11 empty] | Yes | Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and hazardous materials and maintain machineries to reduce noise emission
WATER | 1614 | Supply of assorted pipes and accessories - Muhonia Turasha W/P | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1615 | Supply of assorted pipes and accessories - 3M W/P | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1616 | Kamagoko intake rehabilitation | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1617 | Kiambogo borehole drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | 2999066 |  | CGN |  |  |  | 2999066 | 100% |  |  | 0 | complete
WATER | 1618 | Supply of assorted water pipes | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1700000 | 1699777 |  | CGN |  |  |  | 1699777 | 100% |  |  | 0 | complete
WATER | 1619 | Construction of Geta township water tower and erection of 2No. 10M3 plastic water tanks | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1800000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 1620 | Githima Borehole- Equipping borehole with solar pannels and supply and installation of submersible pump | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 4000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1621 | Githima Water project- Construction of water tower (including erection of 2No. 10m3 plastic tanks) control panel house and fencing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2400000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1622 | Supply of pipes and accessories- Gathiriga | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 700000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1623 | Supply of pipes and accessories- Karuri | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1624 | Supply of pipes and accessories- Kimbo | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1625 | Supply of pipes and accessories- Aberdare | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 500000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1626 | Muhonia, kimbo and aberdare water projects-Supply and laying of assorted pipes and fittings | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2488788 |  |  | CGN | [7 empty] | 0 | complete
WATER | 1627 | Miti-itano borehole drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | 2989890 |  | CGN |  |  |  | 2989890 | 100% |  |  | 0 | complete
WATER | 1628 | Assorted pipes and accessories- Kiburuti and Ndemi | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1629 | Umoja Borehole Gatondo- Drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | 2999968 |  | CGN |  |  |  | 2999968 | 100% |  |  | 0 | complete
WATER | 1630 | Gatondo borehole- Constructuin of 100m3 masonry tank | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2500000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1631 | Gatondo borehole- Supply of pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1800000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1632 | Rironi ECDE borehole- Construction of water tower | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1700000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1633 | Kirima borehole- drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3100000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1634 | Supply and laying of Assorted pipes | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 800000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1635 | Kagongo borehole- drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3100000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and hazardous materials and maintain machineries to reduce noise emission
WATER | 1636 | Supply of 500litre plastic water tanks | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2400000 | - |  | CGN |  |  |  | - |  |  |  |  | Complete
WATER | 1637 | Mahindu B/H Equipping with solar-powered submissible pump and solar panels | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 4000000 | 3999930 |  | CGN |  |  |  | 3999930 | 100% |  |  | 0 | complete
WATER | 1638 | Supply and laying of Assorted pipes and Accessories kaimbaga | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | 2986740 |  | CGN |  |  |  | 2986740 | 100% |  |  | 0 | complete
WATER | 1639 | Mwireri, Kia JM, Kieni and Kiganjo pipeline Extension | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 | 1999780 |  | CGN |  |  |  | 1999780 | 100% |  |  | 0 | complete
WATER | 1640 | Supply and laying of pipes in JM Primary Area Thitai | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 999800 |  |  | CGN | [7 empty] | 0 | complete
WATER | 1641 | Kagaa Borehole- Drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | YES | Adhere to ESMP
WATER | 1642 | Kiringo Kirima Kia Ngotho -Supply of assorted pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 1643 | Kirimaini Primary - EIA, Hydrogeological report, WRA Permit Borehole drilling, and Casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2500000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1644 | Githungo Borehole - Supply of assorted pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 500000 | 499859 |  | CGN |  |  |  | 499859 | 100% |  |  | 0 | complete
WATER | 1645 | Karugutu Village– Supply of assorted pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 | 999957 |  | CGN |  |  |  | 999957 | 100% |  |  | 0 | complete
WATER | 1646 | Nduthi Karugutu W/P - Supply and installation of solar panels | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2500000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1647 | Muiri W/P -Supply and installation of solar panels | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2500000 | 2499800 |  | CGN |  |  |  | 2499800 | 100% |  |  | 0 | complete
WATER | 1648 | Rurii Plot 10- Equipping with solar powered system and installation of submersible water pump | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 4000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1649 | Rurii Plot 10 borehole WP- Water treatment | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 8500000 |  |  | CGN | [7 empty] | 0 | retendered
WATER | 1650 | Supply of distribution pipes and Accessories- Malan | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 750000 | 749500 |  | CGN |  |  |  | 749500 | 100% |  |  | 0 | complete
WATER | 1651 | Drilling of Kimende borehole and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1652 | Rurii- Plot 10 borehole -Construction of power house and water kiosk | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 750000 | 749533 |  | CGN |  |  |  | 749533 | 100% |  |  | 0 | complete
WATER | 1653 | Kihoto borehole drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | yes | monitor ESMP
WATER | 1654 | Rutara Borehole water project- Equipping with submersible pump and solar pannels | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 4000000 | 3999833 |  | CGN |  |  |  | 3999833 | 100% |  |  | 0 | complete
WATER | 1655 | Kanjuiri BH - Hygeological survy, EIA, drilling and casing | water distribution | Enhanced water supply |  |  | Olkalou | kanjuiri |  |  | 2023-07-01 | 2024-06-30 |  | 2800000 |  |  | CGN | [7 empty] | 0 | Complete
WATER | 1656 | Kanjuiri - Wiyumiririe borehole water project construction of water tower and installation of 2 x 10m3 plastic tanks | water distribution | Enhanced water supply |  |  | Olkalou | kanjuiri |  |  | 2023-07-01 | 2024-06-30 |  | 1559600 | 1559600 |  | CGN |  |  |  | 1559600 | 100% |  |  | 0 | complete
WATER | 1657 | Gituamba borehole drilling and casing | water distribution | Enhanced water supply |  |  | Olkalou | MIirangine |  |  | 2023-07-01 | 2024-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1658 | Nyandundo WP- equiping with solar panel, pump and support structure | water distribution | Enhanced water supply |  |  | Olkalou | MIirangine |  |  | 2023-07-01 | 2024-06-30 |  | 3500000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1659 | Supply of assorted pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1660 | Matunda borehole-Equipping of the BH with Solar panels, submersible pump and construction of power House) | water distribution | Enhanced water supply |  |  | olkaluo | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 3500000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1661 | Kwa MOA irrigation project borehole-Mirangine | water distribution | Enhanced water supply |  |  | olkaluo | mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 1998900 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1662 | Nyandundo Borehole -drilling and casing | water distribution | Enhanced water supply |  |  | olkaluo | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 3000000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1663 | Mirangine- Installation of bore hole withdrawal pipes, submersiblle pump,solar pannels and support structure for Gituamba borehole | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 3797450 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1664 | Mirangine- Mumui/Makara -Construction of 100m3 masonry tank | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 2999882 |  |  | CGN | [7 empty] | 0 | ongoing | [11 empty] | YES | Adhere to ESMP
WATER | 1665 | Mirangine- Kihuho-Kibendera Borehole -Steel water tank and other water works | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 4500000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1666 | 322 | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1667 | Mirangine- Kurungu Borehole -Steel water tank and other water works | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 4500000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1668 | Charagita -Olaimutia water project-Rerouting power lines | water distribution | Enhanced water supply |  |  | Oljororok | Charagita |  |  | 2023-07-01 | 2024-06-30 |  | 1500000 |  |  | CGN | [7 empty] | 0 | ongoing | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1669 | Gacheru dam borehole water project-Supply and installation of submersible pump and solar panels | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2023-07-01 | 2024-06-30 |  | 4000000 |  |  | CGN | [7 empty] | 0 | complete | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1670 | Museveni water project- supply and installation of submersible pump and solar panels | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2023-07-01 | 2024-06-30 |  | 4000000 |  |  | CGN | [7 empty] | 0 | ongoing | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1671 | Weru- Kariko water project- Additional solar panels | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2023-07-01 | 2024-06-30 |  | 1000000 |  |  | CGN | [7 empty] | 0 | awaiting payment | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1672 | Oljoro-orok Secondary School Bohore - Hydrogeological Survey, EIA and Drilling | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2023-07-01 | 2024-06-30 |  | 2000000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1673 | Gatimu primary piping | water distribution | Enhanced water supply |  |  | Oljororok | Gatimu |  |  | 2023-07-01 | 2024-06-30 |  | 2000000 | 1999672 |  | CGN |  |  |  | 1999672 | 100% |  |  | 0 | complete | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1674 | Kwa Ngengi- Construction of water tower and erection of 2No. 10M3 Plastic tanks | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1800000 |  |  | CGN | [7 empty] | 0 | awaiting payment
WATER | 1675 | Huhoini water project- supply and laying of assorted pipes | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2023-07-01 | 2024-06-30 |  | 2000000 | 1998308 |  | CGN |  |  |  | 1998308 | 100% |  |  | 0 | Complete and paid | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1676 | Njoro water project- supply and laying of extension pipes | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2023-07-01 | 2024-06-30 |  | 2000000 | 1996616 |  | CGN |  |  |  | 1996616 | 100% |  |  | 0 | Complete and paid | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1677 | Boiman Kerison Muungano extension pipes | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2023-07-01 | 2024-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | awaiting payment | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1678 | Goodfall borehole drilling and casing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1679 | Gathanji- Construction of water kiosk - Huhoini | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2023-07-01 | 2024-06-30 |  | 700000 |  |  | CGN | [7 empty] | 0 | awaiting payment | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1680 | Rehabilitation of Boiman water storage tank- Gathanji | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2023-07-01 | 2024-06-30 |  | 1000000 |  |  | CGN | [7 empty] | 0 | awaiting payment | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1681 | Supply and laying of pipes at Kabatini-Paris Borehole | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2023-07-01 | 2024-06-30 |  | 800000 |  |  | CGN | [7 empty] | 0 | ongoing | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1682 | Gathanji -Kamukunji Water project borehole drilling and casing FY 2020-2021 | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2023-07-01 | 2024-06-30 |  | 2449530 |  |  | CGN | [7 empty] | 0 | ongoing | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1683 | Karagoini water project -Supply of assorted pipes and accessories | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2023-07-01 | 2024-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | ongoing | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1684 | Purchase and supply of 500 litres tanks | water distribution | Enhanced water supply |  |  | Oljororok | Gathanji |  |  | 2023-07-01 | 2024-06-30 |  | 2000000 | 1996716 |  | CGN |  |  |  | 1996716 | 100% |  |  | 0 | complete | [11 empty] | Yes | _
WATER | 1685 | Rehabilitation of Suguroi Borehole | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 500000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1686 | Shamata- Borehole equipping | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 4800000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1687 | Shamata Borehole -construction of powerhouse | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 400000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1688 | Shamata- Wambuku Dam- Fencing and water troughs | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2700000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1689 | Shamata- Pesi Village Water project | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3999876 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1690 | 3M water project- rerouting of distribution main | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 5000000 | 4997112 |  | CGN |  |  |  | 4997112 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1691 | Hydrogeological survey, EIA, drilling and casing Kihuko borehole | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3500000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1692 | Nazareth -Construction of a 100M3 Masonry tank | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1693 | Geta ward - Construction of Marimu B water tank | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1694 | Geta ward - Construction of Mikeu water tank | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | ongoing
WATER | 1695 | Geta ward - Makumbi BH Pump and Solar Equipping | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3500000 | 3499400 |  | CGN |  |  |  | 3499400 | 100% |  |  | 0 | complete
WATER | 1696 | Murungaru ward - Jugimo borehole water project - Supply and laying of pipes and accessories | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2499490 |  |  | CGN | [7 empty] | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1697 | Rehabilitation of degraded Aberdare ranges escarpment- Tree planting at kahindu springs | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 300000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 1698 | Functional storm water drains and culverts in all towns, trading and market centres- mairo inya, Njabini, miharati and oljoorok town | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2023-07-01 | 2024-06-30 |  | 600000 |  |  | CGN | [7 empty] | 0 | complete | [11 empty] | YES | key mitigation measures were implemented. Environmentally, proper drainage structures were designed to prevent flooding, soil erosion, and waterlogging. Socially, community sensitization was conducted to minimize disruptions during construction. Occupational health and safety protocols were observed through the provision of personal protective equipment (PPE), adherence to safety guidelines, and on-site supervision. Gender considerations were integrated by ensuring inclusive community engagement and addressing the specific mobility and safety concerns of women and vulnerable groups.
WATER | 1699 | Kahuru and Kanyugi- Cleanin drainage structures through labour contracting | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | complete | [11 empty] | Yes | Collect and separate organic,plastic and harzadous waste during cleaning,dispose silt and solid matter to authorized site,use of PPEs during maintenance,proper construction of culverts as instructed by the Water Engineer
WATER | 1700 | Munyaka area- Cleaning drainage structures through labour contracting | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 |  |  | CGN | [7 empty] | 0 | complete | [11 empty] | Yes | Collect and separate organic,plastic and harzadous waste during cleaning,dispose silt and solid matter to authorized site,use of PPEs during maintenance,proper construction of culverts as instructed by the Water Engineer
WATER | 1701 | Roof water harvesting for Manyatta -Engineer Ward | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 | 999280 |  | CGN |  |  |  | 999280 | 100% |  |  | 0 | complete | [11 empty] | Yes | Provision of high quality durable tanks that are recyclable, safe transportation and handling and ensure tanks places have community consent and are on a public land with proper authorization
WATER | 1702 | Supply of LPG cylinder to the Elderly- Olbolosat Shamata | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 |  |  | CGN | [7 empty] | 0 | not supplied
WATER | 1703 | Water harvesting intervention for Mbirithi and Kanyugi -Engineer Ward | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3000000 | 2998510 |  | CGN |  |  |  | 2998510 | 100% |  |  | 0 | complete | [11 empty] | Yes | Provision of high quality durable tanks that are recyclable, safe transportation and handling and ensure tanks places have community consent and are on a public land with proper authorization
WATER | 1704 | Supply of LPG cylinder to the Elderly-Kilimanjaro and Canary Shamata | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1954900 |  |  | CGN | [7 empty] | 0 | not supplied
WATER | 1705 | Construction and rehabilitation of small dams and water pans- Mihuti in Kaimbaga Ward | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | Contractor did not report to site
WATER | 1706 | Construction and rehabilitation of small dams and water pans- Kibido in Weru ward | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing. contractor on site
WATER | 1707 | Tree Nursery and Energy Jiko | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1000000 |  |  | CGN | [7 empty] | 0 | complete
WATER | 1708 | Muhonia turasha water project - Kagongo Borehole Drilling | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2300000 | 2300000 |  | CGN |  |  |  | 2300000 | 100% |  |  | 0 | complete | [11 empty] | Yes | - Ensure all workers have PPEs,fence and clearly mark borehole site to prevent accidents,management of waste and hazardous materials and maintain machineries to reduce noise emission
WATER | 1709 | Kieni Bh Supply And Installation Of Solar Powered Pumps And Solar System | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3749000 | - |  | CGN |  |  |  | -
WATER | 1710 | Kandutura Water Tower | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1799928 | - |  | CGN |  |  |  | -
WATER | 1711 | Kieni Water Tower | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1498980 | - |  | CGN |  |  |  | -
WATER | 1712 | Wanjohi ward- Kipkwagary borehole installation of pump and Solar panels | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 4000000 | 3999200 |  | CGN |  |  |  | 3999200 | 100% |  |  | 0 | complete
WATER | 1713 | Kipipiri -Supply of 500litre capacity water storage tanks | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2000000 | 1998000 |  | CGN |  |  |  | 1998000 | 100% |  |  | 0 | complete
WATER | 1714 | Kipipiri Supply of pipes | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 298200 | 298200 |  | CGN |  |  |  | 298200 | 100% |  |  | 0 | complete
WATER | 1715 | Mirangine kurungu borehole water Project equipping | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 3798950 | 3798950 |  | CGN |  |  |  | 3798950 | 100% |  |  | 0 | complete
WATER | 1716 | Construction Of A 50Mᶟ Masonry Storage of Kianjogu water tank | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2199200 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1717 | Kiriita - Baari Borehole water Project- Pitah Enterprises | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2199500 | 2199500 |  | CGN |  |  |  | 2199500 | 100% |  |  |  | complete
WATER | 1718 | Supply of assorted pipes and accessories- Weru Ward- | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2999850 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1719 | Gichungo and Mwireri boreholes drilling | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3999666 | - |  | CGN |  |  |  | - |  |  |  |  | Files held by EACC
WATER | 1720 | Kaimbaga- Mwireri Water Tower | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | Files held by EACC
WATER | 1721 | Kaimbaga- Rumathi Control panel and fencing | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1500000 | - |  | CGN |  |  |  | - |  |  |  |  | Files held by EACC
WATER | 1722 | Construction Of A 50Mᶟ Masonry Storage Tank At Kianugu Water Project | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1199996 | 1199996 |  | CGN |  |  |  | 1199996 | 100% |  |  | 0 | complete
WATER | 1723 | Power connection in Nyakio primary borehole- Githabai/Step Two Limited | water distribution | Enhanced water supply |  |  | Njabini | Nyakio |  |  | 2023-07-01 | 2024-06-30 |  | 499500 | 499500 |  | CGN |  |  |  | 499500 | 100% |  |  | 0 | complete | [11 empty] | yes | Several mitigation measures were instituted. These include ensuring safe electrical installation practices to prevent accidents and environmental hazards, the use of certified electrical materials, and routine inspection protocols to ensure compliance with safety standards. Workers involved in the power connection were provided with appropriate personal protective equipment (PPE) and trained in occupational safety procedures. Socially, local stakeholders were consulted to enhance project acceptance and minimize disruption. Gender-responsive approaches were adopted to ensure inclusive participation, while measures were put in place to prevent gender-based violence and support the involvement of women in project benefits.
WATER | 1724 | Gathanji- Kwa Ngara Borehole Equipping | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3798165 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1725 | Gathiriga line repair ( pillars) for Mawingu water project- Githioro/Gamwaga | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1199850 | 1199850 |  | CGN |  |  |  | 1199850 | 100% |  |  | 0 | complete
WATER | 1726 | Installation of solar powered pump and solar panel in Gachigirira Chief Ndumia | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3899720 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing
WATER | 1727 | Drilling and casing of Gacheru borehole and Karandi Water Project- weru ward | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2023-07-01 | 2024-06-30 |  | 3988462 | 3988462 |  | CGN |  |  |  | 3988462 | 100% |  |  | 0 | complete | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1728 | Drilling and casing of uiguano borehole- weru ward | water distribution | Enhanced water supply |  |  | Oljororok | Weru |  |  | 2023-07-01 | 2024-06-30 |  | 2995600 | 2995600 |  | CGN |  |  |  | 2995600 | 100% |  |  | 0 | complete | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1729 | Construction of water tower and supply of 2No. 10,000Ltrs tanks in Nyakio primary borehole- Githabai ward | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2023-07-01 | 2024-06-30 |  | 1599500 | 1599500 |  | CGN |  |  |  | 1599500 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions have been undertaken to address potential risks. These include ensuring structural integrity through engineering best practices to prevent accidents and water contamination, enforcing occupational health and safety measures such as the use of personal protective equipment (PPE), and conducting regular site safety audits. Environmentally, care has been taken to prevent soil erosion and water runoff, while socially, stakeholder consultations ensured community support and minimized disruption. Gender inclusion has been promoted by encouraging women’s participation in consultation and decision-making processes, with safeguards against gender-based violence also instituted on-site.
WATER | 1730 | Construction of water tower and supply of 2No. 10,000Ltrs tanks in Heni water project- Githabai ward | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2023-07-01 | 2024-06-30 |  | 1599500 | 1599500 |  | CGN |  |  |  | 1599500 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation actions have been undertaken to address potential risks. These include ensuring structural integrity through engineering best practices to prevent accidents and water contamination, enforcing occupational health and safety measures such as the use of personal protective equipment (PPE), and conducting regular site safety audits. Environmentally, care has been taken to prevent soil erosion and water runoff, while socially, stakeholder consultations ensured community support and minimized disruption. Gender inclusion has been promoted by encouraging women’s participation in consultation and decision-making processes, with safeguards against gender-based violence also instituted on-site.
WATER | 1731 | Supply, delivery and installation of pipes and assorted fittings, excavation of pipeline trench, laying and backfilling, construction of valve chambers and pipeline testing - Shamata ward | water distribution | Enhanced water supply |  |  | Ndaragwa | Shamata |  |  | 2023-07-01 | 2024-06-30 |  | 3955000 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1732 | Mirangine- Nyandundo water project-EIA and hydrogeological survey and WRA Permit | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 200000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1733 | Mirangine- Kihuho distribution of pipes Mirangine - Mercross Enterprises | water distribution | Enhanced water supply |  |  | Olkalou | Mirangine |  |  | 2023-07-01 | 2024-06-30 |  | 1999830 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1734 | Charagita- Supply and Installation of Submersible pump for Oleimutia Borehole- | water distribution | Enhanced water supply |  |  | Oljororok | Charagita |  |  | 2023-07-01 | 2024-06-30 |  | 2599380 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | _
WATER | 1735 | Rurii Plot 10 water project -Construction of water tower and supply and installation of 2No. 10m3 plastic tanks and Githioro- Mawingu WP -supply and laying of pipes - Aberdare, Mawingu and Gathiriga Frapert Construction Co Ltd | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2699524 | 2699524 |  | CGN |  |  |  | 2699524 | 100% |  |  | 0 | complete | [11 empty] | YES | Adhere to ESMP
WATER | 1736 | North Kinangop- Gitite Kairia Water project- Construction of water tower | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1700000 | - |  | CGN |  |  |  | - |  |  |  |  | ongoing | [11 empty] | Yes | Provision of PPEs,recyle of construction debris where possible and safe disposal to authorized sites and prevent runoff from contaminating nearby areas
WATER | 1737 | Karau- Gachwe- Glad force borehole supply and installation of solar panel and renovation and repair of Muiri Borehole - MONRICH COMPANY LIMITED | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 599627 | 599627 |  | CGN |  |  |  | 599627 | 100% |  |  | 0 | complete
WATER | 1738 | Repair of Koinange borehole water pump and solar system- Githabai/Merich international Limited | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2023-07-01 | 2024-06-30 |  | 1499910 | 1499910 |  | CGN |  |  |  | 1499910 | 100% |  |  | 0 | complete | [11 empty] | yes | Several mitigation actions were undertaken. These include ensuring safe handling and disposal of old equipment to avoid environmental contamination, implementing safety protocols for workers during electrical and mechanical repair works, and maintaining site cleanliness. Socially, community engagement was prioritized to minimize disruption and ensure local support, while gender considerations included promoting inclusive labor practices and safeguarding against gender-based discrimination or harassment at the project site.
WATER | 1739 | Karandi Irrigation Project- Weru Ward/Jowich International Ltd | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2999990 | 2999980 |  | CGN |  |  |  | 2999980 | 100% |  |  | 0 | complete
WATER | 1740 | Supply of pipes and accessories in Ndothua borehole water project/Merich international Limited | water distribution | Enhanced water supply |  |  | Njabini | Njabini |  |  | 2023-07-01 | 2024-06-30 |  | 1649570 | 1649570 |  | CGN |  |  |  | 1649570 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation measures were implemented to address potential risks. These included ensuring safe storage and transportation of pipes and fittings to prevent environmental pollution, enforcing occupational safety protocols to protect workers during handling and installation, and engaging the local community to foster awareness and support. Social inclusion and gender considerations were also observed by promoting equitable participation and safeguarding against gender-based risks throughout the project activities.
WATER | 1741 | Supply of pipes and accessories in Koinange borehole water project- Githabai/Merich international Limited | water distribution | Enhanced water supply |  |  | Njabini | Githabai |  |  | 2023-07-01 | 2024-06-30 |  | 1648930 | 1648930 |  | CGN |  |  |  | 1648930 | 100% |  |  | 0 | complete | [11 empty] | yes | Mitigation measures were implemented to address potential risks. These included ensuring safe storage and transportation of pipes and fittings to prevent environmental pollution, enforcing occupational safety protocols to protect workers during handling and installation, and engaging the local community to foster awareness and support. Social inclusion and gender considerations were also observed by promoting equitable participation and safeguarding against gender-based risks throughout the project activities.
WATER | 1742 | Githima Irrigation Project- Mirangine Ward/ Afela Limited | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 1999000 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1743 | Drilling and casing of Kenyatta road borehole- magumu/Cosmic Automobiles Limited | water distribution | Enhanced water supply |  |  | Njabini | Magumu |  |  | 2023-07-01 | 2024-06-30 |  | 2999500 | 2999500 |  | CGN |  |  |  | 2999500 | 100% |  |  | 0 | complete | [11 empty] | yes | Several mitigation measures were undertaken. These included safe disposal of drill cuttings to minimize environmental pollution, provision of personal protective equipment (PPE) to workers to enhance occupational safety, and the enforcement of health protocols at the site. Additionally, the project incorporated community sensitization to promote social inclusion and ensured gender considerations were observed through equitable engagement and participation of all stakeholders.
WATER | 1744 | Githima Water Project - Mirangine/ Fadram Enterprises Limited | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2997550 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1745 | Establishment of live fence and planting of indigenous tree in Weru police post- engineer/Tylan Works | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 699618 | 699618 |  | CGN |  |  |  | 699618 | 100% |  |  | 0 | complete | [11 empty] | Yes | Ensure fence is secure and allow proper water flow to avoid stagnation,indigenous trees to be planted to ensure healthy environment and prevent degradation
WATER | 1746 | Reticulation of Matundura borehole- Engineer/Bluedon Ventures Limited | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 2293418 | 2290999 |  | CGN |  |  |  | 2290999 | 100% |  |  | 0 | complete | [11 empty] | Yes | To ensure proper disposal of excavated soil and construction waste,use water spraying to suppress dust and prevent contamination of surface and ground water.
WATER | 1747 | Construction of Githunguchu 225m3 masonary tank- Kiriita- Kandesian Building and civil work | water distribution | Enhanced water supply |  |  | Ndaragwa | Kiriita |  |  | 2023-07-01 | 2024-06-30 |  | 3000000 | 2999700 |  | CGN |  |  |  | 2999700 | 100% |  |  | 0 | complete | [11 empty] | Yes | SPR done + ESMP Monitoring
WATER | 1748 | Rehabilitation of Kilimanjaro water project storage tank- shamata | water distribution | Enhanced water supply |  |  | Ndaragwa | Shamata |  |  | 2023-07-01 | 2024-06-30 |  | 1000000 | 999804 |  | CGN |  |  |  | 999804 | 100% |  |  | 0 | complete | [11 empty] | Yes | _
WATER | 1749 | Drilling and casing of Shamata borehole- Shamata- Kibson General Merchants | water distribution | Enhanced water supply |  |  | Ndaragwa | Shamata |  |  | 2023-07-01 | 2024-06-30 |  | 2994500 | - |  | CGN |  |  |  | - |  |  |  |  | complete | [11 empty] | Yes | SPR + ESMP Monitoring
WATER | 1750 | Supply of 10m3 plastic tank and pipes to Nyakinywa welfare group- leshau pondo-Begajoy limited | water distribution | Enhanced water supply |  |  | Ndaragwa | Leshau Pondo |  |  | 2023-07-01 | 2024-06-30 |  | 999550 | 999550 |  | CGN |  |  |  | 999550 | 100% |  |  | 0 | complete | [11 empty] | Yes | _
WATER | 1751 | Purchase and supply of 500 liter tanks to Kiandogoro,Kiriogo- ndaragwa central- Quality Equipment Bargain Ltd | water distribution | Enhanced water supply |  |  | Ndaragwa | Central |  |  | 2023-07-01 | 2024-06-30 |  | 2999700 | 2999699 |  | CGN |  |  |  | 2999699 | 100% |  |  | 0 | complete | [11 empty] | Yes | _
WATER | 1752 | Construction of pillars and supply and laying of pipes- kanjuiri- Lejojo investment ltd | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 747700 | - |  | CGN |  |  |  | - |  |  |  |  | complete
WATER | 1753 | Drilling of Kahiga borehole- kipipiri- Jackiedaniel Enterprises company | water distribution | Enhanced water supply | [6 empty] | 2023-07-01 | 2024-06-30 |  | 3083625 | - |  | CGN |  |  |  | - |  |  |  |  | complete
EDUCATION | 1754 | Kimathi Primary (ECDE) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Njabini |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1755 | Kieni Nursery (ECDE) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1756 | Githunguri Nursery | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Olkalou | Rurii |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1757 | Gatitu Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Oljororok | Weru |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1758 | Kahia Nursery | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Olkalou | Karau |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1759 | Nyakiambi Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Gathaara |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1760 | Kanamba Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Gathaara |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1761 | Kilimanjaro Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1762 | Kanyugi Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1763 | Rutara (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1764 | Kimuri Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Murungaru |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1765 | Mikeu Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kipipiri | Geta |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1766 | Ritaya Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Ndaragwa | Kiirita |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1767 | Karuri ECD | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1768 | Mutonyora ECD | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Magumu |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1769 | Kware ECD | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1770 | Ndaragwa Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Oljororok | Charagita |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1771 | Ngano Pry Special Class | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Oljororok | Charagita |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1772 | Mwireri Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1773 | Churiri Nursery | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Njabini |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1774 | Machinery ECD Centre | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1775 | Gitite Pry (ECD) | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1776 | Gitwe ECD | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Nyakio |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1777 | Gatimu Special Sch | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Oljororok | Gatimu |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1778 | Githabai Pry ECD | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Githabai |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1779 | Nyandarua school for the deaf | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1780 | Umoja Mbuyu | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1781 | Mlimani | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1782 | Ihiga | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Ndaragwa | Ndaragwa |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1783 | Gikeno | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kipipiri | Githioro |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1784 | Kamaina ECD | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Oljororok | Weru |  | Human resource | Jul13 | Jun14 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1785 | Shauri Youth Polytechnic | Construction of Toilets and staffroom | To create a conducive learning environment | ConstructedToilet and staffroom | 3110299 | Ndaragwa | Kiriita |  | Productive | Jul13 | Jun14 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | [11 empty] | YES
EDUCATION | 1786 | Kahoro Youth polytechnic | Electricity Installation | To create a conducive learning environment | Electricity Installed | 3110299 | Kipipiri | Wanjohi |  | Productive | Jul13 | Jun14 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 251000 | [14 empty] | YES
EDUCATION | 1787 | Kangui Youth Polytechnic | Construction of a hostel | To create a conducive learning environment | Constructed hostel | 3110299 | Oljororok | Weru |  | Productive | Jul13 | Jun14 |  | 6000000 | 6000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 | [14 empty] | YES
EDUCATION | 1788 | Geta Youth polytechnic | Construction of toilets, fencing and electricity installation | To create a conducive learning environment | Constructed toilets, fencing and electricity installed | 3110299 | Kipipiri | Geta |  | Productive | Jul13 | Jun14 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 800000 | [14 empty] | YES
EDUCATION | 1789 | Olkalou Youth Polytechnic | Construction of a twin Workshop | To create a conducive learning environment | Constructed twin Workshop | 3110299 | Olkalou | Kaimbaga |  | Productive | Jul13 | Jun14 |  | 6000000 | 6000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 | [14 empty] | YES
EDUCATION | 1790 | Njambini Youth Polytechnic | Construction of a Girls Hostel |  | Constructed Girls Hostel | 3110299 | Kinangop | Njabini Kiburu |  | Productive | Jul13 | Jun14 |  | 3000000 | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 | [14 empty] | YES
EDUCATION | 1791 | Kijiko | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Engineer |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1792 | Kahuria | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Murungaru |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1793 | St Marys | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Magumu |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1794 | Mbogani | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Githabai |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1795 | Kihunguru | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Nyakio |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1796 | Mucibau | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Njabini |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1797 | Kaugi | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Githabai |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1798 | Chania | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Njabini |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1799 | Mwihoko | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Gathara |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1800 | Githinji | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Magumu |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1801 | Kariahu | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Gathaara |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1802 | Kitogo | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kinangop | Gathara |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1803 | Marimu ECD classroom construction | Construction of a classroom | To provide learning facilities | Constructed Classroom | 3110329 | Kipipiri | Geta |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1804 | Mara Special Unit ECD | Construction of a classroom | To provide learning facilities | Constructed Classroom | 3110329 | Kipipiri | Kipipiri |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1805 | Gichigirira | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kipipiri | Wanjohi |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1806 | Kangondi | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Kipipiri | Githioro |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1807 | Magomano ECD classroom construction | Construction of a classroom | To provide learning facilities | Constructed Classroom | 3110329 | Kipipiri | Wanjohi |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A |  |  |  | 599999 |  | Complete | [11 empty] | YES
EDUCATION | 1808 | Forest one ECD classroom construction | Construction of a classroom | To provide learning facilities | Constructed Classroom | 3110329 | Kipipiri | Githioro |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1809 | Kahindu ECD classroom construction | Construction of a classroom | To provide learning facilities | Constructed Classroom | 3110329 | Ndaragwa | Shamata |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1810 | Kiandongoro | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Ndaragwa | Ndaragwa |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1811 | Kametha ECD classroom construction | Construction of a classroom | To provide learning facilities | Constructed Classroom | 3110329 | Ndaragwa | Shamata |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1812 | Sugurui | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Ndaragwa | Ndaragwa |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1813 | Githunguchu ECD classroom | Construction of a classroom | To provide learning facilities | Constructed Classroom | 3110329 | Ndaragwa | Kiriita |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1814 | Githima | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Ndaragwa | Leshau Pondo |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1815 | Inooro ECD classroom and pit latrine | construction of classroom and a pit latrine | To create a conducive learning environment | Constructed Classroom and Toilet | 3110329 | Oljororok | Weru |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1816 | Gatimu ECD classroom and pit latrine | construction of classroom and a pit latrine | To create a conducive learning environment | Constructed Classroom and Toilet | 3110329 | Oljororok | Gatimu |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1817 | Charagita ECD classroom construction | Construction of a classroom | To create a conducive learning environment | Constructed Classroom | 3110329 | Oljororok | Charagita |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1818 | Kibathi ECD classroom construction | Construction of a classroom | To create a conducive learning environment | Constructed Classroom | 3110329 | Oljororok | Gatimu |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1819 | Equator | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Ndaragwa | Leshau Pondo |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1820 | Mahua ECD classroom construction | Construction of a classroom | To create a conducive learning environment | Constructed Classroom | 3110329 | Oljororok | Gathanji |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1821 | Nyairoko ECD classroom construction | Construction of a classroom | To create a conducive learning environment | Constructed Classroom | 3110329 | Oljororok | Gathanji |  | Human resource | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1822 | Gathima Chaka Reli | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Oljororok | Weru |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1823 | Mathakwa | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Olkalou | Mirangine |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1824 | Bahati | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Olkalou | Kaimbaga |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1825 | Highland | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Olkalou | Karau |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1826 | Huruma | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Olkalou | Kaimbaga |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1827 | Gituamba | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Olkalou | Rurii |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1828 | Murindati | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 |  |  |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1829 | Huho- Ini | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110329 | Olkalou | Rurii |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1830 | Kiganjo Special Unit ECD | construction of 3 door phased Toilet | Provide access to safe and hygienic sanitation facilities | Constructed staff Toilet | 3110329 | Olkalou | Kaimbaga |  | Human resource | Jul14 | Jun15 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1831 | ECDE CHAIRS | distribution of ECDE chairs | To create a conducive learning environment | Chairs were isued | 3110329 | Countywide | County Wide |  | Human resource | Jul14 | Jun15 |  | 2997500 | 2997500 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1832 | KIPENDERA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110329 |  |  |  | Human resource | Jul14 | Jun15 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1833 | Mutarakwa ECD classroom construction | Construction of classroom | Provide learning facilites | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul13 | Jun14 | [13 empty] | Complete
EDUCATION | 1834 | Land for Milangine Youth Polytechnic | Procurement of land | To provide land for Milangine Youth Polytechnic | Land was acquired | 3110299 | Olkalou | Mirangine |  | Productive | Jul14 | Jun15 |  | - | 1500000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1835 | Land for Murungaru Youth Polytechnics | Procurement of land | To provide land for Milangine Youth Polytechnic | Land was acquired | 3110299 | Kinangop | Murungaru |  | Productive | Jul14 | Jun15 |  | - | - |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1836 | Kirinyaga youth polytechnic | Plastering and electricity | To create a conducive learning environment | Plastering and electricity installation done | 3110299 | Ndaragwa | Ndaragwa Central |  | Productive | Jul14 | Jun15 |  | - | 4800000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1837 | Ginning Administration Block | Construction of administration block | To create a conducive learning environment | Administration block was constructed | 3110299 |  |  |  | Productive | Jul14 | Jun15 |  | - | 1800000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1838 | Shauri youth polytechnic | Administration block construction ,toilet and tools | To create a conducive learning environment | Administration block and toilet were constructed | 3110299 | Ndaragwa | Kiriita |  | Productive | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1839 | Rurii polytechnic | Construction of staff toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Rurii |  | Productive | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1840 | Construction of ABT centre at Olkalau polytechnic | Construction of ABT centre | To create a conducive learning environment | Center was constructed | 3110299 | Olkalou | Kaimbaga |  | Productive | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 1841 | Bunyan Youth Polytechnic | electrification | To create a conducive learning environment | Electricity Installed | 3110299 | Kinangop | Njabini |  | Productive | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1842 | Kinangop Youth polytechnic | Piped water connection | Provision of water | Water installed | 3110299 | Kinangop | N.Kinangop |  | Productive | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1843 | Njambini Youth Polytechnic | electricity installation, renovation and toilets | To create a conducive learning environment | Electricity Installed and toilets renovated | 3110299 | Kinangop | Njabini Kiburu |  | Productive | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1844 | Construction of staff toilets at Rurii polytechnic |  |  |  |  | Olkalou | Rurii |  | Productive | Jul14 | Jun15 | [13 empty] | Complete
EDUCATION | 1845 | Renovation works at Pesi YP | Renovation of the Youth Polytechnic | To create a conducive learning environment | Renovated YP | 3110299 | Ndaragwa | Shamata |  | Productive | Jul14 | Jun15 | [13 empty] | Complete
EDUCATION | 1846 | Electricity installation at Kahoro YP and toilets | Electricity installation at Kahoro YP and toilets | To create a conducive learning environment | Electiricy installed in the YP and toilets | 3110299 | Kipipiri | Wanjohi |  | Productive | Jul14 | Jun15 | [13 empty] | Complete
EDUCATION | 1847 | Talent development | Enhance social cohesion | Preservation of our cultural heritage | Increased cultural literacy | 2211399 | Countywide | Countywide |  | Productive | Jul14 | Jun15 |  |  |  |  | CGN | N/A | N/A | N/A
EDUCATION | 1848 | HIV/AIDS awareness | Education on HIV&AIDS | To improve livelihood | Communities were sensitized on HIV | 2211399 | Countywide | County Wide |  | Productive | Jul14 | Jun15 |  | 200000 | - |  | CGN | N/A | N/A | N/A
EDUCATION | 1849 | Social support | Disability mainstreaming | To improve livelihood | Provided social support | 2211399 | Countywide | County Wide |  | Productive | Jul14 | Jun15 |  | 775000 | 50000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1850 | BARAINYA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 2997500 | [14 empty] | YES
EDUCATION | 1851 | CIIRA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 913380 | [14 empty] | YES
EDUCATION | 1852 | GIKENO ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Oljororok | Gathanji |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 908027.2 | [14 empty] | YES
EDUCATION | 1853 | WENDANI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 938186 | [14 empty] | YES
EDUCATION | 1854 | NDONDORI | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Mirangine |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 824275 | [14 empty] | YES
EDUCATION | 1855 | KAHUHO ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Karau |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 749815 | [14 empty] | YES
EDUCATION | 1856 | GITUAMBA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Rurii |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 811901 | [14 empty] | YES
EDUCATION | 1857 | ECDE TABLES | distribution of ECDE tables | To create a conducive learning environment | Tables were delivered | 3110299 | Countywide | County Wide |  | Human resource | Jul15 | Jun16 |  | 2520000 | 2520000 |  | CGN | N/A | N/A | N/A |  |  | 946330 | [14 empty] | YES
EDUCATION | 1858 | MICHINDA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 2520000 | [14 empty] | YES
EDUCATION | 1859 | P.N ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 734458 | [14 empty] | YES
EDUCATION | 1860 | RAITHA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Gathara |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 408530 | [14 empty] | YES
EDUCATION | 1861 | NAIROBI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 800270 | [14 empty] | YES
EDUCATION | 1862 | KARIARA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 882325 | [14 empty] | YES
EDUCATION | 1863 | KIRIMA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 888850 | [14 empty] | YES
EDUCATION | 1864 | ECDE EQUIPMENTS | distribution of ECDE Equipment | To create a conducive learning environment | Equipment were delivered | 3110299 | Countywide | County Wide |  | Human resource | Jul15 | Jun16 |  | 2970000 | 2970000 |  | CGN | N/A | N/A | N/A |  |  | 2970000 | [14 empty] | YES
EDUCATION | 1865 | MIHUTI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 945955 | [14 empty] | YES
EDUCATION | 1866 | UMOJA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Rurii |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 922965 | [14 empty] | YES
EDUCATION | 1867 | KENYATTA ROAD | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Githabai |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1868 | JM ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 893924 | [14 empty] | YES
EDUCATION | 1869 | KIHUNGURU ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 739758 | [14 empty] | YES
EDUCATION | 1870 | MUTHOMI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Engineer |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 936262 | [14 empty] | YES
EDUCATION | 1871 | KIRIMAINI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Karau |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 810632 | [14 empty] | YES
EDUCATION | 1872 | MUNDI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Karau |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 930282 | [14 empty] | YES
EDUCATION | 1873 | MUKABURA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Karau |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 813820 | [14 empty] | YES
EDUCATION | 1874 | MUHUTI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 751379 | [14 empty] | YES
EDUCATION | 1875 | MARTIN ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 898204 | [14 empty] | YES
EDUCATION | 1876 | GATUMBIRO ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Oljororok | Weru |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 886980 | [14 empty] | YES
EDUCATION | 1877 | MWANGAZA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 750770 | [14 empty] | YES
EDUCATION | 1878 | ORAIMUTIA | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Oljororok | Charagita |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1879 | MUNANDA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Oljororok | Gathanji |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 843903 | [14 empty] | YES
EDUCATION | 1880 | KIAMBARIKI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 760021 | [14 empty] | YES
EDUCATION | 1881 | GATITU ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Rurii |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 945024 | [14 empty] | YES
EDUCATION | 1882 | NGARIKARURA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 866090 | [14 empty] | YES
EDUCATION | 1883 | MUKIRI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul15 | Jun16 |  | 1036416 | 1036416 |  | CGN | N/A | N/A | N/A |  |  | 1036416 |  |  | Complete | [11 empty] | YES
EDUCATION | 1884 | KARAI | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1885 | RUCHEGECI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 895008 | [14 empty] | YES
EDUCATION | 1886 | KAMBATA | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Murungaru |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1887 | MUTONYORA ECD | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1888 | KANJOGU ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 925723 | [14 empty] | YES
EDUCATION | 1889 | GITHUNGURI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 911590 | [14 empty] | YES
EDUCATION | 1890 | GATHANJI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Oljororok | Gathanji |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 822310 | [14 empty] | YES
EDUCATION | 1891 | MATUNDURA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Engineer |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 810811 | [14 empty] | YES
EDUCATION | 1892 | SASUMWA ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 881510 | [14 empty] | YES
EDUCATION | 1893 | MUCHEMI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Oljororok | Charagita |  | Human resource | Jul15 | Jun16 |  | 1033129 | 1033129 |  | CGN | N/A | N/A | N/A |  |  | 1033129 | [14 empty] | YES
EDUCATION | 1894 | SUBEGO ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Ndaragwa | Ndaragwa |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 672060 | [14 empty] | YES
EDUCATION | 1895 | MUTURIO ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 761735 |  |  | Complete | [11 empty] | YES
EDUCATION | 1896 | KAHUHO ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Murungaru |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 927457 | [14 empty] | YES
EDUCATION | 1897 | MWIHOTI ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 788250 | [14 empty] | YES
EDUCATION | 1898 | NJOGUINI | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1899 | KANYUGI TOILET | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul15 | Jun16 |  | 400000 | 400000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1900 | BAHATI ECDE RENOVATION | renovation of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Engineer |  | Human resource | Jul15 | Jun16 |  | 221345 | 221345 |  | CGN | N/A | N/A | N/A |  |  | 221345 | [14 empty] | YES
EDUCATION | 1901 | Larrikin ECD | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1902 | Muti ECD | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1903 | Kawabata | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Murungaru |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1904 | Construction of P.N ECDE | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1905 | Maturation ECD | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Engineer |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1906 | Satsuma ECD | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Njabini |  | Human resource | Jul15 | Jun16 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1907 | Nandarasi | construction Phase 1 | To create a conducive learning environment | Construction was done | 3110299 | Kipipiri | Geta |  | Productive | Jul15 | Jun16 |  | 1000000 |  |  | CGN | N/A | N/A | N/A |  |  | 1996442 | [14 empty] | YES
EDUCATION | 1908 | Kangui Hostel | Completion of drainage system and painting | To create a conducive learning environment | Painting and drainage system completed | 3110299 | Oljororok | Gathanji |  | Productive | Jul15 | Jun16 |  | 1000000 |  |  | CGN | N/A | N/A | N/A |  |  | 1990966 | [14 empty] | YES
EDUCATION | 1909 | Mbuyu workshop | Construction and completion | To create a conducive learning environment | Construction was done | 3110299 | Ndaragwa | Leshau Pondo |  | Productive | Jul15 | Jun16 |  | 1000000 |  |  | CGN | N/A | N/A | N/A |  |  | 1000000 | [14 empty] | YES
EDUCATION | 1910 | leshau youth | polytechnic hostels | To create a conducive learning environment | Constructed hostel | 3110299 | Ndaragwa | Leshau Pondo |  | Productive | Jul15 | Jun16 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1911 | Tollbooths YP | Tollbooths YP | To create a conducive learning environment | Tollboths installed | 3110299 |  |  |  | Productive | Jul15 | Jun16 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1912 | Sriracha youth polytechnic | Sriracha youth polytechnic | To create a conducive learning environment | Construction was done | 3110299 |  |  |  | Productive | Jul15 | Jun16 |  |  | 100000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1913 | Trade shows and exhibitions | Trade shows and exhibitions | Preservation of our cultural heritage | Exhibitions was successful | 2211399 |  |  |  | Productive | Jul15 | Jun16 |  | 300000 | 300000 |  | CGN | N/A | N/A | N/A |  |  | 300000
EDUCATION | 1914 | cultural festivals | cultural festivals | Preservation of our cultural heritage | Cultural festivals were successful | 2211399 |  |  |  | Productive | Jul15 | Jun16 |  | 300000 | 300000 |  | CGN | N/A | N/A | N/A |  |  | 300000
EDUCATION | 1915 | National day celebrations | National day celebrations | Preservation of our cultural heritage | Celebrations were successful | 2211399 |  |  |  | Productive | Jul15 | Jun16 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000
EDUCATION | 1916 | County celebrations | National day celebrations | To foster national unity | Celebrations were successful | 2211399 | Countywide | County Wide |  | Productive | Jul15 | Jun16 |  | 460000 | 460000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1917 | HIV/AIDS awareness | People living with HIV&AIDS | Create awareness | Communities were sensitized on HIV | 2211399 | Countywide | County Wide |  | Productive | Jul15 | Jun16 |  | 3500000 | 3500000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1918 | Social support | Disability mainstreaming | To improve livelihood | Provided social support | 2211399 | Countywide | County Wide |  | Productive | Jul15 | Jun16 |  | 7676000 | 7676000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1919 | ECD Mihuti primary school-kaimbaga | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Kaimbaga Ward |  | Human resource | Jul16 | Jun17 |  | 700000 | 693000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1920 | Kanyugi ECDE Toilet | Construction of toilet | To create a conducive learning environment | Constructed classroom | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  |  | 396000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1921 | Barainya ECDE class-nyakio | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul16 | Jun17 |  | 700000 | 693000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1922 | Haraka e ECDE class-nyakio | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul16 | Jun17 |  | 700000 | 693000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1923 | Kihunguru ECDE class-nyakio | construction of classroom | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul16 | Jun17 |  | 700000 | 693000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1924 | Rehabilitation of Munyeki ECD class | renovation of classroom | To create a conducive learning environment | Renovation was done | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  |  | 300000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1925 | Kianjata ECDE plus Toilet & ACC ECDE Renov | Renovation of toilet | To create a conducive learning environment | Renovation was done | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  |  | 1980000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1926 | 3 ECD classses Kipipri Ward(@600,000) | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul16 | Jun17 |  |  | 1800000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1927 | ECD completion kangondi -Githioro | Completion of construction | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul16 | Jun17 |  |  | 227000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1928 | Ngari-Karura ECDE-githioro | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro Ward |  | Human resource | Jul16 | Jun17 |  | 750000 | 742500 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1929 | Kariara ECDE | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  |  | 990000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1930 | Construction of Muthomi ECDE class | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  | 750000 | 742500 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1931 | Construction of Munanda ECDE class | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  | 750000 | 742500 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1932 | Equiping of ECDE's | Supply of equipment | To create a conducive learning environment | Constructed classroom | 3110299 | County wide | County Wide |  | Human resource | Jul16 | Jun17 |  | 8000000 | 4950000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1933 | mbogani ECD class completion | Completion of construction | To create a conducive learning environment | Constructed classroom | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  |  | 200000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1934 | Construction of buildings and others (ECDE Classrooms) | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  | 42000000 | 40000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1935 | Bahati ECDE Renovation | renovation of classroom | To create a conducive learning environment | Renovation was done | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  |  | 198000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1936 | Michinda ECD-githabai | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Githabai |  | Human resource | Jul16 | Jun17 |  | 800000 | 792000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1937 | Phase 2-githabai | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 | Kinangop | Githabai |  | Human resource | Jul16 | Jun17 |  | 800000 | 792000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1938 | Gikeno ECDE-githioro | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul16 | Jun17 |  | 750000 | 792500 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1939 | Mwangaza ECDE-githioro | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro Ward |  | Human resource | Jul16 | Jun17 |  | 750000 | 792500 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1940 | Thaba ECDE Renovation | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Mirangine |  | Human resource | Jul16 | Jun17 |  |  | 198000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1941 | Bethsaida ECDE | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 |  |  |  | Human resource | Jul16 | Jun17 |  |  | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1942 | ECD Classroom in Charagita | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 | Oljoroorok | Charagita |  | Human resource | Jul16 | Jun17 |  | 804528 | 796483 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1943 | Gatitu Nursery (Rurii) | Construction of classrooms | To create a conducive learning environment | Constructed classroom | 3110299 | Olkalou | Rurii |  | Human resource | Jul16 | Jun17 |  | 700000 | 693000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1944 | Infrastructure and Civil Works for hostels | costruction Phase 1 | To create a conducive learning environment | Construction was done | 3110299 | Kipipiri | Geta |  | Productive | Jul16 | Jun17 |  | 12000000 | 0 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1945 | Ol Bolossat Youth Polytechnic | Completion of drainage system and painting | To create a conducive learning environment | Painting and drainage system completed | 3110299 | Oljororok | Gathanji |  | Productive | Jul16 | Jun17 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1946 | Polythecnic-magumu | Construction and completion | To create a conducive learning environment | Construction was completed | 3110299 | Ndaragwa | Leshau Pondo |  | Productive | Jul16 | Jun17 |  | 1000000 | 0 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1947 | Infrastructure and Civil Works for twin workshop | Polythecnic-magumu | To create a conducive learning environment | Construction was completed | 3110299 | Kinangop | Magumu |  | Productive | Jul16 | Jun17 |  | 13000000 | 0 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1948 | Completion works- Mbuyu Youth Polytechnic | Completion work | To create a conducive learning environment | Construction was completed | 3110299 | Ndaragwa | Leshau Pondo |  | Productive | Jul16 | Jun17 |  | 0 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 1949 | National day celebrations | Celebration of national holidays | Preservation of our cultural heritage | Celebrations were successful | 2211399 | Countywide | County Wide |  | Productive | Jul16 | Jun17 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1950 | Social support | Blankets for the Aged(KARAU) | To improve livelihood | Provided social support | 2211399 | Olkalou | Karau |  | Productive | Jul16 | Jun17 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1951 | Social support | Purchase of vilage group tents | To improve livelihood | Provided social support | 2211399 | Countywide | County Wide |  | Productive | Jul16 | Jun17 |  | - | 1500000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1952 | Social support | kagoni & matomi groups tents@shs 150,000 githioro | To improve livelihood | Provided social support | 2211399 | Kipipiri | Githioro |  | Productive | Jul16 | Jun17 |  | 300000 | 300000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1953 | Social support | Community tents(rurii) | To improve livelihood | Provided social support | 2211399 | Olkalou | Rurii |  | Productive | Jul16 | Jun17 |  | 3000000 | 3000000 |  | CGN | N/A | N/A | N/A |  |  |  | 1499540
EDUCATION | 1954 | Social support | Construction of buildings and others (social hall) | To promote community engagement. | Provided social support | 2211399 | Countywide | County Wide |  | Productive | Jul16 | Jun17 |  | 9000000 | - |  | CGN | N/A | N/A | N/A
EDUCATION | 1955 | Social support | TENTS (KES 0.42 M) INCUBATORS(shs 0.4m) AND PRESSURE MACHINE (shs 0.15) -Kiriita | To improve livelihood | Tents were delivered | 2211399 | Olkalou | Kiriita |  | Productive | Jul16 | Jun17 |  | 970000 | 970000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1956 | Social support | Tents North Kinangop; Excell and Kinangop S.H.G | To improve livelihood | Tents were delivered | 2211399 | Kinangop | N. Kinangop |  | Productive | Jul16 | Jun17 |  |  | 100000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1957 | Social support | TENTS-CHARAGITA | To improve livelihood | Tents were delivered | 2211399 | Oljoroorok | Charagita |  | Productive | Jul16 | Jun17 |  | 1900000 | 1900000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1958 | Social support | Community tents(women Nyakio) | To improve livelihood | Tents were delivered | 2211399 | Kinangop | Nyakio |  | Productive | Jul16 | Jun17 |  | 700000 | 700000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1959 | Social support | Car wash machine(youth Nyakio) | To improve livelihood | Machine delivered | 2211399 | Kinangop | Nyakio |  | Productive | Jul16 | Jun17 |  | 300000 | 300000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1960 | Social support | Boda boda licences-githabai | To improve livelihood | Lisences issued | 2211399 | Kinangop | Githabai |  | Productive | Jul16 | Jun17 |  | 240000 | 240000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1961 | Social support | Chairs-mirangine | To improve livelihood | Chairs were isued | 2211399 | Olkalou | Mirangine |  | Productive | Jul16 | Jun17 |  | 750000 | 750000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1962 | Social support | Provision for welfare groups-engineer | To improve livelihood | Provided social support | 2211399 | Kinangop | Engineer |  | Productive | Jul16 | Jun17 |  | 2040000 | 0 |  | CGN | N/A | N/A | N/A
EDUCATION | 1963 | Social support | 8 Car Wash machines-magumu | To improve livelihood | Machines delivered | 2211399 | Kinangop | Magumu |  | Productive | Jul16 | Jun17 |  | 200000 | 200000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1964 | Social support | 5 generators-magumu | To improve livelihood | Machines delivered | 2211399 | Kinangop | Magumu |  | Productive | Jul16 | Jun17 |  | 100000 | 100000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1965 | Social support | Driving school-weru | To improve livelihood | constructed institution | 2211399 | Oljoroorok | Weru |  | Productive | Jul16 | Jun17 |  | 300000 | 300000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1966 | Social support | Group tents -weru | To improve livelihood | Tents were delivered | 2211399 | Oljoroorok | Weru |  | Productive | Jul16 | Jun17 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1967 | Social support | Car wash-weru | To improve livelihood | Machines delivered | 2211399 | Oljoroorok | Weru |  | Productive | Jul16 | Jun17 |  | 100000 | 100000 |  | CGN | N/A | N/A | N/A
EDUCATION | 1968 | Construction of matindiri ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljororok | Charagita |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999627 |  |  | Complete | [11 empty] | YES
EDUCATION | 1969 | Construction of ruiru ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljororok | Charagita |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999864 |  |  | Complete | [11 empty] | YES
EDUCATION | 1970 | Construction of engineer centre ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Engineer |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999852 | [14 empty] | YES
EDUCATION | 1971 | Construction of mwenja ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljororok | Gathanji |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 499870 |  |  | Complete | [11 empty] | YES
EDUCATION | 1972 | Construction of tulaga ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Gathara |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 998764 |  |  | Complete | [11 empty] | YES
EDUCATION | 1973 | Construction of kitiri ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Gathara |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999994 |  |  | Complete | [11 empty] | YES
EDUCATION | 1974 | Construction of riverside ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljororok | Gatimu |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 499967 |  |  | Complete | [11 empty] | YES
EDUCATION | 1975 | Construction of kianjata ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljororok | Gatimu |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 | [14 empty] | YES
EDUCATION | 1976 | Construction of mihato ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Geta |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999955 |  |  | Complete | [11 empty] | YES
EDUCATION | 1977 | Construction of kwa githima ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 998642 |  |  | Complete | [11 empty] | YES
EDUCATION | 1978 | Construction of ririshwa ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 500000 | [14 empty] | YES
EDUCATION | 1979 | Construction of hospital ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 998893 |  |  | Complete | [11 empty] | YES
EDUCATION | 1980 | Construction of captain ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 499982 |  |  | Complete | [11 empty] | YES
EDUCATION | 1981 | Construction of kahigo ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999758 |  |  | Complete | [11 empty] | YES
EDUCATION | 1982 | Construction of munyeki ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 997248 |  |  | Complete | [11 empty] | YES
EDUCATION | 1983 | Construction of kimaru ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999816 |  |  | Complete | [11 empty] | YES
EDUCATION | 1984 | Construction of kiriko ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999346 |  |  | Complete | [11 empty] | YES
EDUCATION | 1985 | Construction of kiandege ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999956 |  |  | Complete | [11 empty] | YES
EDUCATION | 1986 | Construction of kagondo ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999956 |  |  | Complete | [11 empty] | YES
EDUCATION | 1987 | Construction of muchorui ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999730 |  |  | Complete | [11 empty] | YES
EDUCATION | 1988 | Construction of mutonyora ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 997384 |  |  | Complete | [11 empty] | YES
EDUCATION | 1989 | Construction of githima primary ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Milangine |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999514 |  |  | Complete | [11 empty] | YES
EDUCATION | 1990 | Construction of kamuyu ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Milangine |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999980 |  |  | Complete | [11 empty] | YES
EDUCATION | 1991 | Construction of murichu primary ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Ndaragwa Central |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999694 |  |  | Complete | [11 empty] | YES
EDUCATION | 1992 | Construction of mailu-ikumi ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Ndaragwa Central |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999862 |  |  | Complete | [11 empty] | YES
EDUCATION | 1993 | Construction of korobise ecde classroon | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Njabini/Kiburu |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999974 |  |  | Complete | [11 empty] | YES
EDUCATION | 1994 | Construction of bara inya ecde clasroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999870 |  |  | Complete | [11 empty] | YES
EDUCATION | 1995 | Construction of kihunguru ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999885 |  |  | Complete | [11 empty] | YES
EDUCATION | 1996 | Construction of siraanga ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Rurii |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999943 |  |  | Complete | [11 empty] | YES
EDUCATION | 1997 | Construction of magomano ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 998458 |  |  | Complete | [11 empty] | YES
EDUCATION | 1998 | Construction of chakareli ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljororok | Weru |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999201 |  |  | Complete | [11 empty] | YES
EDUCATION | 1999 | Construction of uiguano ecde classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljororok | Weru |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 500000 | [14 empty] | YES
EDUCATION | 2000 | Construction of uiguano toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Oljororok | Weru |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599731 |  |  | Complete | [11 empty] | YES
EDUCATION | 2001 | Construction of ngorika toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 597335 |  |  | Complete | [11 empty] | YES
EDUCATION | 2002 | Construction of gaturumbari toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 596452 |  |  | Complete | [11 empty] | YES
EDUCATION | 2003 | Construction of kanyua ecde toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 597464 |  |  | Complete | [11 empty] | YES
EDUCATION | 2004 | Constructio of muchorui ecde toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Magumu |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 574648 |  |  | Complete | [11 empty] | YES
EDUCATION | 2005 | Construction of mutonyora ecde toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Magumu |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 586386 |  |  | Complete | [11 empty] | YES
EDUCATION | 2006 | Construction of bara inya ecde toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Nyakio |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 598342 |  |  | Complete | [11 empty] | YES
EDUCATION | 2007 | Construction of korobise ecde toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Kinangop | Njabini/Kiburu |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 588714 |  |  | Complete | [11 empty] | YES
EDUCATION | 2008 | Construction of kamuyu ecde toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Olkalou | Milangine |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 568182 |  |  | Complete | [11 empty] | YES
EDUCATION | 2009 | ruiru ecde | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Oljororok | Charagita |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 572958 |  |  | Complete | [11 empty] | YES
EDUCATION | 2010 | Construction of munyeki ecde toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | constructed 3 door phased Toilet | 3110299 | Olkalou | Karau |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 586574 |  |  | Complete | [11 empty] | YES
EDUCATION | 2011 | Completion of Kangui hostel(ongoing) | Construction of hostels | To increase student accommodation capacity. | Constructed hostel | 3110299 | Oljororok | Weru |  | Human resource | Jul17 | Jun18 |  | 1000000 | 2500000 |  | Youth development grant | [5 empty] | 1990000 | [14 empty] | YES
EDUCATION | 2012 | Milangine Boys Hostel | Construction of hostels | To increase student accommodation capacity. | Constructed hostel | 3110299 |  |  |  | Human resource | Jul17 | Jun18 |  | 3760890 | 4500000 |  | Youth development grant | [20 empty] | YES
EDUCATION | 2013 | Kinangop YP - Hostel Boys | Construction of hostels | To increase student accommodation capacity. | Constructed hostel | 3110299 |  |  |  | Human resource | Jul17 | Jun18 |  | 3000000 | 5000000 |  | Youth development grant | [5 empty] | - | [14 empty] | YES
EDUCATION | 2014 | Completion of Olkalou YP (Ongoing) | Completion of construction | To create a condusive learning environment | Constructed hostel | 3110299 |  |  |  | Human resource | Jul17 | Jun18 |  | 2500000 | 2500000 |  | Youth development grant | [5 empty] | 1900000 | [14 empty] | YES
EDUCATION | 2015 | Construction of Kangui Admin block and gate | Administration block and gate | To create a condusive learning environment | Administration block constructed | 3110299 | Oljororok | Weru |  | Human resource | Jul17 | Jun18 |  | 2000000 | 2000000 |  | Youth development grant | [5 empty] | - | 1316100 | [13 empty] | YES
EDUCATION | 2016 | Renovation of Karagoini YP(ongoing) | Renovation | To create a condusive learning environment | Renovation was done | 3110299 |  |  |  | Human resource | Jul17 | Jun18 |  | 1500000 | 1300000 |  | Youth development grant | [20 empty] | YES
EDUCATION | 2017 | Abolution block kaheho TP Toilet shamata | Ablution block | Provide access to safe and hygienic sanitation facilities | Constructed ablution block | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul17 | Jun18 |  | 600000 | 595000 |  | Youth development grant | [5 empty] | 386750 | [14 empty] | YES
EDUCATION | 2018 | Renovation of Leshau | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul17 | Jun18 |  | 1500000 | 1500000 |  | Youth development grant | [5 empty] | - | [14 empty] | YES
EDUCATION | 2019 | Construction of Magumu YP hall | Construction of hall | To create a condusive learning environment | Constructed hall | 3110299 |  |  |  | Human resource | Jul17 | Jun18 |  | 1000000 | 1000000 |  | Youth development grant | [20 empty] | YES
EDUCATION | 2020 | Kianjata Youth Polytechnic | Construction of VTC | To create a condusive learning environment | Center was constructed | 3110299 | Oljororok | Gatimu |  | Human resource | Jul17 | Jun18 |  | 2000000 | - |  | Youth development grant | [20 empty] | YES
EDUCATION | 2021 | Nandarasi YP hall(ongoing) | Construction of hall | To create a condusive learning environment | Constructed hall | 3110299 | Kinangop | North Kinangop |  | Human resource | Jul17 | Jun18 |  | 1500000 | 3000000 |  | Youth development grant | [5 empty] | - | [14 empty] | YES
EDUCATION | 2022 | Completion of Miharati hostel(ongoing) | Construction of hostels | To increase student accommodation capacity. | Constructed hostel | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul17 | Jun18 |  | 3000000 | 2500000 |  | Youth development grant | [5 empty] | - | [14 empty] | YES
EDUCATION | 2023 | Completion of Mbuyu twin workshop(ongoing) | Construction of twin workshop | To create a condusive learning environment | Constructed twin Workshop | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul17 | Jun18 |  | 2500000 | 2000000 |  | Youth development grant | [5 empty] | 950000 | [14 empty] | YES
EDUCATION | 2024 | Ngorika Yp Boarding Facility | Construction of hostels | To increase student accommodation capacity. | Constructed hostel | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul17 | Jun18 |  | 2000000 | 2000000 |  | Youth development grant | [5 empty] | - | [14 empty] | YES
EDUCATION | 2025 | Rurii Yp Aministration Block & a Gate | Administration block and gate | To create a condusive learning environment | Administration block and gate were constructed | 3110299 | Olkalou | Rurii |  | Human resource | Jul17 | Jun18 |  |  | 2000000 |  | Youth development grant | [5 empty] | - | [14 empty] | YES
EDUCATION | 2026 | murungaru youth poly kes 1,500,000 | Fence and Gate | To enhance security | Fence and gate were installed | 3110299 | Kinangop | Murungaru |  | Human resource | Jul17 | Jun18 |  |  | 1500000 |  | Youth development grant | [5 empty] | 1500000 | [14 empty] | YES
EDUCATION | 2027 | Olkalou YP | motor vehicle garage | To create a condusive learning environment | Garag was constructed | 3110299 | Olkalou | Karau |  | Human resource | Jul17 | Jun18 |  | 2000000 | 2000000 |  | Youth development grant | [20 empty] | YES
EDUCATION | 2028 | Purchase of Computers, Printers and other IT Equipment for youth Polytechnics | Supply of equipment | To improve ICT access for trainees. | Equipment were delivered | 3110299 |  |  |  | Human resource | Jul17 | Jun18 |  | 2000000 | 2000000 |  | Youth development grant
EDUCATION | 2029 | Talent search promotion | Enhance social cohesion | Preservation of our cultural heritage | Search was successful | 2211399 | Countywide | County Wide |  | Human resource | Jul17 | Jun18 |  | 200000 | 200000 |  | Youth development grant | [8 empty] | Complete
EDUCATION | 2030 | Sub-County cultural festivals | Enhance social cohesion | Preservation of our cultural heritage | Celebrations were successful | 2211399 | Countywide | County Wide |  | Human resource | Jul17 | Jun18 |  | 680000 | 680000 |  | Youth development grant | [8 empty] | Complete
EDUCATION | 2031 | Social Support | HIV & aids social skills development services | To promote HIV & AIDS awareness and prevention. | Provided social support | 2210805 | Countywide | County Wide |  | Human resource | Jul17 | Jun18 |  | 600000 | 600000 |  | Youth development grant | [8 empty] | Complete
EDUCATION | 2032 | Kimbo Primary ECDE& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Githioro Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 1598062.4 |  |  | Complete | [11 empty] | YES
EDUCATION | 2033 | Kwa Joshua ECDE &Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Githioro Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 753295 |  |  | Complete | [11 empty] | YES
EDUCATION | 2034 | Kamagoko ECDE-Geta | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Geta Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 912065 |  |  | Complete | [11 empty] | YES
EDUCATION | 2035 | MarimuECDE toilet-Geta | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Geta Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599989 |  |  | Complete | [11 empty] | YES
EDUCATION | 2036 | KangogoECDE& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Geta Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2037 | Mahinga ECDE& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Kipipiri Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2038 | GatondoGitei ECDE& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Wanjohi Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2039 | Elite Mubao ECDE &Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Wanjohi Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2040 | Haraka-Mukiri ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Nyakio Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 935900 | [14 empty] | YES
EDUCATION | 2041 | RwanyamboEcde&Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Nyakio Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2042 | Muchurui Primary ECDE ( | Installation of water tank and gutters | To enhance water harvesting and storage | Increased enrollment | 3110299 | Kinangop | Nyakio Ward |  | Human resource | Jul18 | Jun19 |  | 50000 | 50000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2043 | Mutonyora B ECDE TOILET | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Nyakio Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2044 | Rugegechi Ecde toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Nyakio Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2045 | Mberithi ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Engineer Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2046 | Kagutu ECDE Toilets -Engineer | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Engineer Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 1599524 |  |  | Complete | [11 empty] | YES
EDUCATION | 2047 | Mikaro primary ECDE& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Murungaru Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 1159362 |  |  | Complete | [11 empty] | YES
EDUCATION | 2048 | Mugumoni primary ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Murungaru Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2049 | NdunyuNyeruecde toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 |  |  |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2050 | Kianguyo ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Gathara Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2051 | Kiahuho ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Gathara Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2052 | Njabini primary ECDE& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Njabini Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2053 | Kioneki ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Njabini Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2054 | Ndothua ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Githabai Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2055 | Heni ecde toilet Githabai | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Githabai Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2056 | Makereka primary school ECDE& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Central Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2057 | Wangui primary school ECDE& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Central Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2058 | Karuri ECDE/Kiambogo ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Shamata Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2059 | Pesi ECDE |  | To create a condusive learning environment | Increased enrollment | 3110299 | Ndaragwa | Shamata Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | 1000000 | [13 empty] | YES
EDUCATION | 2060 | Simbara ecde (renovation and kitchen) | Renovation | To create a condusive learning environment | Increased enrollment | 3110299 | Ndaragwa | Shamata Ward |  | Human resource | Jul18 | Jun19 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2061 | Mienyere ECDE& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Kiriita Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | 1499175.3 | [13 empty] | YES
EDUCATION | 2062 | Githae ECDE Repair& Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Kiriita Ward |  | Human resource | Jul18 | Jun19 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2063 | Nyakinyua primary ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 572704 |  |  | Complete | [11 empty] | YES
EDUCATION | 2064 | Karai(Gwa Kungu) ECDE Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 302114 |  |  | Complete | [11 empty] | YES
EDUCATION | 2065 | Ndogino ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 584234 |  |  | Complete | [11 empty] | YES
EDUCATION | 2066 | Gichungu ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kaimbaga Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2067 | MumbiEcde | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kaimbaga Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2068 | Blue city toilet ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kaimbaga Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2069 | Rumathi toilet Ecde | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kaimbaga Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2070 | kagaa primary ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Karau Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2071 | St joseph ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Karau Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2072 | Gachwe ECDE Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Karau Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2073 | Wangatabuthi ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Rurii Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 602098 |  |  | Complete | [11 empty] | YES
EDUCATION | 2074 | Kidawa ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Rurii Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2075 | Matura ECDE Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Rurii Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2076 | Kidawa ECDE Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Rurii Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2077 | Micharagepri ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Rurii Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2078 | Makara ECDE toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Mirangine Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599969 |  |  | Complete | [11 empty] | YES
EDUCATION | 2079 | Matundapri ECDE &Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Mirangine Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2080 | Gathimai ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kanjuiri Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 817718 |  |  | Complete | [11 empty] | YES
EDUCATION | 2081 | Kihoto ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kanjuiri Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 1394180 |  |  | Complete | [11 empty] | YES
EDUCATION | 2082 | Nyairoko ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Charagita Ward |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 279789 |  |  | Complete | [11 empty] | YES
EDUCATION | 2083 | Renovation Works -Kibra,Oleimutia&Kiriko ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Charagita Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2084 | Ngatho ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Gathanji |  | Human resource | Jul18 | Jun19 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 1247990 |  |  | Complete | [11 empty] | YES
EDUCATION | 2085 | Kiheo ECDE toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Gathanji |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2086 | Michinda Boiman ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Gathanji |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 896150 |  |  | Complete | [11 empty] | YES
EDUCATION | 2087 | Kangui ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Weru Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2088 | Karandi ECDE & Toilet | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Weru Ward |  | Human resource | Jul18 | Jun19 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2089 | Kanguo ECDE | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Gatimu Ward |  | Human resource | Jul18 | Jun19 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2090 | Equipping yp(workshop equipments) | Supply of equipment | To create a condusive learning environment | Equipment were delivered | 3110299 | Countywide | County Wide |  | Human resource | Jul18 | Jun19 |  | 6360064 | - |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2091 | Ol'kalou YP Administration Block | Administration block | To create a condusive learning environment | Administration block constructed | 3110299 | Olkalou | Kaimbaga Ward |  | Human resource | Jul18 | Jun19 |  | 3000000 | 1500000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2092 | NADARASI youth poly | Construction of hostels | To increase student accommodation capacity. | Constructed hostel | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul18 | Jun19 |  | 2499100 | 2499100 |  | CGN | N/A | N/A | N/A |  |  | 2399982 | 439193 |  | Complete | [11 empty] | YES
EDUCATION | 2093 | YP Admnistration Blocks-Leshau YP | Administration block | To create a condusive learning environment | Administration block constructed | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul18 | Jun19 |  | 2000000 | 1000000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2094 | YP Hostels-Mirangine YP | Construction of hostels | To increase student accommodation capacity. | Constructed hostel | 3110299 | Olkalou | Mirangine Ward |  | Human resource | Jul18 | Jun19 |  | 4500000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2095 | YP Hostels-Kinangop YP | Construction of hostels | To increase student accommodation capacity. | Constructed hostel | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul18 | Jun19 |  | 4500000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2096 | YP Hostels-Miharati YP | Construction of hostels | To increase student accommodation capacity. | Constructed hostel | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul18 | Jun19 |  | 4500000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2097 | Construction of YP sanitation facilities | Construction of toilets | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 |  |  |  | Human resource | Jul18 | Jun19 |  | 3200000 | - |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2098 | Milangine Boys Hostel | Construction of boys hostels | To increase student accommodation capacity. | Constructed Girls Hostel | 3110299 | Olkalou | Mirangine Ward |  | Human resource | Jul18 | Jun19 |  |  | 4500000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2099 | Kinangop YP - Hostel Boys | Construction of boys hostels | To increase student accommodation capacity. | Constructed Girls Hostel | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul18 | Jun19 |  |  | 4500000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2100 | Completion of Olkalou YP (Ongoing) | Completion of construction | To create a condusive learning environment | Construction was completed | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul18 | Jun19 |  |  | 450000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2101 | Construction of Kangui Admin block and gate | Administration block | To create a condusive learning environment | Administration block constructed | 3110299 | Oljororok | Weru |  | Human resource | Jul18 | Jun19 |  |  | 1995900 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2102 | Abolution block kaheho TP Toilet shamata | Ablution block | To create a condusive learning environment | Constructed ablution block | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul18 | Jun19 |  |  | 220000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2103 | Nandarasi YP hall(ongoing) | Construction of hall | To create a condusive learning environment | Constructed hall | 3110299 | Kinangop | N.Kinangop |  | Human resource | Jul18 | Jun19 |  |  | 2999950 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2104 | Completion of Miharati hostel(ongoing) | Construction of hostels | To create a condusive learning environment | Constructed hostel | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul18 | Jun19 |  |  | 2500000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2105 | Completion of Mbuyu twin workshop(ongoing) | Completion of twin workshop | To create a condusive learning environment | Constructed twin Workshop | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul18 | Jun19 |  |  | 1588495 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2106 | Ngorika Yp Boarding Facility | Construction of hostels | To create a condusive learning environment | Constructed hostel | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul18 | Jun19 |  |  | 1998285 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2107 | Rurii Yp Aministration Block & a Gate | Administration block | To create a condusive learning environment | Administration block constructed | 3110299 | Olkalou | Rurii |  | Human resource | Jul18 | Jun19 |  |  | 1999850 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2108 | murungaru youth poly kes 1,500,000 |  | To create a condusive learning environment | Center was constructed | 3110299 | Kinangop | Murungaru |  | Human resource | Jul18 | Jun19 |  |  | 1500000 |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2109 | Sub-County cultural festivals | Sub-County cultural festivals | Preservation of our cultural heritage | Cultural festivals were successful | 2211399 | Countywide | County Wide |  | Productive | Jul18 | Jun19 |  | 899500 | 899500 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete
EDUCATION | 2110 | Refurbishment of Kinyahwe cultural centre | Refurbishment of Kinyahwe cultural centre | Preservation of our cultural heritage | Center was refurbished | 2211399 | Kinangop | Gathaara |  | Productive | Jul18 | Jun19 |  | 2240000 | 2240000 |  | CGN | N/A | N/A | N/A |  |  | -
EDUCATION | 2111 | HIV/AIDS awareness | HIV & aids social skills development services | To promote HIV & AIDS awareness and prevention | Communities were sensitized on HIV | 2110805 | Countywide | County Wide |  | Productive | Jul18 | Jun19 |  | 300000 | 300000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete
EDUCATION | 2112 | Social Support | Disabled Schools support | To promote inclusive and equitable education | Provided social support | 2110805 | Countywide | County Wide |  | Productive | Jul18 | Jun19 |  | 800000 | 800000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete
EDUCATION | 2113 | Social Support | Disability skills development services | To empower persons with disabilities through skills training | Provided social support | 2110805 | Countywide | County Wide |  | Productive | Jul18 | Jun19 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete
EDUCATION | 2114 | Social Support | Social welfare for the vulnerable and Freedom Fighters | To improve livelihood | Provided social support | 2110805 | Countywide | County Wide |  | Productive | Jul18 | Jun19 |  | - | 900000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete
EDUCATION | 2115 | Social Support | Social welfare programs | To improve livelihood | Provided social support | 2110805 | Countywide | County Wide |  | Productive | Jul18 | Jun19 |  | - | 2490000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete
EDUCATION | 2116 | Foods & Rations-Purchase and Delivery of milk (feeding programme) | Foods & Rations-Purchase and Delivery of milk (feeding programme) | To improve nutrition among learners. | Milk was delivered | 3110299 | Countywide | All Wards |  | Human resource | Jul19 | Jun20 |  | 10000000 | 10000000 |  | CGN | N/A | N/A | N/A |  |  | 9766630 |  |  | Complete | [11 empty] | YES
EDUCATION | 2117 |  |  |  |  | 3110299 |  |  |  | Human resource | Jul19 | Jun20 |  | 3000000 |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2118 | Furniture Fittings & Play Equipment and Rest Materials For 38 Ecd Classrooms For 2018/19 Fy-2 Per Ward @ Kshs. 220,000 (Excluding Kaimbaga, Kanjuiri, Weru, Charagita, Nyakio&Wanjohi) | Furniture Fittings & Play Equipment and Rest Materials For 38 Ecd Classrooms For 2018/19 Fy-2 Per Ward @ Kshs. 220,000 (Excluding Kaimbaga, Kanjuiri, Weru, Charagita, Nyakio&Wanjohi) | To create a conducive learning environment | Equipment were delivered | 3110299 | Countywide | All Wards |  | Human resource | Jul19 | Jun20 |  | 1925000 | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2199000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2119 | Furniture Fittings & Play Equipment and Rest Materials For 18 Needy Ecds (2013-19) @ 220,000 Per Ward-Excluding Kaimbaga, Kanjuiri, Nyakio, Gatimu, Weru, Charagita&Wanjohi | Furniture Fittings & Play Equipment and Rest Materials For 18 Needy Ecds (2013-19) @ 220,000 Per Ward-Excluding Kaimbaga, Kanjuiri, Nyakio, Gatimu, Weru, Charagita&Wanjohi | To create a conducive learning environment | Equipment were delivered | 3110299 | Countywide | All Wards |  | Human resource | Jul19 | Jun20 |  | 280000 | 1925000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2120 | Furniture Fittings & Play Equipment and Rest Materials for Huhirio B Ecde Class For 2019/20 Fy-Wanjohi | Furniture Fittings & Play Equipment and Rest Materials for Huhirio B Ecde Class For 2019/20 Fy-Wanjohi | To create a conducive learning environment | Equipment were delivered | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul19 | Jun20 |  | 1200000 | 280000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2121 | Construction of Ecd Centre Of Excellence at Kianjatai Ecd | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljororok | Gatimu |  | Human resource | Jul19 | Jun20 |  | 1200000 | 2620000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2122 | Construction of Kianjogu Ecd | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Geta |  | Human resource | Jul19 | Jun20 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2123 | Construction of Rumwe Ecd | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Geta |  | Human resource | Jul19 | Jun20 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2124 | Construction of Munyu-Ini Ecd | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul19 | Jun20 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2125 | Construction of Turasha Ecd | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul19 | Jun20 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2126 | Construction of Matumi Ecd | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul19 | Jun20 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2127 | Construction of Mukuru A ( Gatondo) Ecd | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul19 | Jun20 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2128 | Construction of Sujui Ecd | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljororok | Gathanji |  | Human resource | Jul19 | Jun20 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2129 | Construction of Equator Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Charagita |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1179261.6 |  |  | Complete | [11 empty] | YES
EDUCATION | 2130 | Construction of Ndarashaini Ecd and Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Murungaru |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1200000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2131 | Construction of Ndunyu-Njeru Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | North Kinangop |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1156335.8 | [14 empty] | YES
EDUCATION | 2132 | Construction of Kamunyaka Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2133 | Construction of Kambaa Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Gathaara |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2134 | Construction of Karuri Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Njabini |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1198000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2135 | Construction of Nyakio Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Githabai |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2136 | Completion/Renovation of Mbogani Ecd Class | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Githabai |  | Human resource | Jul19 | Jun20 |  | 600000 | 220000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2137 | Construction of Haraka Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Nyakio Ward |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2138 | Construction of Mutonyora Pry Ecd-Magumu | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Magumu |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2139 | Construction of Passenga Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Rurii |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2140 | Construction of Muiri Pry Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Karau |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2141 | Completion/Renovation of Thaba classroom | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Karau |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2142 | Construction of Nyaituga Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2143 | Renovation of Wiyumiririe Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul19 | Jun20 |  | 600000 | 280000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2144 | Construction of Ngari Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1077094.8 |  |  | Complete | [11 empty] | YES
EDUCATION | 2145 | Construction of Kwanjora Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2146 | Construction of Mithuri Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul19 | Jun20 |  | 600000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2147 | Construction of Ndururi Ecd | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Ndaragwa Central |  | Human resource | Jul19 | Jun20 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2148 | Construction of Wendani Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599800 |  |  | Complete | [11 empty] | YES
EDUCATION | 2149 | Construction of Wendo Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 390885 |  |  | Complete | [11 empty] | YES
EDUCATION | 2150 | Construction of Mukuru A (Gatondo) Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | 372954 | [13 empty] | YES
EDUCATION | 2151 | Construction of Kiamboga Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2152 | Construction of Mukuru B (Ndemi) Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2153 | Construction of Gikeno Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kipipiri | Githioro |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2154 | Construction of Kimathi Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Charagita |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2155 | Construction of Charagita Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Oljororok | Charagita |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2156 | Construction of Kahuho Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Murungaru |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | 597000 | [13 empty] | YES
EDUCATION | 2157 | Construction of Ndarashaini Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Murungaru |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599920 |  |  | Complete | [11 empty] | YES
EDUCATION | 2158 | Construction of Muhuti Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | North Kinangop |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2159 | Construction of Kiambariki Ecd Toilets | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | North Kinangop |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2160 | Construction of Manyatta Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2161 | Construction of Ciondo Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2162 | Construction of Nyakiambi Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Gathaara |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599840 |  |  | Complete | [11 empty] | YES
EDUCATION | 2163 | Construction of Kambaa Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Gathaara |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 426619 |  |  | Complete | [11 empty] | YES
EDUCATION | 2164 | Construction of Soil Community Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Njabini |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 1193344.6 |  |  | Complete | [11 empty] | YES
EDUCATION | 2165 | Construction of Karuang'i Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Njabini |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2166 | Construction Of Kio Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Githabai |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2167 | Construction Of Mbogani Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Githabai |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2168 | Construction Of Haraka Ecd Toilets | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Nyakio |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2169 | Construction Of Yaang’a Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Kinangop | Nyakio |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 202117.55 |  |  | Complete | [11 empty] | YES
EDUCATION | 2170 | Construction Of Githunguri Ecd Toilets | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Rurii |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2171 | Construction Of Gachwe Ecd Toilets-Karau | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Karau |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599940 |  |  | Complete | [11 empty] | YES
EDUCATION | 2172 | Construction Of Mirangine Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Mirangine |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2173 | Construction Of Nyaituga Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2174 | Construction Of Tumaini Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 616505 |  |  | Complete | [11 empty] | YES
EDUCATION | 2175 | Construction Of Rutara Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2176 | Construction Of Gakoe Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2177 | Construction Of Kwanjora Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Stalled | 66% | 66% | Contractor abandoned site |  |  |  | No |  |  |  |  | YES
EDUCATION | 2178 | Construction Of Ritaya Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599280 |  |  | Complete | [11 empty] | YES
EDUCATION | 2179 | Construction Of Kiandege Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 1034390 |  |  | Complete | [11 empty] | YES
EDUCATION | 2180 | Construction Of Huruma Ecd Toilet | construction of a 3 door phased toilet | Provide access to safe and hygienic sanitation facilities | Constructed Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul19 | Jun20 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Complete | [11 empty] | YES
EDUCATION | 2181 | Mirangine VTC | Construction of Yp Sanitation Facilities-Mirangine Yp Girls | To improve hygiene and sanitation | Sanitatio facilites were constructed | 3110299 | Olkalou | Milangine |  | Human resource | Jul19 | Jun20 |  |  | 1200000 | 1199900 | CGN | N/A | N/A | N/A |  |  | 1199900 |  |  | Complete | [11 empty] | YES
EDUCATION | 2182 | Kanyagia youth polytechnic | Renovation works at Kanyangia Polytechnic | To create a condusive learning environment | Renovation was done | 3110299 | Ndaragwa | Central |  | Human resource | Jul19 | Jun20 |  |  | 1200000 | - | CGN | N/A | N/A | N/A |  |  | - |  |  | Phased project-Ongoing | [11 empty] | YES
EDUCATION | 2183 | Ngano vtc | Renovation works at Ngano Youth Polytechnic | To create a condusive learning environment | Renovation was done | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul19 | Jun20 |  |  | 1500000 | - | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2184 | Social support | Community Multipurpose Centre-Olkalao | To facilitate community engagement | Provided social support | 2110805 | Olkalou | Kaimbaga Ward |  | Productive | Jul19 | Jun20 |  |  | 5000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Requisition/Awaiting BQ
EDUCATION | 2185 | Social support | Jiinue Self Help Group | To improve livelihood | Provided social support | 2110805 |  |  |  | Productive | Jul19 | Jun20 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Delivery of tents and catering items done and payment done
EDUCATION | 2186 | Social support | First world Self Help Group (Karau) | To improve livelihood | Provided social support | 2110805 | Olkalou | Karau |  | Productive | Jul19 | Jun20 |  |  | 200,000S |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2187 | Social support | Njogui-ini Self Help Group (Gathanji) | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Gathanji |  | Productive | Jul19 | Jun20 |  |  | 150000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2188 | Social support | Oasis Self Help Group (Rurii)-Milk pasturerizer | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii |  | Productive | Jul19 | Jun20 |  |  | 300000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2189 | Social support | Social service - tents and chairs to groups | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul19 | Jun20 |  |  | 2500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2190 | Social support | Social service - Blankets for the Elderly-Shamata | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul19 | Jun20 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2191 | Social support | Social service - tents and chairs to groups | To improve livelihood | Provided social support | 2110805 | Kipipiri | Geta |  | Productive | Jul19 | Jun20 |  |  | 750000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2192 | Social support | Social service - Blankets for the Elderly- | To improve livelihood | Provided social support | 2110805 | Kipipiri | Geta |  | Productive | Jul19 | Jun20 |  |  | 1250000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2193 | Social support | Social service - tents to groups-Charagita | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Charagita |  | Productive | Jul19 | Jun20 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2194 | Social support | Support to women groups - Charagita | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Charagita |  | Productive | Jul19 | Jun20 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2195 | Social support | Social service - tents and chairs to groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Kanjuiri Ward |  | Productive | Jul19 | Jun20 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2196 | Social support | Social service - tents and chairs to groups | To improve livelihood | Provided social support | 2110805 |  | Gathanji |  | Productive | Jul19 | Jun20 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2197 | Social support | Social service - tents and chairs to groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine |  | Productive | Jul19 | Jun20 |  |  | 1800000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2198 | Social support | Social service - tents and chairs (Karobise and King'ethere groups) - | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini Kiburu |  | Productive | Jul19 | Jun20 |  |  | 300000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2199 | Social support | Social service - tents and chairs to groups | To improve livelihood | Provided social support | 2110805 |  | Weru |  | Productive | Jul19 | Jun20 |  |  | 1480000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2200 | Social support | Kiriita Youth Empowerment Centre-Equipping | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Kiriita Ward |  | Productive | Jul19 | Jun20 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Studio equipment supplied and installed
EDUCATION | 2201 | Social support | Supply of materials for construction of Githuya Social Hall | To facilitate community engagement | Provided social support | 2110805 |  |  |  | Productive | Jul19 | Jun20 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Award
EDUCATION | 2202 | Social support | Supply of materials for construction of Gatondo Balam Social Hall | To improve livelihood | Provided social support | 2110805 |  |  |  | Productive | Jul19 | Jun20 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Award
EDUCATION | 2203 | Social support | Kiriita Youth Empowerment Centre-Renovation | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Kiriita Ward |  | Productive | Jul19 | Jun20 |  |  | 850000 |  | CGN | N/A | N/A | N/A |  |  | 849492 |  |  | Complete | 100%
EDUCATION | 2204 | Social support | Community Multipurpose Centre-Olkalao-Fencing | To enhance security | Provided social support | 2110805 | Olkalou | Kambaga |  | Productive | Jul19 | Jun20 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Awaiting BQ
EDUCATION | 2205 | Social support | Community Multipurpose Centre-Olkalao-Architectural Designs | To improve livelihood | Provided social support | 2110805 | Olkalou | Kaimbaga |  | Productive | Jul19 | Jun20 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Awaiting BQ
EDUCATION | 2206 | Purchase of Teaching/Learning materials for ECD(Teaching Aids & Charts)-All Wards | Supply of equipment | creating condusive learning environment | Equipment were delivered | 3110299 | All wards | All Wards |  | Human resource | Jul20 | Jun21 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2207 | Furniture fittings & Play Equipment and Rest materials for ECDE | Supply of equipment | creating condusive learning environment | Equipment were delivered | 3110299 | All wards | All Wards |  | Human resource | Jul20 | Jun21 |  | 6000000 | 6000000 |  | CGN | N/A | N/A | N/A |  |  | 6000000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2208 | ECDE Facemasks | Supply of equipment | creating condusive learning environment | Equipment were delivered | 3110299 | All wards | All Wards |  | Human resource | Jul20 | Jun21 |  | 700000 | 700000 |  | CGN | N/A | N/A | N/A |  |  | 700000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2209 | Rehabilitation of 1No. ECDE Classroom- Bongo Pry School | renovation of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul20 | Jun21 |  | 400000 | 400000 |  | CGN | N/A | N/A | N/A |  |  | 299899 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2210 | Mutonyora Pry ECD | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1200000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2211 | Muchorui | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1197109 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2212 | Githinji Pry ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2213 | Kiandege ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Njabini |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 762240 |  |  | Complete | [11 empty] | YES
EDUCATION | 2214 | Lee ECDE Classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Gathaara |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2215 | Nguruka ECDE Classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Gathaara |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1196436 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2216 | Wendani ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Engineer |  | Human resource | Jul20 | Jun21 |  | 1200000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2217 | Completion of Kahuria ECDE classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Murungaru |  | Human resource | Jul20 | Jun21 |  | 500000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 499987 |  |  | Complete-not paid | [11 empty] | YES
EDUCATION | 2218 | Hianyu ECDE Classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Murungaru |  | Human resource | Jul20 | Jun21 |  | 1200000 | 200000 |  | CGN | N/A | N/A | N/A |  |  | 1200000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2219 | Completion of Mwihoti ECDE Classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Murungaru |  | Human resource | Jul20 | Jun21 |  | 200000 | 200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2220 | Completion of Murungaru ECDE Classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Kinangop | Murungaru |  | Human resource | Jul20 | Jun21 |  | 200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2221 | Kariani ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | kipipiri | Geta |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 922425 |  |  | Complete | [11 empty] | YES
EDUCATION | 2222 | Marimu B ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | kipipiri | Geta |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 920000 | 279924 |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2223 | Githinji ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | kipipiri | Geta |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1193217 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2224 | Gichuna ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | kipipiri | Githioro |  | Human resource | Jul20 | Jun21 |  | 1400000 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2225 | Jura ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | kipipiri | Githioro |  | Human resource | Jul20 | Jun21 |  | 1400000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1399980 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2226 | Kahonge ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Olkalou | Rurii |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1192382 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2227 | Thaba ECDE Classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Olkalou | Karau |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1199680 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2228 | Ol'Kalou Disabled school special class | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Olkalou | Karau |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1800000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2229 | Mawingu, Ol'Kalou AC Primary and Migaa ECDE toilets | construction of toilets | Improve sanitation | Constructed Toilet | 3110299 | Olkalou | Karau |  | Human resource | Jul20 | Jun21 |  | 1800000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 598316 |  |  | Migaa toilet complete, others ongoing | [11 empty] | YES
EDUCATION | 2230 | Kanjau ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2231 | Harambee ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1199006 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2232 | Y- ECD Classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Oljoroorok | Gathanji |  | Human resource | Jul20 | Jun21 |  | 1400000 | 300000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2233 | Completion of Ngawa ECD Classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul20 | Jun21 |  | 300000 | 400000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2234 | Completion of Githima ECD Classroom | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul20 | Jun21 |  | 400000 | 800000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2235 | Renovation of Ndogino ECD Classroom (Windows, Doors, Plastering and roofing) | renovation of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul20 | Jun21 |  | 800000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2236 | Renovation of Kwa Njora AIC ECD Classroom (Windows, Doors, Plastering and roofing) | renovation of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul20 | Jun21 |  | 600000 | 800000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2237 | Renovation of 2NO. ECDE Classrooms Kirera Centre | renovation of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul20 | Jun21 |  | 800000 | 300000 |  | CGN | N/A | N/A | N/A |  |  | - | 300000 |  | Complete | [11 empty] | YES
EDUCATION | 2238 | Tank-stand, Guttering and Fittinings for ECDEs |  | creating condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul20 | Jun21 |  | 300000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2239 | Ritaya ECDE | construction of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul20 | Jun21 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 863920 |  |  | Complete | [11 empty] | YES
EDUCATION | 2240 | ECD Classroom Renovations(Madaraka Ecd,Kamaina Ecd,Weru Ecd & Gatitu Ecd) | renovation of classroom | creating condusive learning environment | Constructed classroom | 3110299 | Oljoroorok | Weru |  | Human resource | Jul20 | Jun21 |  | 1200000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2241 | Bongo Pry ECDE Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Nyakio |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 299900 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2242 | Fourteen ECDE Toilets | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2243 | Muti-ini ECDE Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2244 | Wendani ECDE Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2245 | Lee ECD Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Gathaara |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2246 | Kia Nguyo ECD Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Gathaara |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 597719 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2247 | Construction of Wendani Ecd toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | kipipiri | Kipipiri |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2248 | Munyuini ECD TOILET | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | kipipiri | Kipipiri |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2249 | Magomano/Romba ECD Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | kipipiri | Wanjohi |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2250 | Gichigirira ECDE | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | kipipiri | Wanjohi |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599813 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2251 | Kiandege Primary ECDE Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Njabini |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2252 | Rurii ECDE toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Rurii |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2253 | Wagatabuthi ECD Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Rurii |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2254 | Kamukunji ECD Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Oljoroorok | Charagita |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2255 | Kagema ECD Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Oljoroorok | Charagita |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599940 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2256 | Michinda ECDE Toilet | construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul20 | Jun21 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2257 | Transfer of services | Current transfers to Youth Polytechnics | To create a condusive learning environment | Services were transfered | 3110299 | County wide | Countywide |  | Human resource | Jul20 | Jun21 |  |  | 37653046 |  | CGN | N/A | N/A | N/A |  |  | 30949894 |  |  | Complete | [11 empty] | YES
EDUCATION | 2258 | Kanyagia youth polytechnic | Equipping Youth Polytechnics (workshop equipment)-Kanyangia VTC-Ndaragwa Central Ward | To create a condusive learning environment | Equipment were delivered | 3110299 | Ndaragwa | Ndaragwa Central |  | Human resource | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2259 | 7 VTC centers | Equipping Youth Polytechnics (workshop equipment)-7 VTCs centres of excellence | To create a condusive learning environment | Equipment were delivered | 3110299 | Countywide | Countywide |  | Human resource | Jul20 | Jun21 |  |  | 3300000 |  | CGN | N/A | N/A | N/A |  |  | 3300000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2260 | Mirangine VTC | Equipping Youth Polytechnics (workshop equipment)-Mirangine VTC centres of excellence | To create a condusive learning environment | Equipment were delivered | 3110299 | Olkalou | Mirangine |  | Human resource | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2261 | Contracted Proffessional Services | Environmental Impact Assessment VTC Projects | To create a condusive learning environment | Assessment was done | 3110299 | Countywide | County Wide |  | Human resource | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2262 | Lereshwa vtc | Leleshwa VTC hostel -Kipipiri ward | To create a condusive learning environment | Constructed hostel | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul20 | Jun21 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Phased project-Ongoing | [11 empty] | YES
EDUCATION | 2263 | Olkalou vtc | Olkalou VTC Hostel-Kaimbaga ward | To create a condusive learning environment | Constructed hostel | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul20 | Jun21 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2953438 |  |  | Phased project-Ongoing | [11 empty] | YES
EDUCATION | 2264 | Miharati vtc | Twin workshop-Miharati-Kipipiri | To create a condusive learning environment | Constructed twin workshop | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul20 | Jun21 |  |  | 4000000 |  | CGN | N/A | N/A | N/A |  |  | 2934687 |  |  | Phased project-Ongoing | [11 empty] | YES
EDUCATION | 2265 | NADARASI youth poly | Nandarasi YP North Kinangop-Twin workshop | To create a condusive learning environment | Constructed twin workshop | 3110299 | Kinangop | North Kinangop |  | Human resource | Jul20 | Jun21 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 3000000 |  |  | Phased project-Ongoing. Not paid | [11 empty] | YES
EDUCATION | 2266 | Kanyagia youth polytechnic | Kanyagia YP- Ndaragwa Central-Workshop | To create a condusive learning environment | Constructed twin workshop | 3110299 | Ndaragwa | Ndaragwa Central |  | Human resource | Jul20 | Jun21 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1868472 |  |  | Phased project-Ongoing | [11 empty] | YES
EDUCATION | 2267 | Support to women and youth groups-Karau Ward | Support to women and youth groups-Karau Ward | To improve livelihood | Provided social support | 2211399 | Olkalou | Karau |  | Productive | Jul20 | Jun21 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete | 100%
EDUCATION | 2268 | Elderly Men and Women empowerment- Lower Murungaru- Supply of 6kg LPG Cylinders (Gas & burners) | Elderly Men and Women empowerment- Lower Murungaru- Supply of 6kg LPG Cylinders (Gas & burners) | To improve livelihood | Supported the elderly | 2211399 | Kinangop | Murungaru |  | Productive | Jul20 | Jun21 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 3000000 |  |  | Complete | 100%
EDUCATION | 2269 | Elderly Men and Women empowerment- Upper Murungaru - Supply of 6kg LPG Cylinders (Gas & burners) | Elderly Men and Women empowerment- Upper Murungaru - Supply of 6kg LPG Cylinders (Gas & burners) | To improve livelihood | Supported the elderly | 2211399 | Kinangop | Murungaru |  | Productive | Jul20 | Jun21 |  |  | 2500000 |  | CGN | N/A | N/A | N/A |  |  | 2500000 |  |  | Complete | 100%
EDUCATION | 2270 | Construction of Study Prayer, Recreational, Experiential/Retreat Centre - Kinyahwe | Construction of Study Prayer, Recreational, Experiential/Retreat Centre - Kinyahwe | Preservation of our cultural heritage | Facility was constructed | 2211399 | Kinangop | Gathaara |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2271 | Refurbishment of Kinyahwe Cultural Centre | Refurbishment of Kinyahwe Cultural Centre | Preservation of our cultural heritage |  | 2211399 | Kinangop | Gathaara |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 925600 |  |  | Complete | 100%
EDUCATION | 2272 | Social support | Support to Githabai boda boda self-help group | To improve livelihood | Provided social support | 2110805 | Kinangop | Githabai |  | Productive | Jul20 | Jun21 |  |  | 150000 |  | CGN | N/A | N/A | N/A |  |  | 150000 |  |  | Complete | 100%
EDUCATION | 2273 | Social support | Njabini - Support to Women Groups (Warurungana and Gatina Self Help Group) With Tents and Chairs | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini |  | Productive | Jul20 | Jun21 |  |  | 400000 |  | CGN | N/A | N/A | N/A |  |  | 400000 |  |  | Complete | 100%
EDUCATION | 2274 | Social support | Njabini - Tents and Chairs- Kiandege Self Help Group | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini |  | Productive | Jul20 | Jun21 |  |  | 150000 |  | CGN | N/A | N/A | N/A |  |  | 150000 |  |  | Complete | 100%
EDUCATION | 2275 | Social support | Support to boda boda groups- Nyakio | To improve livelihood | Provided social support | 2110805 | Kinangop | Nyakio |  | Productive | Jul20 | Jun21 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 2000000 |  |  | Complete | 100%
EDUCATION | 2276 | Social support | Support to boda boda groups- Mirangine | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine |  | Productive | Jul20 | Jun21 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 700000 |  |  | Complete | 100%
EDUCATION | 2277 | Social support | Ndaragwa Central- Support to welfare groups with tents | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Ndaragwa Central |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2278 | Social support | Support to boda boda groups (Umbrellas) Geta ward | To improve livelihood | Provided social support | 2110805 | Kipipiri | Geta |  | Productive | Jul20 | Jun21 |  |  | 400000 |  | CGN | N/A | N/A | N/A |  |  | 400000 |  |  | Complete | 100%
EDUCATION | 2279 | Social support | Tents and chairs groups Geta ward | To improve livelihood | Provided social support | 2110805 | Kipipiri | Geta |  | Productive | Jul20 | Jun21 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete | 100%
EDUCATION | 2280 | Social support | Mirangine Ward- Tents | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 | 1332000 |  | Complete | 100%
EDUCATION | 2281 | Social support | Support to boda boda groups- Shamata | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul20 | Jun21 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1500000 |  |  | Complete | 100%
EDUCATION | 2282 | Social support | Tents and Chairs for Shamata villages | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2283 | Social support | Support to women welfare groups-Geta | To improve livelihood | Provided social support | 2110805 | Kipipiri | Geta |  | Productive | Jul20 | Jun21 |  |  | 1800000 |  | CGN | N/A | N/A | N/A |  |  | 1800000 |  |  | Complete | 100%
EDUCATION | 2284 | Social support | Support to the elderly(blankets) N. Kinangop ward | To improve livelihood | Provided social support | 2110805 | Kinangop | North Kinangop |  | Productive | Jul20 | Jun21 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete | 100%
EDUCATION | 2285 | Social support | Support to the elderly(blankets) Mirangine ward | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine |  | Productive | Jul20 | Jun21 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1500000 |  |  | Complete | 100%
EDUCATION | 2286 | Social support | Support to the elderly(blankets) Shamata ward | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2287 | Social support | Support to the elderly(blankets) Shamata ward | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul20 | Jun21 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | 100%
EDUCATION | 2288 | Social support | Support to the elderly(blankets) Rurii ward | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2289 | Social support | Support to Oasis Self-help Group Rurii- Milk cooler and ATM | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii |  | Productive | Jul20 | Jun21 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 700000 |  |  | Complete | 100%
EDUCATION | 2290 | Social support | Support to the elderly(blankets) Charagita ward | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Charagita |  | Productive | Jul20 | Jun21 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete | 100%
EDUCATION | 2291 | Social support | Charagita- Support to women welfare groups | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Charagita |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2292 | Social support | Kanjuiri ward - Tents to welfare groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Kanjuiri |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2293 | Social support | Kanjuiri- Support to the elderly (blankets) | To improve livelihood | Provided social support | 2110805 | Olkalou | Kanjuiri |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2294 | Social support | Support to the elderly(blankets) Gathanji ward | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Gathanji |  | Productive | Jul20 | Jun21 |  |  | 1150000 |  | CGN | N/A | N/A | N/A |  |  | 1150000 |  |  | Complete | 100%
EDUCATION | 2295 | Social support | Tents and Chairs- Gathanji Ward | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Gathanji |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2296 | Social support | Support to boda boda operators- Murungaru | To improve livelihood | Provided social support | 2110805 | Kinangop | Murungaru |  | Productive | Jul20 | Jun21 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 3000000 |  |  | Complete | 100%
EDUCATION | 2297 | Social support | Women empowerment- Rurii | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2298 | Social support | Women empowerment- Shamata | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2299 | Social support | Tents and Chairs to welfare groups -Wanjohi ward | To improve livelihood | Provided social support | 2110805 | Kipipiri | Wanjohi |  | Productive | Jul20 | Jun21 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1500000 |  |  | Complete | 100%
EDUCATION | 2300 | Social support | Tents to welfare groups -Rurii ward | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii |  | Productive | Jul20 | Jun21 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2301 | Social support | Support to women welfare groups-Wanjohi ward | To improve livelihood | Provided social support | 2110805 | Kipipiri | Wanjohi |  | Productive | Jul20 | Jun21 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete | 100%
EDUCATION | 2302 | Social support | Leshau Pondo- Tents and Chairs to welfare groups (Mayu, Raicheri, Ex-reitief, Kieni, Ndivai, Mithuri, Kamukunji, Umoja Mbuyu, Kidipa, Gachengo, Nairobi Welfare, Ndogino, Mbuyu Kahuho, Wendani, Legetet and Kiandege Welfare) | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Productive | Jul20 | Jun21 |  |  | 2400000 |  | CGN | N/A | N/A | N/A |  |  | 2400000 |  |  | Complete | 100%
EDUCATION | 2303 | Social support | Leshau Pondo- Support to Women welfare Groups | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Productive | Jul20 | Jun21 |  |  | 450000 |  | CGN | N/A | N/A | N/A |  |  | 450000 |  |  | Complete | 100%
EDUCATION | 2304 | Social support | Leshau-Pondo Blessed Artists Public address systems and generator | To facilitate communication | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Productive | Jul20 | Jun21 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete | 100%
EDUCATION | 2305 | Social support | Assistive devices for PLWD | To improve livelihood | Provided social support | 2110805 | County wide | All Wards |  | Productive | Jul20 | Jun21 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1500000 |  |  | Complete | 100%
EDUCATION | 2306 | Social support | Social Assistance progammes | To improve livelihood | Provided social support | 2110805 | County wide | All Wards |  | Productive | Jul20 | Jun21 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 3000000 |  |  | Complete | 100%
EDUCATION | 2307 | Social support | Christmas day social assistance to the vulnerable | To suport the Vulnerable | Provided social support | 2110805 | County wide | All Wards |  | Productive | Jul20 | Jun21 |  |  | 4000000 |  | CGN | N/A | N/A | N/A |  |  | 4000000 |  |  | Complete | 100%
EDUCATION | 2308 | Social support | Fencing of Charagita Social Hall land | To enhance security | Provided social support | 2110805 | Oljoroorok | Charagita |  | Productive | Jul20 | Jun21 |  |  | 2500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | No t Complete
EDUCATION | 2309 | Social support | Construction of Mawingo Social Hall- Githioro | To facilitate community engagement | Provided social support | 2110805 | Kipipiri | Githioro |  | Productive | Jul20 | Jun21 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2310 | Social support | Construction of Kabati Social Hall-Kipipiri | To facilitate community engagement | Provided social support | 2110805 | Kipipiri | Kipipiri |  | Productive | Jul20 | Jun21 |  |  | 3500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2311 | Holy oak ECDE and Toilet construction | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Njabini Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1800950 |  |  | Complete | [11 empty] | YES
EDUCATION | 2312 | Muchibau Toilet construction | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Njabini Ward |  | Human resource | Jul21 | Jun22 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 1199444 |  |  | Complete | [11 empty] | YES
EDUCATION | 2313 | karuri ecd toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Njabini Ward |  | Human resource | Jul21 | Jun22 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2314 | Warurungana ECDE and toilet Construction | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Njabini Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 399990 |  |  | Stalled land issue | 20% | 20% | Land Issue | [8 empty] | YES
EDUCATION | 2315 | Grace ECDE classroom | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Gathaara Ward |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1259901 |  |  | Complete | [11 empty] | YES
EDUCATION | 2316 | Raitha ECDE classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Gathaara Ward |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1260711 |  |  | Complete | [11 empty] | YES
EDUCATION | 2317 | Kiahuho ECDE classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Gathaara Ward |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 976923 |  |  | Complete | [11 empty] | YES
EDUCATION | 2318 | Lee ECDE classroom and toilet | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Gathaara Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | - | [14 empty] | YES
EDUCATION | 2319 | Kimathi ECDE classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljoroorok | Charagita Ward |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 979870 |  |  | Complete | [11 empty] | YES
EDUCATION | 2320 | Munga ECDE classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Oljoroorok | Charagita Ward |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 979870 |  |  | Complete | [11 empty] | YES
EDUCATION | 2321 | Turasha ECDE classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro Ward |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2322 | Gikeno ECDE toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kipipiri | Githioro Ward |  | Human resource | Jul21 | Jun22 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2323 | Mumui ECDE toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kipipiri | Githioro Ward |  | Human resource | Jul21 | Jun22 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2324 | Kiambaa ECDE and Toilet consruction | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Murungaru Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1810812 |  |  | Complete | [11 empty] | YES
EDUCATION | 2325 | Kihumbu ECDE and Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Murungaru Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1800585 |  |  | Complete | [11 empty] | YES
EDUCATION | 2326 | Nyakio Ecd classroom and toilet | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Githabai Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1399965 |  |  | Complete | [11 empty] | YES
EDUCATION | 2327 | AC Olkalou ECDE class construction | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Karau Ward |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1358969 | 41031 |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2328 | New Nyairoko ECDE Class and toilet construction | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Karau Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1799489 |  |  | Complete | [11 empty] | YES
EDUCATION | 2329 | New Vatican Mukira ECDE class and toilet construction | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Karau Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 399887 |  |  | Stalled-Land issue | [11 empty] | YES
EDUCATION | 2330 | Migaa ECDE Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Karau Ward |  | Human resource | Jul21 | Jun22 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2331 | Ngorika Mwireri ECDE and Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1799829 |  |  | Complete | [11 empty] | YES
EDUCATION | 2332 | Rutara ECDE Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul21 | Jun22 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 419804 |  |  | Complete | [11 empty] | YES
EDUCATION | 2333 | Plot 11 ECDE Classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 |  |  |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 979870 |  |  | Complete | [11 empty] | YES
EDUCATION | 2334 | Huhoini ECDE and toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Oljoroorok | Gathanji |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1800000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2335 | Muthomi ECDE classroom and toilet construction | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Engineer Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1399779 |  |  | Complete | [11 empty] | YES
EDUCATION | 2336 | Makara ECDE classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Mirangine Ward |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1259833 |  |  | Complete | [11 empty] | YES
EDUCATION | 2337 | Kirima ECDE - Construction of toilet and renovation of classroom | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Mirangine Ward |  | Human resource | Jul21 | Jun22 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 419915 |  |  | Complete | [11 empty] | YES
EDUCATION | 2338 | Kihuho - construction of ECDE and Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Mirangine Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1800000 |  |  | Complete | [11 empty] | YES
EDUCATION | 2339 | CCM Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Mirangine Ward |  | Human resource | Jul21 | Jun22 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 419661 |  |  | Complete | [11 empty] | YES
EDUCATION | 2340 | Nyandundo/Kanyotu ECDE classroom and toilet | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Mirangine Ward |  | Human resource | Jul21 | Jun22 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 698713 |  |  | Complete | [11 empty] | YES
EDUCATION | 2341 | Haraka ECDE Classroom and kitchen | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 979923 |  |  | Complete | [11 empty] | YES
EDUCATION | 2342 | Rehabilitation / Repair of Bongo ECDE Classroom and fencing | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio Ward |  | Human resource | Jul21 | Jun22 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1048787 |  |  | Complete | [11 empty] | YES
EDUCATION | 2343 | Karai ECDE Classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul21 | Jun22 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 279963 |  |  | Complete | [11 empty] | YES
EDUCATION | 2344 | Kwale ECDE Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul21 | Jun22 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 539418 |  |  | Complete | [11 empty] | YES
EDUCATION | 2345 | Githabai/Satellite ECDE and Toilet construction | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 |  | Wanjohi Ward |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 399844 |  |  | Complete | [11 empty] | YES
EDUCATION | 2346 | Completion of Nandarasi YP Twin workshop phased financing project-North Kinangop | Construction of a twin Workshop | To create a condusive learning environment | Constructed twin Workshop | 3110299 | Kinangop | North Kinangop |  | Human resource | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 2000000 |  |  | Ongoing | [11 empty] | YES
EDUCATION | 2347 | Women groups training Expenses (Capacity Building) | Women groups training Expenses (Capacity Building) | To improve livelihood | Training was done | 2211399 | County wide | County Wide |  | Productive | Jul21 | Jun22 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2348 | FGM and gender-based violence awareness campaign | FGM and gender-based violence awareness campaign | Sensitization on FGM and GBV | Increassed literacy on FGM and GBV | 2211399 | County wide | County Wide |  | Productive | Jul21 | Jun22 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2349 | HIV & aids social skills development services | HIV & aids social skills development services | To promote HIV & AIDS awareness and prevention | Provided social support | 2211399 | County wide | County Wide |  | Productive | Jul21 | Jun22 |  |  |  |  | CGN | N/A | N/A | N/A | [17 empty] | YES
EDUCATION | 2350 | Social support | Tents and chairs for welfare groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Nyakio Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999900 |  |  | Complete | 100%
EDUCATION | 2351 | Social support | Support to welfare groups ( tents and chairs) | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Kiriita Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 999950 |  |  | Complete | 100%
EDUCATION | 2352 | Social support | Support to welfare groups ( kiriita pastoral association) PA system | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Kiriita Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999998 |  |  | Complete | 100%
EDUCATION | 2353 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Nyakio Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999900 |  |  | Complete | 100%
EDUCATION | 2354 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Nyakio Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 997900 |  |  | Complete | 100%
EDUCATION | 2355 | Social support | Supply of LPG cylinders | To improve livelihood | Provided social support | 2110805 | Kipipiri | Githioro Ward |  | Productive | Jul21 | Jun22 |  |  | 4000000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete
EDUCATION | 2356 | Social support | Support to boda boda | To improve livelihood | Provided social support | 2110805 | Kipipiri | Githioro Ward |  | Productive | Jul21 | Jun22 |  |  | 800000 |  | CGN | N/A | N/A | N/A |  |  | 799900 |  |  | Complete | 100%
EDUCATION | 2357 | Social support | Purchase of tents and chairs | To improve livelihood | Provided social support | 2110805 | Kipipiri | Githioro Ward |  | Productive | Jul21 | Jun22 |  |  | 660000 |  | CGN | N/A | N/A | N/A |  |  | 660000 |  |  | Complete | 100%
EDUCATION | 2358 | Social support | Women empowerment | To improve livelihood | Provided social support | 2110805 | Kipipiri | Githioro Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999995 |  |  | Complete | 100%
EDUCATION | 2359 | Social support | Purchase of blankets for the elderly | To improve livelihood | Provided social support | 2110805 | Kipipiri | Githioro Ward |  | Productive | Jul21 | Jun22 |  |  | 800000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | 100%
EDUCATION | 2360 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999600 |  |  | Complete | 100%
EDUCATION | 2361 | Social support | Supply and distribution of 500 litres water tanks | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini Ward |  | Productive | Jul21 | Jun22 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2999900 |  |  | Complete | 100%
EDUCATION | 2362 | Social support | Tents and chairs | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999900 |  |  | Complete | 100%
EDUCATION | 2363 | Social support | Support to elderly people ( blankets) | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999850 |  |  | Complete | 100%
EDUCATION | 2364 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Engineer |  | Productive | Jul21 | Jun22 |  |  | 900000 |  | CGN | N/A | N/A | N/A |  |  | 899900 |  |  | Complete | 100%
EDUCATION | 2365 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Engineer |  | Productive | Jul21 | Jun22 |  |  | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 1600000 |  |  | Complete | 100%
EDUCATION | 2366 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Kanjuiri Ward |  | Productive | Jul21 | Jun22 |  |  | 900000 |  | CGN | N/A | N/A | N/A |  |  | 900000 |  |  | Complete | 100%
EDUCATION | 2367 | Social support | LPG gas for the elderly | To improve livelihood | Provided social support | 2110805 | Olkalou | Kanjuiri Ward |  | Productive | Jul21 | Jun22 |  |  | 2800000 |  | CGN | N/A | N/A | N/A |  |  | 2800000 |  |  | Complete | 100%
EDUCATION | 2368 | Social support | Mattresses for the elderly ( size 4ft*6’2ft) | To improve livelihood | Provided social support | 2110805 | Kipipiri | Geta Ward |  | Productive | Jul21 | Jun22 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2999400 |  |  | Complete | 100%
EDUCATION | 2369 | Social support | Mattresses for the elderly ( size 3’6*6’2ft) | To improve livelihood | Provided social support | 2110805 | Kipipiri | Geta Ward |  | Productive | Jul21 | Jun22 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | _ |  |  | Complete
EDUCATION | 2370 | Social support | Women empowerment | To improve livelihood | Provided social support | 2110805 | Kipipiri | Geta Ward |  | Productive | Jul21 | Jun22 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 499900 |  |  | Complete | 100%
EDUCATION | 2371 | Social support | Blankets for the elderly | To improve livelihood | Provided social support | 2110805 | Olkalou | Kanjuiri Ward |  | Productive | Jul21 | Jun22 |  |  | 1250000 |  | CGN | N/A | N/A | N/A |  |  | 1249986 |  |  | Complete | 100%
EDUCATION | 2372 | Social support | Blankets for the elderly | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999850 |  |  | Complete | 100%
EDUCATION | 2373 | Social support | Tents for welfare groups | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata Ward |  | Productive | Jul21 | Jun22 |  |  | 800000 |  | CGN | N/A | N/A | N/A |  |  | 799000 |  |  | Complete | 100%
EDUCATION | 2374 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata Ward |  | Productive | Jul21 | Jun22 |  |  | 800000 |  | CGN | N/A | N/A | N/A |  |  | 800000 | 499800 |  | Complete | 100%
EDUCATION | 2375 | Social support | Supply of water tanks | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999850 |  |  | Complete | 100%
EDUCATION | 2376 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Kanjuiri Ward |  | Productive | Jul21 | Jun22 |  |  | 900000 |  | CGN | N/A | N/A | N/A |  |  | 900000 |  |  | Complete | 100%
EDUCATION | 2377 | Social support | Tents for welfare groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Kanjuiri Ward |  | Productive | Jul21 | Jun22 |  |  | 1300000 |  | CGN | N/A | N/A | N/A |  |  | 1300000 |  |  | Complete | 100%
EDUCATION | 2378 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Karau Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1950000 |  |  | Complete | 100%
EDUCATION | 2379 | Social support | Tents for welfare groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Karau Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999900 |  |  | Complete | 100%
EDUCATION | 2380 | Social support | Youth empowerment | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Weru Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999850 |  |  | Complete | 100%
EDUCATION | 2381 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Weru Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999900 |  |  | Complete | 100%
EDUCATION | 2382 | Social support | Tents and chairs | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Weru Ward |  | Productive | Jul21 | Jun22 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2999800 |  |  | Complete | 100%
EDUCATION | 2383 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Kipipiri | Wanjohi Ward |  | Productive | Jul21 | Jun22 |  |  | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 1599992 |  |  | Complete | 100%
EDUCATION | 2384 | Social support | Support to potato brokers | To improve livelihood | Provided social support | 2110805 | Kipipiri | Wanjohi Ward |  | Productive | Jul21 | Jun22 |  |  | 400000 |  | CGN | N/A | N/A | N/A |  |  | 399700 |  |  | Complete | 100%
EDUCATION | 2385 | Social support | Tents to welfare groups | To improve livelihood | Provided social support | 2110805 | Kipipiri | Wanjohi Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999900 |  |  | Complete | 100%
EDUCATION | 2386 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Kipipiri | Wanjohi Ward |  | Productive | Jul21 | Jun22 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | 100%
EDUCATION | 2387 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Kipipiri | Kipipiri Ward |  | Productive | Jul21 | Jun22 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 700000 |  |  | Complete | 100%
EDUCATION | 2388 | Social support | Tents and chairs for welfare groups | To improve livelihood | Provided social support | 2110805 | Kipipiri | Kipipiri Ward |  | Productive | Jul21 | Jun22 |  |  | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 1599.9 |  |  | Complete | 100%
EDUCATION | 2389 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Gathanji |  | Productive | Jul21 | Jun22 |  |  | 800000 |  | CGN | N/A | N/A | N/A |  |  | 799800 |  |  | Complete | 100%
EDUCATION | 2390 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Gathanji |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999900 |  |  | Complete | 100%
EDUCATION | 2391 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Murungaru Ward |  | Productive | Jul21 | Jun22 |  |  | 2500000 |  | CGN | N/A | N/A | N/A |  |  | 2499980 |  |  | Complete | 100%
EDUCATION | 2392 | Social support | Support to youth groups | To improve livelihood | Provided social support | 2110805 | Kinangop | North Kinangop Ward |  | Productive | Jul21 | Jun22 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2999000 |  |  | Complete | 100%
EDUCATION | 2393 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Kinangop | North Kinangop |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1980000 |  |  | Complete | 100%
EDUCATION | 2394 | Social support | Support to boda boda groups (tyres) | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii Ward |  | Productive | Jul21 | Jun22 |  |  | 1700000 |  | CGN | N/A | N/A | N/A |  |  | 1698840 |  |  | Complete | 100%
EDUCATION | 2395 | Social support | Tents for welfare groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii Ward |  | Productive | Jul21 | Jun22 |  |  | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1199965 |  |  | Complete | 100%
EDUCATION | 2396 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | 100%
EDUCATION | 2397 | Social support | Tents for welfare groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1995000 |  |  | Complete | 100%
EDUCATION | 2398 | Social support | Support to youth groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine Ward |  | Productive | Jul21 | Jun22 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1499820 |  |  | Complete | 100%
EDUCATION | 2399 | Social support | Support to boda boda groups ( tyres) | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Productive | Jul21 | Jun22 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1500000 |  |  | Complete | 100%
EDUCATION | 2400 | Social support | Support to vulnerable | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Ndaragwa Central Ward |  | Productive | Jul21 | Jun22 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2999900 |  |  | Complete | 100%
EDUCATION | 2401 | Social support | Food donation to the needy | To improve livelihood | Provided social support | 2110805 | Olkalou | Kaimbaga Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999980 |  |  | Complete | 100%
EDUCATION | 2402 | Social support | Ndemi rehabilitation center | To enhance care and recovery services for persons in rehabilitation. | Provided social support | 2110805 | Kipipiri | Wanjohi Ward |  | Productive | Jul21 | Jun22 |  |  | 800000 |  | CGN | N/A | N/A | N/A |  |  | 638647 |  |  | Complete | 100%
EDUCATION | 2403 | Social support | Women empowerment | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999997 |  |  | Complete | 100%
EDUCATION | 2404 | Social support | Self help group support | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999999 |  |  | Complete | 100%
EDUCATION | 2405 | Social support | Support to elderly | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999900 |  |  | Complete | 100%
EDUCATION | 2406 | Social support | LPG Cylinders | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Upper Shamata |  | Productive | Jul21 | Jun22 |  |  | 2500000 |  | CGN | N/A | N/A | N/A |  |  | 2499900 |  |  | Complete | 100%
EDUCATION | 2407 | Social support | Support to the elderly (blankets) | To improve livelihood | Provided social support | 2110805 | Kinangop | Gathaara Ward |  | Productive | Jul21 | Jun22 |  |  | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1199900 |  |  | Complete | 100%
EDUCATION | 2408 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999900 |  |  | Complete | 100%
EDUCATION | 2409 | Social support | Social assistance to needy learners (uniforms) | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999900 |  |  | Complete | 100%
EDUCATION | 2410 | Social support | Blankets for elderly | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Kiriita Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999999 |  |  | Complete | 100%
EDUCATION | 2411 | Social support | Mattressses for the elderly | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Kiriita Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999900 |  |  | Complete | 100%
EDUCATION | 2412 | Social support | Tents and chairs | To improve livelihood | Provided social support | 2110805 | Kipipiri | Kipipiri Ward |  | Productive | Jul21 | Jun22 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2999900 |  |  | Complete | 100%
EDUCATION | 2413 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Murungaru |  | Productive | Jul21 | Jun22 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2999900 |  |  | Complete | 100%
EDUCATION | 2414 | Social support | Tents for welfare groups | To improve livelihood | Provided social support | 2110805 | Kinangop | North Kinangop |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999900 |  |  | Complete | 100%
EDUCATION | 2415 | Social support | Support to welfare groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Kaimbaga Ward |  | Productive | Jul21 | Jun22 |  |  | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 2999900 |  |  | Complete | 100%
EDUCATION | 2416 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Kaimbaga Ward |  | Productive | Jul21 | Jun22 |  |  | 1800000 |  | CGN | N/A | N/A | N/A |  |  | 1799900 | 1798900 |  | Complete | 100%
EDUCATION | 2417 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Oljoroorok | Gatimu Ward |  | Productive | Jul21 | Jun22 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete
EDUCATION | 2418 | Social support | Supply and delivery of mattresses for the elderly | To improve livelihood | Provided social support | 2110805 | Olkalou | Kanjuiri Ward |  | Productive | Jul21 | Jun22 |  |  | 2500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100%
EDUCATION | 2419 | Social support | Supply and delivery of blankets to the elderly | To improve livelihood | Provided social support | 2110805 | Kipipiri | Geta Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999900 |  |  | Complete | 100%
EDUCATION | 2420 | Social support | Support to women groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine Ward |  | Productive | Jul21 | Jun22 |  |  | 2500000 |  | CGN | N/A | N/A | N/A |  |  | 2499900 |  |  | Complete | 100%
EDUCATION | 2421 | Social support | Supply of milk ATM | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata Ward |  | Productive | Jul21 | Jun22 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 499900 |  |  | Complete | 100%
EDUCATION | 2422 | Social support | Food donation to the needy | To support the needy | Provided social support | 2110805 | Ndaragwa | Kiriita Ward |  | Productive | Jul21 | Jun22 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999900 |  |  | Complete | 100%
EDUCATION | 2423 | Social support | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini Ward |  | Productive | Jul21 | Jun22 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1499900 |  |  | Complete | 100%
EDUCATION | 2424 | Social support | Support to church groups ( concrete mixer and other equipment) | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Ndaragwa Central Ward |  | Productive | Jul21 | Jun22 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999998 |  |  | Complete
EDUCATION | 2425 | Foods & Rations-Purchase and Delivery of milk(feeding programme) - Kinangop | Delivery of milk | To improve nutrition among learners | Milk was delivered | 3110299 | Kinangop | 8 Wards In Kinangop Sub County |  | Human resource | Jul22 | Jun23 |  | 2945052 | 2945052 |  | CGN | N/A | N/A | N/A |  |  | 2945052 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2426 | Foods & Rations-Purchase and Delivery of milk(feeding programme) - Kipipiri | Delivery of milk | To improve nutrition among learners | Milk was delivered | 3110299 | Kipipiri | 4 Wards In Kipipiri Sub County |  | Human resource | Jul22 | Jun23 |  | 1796108 | 1796108 |  | CGN | N/A | N/A | N/A |  |  | 1796108 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2427 | Foods & Rations-Purchase and Delivery of milk(feeding programme) - Ndaragwa | Delivery of milk | To improve nutrition among learners | Milk was delivered | 3110299 | Ndaragwa | 4 Wards In Ndaragwa Sub County |  | Human resource | Jul22 | Jun23 |  | 1593457 | 1593969 |  | CGN | N/A | N/A | N/A |  |  | 1593457 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2428 | Foods & Rations-Purchase and Delivery of milk(feeding programme) – Ol-joro-orok | Delivery of milk | To improve nutrition among learners | Milk was delivered | 3110299 | Oljoroorok | 4 Wards In Ol-Joro-Orok Sub County |  | Human resource | Jul22 | Jun23 |  | 1294840 | 1295227 |  | CGN | N/A | N/A | N/A |  |  | 1294840 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2429 | Foods & Rations-Purchase and Delivery of milk(feeding programme) – Ol-kalou | Delivery of milk | To improve nutrition among learners | Milk was delivered | 3110299 | Olkalou | 5 Wards In Ol-Kalou Sub County |  | Human resource | Jul22 | Jun23 |  | 2369644 | 2369644 |  | CGN | N/A | N/A | N/A |  |  | 2369644 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2430 | Contracted professional Services – Environmental Impact Assessment ECDE Projects | Environmental Impact Assessment ECDE Projects | To identify and mitigate potential environmental risks. | Milk was delivered | 3110299 | Countywide | Countywide |  | Human resource | Jul22 | Jun23 |  | 1100000 | 1100000 |  | CGN | N/A | N/A | N/A |  |  | 1100000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2431 | ECDE furniture for new classrooms | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Countywide | All Wards |  | Human resource | Jul22 | Jun23 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 2000000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2432 | ECDE furniture for Additional classrooms | supply of furniture | To create a condusive learning environment | Furnitire was delivered | 3110299 | Countywide | All Wards |  | Human resource | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2433 | Purchase of Teaching/Learning materials for ECD | Purchase of teaching aid | To create a condusive learning environment | Teaching aid were provided | 3110299 | Countywide | All Wards |  | Human resource | Jul22 | Jun23 |  | 700000 | 700000 |  | CGN | N/A | N/A | N/A |  |  | 700000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2434 | Construction of Gitwe ECDE Classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Nyakio |  | Human resource | Jul22 | Jun23 |  | 1399590 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1399590 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2435 | Kabongo ECDE Classroom and toilet | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Njabini |  | Human resource | Jul22 | Jun23 |  | 1970524 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Site already handed over | [11 empty] | YES
EDUCATION | 2436 | X-Lee Community ECDE Classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Gathaara |  | Human resource | Jul22 | Jun23 |  | 1399000 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 0 | 1399388 |  | complete | [11 empty] | YES
EDUCATION | 2437 | Urumwe ECDE Classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Gathaara |  | Human resource | Jul22 | Jun23 |  | 1397000 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 0 | 1373025 |  | Site already handed over | [11 empty] | YES
EDUCATION | 2438 | Ngimeri ECDE toilet | Construction of toilets | To create a condusive learning environment | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul22 | Jun23 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2439 | Renovation of Kijiko ECDE classroom | construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | Engineer |  | Human resource | Jul22 | Jun23 |  | 499672 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 499672 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2440 | Ciondo ECDE Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul22 | Jun23 |  | 599970 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599970 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2441 | Manyatta ECDE Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul22 | Jun23 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2442 | Construction of Muti-ini ECDE Toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul22 | Jun23 |  | 599650 | 599650 |  | CGN | N/A | N/A | N/A |  |  | 599650 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2443 | Mwihoti ECDE classroom and toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Murungaru |  | Human resource | Jul22 | Jun23 |  | 1998492 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1998492 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2444 | Kirarwa ECDE classroom and toilet | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Murungaru |  | Human resource | Jul22 | Jun23 |  | 1999087 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999087 | 2000000 |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2445 | Renovation of Mumui ECDE Classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul22 | Jun23 |  | 0 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2446 | St. Peters ECDE Classroom | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kipipiri | Githioro |  | Human resource | Jul22 | Jun23 |  | 1497670 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Site already handed over | [11 empty] | YES
EDUCATION | 2447 | Githinji ECDE toilet | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Geta |  | Human resource | Jul22 | Jun23 |  | 599000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2448 | Mubau (Magomano) ECDE classroom | Construction of toilets | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul22 | Jun23 |  | 1399995 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1399995 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2449 | Manyatta munyeki ECDE classroom and toilet | Construction of classrooms and toilet | To create a condusive learning environment | Constructed Toilet and classroom | 3110299 | Olkalou | Karau |  | Human resource | Jul22 | Jun23 |  | 0 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2450 | Construction of Mawingu ECDE Centre Classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Karau |  | Human resource | Jul22 | Jun23 |  | 1399995 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1399995 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2451 | Muiri ECDE Centre- Construction of Toliet | Construction of Toliet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Karau |  | Human resource | Jul22 | Jun23 |  | 599089 | 730000 |  | CGN | N/A | N/A | N/A |  |  | 599089 | 129986 |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2452 | Bosinia – Huhoini ECDE classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Rurii |  | Human resource | Jul22 | Jun23 |  | 1395000 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | ECDE Walling has been done | [11 empty] | YES
EDUCATION | 2453 | JM ECDE Centre - toilet | Construction of toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Rurii |  | Human resource | Jul22 | Jun23 |  | 599992 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599992 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2454 | Mihuti ECDE Toilet | Construction of toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul22 | Jun23 |  | 599719 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599719 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2455 | Mathakwa ECDE Classroom | Construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Mirangine |  | Human resource | Jul22 | Jun23 |  | 1397456 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1397456 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2456 | Nyandundo ECDE Classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Mirangine |  | Human resource | Jul22 | Jun23 |  | 1397456 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1397456 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2457 | Dundori Primary School – CCM 2 Blocs Renovation |  | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Mirangine |  | Human resource | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Site already handed over | [11 empty] | YES
EDUCATION | 2458 | Tumaini ECDE Classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul22 | Jun23 |  | 1396834 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1396834 |  |  | Constructor plastering the ECDE Classroom | [11 empty] | YES
EDUCATION | 2459 | Tumaini ECDE Fencing | Fencing | Fencing | Fenced ECDE | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul22 | Jun23 |  | 599923 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 599923 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2460 | Construction of ECDE at St. Mary's Ngorika special school | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul22 | Jun23 |  | 0 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2461 | Construction and completion of Kanjau ECDE classroom | Construction of toilets | To create a condusive learning environment | Constructed Toilet | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul22 | Jun23 |  | 0 | 1193906 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2462 | Ol-joro-orok primary ECDE Classroom and Toilet | Construction of toilets | To create a condusive learning environment | Constructed Toilet | 3110299 | Oljoroorok | Weru |  | Human resource | Jul22 | Jun23 |  | 1998894 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1998894 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2463 | Kianjata ECDE Toilet | Construction of toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Oljoroorok | Gatimu |  | Human resource | Jul22 | Jun23 |  | 0 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | 1999990 | [13 empty] | YES
EDUCATION | 2464 | Githae ECDE toilet | Construction of toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul22 | Jun23 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2465 | Githae ECDE classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul22 | Jun23 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1500000 |  |  | Contractor working on the finishes | [11 empty] | YES
EDUCATION | 2466 | Mienyere ECDE Classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul22 | Jun23 |  | 0 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | 0 | [14 empty] | YES
EDUCATION | 2467 | Renovation of Kwa Njora AIC ECD Classroom (Windows, Doors, Plastering and roofing) FY 2020-21 | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul22 | Jun23 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2468 | Renovation of 2NO. ECDE Classrooms Kirera Centre FY 2020-21 | Construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Leshau Pondo |  | Human resource | Jul22 | Jun23 |  | 799350 | 800000 |  | CGN | N/A | N/A | N/A |  |  | 799350 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2469 | Kipipiri - Construction of Mithanduku ECDE Classroom | Construction of classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul22 | Jun23 |  | 0 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 0 | 4193808.96 |  | Complete | [11 empty] | YES
EDUCATION | 2470 | Construction of Mithanduku ECD Toilet | Construction of toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul22 | Jun23 |  | 0 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2471 | Kipipiri - Construction of Mahinga ECDE classroom | Construction of classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul22 | Jun23 |  | 0 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2472 | Kipipiri - Construction of Mahinga ECDE Toilet | Construction of toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul22 | Jun23 |  | 0 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2473 | Contracted Professional Service | Environmental Impact Assessment VTC Projects | To create a condusive learning environment | Assessment was done | 3110299 | Countywide | All Wards |  | Human resource | Jul22 | Jun23 |  | 0 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Allocation was not spent | [11 empty] | YES
EDUCATION | 2474 | Nandarasi vtc | Completion of Nandarasi VTC | To create a condusive learning environment | Construction was completed | 3110299 | Kinangop | N. Kinangop |  | Human resource | Jul22 | Jun23 |  | 3000000 | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 3000000 |  |  | Complete | 90% | [10 empty] | YES
EDUCATION | 2475 | Pesi VTC | Construction of workshop pesi VTC | To create a condusive learning environment | Constructed Workshop | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul22 | Jun23 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Ongoing | [11 empty] | YES
EDUCATION | 2476 | Ngano vtc | Construction of Ngano VTC Toilet - Charagita | To create a condusive learning environment | Constructed Toilet | 3110299 | Oljoroorok | Charagita |  | Human resource | Jul22 | Jun23 |  | 1199928 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1199928 |  |  | VTC Toilet at Finishes stage | [11 empty] | YES
EDUCATION | 2477 | Kanyagia youth polytechnic | Final Contract Payment Twin workshop at kanyagia vtc - Phased Financing | To create a condusive learning environment | Constructed twin Workshop | 3110299 | Ndaragwa | Ndaragwa Central |  | Human resource | Jul22 | Jun23 |  | 3000000 | 3000000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Ongoing | [11 empty] | YES
EDUCATION | 2478 | Community library-Olkalou | Fence and Gate | Preservation of our cultural heritage |  | 2211399 | Olkalou | Karau |  | Productive | Jul22 | Jun23 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 0 | 1999761 |  | Complete
EDUCATION | 2479 | Social support | Purchase of Specialised Plant, Equipment & Machines for youth groups- Concrete Mixer Shamata- Wafici-ini Masonry Self Help Group | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul22 | Jun23 |  | 400000 | 400000 |  | CGN | N/A | N/A | N/A | [5 empty] | Paid | 100%
EDUCATION | 2480 | Social support | Purchase of Specialised Plant, Equipment & Machinery for youth groups (Carwash machines, salon and barber equipment and accessories, Posho mills and concrete mixers)- Magumu Ward | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999100 |  |  | Paid | 100%
EDUCATION | 2481 | Social support | Purchase of Specialised Plant, Equipment & Machinery for youth groups - North Kinangop Ward | To improve livelihood | Provided social support | 2110805 | Countywide | Countywide |  | Productive | Jul22 | Jun23 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 2000000 |  |  | Paid | 100%
EDUCATION | 2482 | Social support | Purchase of Specialised Plant, Equipment & Machinery for youth - Engineer | To improve livelihood | Provided social support | 2110805 | Kinangop | Engineer |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999950 |  |  | Paid | 100%
EDUCATION | 2483 | Social support | Purchase of Specialised Plant, Equipment & Machinery for youths - Njabini | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 959699 |  |  | Paid | 100%
EDUCATION | 2484 | Social support | Shamata - Purchase of Specialised Plant, Equipment & Machinery for youths (Musical instruments for Mwihoti youth group) | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul22 | Jun23 |  | 300000 | 300000 |  | CGN | N/A | N/A | N/A |  |  | 300000 |  |  | Paid | 100%
EDUCATION | 2485 | Social support | Purchase of Specialised Plant, Equipment & Machinery for youths - Gathaara | To improve livelihood | Provided social support | 2110805 | Kinangop | Gathaara |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Paid | 100%
EDUCATION | 2486 | Social support | Purchase of Specialised Plant, Equipment & Machinery - ( 5No. Motor bikes)- Leshau Pondo | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Paid | 100%
EDUCATION | 2487 | Social support | Purchase of Specialised Plant, Equipment & Machinery for youths- 5No. 2No.Welding Machines, 2No. Incubators, 1No. Powersaw (Husqvarna)-Mirangine | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine |  | Productive | Jul22 | Jun23 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1500000 |  |  | Paid | 100%
EDUCATION | 2488 | Social support | Purchase of Specialised Plant, Equipment & Machines- Public address system and generator - Leshau-Pondo- FY 2020-21 | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Productive | Jul22 | Jun23 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 499300 |  |  | Paid | 100%
EDUCATION | 2489 | Social support | Procurement and distribution of food & non food items for the vulnerable (including during Christmas eve) | To improve livelihood | Provided social support | 2110805 | Countywide | Countywide |  | Productive | Jul22 | Jun23 |  | 4500000 | 4500000 |  | CGN | N/A | N/A | N/A |  |  | 4500000 |  |  | Paid | 100%
EDUCATION | 2490 | Social support | Social support to boda boda operators- Nyakio | To improve livelihood | Provided social support | 2110805 | Kinangop | Nyakio |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999990 |  |  | Paid | 100%
EDUCATION | 2491 | Social support | Social support (Women empowerment)- kiriita | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Kiriita |  | Productive | Jul22 | Jun23 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Paid | 100%
EDUCATION | 2492 | Social support | Social support (Women empowerment)- Nyakio | To improve livelihood | Provided social support | 2110805 | Kinangop | Nyakio |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 800000 |  |  | Paid | 100%
EDUCATION | 2493 | Social support | Social support (Women empowerment)- Mirangine | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 890000 |  |  | Paid | 100%
EDUCATION | 2494 | Social support | Social Support- Small scale milk cooler, Pasteurizer, ATM -Rurii | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii |  | Productive | Jul22 | Jun23 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1499960 |  |  | Paid | 100%
EDUCATION | 2495 | Social support | Kipipiri - support to Bodaboda self group | To improve livelihood | Provided social support | 2110805 | Kipipiri | Kipipiri |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 960000 |  |  | Paid | 100%
EDUCATION | 2496 | Social support | Social support to welfare group(tent )kipipiri | To improve livelihood | Provided social support | 2110805 | Kipipiri | Kipipiri |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 | 1495250 |  | Paid | 100%
EDUCATION | 2497 | Social support | kipipiri water tank for kirima CBO | To improve livelihood | Provided social support | 2110805 | Kipipiri | Kipipiri |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999900 |  |  | Paid | 100%
EDUCATION | 2498 | Social support | kipipiri water tank | To improve livelihood | Provided social support | 2110805 | Kipipiri | Kipipiri |  | Productive | Jul22 | Jun23 |  | 1900000 | 1900000 |  | CGN | N/A | N/A | N/A |  |  | 1899900 |  |  | Paid | 100%
EDUCATION | 2499 | Social support | Social support- Water tanks for Kahuruko wome group-Njabini | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Paid | 100%
EDUCATION | 2500 | Social support | Social support to the elderly and the needy with water tanks- Njabini | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Paid | 100%
EDUCATION | 2501 | Social support | Social support to welfare groups (Tents) -KIRIITA | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Kiriita |  | Productive | Jul22 | Jun23 |  | 1400000 | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1400000 |  |  | Paid | 100%
EDUCATION | 2502 | Social support | Social support to welfare groups (Tents) - Wanjohi | To improve livelihood | Provided social support | 2110805 | Kipipiri | Wanjohi |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 960240 |  |  | Paid | 100%
EDUCATION | 2503 | Social support | Social support to welfare groups (Tents and Chairs) Githioro | To improve livelihood | Provided social support | 2110805 | Kipipiri | Githioro |  | Productive | Jul22 | Jun23 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1474132 | 1332000 |  | Paid | 100%
EDUCATION | 2504 | Social support | Social Support to welfare groups-10 NO.Tents and chairs (100 seater each -karau | To improve livelihood | Provided social support | 2110805 | Olkalou | Karau |  | Productive | Jul22 | Jun23 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1500000 |  |  | Paid | 100%
EDUCATION | 2505 | Social support | Social support to welfare groups (Tents and Chairs)- Magumu | To improve livelihood | Provided social support | 2110805 | Kinangop | Magumu |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Paid | 100%
EDUCATION | 2506 | Social support | Social Support to welfare groups-6 NO.Tents(100 seater each -kaimbaga | To improve livelihood | Provided social support | 2110805 | Olkalou | Kaimbaga |  | Productive | Jul22 | Jun23 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Paid | 100%
EDUCATION | 2507 | Social support | Social Support to welfare groups-2 NO.Tents-Githioro | To improve livelihood | Provided social support | 2110805 |  | Githioro |  | Productive | Jul22 | Jun23 |  | 350000 | 350000 |  | CGN | N/A | N/A | N/A |  |  | 350000 |  |  | Paid | 100%
EDUCATION | 2508 | Social support | Social Support to welfare groups-9 NO.Tents-Mirangine | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine |  | Productive | Jul22 | Jun23 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1500000 |  |  | Paid | 100%
EDUCATION | 2509 | Social support | Social support- Christmas foodstuff for the elderly and the needy- Leshau Pondo | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Productive | Jul22 | Jun23 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Paid | 100%
EDUCATION | 2510 | Social support | Social Support to welfare groups (Tents)- Leshau Pondo | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Productive | Jul22 | Jun23 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999597 |  |  | Paid | 100%
EDUCATION | 2511 | Social support | Ndaragwa Central- Support to youth- Needy Students (Shoes)- | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Ndaragwa Central |  | Productive | Jul22 | Jun23 |  | 2990000 | 2990000 |  | CGN | N/A | N/A | N/A |  |  | 2990000 |  |  | Paid | 100%
EDUCATION | 2512 | Social support | Social assistance to needy learners (uniforms)- Shamata | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul22 | Jun23 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 2000000 |  |  | Paid | 100%
EDUCATION | 2513 | Social support | Supply of LPG cylinder to the Elderly- Upper Shamata | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Productive | Jul22 | Jun23 |  | 2500000 | 2500000 |  | CGN | N/A | N/A | N/A |  |  | 2500000 |  |  | Paid | 100%
EDUCATION | 2514 | Social support | Purchase of Specialised Plant, Equipment & Machines- Ndaragwa Central | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Ndaragwa Central |  | Productive | Jul22 | Jun23 |  | 1990000 | 1990000 |  | CGN | N/A | N/A | N/A |  |  | 1976710 |  |  | Paid | 100%
EDUCATION | 2515 | Social support | Supply of Matressess for the Elderly 5*6 - Geta Ward - Lettap Development Limited | To improve livelihood | Provided social support | 2110805 | Countywide | Countywide |  | Productive | Jul22 | Jun23 |  | 799705 | 799705 |  | CGN | N/A | N/A | N/A |  |  | 799705 |  |  | Paid | 100%
EDUCATION | 2516 | Social support | Supply of Tents - Leshau Pondo (2020/21) - Breshan Investment Limited | To improve livelihood | Provided social support | 2110805 | Countywide | Countywide |  | Productive | Jul22 | Jun23 |  | 2997500 | 2997500 |  | CGN | N/A | N/A | N/A |  |  | 2398700 |  |  | Paid | 100%
EDUCATION | 2517 | Formulation of ECDE Act to accommodate capitation | Formulation of ECDE Act to accommodate capitation | To facilitate provision of capitation | Formulated Act | 3110299 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1499550 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2518 | Purchase of ECDE furniture for Additional Classrooms | Purchase of ECDE furniture for Additional Classrooms | To create a condusive learning environment | Equipment were delivered | 3110299 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 2630000 | 2630000 |  | CGN | N/A | N/A | N/A |  |  | 2630000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2519 | Githabai - Construction and completion of Koinange ECDE Classroom | Githabai - Construction and completion of Koinange ECDE Classroom | To create a condusive learning environment | Construction was completed | 3110299 | Kinangop | Githabai |  | Human resource | Jul23 | Jun24 |  | 1499376 | 1499376 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Pending bill is not paid | [11 empty] | YES
EDUCATION | 2520 | Repair of ECDE Classrooms/Toilets - Coloboise, Soilo | Repair of ECDE Classrooms/Toilets - Coloboise, Soilo | To create a condusive learning environment | Constructed Toilet and classroom | 3110299 | Kinangop | Njabini |  | Human resource | Jul23 | Jun24 |  | 700000 | 700000 |  | CGN | N/A | N/A | N/A |  |  | 0 | 699223 |  | Ongoing | [11 empty] | YES
EDUCATION | 2521 | Renovation of Kanyugi ECDE Classroom | Renovation of Kanyugi ECDE Classroom | To create a condusive learning environment | Renovation was done | 3110299 | Kinangop | Engineer |  | Human resource | Jul23 | Jun24 |  | 400000 | 400000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2522 | Mbirithi ECDE Toilet | Mbirithi ECDE Toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kinangop | Engineer |  | Human resource | Jul23 | Jun24 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2523 | Ciondo ECDE Toilet - Appraisal | Ciondo ECDE Toilet - Appraisal | To improve hygiene and sanitation | Increased enrollment | 3110299 | Kinangop | Engineer |  | Human resource | Jul23 | Jun24 |  | 200000 | 200000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2524 | Rumwe village ECDE Classroom | Rumwe village ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kinangop | North Kinangop |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - | 1499998 |  | Complete | [11 empty] | YES
EDUCATION | 2525 | Matumi ECDE Classroom | Construction of Matumi ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - | 1499675 |  | Procurement process in progress | [11 empty] | YES
EDUCATION | 2526 | St. Peters ECDE Classroom | St. Peters ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2527 | Renovation of Mumui ECDE Classroom | Renovation of Mumui ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Githioro |  | Human resource | Jul23 | Jun24 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 0 | 499606 |  | Procurement process in progress | [11 empty] | YES
EDUCATION | 2528 | Kipipiri - Construction of Mahinga ECDE Classroom | Kipipiri - Construction of Mahinga ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Procurement process in progress | [11 empty] | YES
EDUCATION | 2529 | Kipipiri - Construction of Mahinga ECDE Toilet | Kipipiri - Construction of Mahinga ECDE Toilet | To improve hygiene and sanitation | Increased enrollment | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul23 | Jun24 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2530 | Kipipiri - Construction of Mithanduku ECDE Classroom | Kipipiri - Construction of Mithanduku ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2531 | Construction of Mithanduku ECD Toilet | Construction of Mithanduku ECD Toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul23 | Jun24 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2532 | Huhirio ECDE Classroom and Toilet | Huhirio ECDE Classroom and Toilet | To improve hygiene and sanitation | Constructed Toilet and classroom | 3110299 | Kipipiri | Wanjohi |  | Human resource | Jul23 | Jun24 |  | 2100000 | 2100000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2533 | Mahinga ECDE Classroom | Mahinga ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - | 1493300 |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2534 | Huruma ECDE Toilet | Huruma ECDE Toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul23 | Jun24 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | 599198 |  | 90% Done | 90% | [10 empty] | YES
EDUCATION | 2535 | Kaimbaga Centre ECDE Classroom- Renovation | Kaimbaga Centre ECDE Classroom- Renovation | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul23 | Jun24 |  | 700000 | 700000 |  | CGN | N/A | N/A | N/A |  |  | - | 549568.5 |  | Complete | [11 empty] | YES
EDUCATION | 2536 | Kamande - Server | Kamande - Server | Provision of Server | Server Provided | 3110299 | Olkalou | Kaimbaga |  | Human resource | Jul23 | Jun24 |  | 100000 | 100000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | YES
EDUCATION | 2537 | Manyatta munyeki ECDE Classroom | Manyatta munyeki ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Karau |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2538 | Tumaini ECDE classroom | Tumaini ECDE classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2539 | Kanjuiri Primary ECDE Classroom | Kanjuiri Primary ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 855013 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2540 | Tumaini ECDE gate | Tumaini ECDE gate | To create a condusive learning environment | Increased enrollment | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul23 | Jun24 |  | 400000 | 400000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2541 | Ndothua ECDE Classroom | Ndothua ECDE Classroom | To create a condusive learning environment | Constructed classroom | 3110299 | Olkalou | Kanjuiri |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2542 | ECDE Classroom - PBK | ECDE Classroom - PBK | To create a condusive learning environment | Constructed classroom | 3110299 | Oljoroorok | Charagita |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - | 1499098 |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2543 | ECD Classroom Renovations (Simba Ecd, Kamaina ECD & LeeSirko - Weru ward | ECD Classroom Renovations (Simba Ecd, Kamaina ECD & LeeSirko - Weru ward | To create a condusive learning environment | Constructed classroom | 3110299 | Oljoroorok | Weru |  | Human resource | Jul23 | Jun24 |  | 1700000 | 1700000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2544 | Gatumbiro ECDE Toilet | Gatumbiro ECDE Toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Oljoroorok | Weru |  | Human resource | Jul23 | Jun24 |  | 800000 | 800000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2545 | Gatumbiro ECDE Toilet | Gatumbiro ECDE Toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Oljoroorok | Weru |  | Human resource | Jul23 | Jun24 |  | 800000 | 800000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2546 | Gatitu ECDE Toilet | Gatitu ECDE Toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Oljoroorok | Weru |  | Human resource | Jul23 | Jun24 |  | 800000 | 800000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2547 | Kibathi ECDE Classroom and Toilet | Kibathi ECDE Classroom and Toilet | To create a condusive learning environment | Constructed Toilet and classroom | 3110299 | Oljoroorok | Gatimu |  | Human resource | Jul23 | Jun24 |  | 2100000 | 2100000 |  | CGN | N/A | N/A | N/A |  |  | - | 2098252 |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2548 | Kiriita ECDE Classrooms | Kiriita ECDE Classrooms | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Kiriita |  | Human resource | Jul23 | Jun24 |  | 3000000 | 3000000 |  | CGN | N/A | N/A | N/A |  |  | - | 2998912 |  | One class is done, one not fully done | [11 empty] | YES
EDUCATION | 2549 | Mienyere ECDE Classroom FY 2022-23 | Mienyere ECDE Classroom FY 2022-23 | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul23 | Jun24 |  | 1600000 | 1600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2550 | Repair and renovation of Simbara ECDE | Repair and renovation of Simbara ECDE | To create a condusive learning environment | Increased enrollment | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul23 | Jun24 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2551 | Njamba ECDE Class | Njamba ECDE Class | To create a condusive learning environment | Increased enrollment | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul23 | Jun24 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2552 | Construction of Pesi kihuha ECDE Classroom - Shamata - FY 2021/2022 | Construction of Pesi kihuha ECDE Classroom - Shamata - FY 2021/2022 | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul23 | Jun24 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | 2393977.5 |  | Complete | [11 empty] | YES
EDUCATION | 2553 | Construction of Warukira ECD Classroom - FY 2021/2022 | Construction of Warukira ECD Classroom - FY 2021/2022 | To create a condusive learning environment | Constructed classroom | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul23 | Jun24 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2554 | Construction of Gakoe ECD toilet - Shamata - FY 2018/2019 | Construction of Gakoe ECD toilet - Shamata - FY 2018/2019 | To improve hygiene and sanitation | Constructed Toilet and classroom | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul23 | Jun24 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | [11 empty] | YES
EDUCATION | 2555 | Gachurio ECDE Classroom and Toilet - Magumu | Gachurio ECDE Classroom and Toilet - Magumu | To improve hygiene and sanitation | Constructed Toilet and classroom | 3110299 | Kinangop | Magumu |  | Human resource | Jul23 | Jun24 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | - | 1999999 |  | Complete | [11 empty] | YES
EDUCATION | 2556 | Githinji ECDE toilet | Githinji ECDE toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kipipiri | Geta |  | Human resource | Jul23 | Jun24 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | 599939 |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2557 | Kianjogu ECDE and Toilet | Kianjogu ECDE and Toilet | To improve hygiene and sanitation | Constructed Toilet | 3110299 | Kipipiri | Geta |  | Human resource | Jul23 | Jun24 |  | 2100000 | 2100000 |  | CGN | N/A | N/A | N/A |  |  | - | 2099203 |  | Complete | [11 empty] | YES
EDUCATION | 2558 | Formulation of County vocational Education Training Policy | Formulation of County vocational Education Training Policy | To standardize and strengthen Vocational Training | Policy was formulated | 3110299 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1450000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2559 | Current transfers to Youth Polytechnics for 2301 students @ 15,000 per student | Current transfers to Youth Polytechnics for 2301 students @ 15,000 per student | To reduce the financial burden on trainees and guardians | Funds were transferred | 3110299 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 34515000 | 34515000 |  | CGN | N/A | N/A | N/A |  |  | 33470000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2560 | Purchase of Modern tools and equipment for Kanyagia VTC (Fashion design and Hair Dressing) | Purchase of Modern tools and equipment for Kanyagia VTC (Fashion design and Hair Dressing) | To create a condusive learning environment | Equipment were delivered | 3110299 | Ndaragwa | Ndaragwa Central |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2561 | Purchase of Modern tools and equipment for Kangui VTC (Motor Vehicle Mechanic) | Purchase of Modern tools and equipment for Kangui VTC (Motor Vehicle Mechanic) | To create a condusive learning environment | Equipment were delivered | 3110299 | Oljoroorok | Weru |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999079 |  |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2562 | Completion of Nandarasi VTC Workshop | Completion of Nandarasi VTC Workshop | To create a condusive learning environment | Constructed Workshop | 3110299 | Kinangop | North Kinangop |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Not yet done | [11 empty] | YES
EDUCATION | 2563 | Nandarasi VTC Toilet with Biogester | Nandarasi VTC Toilet with Biogester | To improve sanitation facilities | Constructed Toilet with biodigester | 3110299 | Kinangop | North Kinangop |  | Human resource | Jul23 | Jun24 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | - | 1999391 |  | Not yet done | [11 empty] | YES
EDUCATION | 2564 | Construction of Lecture room - Pesi VTC | Construction of Lecture room - Pesi VTC | To create a condusive learning environment | Lecture room was constructed | 3110299 | Ndaragwa | Shamata |  | Human resource | Jul23 | Jun24 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | - | 1999462 |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2565 | Completion of Lereshwa VTC Hostel | Completion of Lereshwa VTC Hostel | To provide accomodation to students | Constructed hostel | 3110299 | Kipipiri | Kipipiri |  | Human resource | Jul23 | Jun24 |  | 3000000 | 3000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Contractor abonded site | [11 empty] | YES
EDUCATION | 2566 | Completion of Olkalou VTC Hostel | Completion of Olkalou VTC Hostel | To provide accomodation to students | Constructed hostel | 3110299 | Olkalou | Karau |  | Human resource | Jul23 | Jun24 |  | 2300000 | 2300000 |  | CGN | N/A | N/A | N/A |  |  | 1305361 | 2299439 |  | Complete | 100% | [10 empty] | YES
EDUCATION | 2567 | Formulation of Cultural Heriatge Policy | Formulation of Cultural Heriatge Policy | Preservation of our cultural heritage | Policy was formulated | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1400000 |  |  | Policy already submitted to Assembly
EDUCATION | 2568 | Annual Prayer Breakfast/Day | Formulation of Cultural Heriatge Policy | Preservation of our cultural heritage | Prayer day was successful | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999750 |  |  | to be done on 20th July 2024
EDUCATION | 2569 | Cultural Exhibitions Day and Community sensitization on Cultural Diversity | Cultural Exhibitions Day and Community sensitization on Cultural Diversity | Preservation of our cultural heritage | Community was sensitized | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | 325000 |  |  | to be done on 20th July 2024
EDUCATION | 2570 | Vetting and registration of cultural groups and Mapping of Mau mau veterans and other heros and heroines | Vetting and registration of cultural groups and Mapping of Mau mau veterans and other heros and heroines | Preservation of our cultural heritage & Honouring national Heroes and Heroines | Maumau heroes and heroins wer registered | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 650000 | 650000 |  | CGN | N/A | N/A | N/A |  |  | 650000 |  |  | Complete | 100%
EDUCATION | 2571 | Support Gordon Cultural Initiation Mentorship Training | Support Gordon Cultural Initiation Mentorship Training | Preservation of our cultural heritage | Training was done | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 250000 | 250000 |  | CGN | N/A | N/A | N/A |  |  | 275000 |  |  | Complete | 100%
EDUCATION | 2572 | Construction of Gordon Cultural and mentorship centre | Construction of Gordon Cultural and mentorship centre | Preservation of our cultural heritage | Center was constructed | 2211399 | Kinangop | Engineer |  | Human resource | Jul23 | Jun24 |  | 5000000 | 5000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Not complete
EDUCATION | 2573 | Library Outreach services with learning institutions /schools within the County | Library Outreach services with learning institutions /schools within the County | Advertisement of library services | Community was educated on library services | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 480000 |  |  | Complete | 100%
EDUCATION | 2574 | International Day of the African Child (16th June) | International Day of the African Child (16th June) | Education on child rights | Communities were sensitized | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 300000 | 300000 |  | CGN | N/A | N/A | N/A |  |  | 299070 |  |  | Not yet done
EDUCATION | 2575 | Corrective Surgeries for Children | Corrective Surgeries for Children | Offer medical services | Surgeries were conducted | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 700000 | 700000 |  | CGN | N/A | N/A | N/A |  |  | 700000 |  |  | Complete | 100%
EDUCATION | 2576 | Support for orphans and destitute children | Support for orphans and destitute children | Offering help to orphans | Children were supported | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 100000 | 100000 |  | CGN | N/A | N/A | N/A |  |  | 100000 |  |  | Complete | 100%
EDUCATION | 2577 | Sensitization on Children and Media | Sensitization on Children and Media | Sensitization on child media | Communities were sensitized | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 300000 | 300000 |  | CGN | N/A | N/A | N/A |  |  | 300000 |  |  | Complete | 100%
EDUCATION | 2578 | Women and Men empowerment (Capacity Building) | Women and Men empowerment (Capacity Building) | To improve livelihood | Provided social support | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 900000 | 900000 |  | CGN | N/A | N/A | N/A |  |  | 900000 |  |  | Complete | 100%
EDUCATION | 2579 | Commemoration of 16 days of activism on GBV issues | Commemoration of 16 days of activism on GBV issues | To improve livelihood | Provided social support | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete | 100%
EDUCATION | 2580 | Kebs Certification, Copyrights, and Accredation of County Sanitary Towels Programme | Kebs Certification, Copyrights, and Accredation of County Sanitary Towels Programme | To improve livelihood | Provided social support | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 100000 | 100000 |  | CGN | N/A | N/A | N/A |  |  | 100000 |  |  | Complete | 100%
EDUCATION | 2581 | Mentorship programme on adolescence and puberty for boys and girls | Mentorship programme on adolescence and puberty for boys and girls | To improve livelihood | Provided social support | 2211399 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 400000 | 400000 |  | CGN | N/A | N/A | N/A |  |  | 396220 |  |  | Complete | 100%
EDUCATION | 2582 | Formulation of a disabilty Policy | Formulation of a disabilty Policy | To promote inclusion and equal opportunities for persons with disabilities. | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1434600 |  |  | Complete | 100%
EDUCATION | 2583 | Registration of Indigents | Registration of Indigents | To identify and document vulnerable individuals for social support. | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 440000 | 440000 |  | CGN | N/A | N/A | N/A |  |  | 430000 |  |  | Not yet done
EDUCATION | 2584 | Empowerment of vulnerable groups through capacity building | Empowerment of vulnerable groups through capacity building | Empowerment of vulnerable groups | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 400000 | 400000 |  | CGN | N/A | N/A | N/A |  |  | 400000 |  |  | Capacity building is not done
EDUCATION | 2585 | Capacity building and sensitization to women and men groups - Githibai | Capacity building and sensitization to women and men groups - Githibai | Capacity building and sensitization | Provided social support | 2110805 | Kinangop | Githabai |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Capacity building is not done
EDUCATION | 2586 | Procurement and distribution of foodstuff for the vulnerable (including during Christmas eve) | Procurement and distribution of foodstuff for the vulnerable (including during Christmas eve) | To support the needy | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 5000000 | 5000000 |  | CGN | N/A | N/A | N/A |  |  | 4999950 |  |  | Foodstuff have been provided
EDUCATION | 2587 | Distribution/Logistics of Christmas food for 25 wards (County and Ward Committees) | Distribution/Logistics of Christmas food for 25 wards (County and Ward Committees) | To support the needy | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete | 100%
EDUCATION | 2588 | Procurement and distribution of foodstuff to the needy/vulnerable on Christmas eve- Leshau Pondo | Procurement and distribution of foodstuff to the needy/vulnerable on Christmas eve- Leshau Pondo | To support the needy | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | 200000 |  |  | Complete | 100%
EDUCATION | 2589 | Provision of income generating equipment to vulnerable households | Provision of income generating equipment to vulnerable households | To improve livelihood | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 800000 | 800000 |  | CGN | N/A | N/A | N/A |  |  | 599970 |  |  | Not yet done
EDUCATION | 2590 | Identification and documentation of PWDs into a database | Identification and documentation of PWDs into a database | To create a reliable database for planning and service delivery. | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 200000 | 200000 |  | CGN | N/A | N/A | N/A |  |  | 200000 |  |  | Complete | 100%
EDUCATION | 2591 | PWDs assessments support | PWDs assessments support | PWDs assessments support | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 100000 | 100000 |  | CGN | N/A | N/A | N/A |  |  | 100000 |  |  | Complete | 100%
EDUCATION | 2592 | International PWD Day celebrations (3rd December) | International PWD Day celebrations (3rd December) | To promote awareness and inclusion of persons with disabilities. | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 400000 | 400000 |  | CGN | N/A | N/A | N/A |  |  | 400000 |  |  | Complete | 100%
EDUCATION | 2593 | Provision of PWDs assisitive devices and Sunscreen lotion for persons with Albinism | Provision of PWDs assisitive devices and Sunscreen lotion for persons with Albinism | To improve livelihood | Provided social support | 2110805 | Countywide | Countywide |  | Human resource | Jul23 | Jun24 |  | 800000 | 800000 |  | CGN | N/A | N/A | N/A |  |  | 797000 |  |  | Not yet done
EDUCATION | 2594 | Social Support to welfare groups- 10No. (100 seat capacity tents and chairs) | Social Support to welfare groups- 10No. (100 seat capacity tents and chairs) | To improve livelihood | Provided social support | 2110805 | Kinangop | Magumu |  | Human resource | Jul23 | Jun24 |  | 2500000 | 2500000 |  | CGN | N/A | N/A | N/A |  |  | 2500000 | 2499900 |  | Procurement Done
EDUCATION | 2595 | Training and capacity building of youth, women and men groups | Training and capacity building of youth, women and men groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Magumu |  | Human resource | Jul23 | Jun24 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1200000 |  |  | Not yet done
EDUCATION | 2596 | Women and youth empowerment | Women and youth empowerment | To improve livelihood | Provided social support | 2110805 | Kinangop | Nyakio |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999600 |  |  | Complete | 100%
EDUCATION | 2597 | Men economic empowerment (Mini-tipper) | Men economic empowerment (Mini-tipper) | To improve livelihood | Provided social support | 2110805 | Kinangop | Nyakio |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete | 100%
EDUCATION | 2598 | Supply and deliver 4No. 100 seat capacity branded tents to Mukuru SHG-Koinange, Kirima Welfare Group- Kaugi, Umoja Bogani Women SHG-Bogani, Kamwene SHG-Bogani | Supply and deliver 4No. 100 seat capacity branded tents to Mukuru SHG-Koinange, Kirima Welfare Group- Kaugi, Umoja Bogani Women SHG-Bogani, Kamwene SHG-Bogani | To improve livelihood | Provided social support | 2110805 | Kinangop | Githabai |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 838750 | 1000000 |  | Complete | 100%
EDUCATION | 2599 | Supply and deliver 200No. 500 litre Capacity plastic water tanks | Supply and deliver 200No. 500 litre Capacity plastic water tanks | To improve livelihood | Provided social support | 2110805 | Kinangop | Githabai |  | Human resource | Jul23 | Jun24 |  | 1200000 | 1200000 |  | CGN | N/A | N/A | N/A |  |  | - | 1200000 |  | Complete | 100%
EDUCATION | 2600 | Social Support to welfare groups (7No. 100 seat capacity tents) | Social Support to welfare groups (7No. 100 seat capacity tents) | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100%
EDUCATION | 2601 | Blankets for the elderly | Blankets for the elderly | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - | 1989800 |  | Complete | 100%
EDUCATION | 2602 | Tanks for the elderly | Tanks for the elderly | To improve livelihood | Provided social support | 2110805 | Kinangop | Njabini |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999875 |  |  | Complete | 100%
EDUCATION | 2603 | 5No. Tents (100 Seat Capacity) and Chairs for Jerusalem, Wisdom, Muriganio and Kanyugi welfare groups | 5No. Tents (100 Seat Capacity) and Chairs for Jerusalem, Wisdom, Muriganio and Kanyugi welfare groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Engineer |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 | 2099650 |  | Complete | 100%
EDUCATION | 2604 | 2No. Tents (100 Seat Capacity) and Chairs for Manyatta and Fourteen Windows welfare groups | 2No. Tents (100 Seat Capacity) and Chairs for Manyatta and Fourteen Windows welfare groups | To improve livelihood | Provided social support | 2110805 | Kinangop | Engineer |  | Human resource | Jul23 | Jun24 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100%
EDUCATION | 2605 | Purchase of specialised plant, equipment & machinerly - public address system - Engineer | Purchase of specialised plant, equipment & machinerly - public address system - Engineer | To improve livelihood | Provided social support | 2110805 | Kinangop | Engineer |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999314 | 999560 |  | Complete | 100%
EDUCATION | 2606 | Social Support to welfare groups- tents and chairs | Social Support to welfare groups- tents and chairs | To improve livelihood | Provided social support | 2110805 | Kinangop | Murungaru |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - | 1499940 |  | Complete | 100%
EDUCATION | 2607 | Social Support to welfare groups- 4No. (100 seat capacity) | Social Support to welfare groups- 4No. (100 seat capacity) | To improve livelihood | Provided social support | 2110805 | Kipipiri | Githioro |  | Human resource | Jul23 | Jun24 |  | 700000 | 700000 |  | CGN | N/A | N/A | N/A |  |  | 699998 |  |  | Complete | 100%
EDUCATION | 2608 | Support to boda boda groups | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Kipipiri | Githioro |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999600 |  |  | Complete | 100%
EDUCATION | 2609 | Unga processing Mill - RIGA SHG - Wanjohi ward | Unga processing Mill - RIGA SHG - Wanjohi ward | To improve livelihood | Provided social support | 2110805 | Kipipiri | Wanjohi |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 999200 |  |  | Complete | 100%
EDUCATION | 2610 | Social Support welfare groups (Chairs for tents) | Social Support welfare groups (Chairs for tents) | To improve livelihood | Provided social support | 2110805 | Kipipiri | Kipipiri |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100%
EDUCATION | 2611 | Social Support to welfare groups- 6No. Tents (100 seat capacity) | Social Support to welfare groups- 6No. Tents (100 seat capacity) | To improve livelihood | Provided social support | 2110805 | Olkalou | Kaimbaga |  | Human resource | Jul23 | Jun24 |  | 600000 | 600000 |  | CGN | N/A | N/A | N/A |  |  | - | 599960 |  | Complete
EDUCATION | 2612 | Social Support to welfare groups - 10No. Tents (100 seat capacity) | Social Support to welfare groups - 10No. Tents (100 seat capacity) | To improve livelihood | Provided social support | 2110805 | Olkalou | Karau |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - | 999500 |  | Complete
EDUCATION | 2613 | Social Support to women, men and social welfare groups | Social Support to women, men and social welfare groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Rurii |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | No tents
EDUCATION | 2614 | Social Support to women, men and social welfare groups | Social Support to women, men and social welfare groups | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine |  | Human resource | Jul23 | Jun24 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999416 |  |  | Complete | 100%
EDUCATION | 2615 | Social Support to women groups - Mirangine | Social Support to women groups - Mirangine | To improve livelihood | Provided social support | 2110805 | Olkalou | Mirangine |  | Human resource | Jul23 | Jun24 |  | 1000000 | 1000000 |  | CGN | N/A | N/A | N/A |  |  | - | 999350 |  | Complete | 100%
EDUCATION | 2616 | Social support to community welfare groups | Social support to community welfare groups | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Kiriita |  | Human resource | Jul23 | Jun24 |  | 2200000 | 2200000 |  | CGN | N/A | N/A | N/A |  |  | 1676550 | 2199600 |  | Complete | 100%
EDUCATION | 2617 | Social Support to welfare groups- 4No. Tents (100 seat capacity) | Social Support to welfare groups- 4No. Tents (100 seat capacity) | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Leshau Pondo |  | Human resource | Jul23 | Jun24 |  | 700000 | 700000 |  | CGN | N/A | N/A | N/A |  |  | 699200 |  |  | Complete | 100%
EDUCATION | 2618 | Social Support to women social welfare groups | Social Support to women social welfare groups | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Shamata |  | Human resource | Jul23 | Jun24 |  | 500000 | 500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100%
EDUCATION | 2619 | Social Support to welfare groups- 10No. Tents (100 seat capacity) | Social Support to welfare groups- 10No. Tents (100 seat capacity) | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Ndaragwa Central |  | Human resource | Jul23 | Jun24 |  | 1500000 | 1500000 |  | CGN | N/A | N/A | N/A |  |  | - | 1499000 |  | Complete | 100%
EDUCATION | 2620 | Support to boda boda groups | Support to boda boda groups | To improve livelihood | Provided social support | 2110805 | Ndaragwa | Ndaragwa Central |  | Human resource | Jul23 | Jun24 |  | 2000000 | 2000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Complete | 100%
EDUCATION | 2621 | Economic Support to the PWDs across the County | Economic Support to the PWDs across the County | To improve livelihood | Provided social support | 2110805 | Countywide | County Wide |  | Human resource | Jul23 | Jun24 |  | 4000000 | 4000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Partly done
EDUCATION | 2622 | County Sanitary Towels Light industry Affirmative Action programme - Oleliondo Cottage Industry | County Sanitary Towels Light industry Affirmative Action programme - Oleliondo Cottage Industry | To empower women and girls through local production of sanitary towels. | Provided social support | 2110805 |  | - |  | Human resource | Jul23 | Jun24 |  | 4000000 | 4000000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Not yet done
EDUCATION | 2623 | Kipipiri - Construction of Kabati social hall | Kipipiri - Construction of Kabati social hall | To facilitate community engagement | Provided social support | 2110805 | Kipipiri | Kipipiri |  | Human resource | Jul23 | Jun24 |  | 3500000 | 3500000 |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Not yet done
EDUCATION | 2624 | Githinji Primary ECDE classroom and toilet | Githinji Primary ECDE classroom and toilet | To improve hygiene and sanitation and provide learning space | Improved hygiene and sanitation, and improved learning space | 3110299 | Kinangop | Magumu |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2344523 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Contractor abandoned site
EDUCATION | 2625 | Construction of Githabai ECDE toilet | Construction of Githabai ECDE toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kinangop | Githabai |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Procurement Ongoing
EDUCATION | 2626 | Construction of ECDE Toilet -Njoguini | Construction of ECDE Toilet -Njoguini | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kinangop | nyakio |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Procurement Ongoing
EDUCATION | 2627 | Construction of ECDE Toilet - Mukeu | Construction of ECDE Toilet - Mukeu | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kinangop | nyakio |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Procurement Ongoing
EDUCATION | 2628 | Construction of Kinamba ECDE class | Construction of Kinamba ECDE class | To create a condusive learning environment | Condusive learning environment | 3110299 | Kinangop | Njabini |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2629 | Construction of Bethsaida ECDE toilet | Construction of Bethsaida ECDE toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kinangop | Njabini |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2630 | Construction of Kiamweri ECDE Class and toilet | Construction of Kiamweri ECDE Class and toilet | To improve hygiene and sanitation and provide learning space | Improved hygiene and sanitation, and improved learning space | 3110299 | Kinangop | Njabini |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Procurement Ongoing
EDUCATION | 2631 | Construction of Kariahu ECDE toilet | Construction of Kariahu ECDE toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kinangop | njabini |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Procurement Ongoing
EDUCATION | 2632 | Construction of Nyakiambi ECDE Classroom | Construction of Nyakiambi ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Kinangop | Gathaara |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1467115 |  | CGN | N/A | N/A | N/A |  |  | 1467115 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2633 | Completion of Gitite ECDE Class | Completion of Gitite ECDE Class | To create a condusive learning environment | Condusive learning environment | 3110299 | Kinangop | Gathaara |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 500000 |  | CGN | N/A | N/A | N/A | [5 empty] | There were BoQ issues
EDUCATION | 2634 | Fencing of Makutano ECDE Land and construction of Class and toilet | Construction of a classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Kinangop | engineer |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | 1800000 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2635 | Construction of Mbirithi ECDE toilet | Construction of Mbirithi ECDE toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kinangop | engineer |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 675887 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2636 | Construction of Ndunyu Njeru Pry ECDE Toilet | Construction of Ndunyu Njeru Pry ECDE Toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kinangop | North Kinangop |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Contractor not responsive
EDUCATION | 2637 | Construction of Gathiriga ECDE Classroom | Construction of Gathiriga ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Kipipiri | Githioro |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1700000 |  | CGN | N/A | N/A | N/A |  |  | 1700000 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2638 | Construction of St. Peter ECDE Toilet | Construction of St. Peter ECDE Toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kipipiri | Githioro |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 700000 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2639 | Renovation of Kagondi ECDE Classroom | Renovation of Kagondi ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Kipipiri | Githioro |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 497424 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2640 | Extension of Renovation works- Mumui ECDE | Extension of Renovation works- Mumui ECDE | To create a condusive learning environment | Condusive learning environment | 3110299 | Kipipiri | Githioro |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2641 | Construction of ECDE Toilet - Mahinga | Construction of ECDE Toilet - Mahinga | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Olkalou | Kaimbaga |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Procurement Ongoing
EDUCATION | 2642 | Roofing of Gichungo ECDE clasroom | Roofing of Gichungo ECDE clasroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Olkalou | Kaimbaga |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 499647 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2643 | Construction of Gatitu ECDE Toilet | Construction of Gatitu ECDE Toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Olkalou | Rurii |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 700000 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2644 | Construction of Gatuamba ECDE Toilet | Construction of Gatuamba ECDE Toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Olkalou | Rurii |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Stalled due to Rocky ground |  |  | Stalled due to Rocky ground | 2024/25 | 6 Months | 700000 | No | Change of design to waterborne, construction of a septic tank, provision of water services and consequently more budgetary allocation
EDUCATION | 2645 | Construction of St. Thomas ECDE Classroom | Construction of St. Thomas ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Olkalou | Rurii |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1378265 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2646 | Construction of Thaba ECDE Classroom | Construction of Thaba ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Olkalou | Kanjuiri |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1498178 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2647 | Construction of Kanjuiri ECDE Classroom | Construction of Kanjuiri ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Olkalou | kanjuiri |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1499163 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2648 | Completion of Ndothua ECDE Classroom | Completion of Ndothua ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Olkalou | kanjuiri |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1000000 |  | CGN | N/A | N/A | N/A | [5 empty] | Procurement Ongoing
EDUCATION | 2649 | Construction of Kanyotu ECDE Classroom | Construction of Kanyotu ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Olkalou | mirangine |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1497376 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2650 | Construction of Matunda ECDE Toilet | Construction of Matunda ECDE Toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Olkalou | Mirangine |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 600000 |  | CGN | N/A | N/A | N/A | [5 empty] | Procurement Ongoing
EDUCATION | 2651 | Construction of Charagita Pry Sch ECDE Classroom | Construction of Charagita Pry Sch ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Oljoroorok | charagita |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A | [5 empty] | Procurement Ongoing
EDUCATION | 2652 | Construction of Classroom -Kibera ECDE | Construction of Classroom -Kibera ECDE | To create a condusive learning environment | Condusive learning environment | 3110299 | Oljoroorok | charagita |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1413041 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2653 | Ruiru ECDE Toilet | Ruiru ECDE Toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | oljoroorok | CHARAgita |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Procurement Ongoing
EDUCATION | 2654 | Renovation of ECDEs | Renovation of ECDEs | To create a condusive learning environment | Condusive learning environment | 3110299 | Oljoroorok | Gathanji |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 961066 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2655 | Mwenja ECDE toilet - County contribution | Mwenja ECDE toilet - County contribution | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Oljoroorok | Gathanji |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 240000 |  | CGN | N/A | N/A | N/A | [5 empty] | Procurement Ongoing
EDUCATION | 2656 | Construction of ECDE classroom | Construction of ECDE classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Ndaragwa | Kiriita |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1459803 |  | CGN | N/A | N/A | N/A |  |  | 1459803 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2657 | Construction of Nairobi ECDE Class | Construction of Nairobi ECDE Class | To create a condusive learning environment | Condusive learning environment | 3110299 | Ndaragwa | Kiriita |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1800000 |  | CGN | N/A | N/A | N/A | [5 empty] | Procurement Ongoing
EDUCATION | 2658 | Renovation of Kihingo ECDE Classroom | Renovation of Kihingo ECDE Classroom | To create a condusive learning environment | Condusive learning environment | 3110299 | Ndaragwa | Leshau Pondo |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 600000 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2659 | Construction of Kihingo ECDE toilet | Construction of Kihingo ECDE toilet | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Ndaragwa | Leshau Pondo |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 593245 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2660 | Tank-stand, guttering and fittings for ECDEs | Tank-stand, guttering and fittings for ECDEs | To provide water | Water availability | 3110299 | ndaragwa | Leshau Pondo |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 870000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | There were BoQ issues
EDUCATION | 2661 | Purchase of ECDE furniture for Additional Classrooms | Purchase of ECDE furniture for Additional Classrooms | To facilitate efficient learning | Efficient learning | 3111099 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1420000 |  | CGN | N/A | N/A | N/A |  |  | 1420000 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2662 | Purchase of ECDE stationery and learning materials | Purchase of ECDE stationery and learning materials | To facilitate efficient learning | Efficient learning | 2211101 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2550000 |  | CGN | N/A | N/A | N/A |  |  | 2550000 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2663 | Purchase of ECDE furniture - Gatimu Ward | Purchase of ECDE furniture - Gatimu Ward | To facilitate efficient learning | Efficient learning | 3111099 | Oljoroorok | Gatimu |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2600000 |  | CGN | N/A | N/A | N/A |  |  | 2600000 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2664 | Digitization of ECDE Curriculum | Digitization of ECDE Curriculum | To empower ECDE teachers with digital tools and training for effective curriculum delivery using EIDU. | Empowered ECDE teachers with digital tools and training | 3111001 | countrywide | countrywide |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 4998672 |  | CGN | N/A | N/A | N/A |  |  | 4998672 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2665 | Construction of Grace ECDE classroom - M/S Kinangop Vocational Training Centre 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Payment Process
EDUCATION | 2666 | Construction of Raitha ECDE classroom - M/S Miharati Vocational Training Centre 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2667 | Construction of Kiahuho ECDE classroom - M/S Mukeu Vocational Training Center 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Payment Process
EDUCATION | 2668 | Construction of Munga ECDE classroom - M/S Melangine Vocational Training Center 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2669 | Construction of Kiambaa ECDE and Toilet consruction - M/S Miharati Vocational Training Centre 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Payment Process
EDUCATION | 2670 | Construction of AC Olkalou ECDE class construction - M/S Olkalou Vocational Training Centre 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Payment Process
EDUCATION | 2671 | Construction of Ngorika Mwireri ECDE and Toilet - M/S Melangine Vocational Training Center 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2672 | Construction of Rutara ECDE Toilet - M/S Ngorika Vocational Training Center 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Payment Process
EDUCATION | 2673 | Construction of Makara ECDE classroom - M/S Melangine Vocational Training Center 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2674 | Construction of CCM Toilet mirangine ward - M/S Olkalou Vocational Training Centre 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2675 | Construction and completion of Kianjata ECDE toilet in Gatimu ward-Quality Bargains Limited FY 2022-23 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2676 | Construction of Nyandundo/Kanyotu ECDE classroom and toilet - M/S Olkalou Vocational Training Centre | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Payment Process
EDUCATION | 2677 | Huhoini Classroom and Toilet - Mirangine VTC 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Payment Process
EDUCATION | 2678 | New Nyairoko ECDE Class AND Toilet Construction - Olkaou VTC 2021/2022 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Payment Process
EDUCATION | 2679 | Construction of Ngatho ECDE classroom and Toilet Appraisal - Gathanji ward- FY2018/19- Mbisaw Enterprises Ltd | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2680 | Construction of Githinji ECDE Classroom appraisal - M/S perfect Mansion Limited - 2020/21 | Payment of the Pending bill | Payment of the Pending bill | Paid pending bill | 3110299 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2681 | Completion of Lereshwa VTC - Ladies' Hostel | Completion of Lereshwa VTC - Ladies' Hostel | To provide accomodation to students | Available accomodation for students | 3110299 | Kipipiri | Kipipiri ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2944234 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Construction is ongoing | 40%
EDUCATION | 2682 | Completion of Kanyagia VTC - Twin workshop | Completion of Kanyagia VTC - Twin workshop | To provide learning facilities | Available learning facilities | 3110299 | Ndaragwa | Ndaragwa central ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 4402195 |  | CGN | N/A | N/A | N/A |  |  | 2200000 |  |  | Ongoing | 50%
EDUCATION | 2683 | Construction of Kinangop VTC trainees Sanitation facility | Construction of Kinangop VTC trainees Sanitation facility | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kinangop | North kinangop ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1199990 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2684 | Construction of Pesi VTC trainees Sanitation facility - Shamata ward | Construction of Pesi VTC trainees Sanitation facility - Shamata ward | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Ndaragwa | Shamata ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1196153 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2685 | Construction of Miharati VTC staff Sanitation facility | Construction of Miharati VTC staff Sanitation facility | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Kipipiri | Kipipiri ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1196153 |  | CGN | N/A | N/A | N/A |  |  | 1196153 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2686 | Construction of Nandarasi VTC administration Block North Kinangop | Construction of Nandarasi VTC administration Block North Kinangop | To provide an administration block | An admin block that improves efficiency in provision of administrative services | 3110299 | Kinangop | North kinangop ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2400000 |  | CGN | N/A | N/A | N/A |  |  | 0 |  |  | Contractor abandoned site
EDUCATION | 2687 | Support for Mukeu Vocational Training Centre including support for Jua Kali Artisan Specialized Training -Nyakio | Support for Mukeu Vocational Training Centre including support for Jua Kali Artisan Specialized Training -Nyakio | To improved skills and provide certification to Jua Kali Artisans | Improved skills and provision of certification to Jua Kali Artisans | 2640499 | Kinangop | Nyakio ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete
EDUCATION | 2688 | Karau ward - Jua Kali Artisan Specialized Training | Karau ward - Jua Kali Artisan Specialized Training | To improved skills and provide certification to Jua Kali Artisans | Improved skills and provision of certification to Jua Kali Artisans | 2640499 | Olkalou | Karau ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 997920 |  |  | Complete
EDUCATION | 2689 | Renovation of Kagaa Social Hall-Karau | Renovation of Kagaa Social Hall-Karau | To facilitate community engagement | Provided social support | 2211399 | olkalou | Karau ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 484901 |  | CGN | N/A | N/A | N/A |  |  | 484900 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2690 | Completion of Gordon Cultural and mentorship centre Engineer | Completion of Gordon Cultural and mentorship centre Engineer | To provide a facility for the promotion and preservation of local culture, traditions, and heritage | Available facility for the promotion and preservation of local culture, traditions, and heritage. | 3110299 | Kinangop | Engineer ward |  | Human Resource | 2023/24 | 2025/26 |  |  | 6300000 |  | CGN | N/A | N/A | N/A |  |  | 6187694 |  |  | Construction is ongoing(phased financing) | 80% | [10 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2691 | Construction of modern toilets- Kiriita Ward | Construction of modern toilets- Kiriita Ward | To improve hygiene and sanitation | Improved hygiene and sanitation | 3110299 | Ndaragwa | Kiriita ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1498638 |  |  | Complete | [11 empty] | Yes | Implemented basic environmental safeguards
EDUCATION | 2692 | Procurement of Education Dept. Tent and Chairs | Procurement of Education Dept. Tent and Chairs | Provide tents and chairs | Tents and Chairs | 2211031 | Headquarter | Headquarter |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 267000 |  | CGN | N/A | N/A | N/A |  |  | 50600 |  |  | Ongoing
EDUCATION | 2693 | Support to boda boda groups- Purchase of 8No. motor cycles- Geta Ward | Support to boda boda groups- Purchase of 8No. motor cycles- Geta Ward | Social economic empowerment | Boda bodas provided to groups | 3110701 | Kipipiri | Geta ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 2000000 |  |  | Complete
EDUCATION | 2694 | Support for completion of Njoro Social Hall- Gathanji ward | Support for completion of Njoro Social Hall- Gathanji ward | Social economic empowerment | Supported Njoro Social Hall | 3110299 | Oljoororok | Gathanji ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete
EDUCATION | 2695 | Supply and deliver 4No. tents (100 chair capacity) and chairs for welfare groups- Gathaara Ward | Supply and deliver 4No. tents (100 chair capacity) and chairs for welfare groups- Gathaara Ward | Social economic empowerment | Tents and Chairs | 2211031 | Kinangop | Gathaara ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 960000 |  | CGN | N/A | N/A | N/A |  |  | 960000 |  |  | Complete
EDUCATION | 2696 | Supply of Complete set public address system including Generator- Gathaara Ward | Supply of Complete set public address system including Generator- Gathaara Ward | Social economic empowerment | Public Address system | 2211031 | Kinangop | Gathaara ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 977994 |  |  | Complete
EDUCATION | 2697 | Magumu ward- Supply of a complete set public address system inclusive of generator | Magumu ward- Supply of a complete set public address system inclusive of generator | Social economic empowerment | Public Address system | 2211031 | Kinangop | Magumu ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1200000 |  | CGN | N/A | N/A | N/A |  |  | 1199568 |  |  | Complete
EDUCATION | 2698 | Supply and deliver 10No. tents (100 chair capacity) and chairs - Magumu ward | Supply and deliver 10No. tents (100 chair capacity) and chairs - Magumu ward | Social economic empowerment | Tents and Chairs | 2211031 | Kinangop | Magumu ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1841000 |  | CGN | N/A | N/A | N/A |  |  | 1841000 |  |  | Complete
EDUCATION | 2699 | Training and capacity building of youth, women and men groups - Driving Licence -Magumu ward | Training and capacity building of youth, women and men groups - Driving Licence -Magumu ward | Empowerment of the youth, women and men | Trained and Capacity built youth, women and men | 2211031 | Kinangop | Magumu ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1496250 |  | CGN | N/A | N/A | N/A |  |  | 1496250 |  |  | Complete
EDUCATION | 2700 | Supply and deliver blankets for the elderly - Njabini ward | Supply and deliver blankets for the elderly - Njabini ward | Support to the elderly | Delivered blankets | 2211031 | Kinangop | Njabini ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 495000 |  |  | Complete
EDUCATION | 2701 | Water harvesting interventions- Ciondo -Engineer Ward | Water harvesting interventions- Ciondo -Engineer Ward | Facilitate water harvesting | Water harvesting interventions | 3110502 | Kinangop | Engineer ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1998000 |  |  | Complete
EDUCATION | 2702 | Women empowerment- Water harvesting-Kanyugi- Engineer | Women empowerment- Water harvesting-Kanyugi- Engineer | Women empowerment | Empowered women | 2211031 | Kinangop | Engineer ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 3537600 |  | CGN | N/A | N/A | N/A |  |  | 3537600 |  |  | Complete
EDUCATION | 2703 | Supply and deliver 4No. Tents - Githioro ward | Supply and deliver 4No. Tents - Githioro ward | Support to groups with tents | Tents and Chairs | 2211031 | Kipipiri | Githioro ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 690000 |  | CGN | N/A | N/A | N/A |  |  | 690000 |  |  | Complete
EDUCATION | 2704 | Supply and deliver Sufurias and thermos flasks- Githioro ward | Supply and deliver Sufurias and thermos flasks- Githioro ward | Support to groups | Sufurias and thermos flasks provided | 2211031 | Kipipiri | Githioro ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 300000 |  | CGN | N/A | N/A | N/A |  |  | 298500 |  |  | Complete
EDUCATION | 2705 | Supply and delivery of 1No. Poshomill and digital weighing machine (30kg electric powered)- Githioro | Supply and delivery of 1No. Poshomill and digital weighing machine (30kg electric powered)- Githioro | Economic empowerment | 1No. Poshomill and digital weighing machine (30kg electric powered) | 2211031 | Kipipiri | Githioro ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 499890 |  |  | Complete
EDUCATION | 2706 | Supply and deliver tents for welfare groups - Kipipiri ward | Supply and deliver tents for welfare groups - Kipipiri ward | Social economic empowerment | Tents and Chairs | 2211031 | Kipipiri | Kipipiri ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 660000 |  | CGN | N/A | N/A | N/A |  |  | 660000 |  |  | Complete
EDUCATION | 2707 | Supply and deliver chairs for welfare tents - Kipipiri ward | Supply and deliver chairs for welfare tents - Kipipiri ward | Social economic empowerment | Tents and Chairs | 2211031 | Kipipiri | Kipipiri ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete
EDUCATION | 2708 | Supply and deliver 500L plastic water tanks - Kipipiri ward | Supply and deliver 500L plastic water tanks - Kipipiri ward | Facilitate water storage | 500L plastic water tanks delivered | 2211031 | Kipipiri | Kipipiri ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 2000000 |  |  | Complete
EDUCATION | 2709 | Supply and deliver 1No. Tents (100 Seats capacity) and Chairs- Rurii | Supply and deliver 1No. Tents (100 Seats capacity) and Chairs- Rurii | Social economic empowerment | Tents and Chairs | 2211031 | Olkalou | Rurii ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 270000 |  | CGN | N/A | N/A | N/A |  |  | 267000 |  |  | Complete
EDUCATION | 2710 | Support to women welfare groups -Kaimbaga | Support to women welfare groups -Kaimbaga | Support to women welfare groups | Supported women welfare groups | 2211031 | Olkalou | Kaimbaga ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 298000 |  | CGN | N/A | N/A | N/A |  |  | 296250 |  |  | Complete
EDUCATION | 2711 | Support to welfare groups with 3No. Tents (100 seat capacity)- Kaimbaga | Support to welfare groups with 3No. Tents (100 seat capacity)- Kaimbaga | Support to welfare groups with 3No. Tents (100 seat capacity) | Supported welfare groups with 3No. Tents (100 seat capacity) | 2211031 | Olkalou | Kaimbaga ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 495000 |  | CGN | N/A | N/A | N/A |  |  | 495000 |  |  | Complete
EDUCATION | 2712 | Support welfare groups with 2No. Public Address System- Kaimbaga | Support welfare groups with 2No. Public Address System- Kaimbaga | Support welfare groups with 2No. Public Address System | Supported welfare groups with 2No. Public Address System | 2211031 | Olkalou | Kaimbaga ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 200000 |  | CGN | N/A | N/A | N/A |  |  | 200000 |  |  | Complete
EDUCATION | 2713 | Social support to vulnerable - Marubani group - Kaimbaga ward- Kaimbaga | Social support to vulnerable - Marubani group - Kaimbaga ward- Kaimbaga | Social support to vulnerable | Empowered Marubani group | 3111302 | Olkalou | Kaimbaga ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 200000 |  | CGN | N/A | N/A | N/A |  |  | 200000 |  |  | Complete
EDUCATION | 2714 | Support to boda boda groups with tyres, protective wear and driving licenses- Kaimbaga | Support to boda boda groups with tyres, protective wear and driving licenses- Kaimbaga | Support to boda boda groups | Supported boda boda groups | 2211031 | Olkalou | Kaimbaga ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 820000 |  | CGN | N/A | N/A | N/A |  |  | 809600 |  |  | Complete
EDUCATION | 2715 | Support welfare groups with 2No. Power Saw- Kaimbaga | Support welfare groups with 2No. Power Saw- Kaimbaga | Support welfare groups with 2No. Power Saw | Supported welfare groups with 2No. Power Saw | 2211031 | Olkalou | Kaimbaga ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 200000 |  | CGN | N/A | N/A | N/A |  |  | 200000 |  |  | Complete
EDUCATION | 2716 | Support welfare groups with sewing machines- Kaimbaga | Support welfare groups with sewing machines- Kaimbaga | Support welfare groups with sewing machines | Supported welfare groups with sewing machines | 2211031 | olkalou | Kaimbaga ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 100000 |  | CGN | N/A | N/A | N/A |  |  | 98209 |  |  | Complete
EDUCATION | 2717 | Supply and deliver tents for welfare groups - Karau Ward | Supply and deliver tents for welfare groups - Karau Ward | Supply and deliver tents for welfare groups | Empowered groups with tents and chairs | 2211031 | Olkalou | Karau ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete
EDUCATION | 2718 | Social economic support to organized groups - Rurii ward | Social economic support to organized groups - Rurii ward | Social economic support to organized groups | Empowered groups | 2211031 | Olkalou | Rurii ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 997500 |  |  | Complete
EDUCATION | 2719 | Supply and delivery of chairs - Kanjuiri ward | Supply and delivery of chairs - Kanjuiri ward | Supply and delivery of chairs | Chairs delivered | 2211031 | Olkalou | Kanjuiri ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1770000 |  | CGN | N/A | N/A | N/A |  |  | 1770000 |  |  | Complete
EDUCATION | 2720 | Procurement of 2 No. Tents Thayu Women Group - Karau ward | Procurement of 2 No. Tents Thayu Women Group - Karau ward | Support to Thayu Women Group | Tents | 2211031 | olkalou | Karau ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 400000 |  | CGN | N/A | N/A | N/A |  |  | 400000 |  |  | Complete
EDUCATION | 2721 | Supply and delivery of tents to welfare groups - | Supply and delivery of tents to welfare groups - | Supply and delivery of tents to welfare groups | Tents | 2211031 | Oljoroorok | Charagita ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1498500 |  |  | Complete
EDUCATION | 2722 | Supply and deliver 4No. incubators - Weru ward | Supply and deliver 4No. incubators - Weru ward | Economic empowerment | Empowered groups with 4 Incubators |  | Oljoroorok | Weru ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 600000 |  | CGN | N/A | N/A | N/A |  |  | 598000 |  |  | Complete
EDUCATION | 2723 | Supply and deliver 6No. tents (100 Seats capacity) for welfare groups groups - Weru ward | Supply and deliver 6No. tents (100 Seats capacity) for welfare groups groups - Weru ward | Supply and deliver 6No. tents (100 Seats capacity) for welfare groups groups | Tents and Chairs | 2211031 | Oljoroorok | Weru ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 900000 |  | CGN | N/A | N/A | N/A |  |  | 899400 |  |  | Complete
EDUCATION | 2724 | Supply and deliver tents for welfare groups- Gatimu ward | Supply and deliver tents for welfare groups- Gatimu ward | Supply and deliver tents for welfare groups | Tents | 2211031 | Oljoroorok | Gatimu ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete
EDUCATION | 2725 | Supply and delivery of additional tents and chairs- Gatimu ward | Supply and delivery of additional tents and chairs- Gatimu ward | Supply and delivery of additional tents and chairs- | Tents and Chairs | 2211031 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1400000 |  | CGN | N/A | N/A | N/A |  |  | 1399999 |  |  | Complete
EDUCATION | 2726 | Social economic support to organized groups - Kiriita ward | Social economic support to organized groups - Kiriita ward | Social economic support to organized groups | Empowered groups | 2211031 | ndaragwa | Kiriita ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1999250 |  |  | Complete
EDUCATION | 2727 | Supply and delivery of tents for welfare groups- Leshau Pondo ward | Supply and delivery of tents for welfare groups- Leshau Pondo ward | Supply and delivery of tents for welfare groups | Tents | 2211031 | ndaragwa | Leshau Pondo ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1500000 |  | CGN | N/A | N/A | N/A |  |  | 1499999 |  |  | Complete
EDUCATION | 2728 | Supply and delivery of incubators for welfare groups- Leshau Pondo ward | Supply and delivery of incubators for welfare groups- Leshau Pondo ward | Supply and delivery of incubators for welfare groups | Empowered groups with incubators | 2211031 | Ndaragwa | Leshau Pondo ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 150000 |  | CGN | N/A | N/A | N/A |  |  | 150000 |  |  | Complete
EDUCATION | 2729 | Supply and delivery of 3No. 10,000 litres plastic tanks- Leshau Pondo ward | Supply and delivery of 3No. 10,000 litres plastic tanks- Leshau Pondo ward | Supply and delivery of 3No. 10,000 litres plastic tanks | Supported groups with tanks for water storage | 2211031 | ndaragwa | Leshau Pondo ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 450000 |  | CGN | N/A | N/A | N/A |  |  | 448635 |  |  | Complete
EDUCATION | 2730 | Supply and delivery of chairs - Leshau Pondo ward | Supply and delivery of chairs - Leshau Pondo ward | Supply and delivery of chairs | Chairs delivered | 2211031 | ndaragwa | Leshau Pondo ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 400000 |  | CGN | N/A | N/A | N/A |  |  | 400000 |  |  | Complete
EDUCATION | 2731 | Support to Women welfare groups- Shamata Ward | Support to Women welfare groups- Shamata Ward | Support to Women welfare groups- Shamata Ward | Supported women welfare groups | 2211031 | ndaragwa | Shamata ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 2000000 |  | CGN | N/A | N/A | N/A |  |  | 1990019 |  |  | Complete
EDUCATION | 2732 | Supply and delivery of tents for welfare groups- Shamata Ward | Supply and delivery of tents for welfare groups- Shamata Ward | Supply and delivery of tents for welfare groups- Shamata Ward | tents delivered | 2211031 | ndaragwa | Shamata ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 700000 |  | CGN | N/A | N/A | N/A |  |  | 700000 |  |  | Complete
EDUCATION | 2733 | Purchase of uniforms for learners - Shamata ward | Purchase of uniforms for learners - Shamata ward | Purchase of uniforms for learners - Shamata ward | Uniforms delivered | 2211018 | ndaragwa | Shamata ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1601475 |  | CGN | N/A | N/A | N/A |  |  | 1601475 |  |  | Complete
EDUCATION | 2734 | Supply and delivery of Jua Kali jikos - Shamata water | Supply and delivery of Jua Kali jikos - Shamata water | Supply and delivery of Jua Kali jikos - Shamata water | Jua Kali jikos delivered | 2211031 | ndaragwa | Shamata ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 498050 |  | CGN | N/A | N/A | N/A |  |  | 498050 |  |  | Complete
EDUCATION | 2735 | 2No. Tents | 2No. Tents | Support of groups with tents | Tents delivered | 2211031 | 0 | 0 |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 300000 |  | CGN | N/A | N/A | N/A |  |  | 295000 |  |  | Complete
EDUCATION | 2736 | Support of PWDs with with foodstuff and other basic supplies | Support of PWDs with with foodstuff and other basic supplies | Support of PWDs with foodstuff and other basic supplies | Supported PWDs with foodstuff and other basic supplies | 2211015 | Countywide | Countywide |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1000000 |  | CGN | N/A | N/A | N/A |  |  | 1000000 |  |  | Complete
EDUCATION | 2737 | Support of vulnerable groups (child - headed families, the elderly, PWDs, the chronically sick, poverty stricken) with with foodstuff and other basic supplies | Support of vulnerable groups (child - headed families, the elderly, PWDs, the chronically sick, poverty stricken) with foodstuff and other basic supplies | Support of vulnerable groups (child - headed families, the elderly, PWDs, the chronically sick, poverty stricken) with foodstuff and other basic supplies | Supported vulnerable groups (child - headed families, the elderly, PWDs, the chronically sick, poverty stricken) with foodstuff and other basic supplies | 2211015 | Countywide | Countywide |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | 2000000 |  |  | Complete
EDUCATION | 2738 | Support of PWDs with income generating programs | Support of PWDs with income generating programs | Support of PWDs with income generating programs | Support of PWDs with income generating programs | 2211399 | Countywide | Countywide |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1494000 |  | CGN | N/A | N/A | N/A |  |  | 1494000 |  |  | Complete
EDUCATION | 2739 | Support of vulnerable groups (child - headed families, the elderly, the chronically sick, poverty stricken) with income generating programs across the County | Support of vulnerable groups (child - headed families, the elderly, the chronically sick, poverty stricken) with income generating programs across the County | Support of vulnerable groups (child - headed families, the elderly, the chronically sick, poverty stricken) with income generating programs across the County | Supported vulnerable groups (child - headed families, the elderly, the chronically sick, poverty stricken) with income generating programs across the County | 2211399 | Countywide | Countywide |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 3474800 |  | CGN | N/A | N/A | N/A |  |  | 3474800 |  |  | Complete
EDUCATION | 2740 | Social assistance to the vulnerable with foodstuff- Njabini | Social assistance to the vulnerable with foodstuff- Njabini | Social assistance to the vulnerable with foodstuff- Njabini | Supported vulnerable individuals with foodstuff- Njabini | 2211399 | Kinangop | Njabini ward |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 500000 |  | CGN | N/A | N/A | N/A |  |  | 500000 |  |  | Complete
EDUCATION | 2741 | Support to PWDs and terminally ill with with adult diapers and colostomy bags | Support to PWDs and terminally ill with with adult diapers and colostomy bags | Support to PWDs and terminally ill with with adult diapers and colostomy bags | Supported PWDs and terminally ill with with adult diapers and colostomy bags | 2211399 | Countywide | Countywide |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 800000 |  | CGN | N/A | N/A | N/A |  |  | 800000 |  |  | Complete
EDUCATION | 2742 | Support to PWDS- Fitting assistive devices- calipers, prosthetics, wheel chairs etc | Support to PWDS- Fitting assistive devices- calipers, prosthetics, wheel chairs etc | Support to PWDS- Fitting assistive devices- calipers, prosthetics, wheel chairs etc | Supported PWDS- Fitting assistive devices- calipers, prosthetics, wheel chairs etc | 2211399 | Countywide | Countywide |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  | 1300000 |  | CGN | N/A | N/A | N/A |  |  | 1300000 |  |  | Complete
EDUCATION | 2743 | Supply and delivery of assorted equipment to support cancer patients- Commorant Investment Limited – FY 2021/2022 | Payment of the pending bill | Payment of the pending bill | Paid pending bill | 2211031 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2744 | Social support to women groups- Mirangine - KENWIZ GLOBAL LTD- FY 2023-24 | Payment of the pending bill | Payment of the pending bill | Paid pending bill | 2211031 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
EDUCATION | 2745 | Supply and delivery of tanks- Githabai Ward FY 2023-24- tender no. 1484164-2023/2024 CHENJO HOLDINGS LIMITED | Payment of the pending bill | Payment of the pending bill | Paid pending bill | 2211031 |  |  |  | Human Resource | 2024-07-01 | 2025-06-30 |  |  |  |  | CGN | N/A | N/A | N/A |  |  | - |  |  | Paid
YOUTH | 2746 | Sports Development | Sports events(tournaments) | Sports Development | sport events | No code | Countywide | Countywide |  | Human resource | 2013-07-01 | 2014-06-30 |  | 5946420 | 5946420 | 5946420 | CGN | N/A | 5946420 | N/A | 5946420 | 100% | 5946420 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | N/A | N/A | N/A | N/A | N/A | N/A | Continuous every FY
YOUTH | 2747 | Sports Development | Purchase of Sports equipment | Sports Development | Purchased and distributed sports equipment | No code | Countywide | Countywide |  | Human resource | 2013-07-01 | 2014-06-30 |  | 5000000 | 5000000 | 5000000 | CGN | N/A | 5000000 | N/A | 4999950 | 100% | 4999950 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | N/A | N/A | N/A | N/A | N/A | N/A | The project is Continuous,implemented every fy
YOUTH | 2748 | Sports Development | Ward sport activities | Sports Development | Sports events | No code | Countywide | Countywide |  | Human resource | 2013-07-01 | 2014-06-30 |  | 7500000 | 7500000 | 7500000 | CGN | N/A | 7500000 | N/A | 7500000 | 100% | 7500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | N/A | N/A | N/A | N/A | N/A | N/A | Continuous every FY
YOUTH | 2749 | Sporting infrastructure development and upgrade | Laveling and fencing of Olkalou Stadium | Sports Development | Leveled stadium | No code | Olkalou | Kaimbaga |  | Human resource | 2013-07-01 | 2014-06-30 |  | 21000000 | 21000000 | 21000000 | CGN | N/A | 21000000 | N/A | 0 | 0% | 0 | 0 | 0 | Not sarted | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No development project was implemented in in FY 2013/2014
YOUTH | 2750 | Youth skills and capacity development | Equipping Miharati youth empowerment center | Youth empowerment | Equipped youth empowerment centre | No code | Kipipiri | Kipipiri |  | Human resource | 2013-07-01 | 2014-06-30 |  | 18140000 | 18140000 | 18140000 | CGN | N/A | 18140000 | N/A | 0 | 0% | 0 | 0 | 0 | Not sarted | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No development project was implemented in in FY 2013/2015
YOUTH | 2751 | Sporting infrastructure development and upgrade | Leveling and backfilling of ol kalou stadia | Sports Development | leveled stadium | No code | Olkalou | Kaimbaga |  | Productive | 2014-07-01 | 2015-06-30 |  | 3,000 000 | 3,000 000 | 3,000 000 | CGN | N/A | 3,000 000 | N/A | 1210762 | 40% | 1210762 | 1789238 | 1789238 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | Construction of drainage systems to avert floods,construction of sewerline for disposal of foul water and waste | Yes | Preparation of BoQ was done as per the recommendations in the report | Done to completion
YOUTH | 2752 | Sporting infrastructure development and upgrade | Leveling of Ngano Stadium | Sports Development | leveled stadium | 3110299 | Oljoro Orok | Charagita |  | Productive | 2014-07-01 | 2015-06-30 |  | 15000000 | 15000000 | 15000000 | CGN | CGN | 15000000 | N/A | 1499867 | 100% | 1499867 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2753 | Sporting infrastructure development and upgrade | Leveling of Oljoro Orok stadium | Sports Development | leveled stadium | 3110299 | Oljoro Orok | Weru |  | Productive | 2014-07-01 | 2015-06-30 |  |  |  |  | CGN | N/A |  | N/A | 1499998 | 100% | 1499998 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2754 | Sporting infrastructure development and upgrade | Construction of Dias at Oljororook stadium | Sports Development | Dias | 3110299 | Oljoro Orok | Weru |  | Productive | 2014-07-01 | 2015-06-30 |  |  |  |  | CGN | N/A |  | N/A | 1499900 | 100% | 1499900 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the dias,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2755 | Sporting infrastructure development and upgrade | Walling of Heni Stadium | Sports Development | constructed wall | 3110299 | Kinangop | Githabai |  | Productive | 2014-07-01 | 2015-06-30 |  |  |  |  | CGN | N/A |  | N/A | 1499867 | 100% | 1499867 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the wall,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2756 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and urinal at Heni stadium | Sports Development | Constructed toilet | 3110299 | Kinangop | Githabai |  | Productive | 2014-07-01 | 2015-06-30 |  |  |  |  | CGN | N/A |  | N/A | 999998 | 100% | 999998 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2757 | Sporting infrastructure development and upgrade | Leveling of Rurinja Stadium | Sports Development | leveled playground | 3110299 | Kinangop | Njabini |  | Productive | 2014-07-01 | 2015-06-30 |  |  |  |  | CGN | N/A |  | N/A | 1499342 | 100% | 1499342 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2758 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and urinal at Geta stadium | Sports Development | Constructed toilet | 3110299 | Kinangop | Geta |  | Productive | 2014-07-01 | 2015-06-30 |  |  |  |  | CGN | N/A |  | N/A | 999998 | 100% | 999998 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2759 | Sporting infrastructure development and upgrade | Construction of wall at Heni Stadium | Sports Development | Ongoing construction of wall | 3110299 | Kinangop | Githabai |  | Productive | 2014-07-01 | 2015-06-30 |  |  |  |  | CGN | N/A |  | N/A | 1499342 | 100% | 1499342 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the wall,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2760 | Sporting infrastructure development and upgrade | Leveling of turasha playground | Sports Development | leveled playground | 3110299 | Kipipiri | Githioro |  | Productive | 2014-07-01 | 2015-06-30 |  |  |  |  | CGN | N/A |  | N/A | 499900 | 100% | 499900 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2761 | Sporting infrastructure development and upgrade | Construction of Murram running track at Olkalou stadium | Sports Development | Constructed running track | 3110299 | Olkalou | Kaimbaga |  | Productive | 2014-07-01 | 2015-06-30 |  |  |  |  | CGN | N/A |  | N/A | 2988009 | 100% | 2988009 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the running track,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | Construction of drainage systems to avert floods,construction of sewerline for disposal of foul water and waste | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2762 | Sports Development | Sports events | Sports Development | Governors tournament events | 2211016 | Countywide | Countywide |  | Productive | 2014-07-01 | 2015-06-30 |  | 3500000 | 3500000 | 3500000 | CGN | N/A | 3500000 | N/A | 3500000 | 100% | 3500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2763 | Sports Development | Purchase and distribution of Sports equipment | Sports Development | purchased a nd distributed Sports equipment and uniform | 2211016 | Countywide | Countywide |  | Productive | 2014-07-01 | 2015-06-30 |  | 195000 | 195000 | 195000 | CGN | N/A | 195000 | N/A | 195000 | 100% | 195000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2764 | Youth skills and capacity development | Training of Youth on driving | Youth empowerment | Youth training forums | 3110504 | Oljoro Orok | Weru |  | Productive | 2015-07-01 | 2016-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2765 | Sporting infrastructure development and upgrade | Construction of perimeter stone wall at Olkalou Stadium | Sports Development | Upgrade of Olkalou stadium | 3110504 | Olkalou | Kaimbaga |  | Productive | 2015-07-01 | 2016-06-30 |  | 24000000 | 24000000 | 24000000 | CGN | N/A | 24000000 | N/A | 28609297.7 | 100% | 28609297.7 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the wall,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | Construction of drainage systems to avert floods;construction of sewerline for disposal of foul water and waste;Construction of stable base in unsuitable soils | Yes | Preparation of BoQ was done as per the recommendations in the report | Done to completion
YOUTH | 2766 | Youth skills and capacity development | Training of Youth on driving | Youth empowerment | Youth training forums | 3110504 | Kinangop | N.Kinangop |  | Productive | 2015-07-01 | 2016-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2767 | Youth livelihood support | Procurement and distribution of Car wash machine | Youth empowerment | Procured and distributed Car wash machine | 3110504 | Kinangop | N.Kinangop |  | Productive | 2015-07-01 | 2016-06-30 |  | 150000 | 150000 | 150000 | CGN | N/A | 150000 | N/A | 150000 | 100% | 150000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2768 | Sporting infrastructure development and upgrade | Construction of wall at Rurinja Stadium | Sports Development | Constructed wall | 3110299 | Kinangop | Njabini |  | Productive | 2015-07-01 | 2016-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1999200 | 100% | 1999200 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the wall,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2769 | Sporting infrastructure development and upgrade | Construction of Dias at Rurinja Stadium | Sports Development | Constructed Dias | 3110299 | Kinangop | Njabini |  | Productive | 2015-07-01 | 2016-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499990 | 100% | 1499990 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the Dias,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2770 | Sporting infrastructure development and upgrade | Construction of Dias at Engineer stadium | Sports Development | Constructed Dias | 3110299 | Kinangop | Gathaara |  | Productive | 2015-07-01 | 2016-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499867 | 100% | 1499867 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the Dias,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2771 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and urinal at Heni stadium | Sports Development | Constructed toilet | 3110299 | Kinangop | Githabai |  | Productive | 2015-07-01 | 2016-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999458 | 100% | 999458 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2772 | Sporting infrastructure development and upgrade | Construction of wall at Heni Stadium | Sports Development | Constructed wall to completion | 3110299 | Kinangop | Githabai |  | Productive | 2015-07-01 | 2016-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499500 | 100% | 1499500 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the wall,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2773 | Sporting infrastructure development and upgrade | Leveling and erection of goal posts at Tumaini playground | Sports Development | Leveled stadium and erected goal posts | 3110299 | Olkalou | Kanjuiri |  | Productive | 2015-07-01 | 2016-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 499990 | 100% | 499990 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Vandalism of goal posts | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | No risks identified | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2774 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and urinal at Githabai/ Karangatha playground | Sports Development | Constructed toilet | 3110299 | Kinangop | Githabai |  | Productive | 2015-07-01 | 2016-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 835896 | 100% | 999458 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2775 | Sporting infrastructure development and upgrade | Leveling of Mutanga playground-Ndaragwa central | Sports Development | Leveled stadium | 3110299 | Ndaragwa | Kiriita |  | Productive | 2015-07-01 | 2016-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499800 | 100% | 1499800 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2776 | Sporting infrastructure development and upgrade | Grading of Ndemi Stadium | Sports Development | leveled stadium | 3110504 | Kipipiri | Wanjohi |  | Productive | 2015-07-01 | 2016-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 499988 | 100% | 499988 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | yes | No risks identified | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2777 | Sports Development | Other events KYSA games | Promotion of sports participation and competitiveness. | KYSA game events | No code | Countywide | Countywide |  | Productive | 2016-07-01 | 2017-06-30 |  | 7000000 | 7000000 | 7000000 | CGN | N/A | 7000000 | N/A | 7000000 | 100% | 7000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2778 | Sports Development | Other events (cross country games | Promotion of sports participation and competitiveness. | Cross Country games | No code | Countywide | Countywide |  | Productive | 2016-07-01 | 2017-06-30 |  | 1200000 | 1200000 | 1200000 | CGN | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2779 | Sports Development | Other events(beyond zero) | Promotion of sports participation and competitiveness. | Beyond Zero Marathon event | No code | Countywide | Countywide |  | Productive | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2780 | Sports Development | Other events(track and field events) | Promotion of sports participation and competitiveness. | Track and field events | No code | Countywide | Countywide |  | Productive | 2016-07-01 | 2017-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2781 | Sports Development | Promotion of sports in Gathanji | Promotion of sports participation and competitiveness. | Gathanji ward Sport Events | No code | Oljoro Orok | Gathanji |  | Productive | 2016-07-01 | 2017-06-30 |  | 1350000 | 1350000 | 1350000 | CGN | N/A | 1350000 | N/A | 1350000 | 100% | 1350000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2782 | Sports Development | Other events(lake olbolosat marathon) | Promotion of sports participation and competitiveness. | Lake Olbolossat Marathon event | No code | Countywide | Countywide |  | Productive | 2016-07-01 | 2017-06-30 |  | 270000 | 270000 | 270000 | CGN | N/A | 270000 | N/A | 270000 | 100% | 270000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2783 | Talent development | Other events(talent search development) | Talent search, nurturing and promotion | Talent search events | No code | Countywide | Countywide |  | Productive | 2016-07-01 | 2017-06-30 |  | 2700000 | 2700000 | 2700000 | CGN | N/A | 2700000 | N/A | 2700000 | 100% | 2700000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low turn out of Artists | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2784 | Sporting infrastructure development and upgrade | Construction Of Vip Dias at Olkalou Stadium | Sports Development | VIP dias | No code | Olkalou | Kaimbaga |  | Productive | 2016-07-01 | 2017-06-30 |  | 96000000 | 51000000 | 51000000 | CGN | N/A | 51000000 | N/A | 48068880.24 | 94.25% | 48068880.24 | 0 | 2931119.76 | Stalled | 80% | 80% | Inadequate budgetary allocation | 2019/2020 | 4months | 35000000 | No | Complete | financial-Wearing out of the Dias,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | Construction of drainage systems to avert floods;construction of sewerline for disposal of foul water and waste;Construction of stable base | Yes | Preparation of BoQ was done as per the recommendations in the report | There is a proposal for Completion of the project by Department of Defence
YOUTH | 2785 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and urinal at Oljoro orok stadium | Sports Development | Constructed toilet | No code | Oljoro Orok | Weru |  | Productive | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999908 | 100% | 999908 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2786 | Sporting infrastructure development and upgrade | Fencing of Mutanga stadium | Sports Development | Constructed fence | No code | Ndaragwa | Kiriita |  | Productive | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499998 | 100% | 1499998 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the fence,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2787 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and urinal at kasuku playground | Sports Development | Constructed toilet | No code | Oljoro Orok | Weru |  | Productive | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 900400 | 100% | 900400 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2788 | Sporting infrastructure development and upgrade | Construction of Ndunyu Njeru Stadium Walling And Gate | Sports Development | gate and fencing | No code | Kinangop | North Kinangop |  | Productive | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1497670 | 100% | 1497670 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the wall,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2789 | Sporting infrastructure development and upgrade | Levelling Of Kianjata Stadium | Sports Development | leveled stadium | No code | Oljoro Orok | Gatimu |  | Productive | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499430 | 100% | 1499430 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2790 | Sporting infrastructure development and upgrade | Construction of Dias at Ngano stadium | Sports Development | Constructed Dias | No code | Oljoro Orok | Charagita |  | Productive | 2016-07-01 | 2017-06-30 |  | 4000000 | 4000000 | 4000000 | CGN | N/A | 4000000 | N/A | 1227413.8 | 30.69% | 1227413.8 | 0 | 2772586.2 | Stalled | 40% | 40% | contract terminated on contractors desertion due to increased cost of materials | 2021/2022 | 10months | 2772586.2 | No | Complete | Financial-Wearing out of the Dias structure and materials | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Project Stalled
YOUTH | 2791 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and urinal at Ngano stadium | Sports Development | Constructed toilet | No code | Oljoro Orok | Charagita |  | Productive | 2016-07-01 | 2017-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 996300 | 100% | 996300 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2792 | Sporting infrastructure development and upgrade | Fencing of Shamata stadium with concrete post and chainlink | Sports Development | Constructed fence | No code | Ndaragwa | Shamata |  | Productive | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499435 | 100% | 1499435 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the fence,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2793 | Youth livelihood support | Purchase of incubators | Youth empowerment | procured and distributed Incubators | No code | Countywide | Countywide |  | Productive | 2016-07-01 | 2017-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2794 | Youth livelihood support | Purchase of Public Address System North Kinangop | Youth empowerment | Procured and distributed Public Address system | No code | Kinangop | North Kinangop |  | Productive | 2016-07-01 | 2017-06-30 |  | 150000 | 150000 | 150000 | CGN | N/A | 150000 | N/A | 150000 | 100% | 150000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2795 | Youth livelihood support | Purchase of green houses | Youth empowerment | procured and distributed Green houses | No code | Countywide | Countywide |  | Productive | 2016-07-01 | 2017-06-30 |  | 2500000 | 2500000 | 2500000 | CGN | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2796 | Sporting infrastructure development and upgrade | Other events KYSA games | Promotion of sports participation and competitiveness. | KYSA games event | 2210807 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 11949050 | 11949050 | 11949050 | CGN | N/A | 11949050 | N/A | 11949050 | 100% | 11949050 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2797 | Sporting infrastructure development and upgrade | Other events (cross country games | Promotion of sports participation and competitiveness. | Cross Country games | 2210807 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 830000 | 830000 | 830000 | CGN | N/A | 830000 | N/A | 830000 | 100% | 830000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2798 | Sporting infrastructure development and upgrade | Other events(track and field events) | Promotion of sports participation and competitiveness. | Track and field events | 2210807 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 720950 | 720950 | 720950 | CGN | N/A | 720950 | N/A | 720950 | 100% | 720950 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2799 | Sporting infrastructure development and upgrade | Lavelling at Heni playground | Sports Development | leveled playground | No code | Kinangop | Githabai |  | Productive | 2017-07-01 | 2018-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1,890 788 | 100% | 1,890 788.00 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2800 | Sporting infrastructure development and upgrade | Fencing of Ngano Stadium with concrete posts and chainlink | Sports Development | Constructed fence and erected goal posts | No code | Oljoro Orok | Charagita |  | Productive | 2017-07-01 | 2018-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499000 | 100% | 1499000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the fence,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2801 | Sporting infrastructure development and upgrade | Fencing of Tumaini playground with concrete posts and chainlink | Sports Development | Constructed fence and erected goal posts | No code | Olkalou | Kanjuiri |  | Productive | 2017-07-01 | 2018-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 900001 | 100% | 900001 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the fence,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | yes | No risk identified | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2802 | Sporting infrastructure development and upgrade | Fencing of Ndemi playground with concrete posts and chainlink | Sports Development | Constructed fence and erected goal posts | No code | Kipipiri | Wanjohi |  | Productive | 2017-07-01 | 2018-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1498090 | 100% | 1498090 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the fence,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | yes | No risk identified | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2803 | Sporting infrastructure development and upgrade | Fencing of Kianjata playground with concrete posts and chainlink | Sports Development | Constructed fence and erected goal posts | No code | Oljoro Orok | Gatimu |  | Productive | 2017-07-01 | 2018-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1498090 | 100% | 1498090 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the fence,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2804 | Sporting infrastructure development and upgrade | Construction of 3 Door toilet and urinal at Rurii playground | Sports Development | 3 door toilet and urinal | No code | Olkalou | Rurii |  | Productive | 2017-07-01 | 2018-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 663314.25 | 0% | 663314.25 | 336685.75 | 336685.75 | stalled | 20% | 20% | collapsed due to unstable grounds | 2019/2020 | Cannot be complete | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Project stalled
YOUTH | 2805 | Sporting infrastructure development and upgrade | Construction of toilets 3 door and urinal Njabiini stadium | Sports Development | 3 door toilet and urinal | No code | Kinangop | Njabini |  | Productive | 2017-07-01 | 2018-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 860783 | 100% | 860783 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2806 | Sporting infrastructure development and upgrade | Construction of 3 Door toilet and urinal at NdunyuNjeru Stadium | Sports Development | 3 door toilet and urinal | No code | Kinangop | North Kinangop |  | Productive | 2017-07-01 | 2018-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 998566 | 100% | 998566 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2807 | Sporting infrastructure development and upgrade | erecting of metallic goal posts (KMTC, Olk poly, Shamata, Kanjuiri,ol kalou & Heni) | Sports Development | erected metallic goal posts | No code | Olkalou,Kinangop,Ndaragwa | Shamata,Githabai,kanjuiri,karau |  | Productive | 2017-07-01 | 2018-06-30 |  | 460000 | 460000 | 460000 | CGN | N/A | 460000 | N/A | 459500 | 100% | 459500 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Vandalism of goal posts | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2808 | Stadium Improvement | Other Infrastructur & Civil Works (Koinange fencing) | Sports Development | fencing | 3110504 | Kinangop | Githabai |  | Productive | 2018-07-01 | 2019-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1491876 | 100% | 1491876 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the fence,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2809 | Youth training and capacity building | Capacity development(Youth mainstreaming) | Youth empowerment | Youth training forums | 2210303 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 3500000 | 3500000 | 3500000 | CGN | N/A | 3500000 | N/A | 3500000 | 100% | 3500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of the trainees | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2810 | Talent development | talent search & support | Talent search, nurturing and promotion | Talent search events |  | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 850000 | 850000 | 850000 | CGN | N/A | 850000 | N/A | 850000 | 100% | 850000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Artists | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2811 | Youth livelihood support | Purchase of incubators | Youth empowerment | Purchased and distributed incubators | 3111002 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 3170915 | 3170915 | 3170915 | CGN | N/A | 3170915 | N/A | 3170915 | 100% | 3170915 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2812 | Youth livelihood support | purchase of car wash machines | Youth empowerment | Purchased and distributed car wash machines | 3111002 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 2500000 | 2500000 | 2500000 | CGN | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2813 | Youth livelihood support | purchase of salon equipment | Youth empowerment | Purchased and distributed salon equipment | 3111002 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 2500000 | 2500000 | 2500000 | CGN | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2814 | Youth livelihood support | purchase of welding machines | Youth empowerment | Peurchased and distributed welding machines | 3111002 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 2500000 | 2500000 | 2500000 | CGN | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2815 | Youth livelihood support | concrete mixers | Youth empowerment | Purchased and distributed concrete mixers | 3111002 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 2500000 | 2500000 | 2500000 | CGN | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2816 | Youth livelihood support | sewing machines | Youth empowerment | Purchased and distributed sewing machines | 3111002 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 2500000 | 2500000 | 2500000 | CGN | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2817 | Youth livelihood support | Purchase of green houses | Youth empowerment | Purchased and distributed green houses | 3111002 | Countywide | Countywide |  | Productive | 2017-07-01 | 2018-06-30 |  | 3500000 | 3500000 | 3500000 | CGN | N/A | 3500000 | N/A | 3500000 | 100% | 3500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2818 | Sports Development | KYSA games | Promotion of sports participation and competitiveness. | KYSA game events | 2211399 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 8871200 | 8871200 | 8871200 | CGN | N/A | 8871200 | N/A | 8871200 | 100% | 8871200 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2819 | Sports Development | cross country games | Promotion of sports participation and competitiveness. | Cross Country games | 2211399 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2820 | Sports Development | track and field events | Promotion of sports participation and competitiveness. | Track and field events | 2211399 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2821 | Sports Development | FKF Football League | Promotion of sports participation and competitiveness. | Participation in FKF events | 2211399 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 2500000 | 2500000 | 2500000 | CGN | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2822 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and Urinal at Mutanga Stadium | Sports Development | Constructed 3 door toilet | 3110504 | Ndaragwa | Kiriita |  | Productive | 2018-07-01 | 2019-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 998400 | 100% | 998400 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2823 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and Urinal at Tumaini playground | Sports Development | Constructed 3 door toilet | 3110504 | Olkalou | Kanjuiri |  | Productive | 2018-07-01 | 2019-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 900459 | 100% | 900459 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | yes | No risk identified | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2824 | Sporting infrastructure development and upgrade | Laveling in Mirangine ward stadium | Sports Development | leveled stadium | 3110504 | Ol'kalou | Mirangine |  | Productive | 2018-07-01 | 2019-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499787 | 100% | 1499787 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2825 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and Urinal at Ndemi playground | Sports Development | Constructed 3 door toilet | 3110504 | Kipipiri | Wanjohi |  | Productive | 2018-07-01 | 2019-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999456 | 100% | 999456 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | yes | No risk identified | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2826 | Sporting infrastructure development and upgrade | Fencing and gate installation in Rurii Playing Ground | Sports Development | Fencing and gate installation | 3110504 | Olkalou | Rurii |  | Productive | 2018-07-01 | 2019-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 726491 | 72.65% | 726491 | 0 | 273509 | Stalled | 80% | 80% | contractor deserted site | 2018/19 | 6months | 500000 | No | Complete | financial-Wearing out of the fence,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Project stalled
YOUTH | 2827 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and Urinal at koinange Stadium | Sports Development | Constructed 3 door toilet | 3110504 | Kinangop | Githabai |  | Productive | 2018-07-01 | 2019-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 998400 | 100% | 998400 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2828 | Sporting infrastructure development and upgrade | Lavelling at Kanyagia playground | Sports Development | leveled playground | 3110504 | Ndaragwa | Ndaragwa Central |  | Productive | 2018-07-01 | 2019-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 946200 | 47.31% | 946200 | 0 | 1053800 | Stalled | 50% | 50% | contractor deserted site | 2018/19 | 4months | 3000000 | No | Complete | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Project stalled
YOUTH | 2829 | Stadium Improvement | Lavelling of Gathaara playground | Sports Development | Leveling of Stadium | 3110504 | Kinangop | Gathaara |  | Productive | 2018-07-01 | 2019-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1496783 | 100% | 1496783 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2830 | Stadium Improvement | Fencing of playing ground(kanjuiri) | Sports Development | Fencing | 3110504 | olkalou | Kanjuiri |  | Productive | 2018-07-01 | 2019-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499462 | 100% | 1499462 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the fence,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | yes | No risk identified | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2831 | Youth Support | Gender Mainstreaming(Youth Company registration) | Youth empowerment | Registration of companies | 2210714 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2832 | Youth training and capacity building | Youth Capacity building and development | Youth empowerment | Training and capacity building forums | 2210799 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 1350000 | 1350000 | 1350000 | CGN | N/A | 1350000 | N/A | 1350000 | 100% | 1350000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2833 | Youth livelihood support | Purchase of Specialised Plant, Equipment & Machines - Youth Groups | Youth empowerment | procured and distributed youth equipment | 3111120 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 5000000 | 5000000 | 5000000 | CGN | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2834 | Youth livelihood support | Purchase and Installation of greenhouses | Youth empowerment | Installed greenhouses | 3111103 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2835 | Youth Support | Development of Youth One-Stop Empowerment Centres | Youth empowerment | Equipping of Youth empowerm ent Centres | 3110202 | Olkalou,Kipipiri,Kinangop | Kipipiri,kaimbaga,Njabini |  | Productive | 2018-07-01 | 2019-06-30 |  | 10000000 | 10000000 | 10000000 | CGN | N/A | 10000000 | N/A | 10000000 | 100% | 10000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Vandalism of equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2836 | Youth livelihood support | Purchase of Assorted equipments for Youth groups - All Wards | Youth empowerment | procured and distributed youth equipment | 3112299 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 11000000 | 11000000 | 11000000 | CGN | N/A | 11000000 | N/A | 11000000 | 100% | 11000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2837 | Youth livelihood support | Purchase of Assorted equipments for Youth groups (Geta) | Youth empowerment | procured and distributed youth equipment | 3112299 | Kipipiri | Geta |  | Productive | 2018-07-01 | 2019-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2838 | Youth livelihood support | Purchase of Assorted equipments for Youth groups (Nyakio) | Youth empowerment | procured and distributed youth equipment | 3112299 | Kinangop | Nyakio |  | Productive | 2018-07-01 | 2019-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2839 | Talent Identification and development | Talent Indentification and Development Events | Talent search, nurturing and promotion | Talent search activities | 2211399 | Countywide | Countywide |  | Productive | 2018-07-01 | 2019-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Finanial-Low turn out of Artists | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2840 | Talent development | Development of Production Studio-Kaimbaga | Talent search, nurturing and promotion | Equipping of Production studio | 3110202 | Olkalou | Kaimbaga |  | Productive | 2018-07-01 | 2019-06-30 |  | 5000000 | 5000000 | 5000000 | CGN | N/A | 5000000 | N/A | 4449892 | 100% | 4449892 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Vandalism of studio equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2841 | Sports Development | KYSA games | Promotion of sports participation and competitiveness. | KYSA games events | 2211399 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 8871200 | 8871200 | 8871200 | CGN | N/A | 8871200 | N/A | 8871200 | 100% | 8871200 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2842 | Sports Development | cross country games | Promotion of sports participation and competitiveness. | Cross Country games | 2211399 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1400000 | 1400000 | 1400000 | CGN | N/A | 1400000 | N/A | 1400000 | 100% | 1400000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2843 | Sports Development | track and field events | Promotion of sports participation and competitiveness. | track and field events | 2211399 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 400000 | 400000 | 400000 | CGN | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2844 | Sports Development | County Football Team | Promotion of sports participation and competitiveness. | participation in football tournaments | 2211399 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2845 | Sports Development | Other championship (Darts, Wrestling,Tae kwodo and Pool) | Promotion of sports participation and competitiveness. | indoor games tournaments | 2211399 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 400000 | 400000 | 400000 | CGN | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2846 | Sporting infrastructure development and upgrade | Construction of sewer line,septic tank and high and low water tank | Sports Development | Constructed sewerline,installed setic tank,Installed high and low water tank | 3110504 | Olkalou | Kaimbaga |  | Productive | 2019-07-01 | 2020-06-30 |  | 14000000 | 14000000 | 14000000 | CGN | N/A | 14000000 | N/A | 10988890 | 78.49% | 10988890 | 0 | 3011110 | Low level tank Stalled | 95% | 95% | Increased cost of steel | 2022/2023 | 12months | 3000000 | No | Complete | financial-Wearing out of the tanks and sewer line,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | Construction of drainage systems to avert floods;construction of sewerline for disposal of foul water and waste;Construction of stable base | Yes | Preparation of BoQ was done as per the recommendations in the report | There is a proposal for Completion of the project by Department of Defence
YOUTH | 2847 | Sporting infrastructure development and upgrade | Other infrastructure and civil works (Mirangine levelling) | Sports Development | leveled playground | 3110504 | Olkalou | Mirangine |  | Productive | 2019-07-01 | 2020-06-30 |  | 3000000 | 3000000 | 3000000 | CGN | N/A | 3000000 | N/A | 956188 | 31.87% | 956188 | 2043812 | 2043812 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2848 | Youth Support | Youth Company registration | Youth empowerment | Registered youth companies | 2210714 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2849 | Youth training and capacity building | Youth Capacity building and development | Youth empowerment | Youth training and capacity development forums | 2210799 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 6000000 | 6000000 | 6000000 | CGN | N/A | 6000000 | N/A | 6000000 | 100% | 6000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2850 | Youth Support | Purchase of Specialised Plant, Equipment & Machines - (Knitting Machine and others)Youth Groups | Youth empowerment | Procured and distributed machines | 3111120 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2851 | Youth Support | Purchase of Specialised Plant, Equipment & Machines - (Welding machine and others)Youth Groups | Youth empowerment | Procured and distributed machines | 3111120 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2852 | Youth Support | Purchase of Specialised Plant, Equipment & Machines (Chaff Cutter,Ballast crusher and others) - Youth Groups | Youth empowerment | Procured and distributed machines | 3111120 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2853 | Youth Support | Support to youth groups (equiment, tools and seeds) Murungaru | Youth empowerment | Procured and distributed equipment,tools and seeds | 3111120 | Kinangop | Murungaru |  | Productive | 2019-07-01 | 2020-06-30 |  | 1400000 | 1400000 | 1400000 | CGN | N/A | 1400000 | N/A | 1400000 | 100% | 1400000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2854 | Youth Support | Purchase of Specialised Plant, Equipment and Machines (chaff cutters and others) Youth Groups | Youth empowerment | procured and distributed equipment and machine | 3111120 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2855 | Youth Support | Purchase of Specialised Plant, Equipment and Machines (Block, brick and concrete machine) Youth Groups | Youth empowerment | procured and distributed equipment and machine | 3111120 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2856 | Youth Support | Purchase of Specialised Plant, Equipment and Machines (storage) | Youth empowerment | procured and distributed equipment and machine | 3111120 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 450000 | 450000 | 450000 | CGN | N/A | 450000 | N/A | 450000 | 100% | 450000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2857 | Youth Support | Purchase of Specialised Plant, Equipment and Machines (Posho Mill and Catering Equipment and others) Youth Groups | Youth empowerment | procured and distributed equipment and machine | 3111120 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2858 | Youth Support | Purchase of equipment to the youth- Ndaragwa Central | Youth empowerment | procured and distributed equipment and machine | 3111120 | Ndaragwa | Ndaragwa Central |  | Productive | 2019-07-01 | 2020-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2859 | Youth Support | Purchase of Specialised Plant, Equipment and Machines (blast crusher and others) Youth Groups | Youth empowerment | procured and distributed equipment and machine | 3111120 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2860 | Youth Support | Purchase of Specialised Plant, Equipment & Machines (Block and brick and concreate machine and others) - Youth Groups | Youth empowerment | procured and distributed equipment and machine | 3111120 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2861 | Youth Support | Development of Youth One-Stop Empowerment Centres | Youth empowerment | Equipping of Youth Centres | 3110202 |  |  |  | Productive | 2019-07-01 | 2020-06-30 |  | 350000 | 350000 | 350000 | CGN | N/A | 350000 | N/A | 348200 | 100% | 348200 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Vandalism of Equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2862 | Youth Support | Installation of greenhouses for Youth Groups | Youth empowerment | Installed greenhouses | 3110202 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1998504 | 100% | 1998504 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2863 | Arts development | Talent search and identification | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2019-07-01 | 2020-06-30 |  | 1050000 | 1050000 | 1050000 | CGN | N/A | 1050000 | N/A | 1050000 | 100% | 1050000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Artists | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2864 | Sports developm ent | Purchase of Uniforms and Clothing - Sportswear for Trainees) | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2865 | Sports developm ent | purchase of Specialised Materials-Sports Equipments | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2866 | Sports developm ent | Purchase of uniforms and other sport equipment- Nabini Ward | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | Kinangop | Njabini |  | Productive | 2020-07-01 | 2021-06-30 |  | 350000 | 350000 | 350000 | CGN | N/A | 350000 | N/A | 350000 | 100% | 350000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2867 | Sports developm ent | Purchase of uniforms and other sport equipment- Karau Ward | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | Olkalou | Karau |  | Productive | 2020-07-01 | 2021-06-30 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2868 | Sports developm ent | Purchase of uniforms and other sport equipment- Ndaragwa Central | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | Ndaragwa | Ndaragwa Central |  | Productive | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2869 | Sports developm ent | Purchase of uniforms and other sport equipment- Kanjuiri Ward | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | olkalou | Kanjuiri |  | Productive | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 350000 | 100% | 350000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2870 | Sports developm ent | Purchase of uniforms and other sport equipment- Charagita Ward | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | Oljoro Orok | Charagita |  | Productive | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 300000 | 100% | 300000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2871 | Sports developm ent | Purchase of uniforms and other sport equipment- Githioro Ward | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | Kipipiri | Githioro |  | Productive | 2020-07-01 | 2021-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2872 | Sports developm ent | Purchase of uniforms and other sport equipment-Mirangine | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | olkalou | Mirangine |  | Productive | 2020-07-01 | 2021-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2873 | Sports developm ent | Purchase of uniforms and other sport equipment- Rurii | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | olkalou | rurii |  | Productive | 2020-07-01 | 2021-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2874 | Sports developm ent | Purchase of uniforms and other sport equipment- Leshau PondoWard | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | Ndaragwa | leshau pondo |  | Productive | 2020-07-01 | 2021-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2875 | Sports developm ent | Purchase of uniforms and other sport equipment- Gathanji | Sports Development | Purchased and distributed sports equipment and uniform | 2211031 | Oljoro Orok | Gathanji |  | Productive | 2020-07-01 | 2021-06-30 |  | 540000 | 540000 | 540000 | CGN | N/A | 540000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2876 | Sports developm ent | KYSA games | Promotion of sports participation and competitiveness. | KYSA game events | 2211399 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 6500000 | 6500000 | 6500000 | CGN | N/A | 6500000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2877 | Sports developm ent | cross country games | Promotion of sports participation and competitiveness. | cross country games | 2211399 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2878 | Sports developm ent | track and field events | Promotion of sports participation and competitiveness. | track and field events | 2211399 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 540000 | 100% | 540000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2879 | Sports developm ent | County Football Team | Promotion of sports participation and competitiveness. | participation in football tournaments | 2211399 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2880 | Sports developm ent | Other championship (Darts, Wrestling,Tae kwodo and Pool) | Promotion of sports participation and competitiveness. | Participation in championship | 2211399 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out of Athletes | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2881 | Sporting infrastructure development and upgrade | Construction of football pitch,water drainage system,watering system and planting of grass at Olkalou stadium | Sports Development | Constructed Football pitch,water drainage system,watering system and planted grass | 3110504 | Olkalou | Kaimbaga |  | Productive | 2020-07-01 | 2021-06-30 |  | 34000000 | 34000000 | 34000000 | CGN | N/A | 34000000 | N/A | 38000000 | 100% | 38000000 | 0 | 0 | Stalled | 80% | 80% | Delays in installation of water tank | 2021/2022 | 3months | 5000000 | No | Complete | financial-Wearing out of the drainage and watering systems,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | Construction of drainage systems to avert floods;construction of sewerline for disposal of foul water and waste | Yes | Preparation of BoQ was done as per the recommendations in the report | There is a proposal for Completion of the project by the Department of Defence
YOUTH | 2882 | Sporting infrastructure development and upgrade | Leveling of Ndemi playground | Sports Development | leveled playground | 3110504 | Kipipiri | Wanjohi |  | Productive | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999479 | 100% | 999479 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | No risks identified | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2883 | Sporting infrastructure development and upgrade | Murungaru- Levelling of Murungaru stadium | Sports Development | leveled stadium | 3110504 | Kinangop | Murungaru |  | Productive | 2021-07-01 | 2022-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499735 | 100% | 1499735 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2884 | Youth Support | Youth Company registration and training | Youth empowerment | Registered youth companies | 2210714 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 400000 | 400000 | 400000 | CGN | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2885 | Youth Support | Youth Capacity building and development | Youth empowerment | Youth train ing forums | 2210799 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2886 | Youth Support | Purchase of Specialised Plant, Equipment & Machines- Ndaragwa Central | Youth empowerment | procured and distributed youth equipment | 3111120 | Ndaragwa | Ndaragwa Central |  | Productive | 2020-07-01 | 2021-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2887 | Youth Support | Purchase of Specialised Plant, Equipment & Machines- Ndaragwa Central (Kanyagia) | Youth empowerment | procured and distributed youth equipment | 3111120 | Ndaragwa | Ndaragwa Central |  | Productive | 2020-07-01 | 2021-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2888 | Youth Support | Purchase of Specialised Plant, Equipment & Machines- Rurii | Youth empowerment | procured and distributed youth equipment | 3111120 | Olkalou | rurii |  | Productive | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2889 | Youth Support | Purchase of Specialised Plant, Equipment & Machines- North Kinangop | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | N.Kinangop |  | Productive | 2020-07-01 | 2021-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2890 | Youth Support | Purchase of Youth Equipment, Tools, Machines & certified seeds -Shamata | Youth empowerment | procured and distributed youth equipment | 3111120 | Ndaragwa | Shamata |  | Productive | 2020-07-01 | 2021-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2891 | Youth Support | Kiriita Youth Empowerment Centre- Equipment | Youth empowerment | Equipping of Kiriita Youth equipment centre | 3111120 | Ndaragwa | Kiriita |  | Productive | 2020-07-01 | 2021-06-30 |  | 3000000 | 3000000 | 3000000 | CGN | N/A | 3000000 | N/A | 2999799 | 100% | 2999799 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Vandalism of Equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2892 | Youth Support | Githioro- Support to Youth -Turasha Boda Boda (MotorBike Spare Part) | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Githioro |  | Productive | 2020-07-01 | 2021-06-30 |  | 260000 | 260000 | 260000 | CGN | N/A | 260000 | N/A | 260000 | 100% | 260000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No risk | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2893 | Youth Support | Purchase of Specialised Plant, Equipment & Machines -(Carwash machines, incubators, Posho mill, Selection Hauler, Saloon and Barber)Leshau Pondo Ward | Youth empowerment | procured and distributed youth equipment | 3111120 | Ndaragwa | leshau pondo |  | Productive | 2020-07-01 | 2021-06-30 |  | 900000 | 900000 | 900000 | CGN | N/A | 900000 | N/A | 900000 | 100% | 900000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2894 | Youth Support | Purchase of Specialised Plant, Equipment & Machines & Certified seeds -Geta Ward | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Geta |  | Productive | 2020-07-01 | 2021-06-30 |  | 1400000 | 1400000 | 1400000 | CGN | N/A | 1400000 | N/A | 1400000 | 100% | 1400000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2895 | Youth Support | Purchase of Specialised Plant, Equipment & Machines & -Kipipiri Ward | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Kipipiri |  | Productive | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2896 | Youth Support | Purchase of Youth Equipment, Tools, Machines & certified seeds -Lower Murungaru | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Murungaru |  | Productive | 2020-07-01 | 2021-06-30 |  | 3000000 | 3000000 | 3000000 | CGN | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2897 | Youth Support | Purchase of Youth Equipment, Tools, Machines & certified seeds -Upper Murungaru | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Murungaru |  | Productive | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2898 | Youth Support | Purchase of Equipment & Machines -Karau | Youth empowerment | procured and distributed youth equipment | 3111120 | Olkalou | Karau |  | Productive | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2899 | Youth Support | Purchase of Specialised Plant, Equipment & Machines - Charagita | Youth empowerment | procured and distributed youth equipment | 3111120 | Oljoro Orok | Charagita |  | Productive | 2020-07-01 | 2021-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2900 | Youth Support | Purchase of Specialised Plant, Equipment & Machines (Posho mill and other) - Wanjohi Ward Youth Groups | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Wanjohi |  | Productive | 2020-07-01 | 2021-06-30 |  | 1200000 | 1200000 | 1200000 | CGN | N/A | 1200000 | N/A | 1199949 | 100% | 1199949 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2901 | Youth Support | Githabai- 3No. Greenhouses | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Githabai |  | Productive | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2902 | Youth Support | Installation of greenhouses for Youth Groups | Youth empowerment | Installed greenhouses | 3110202 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2903 | Youth Support | Talent search and identification | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2020-07-01 | 2021-06-30 |  | 2200000 | 2200000 | 2200000 | CGN | N/A | 2200000 | N/A | 2200000 | 100% | 2200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2904 | Youth Support | Development and Enhancement of Production Studio-Kaimbaga | Talent search, nurturing and promotion | Equipping of production studio | 3110202 | Olkalou | Karau |  | Productive | 2020-07-01 | 2021-06-30 |  | 3000000 | 3000000 | 3000000 | CGN | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Vandalism of Studio Equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2905 | Sports Development | Specialised Materials-Sports Equipments for athletees | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999999 | 100% | 999999 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2906 | Sports Development | Purchase of uniforms and other sport equipment- Magumu | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Kinangop | Magumu |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 499500 | 100% | 499500 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2907 | Sports Development | Purchase of uniforms and other sport equipment- Charagita | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Oljoro Orok | Charagita |  | Productive | 2021-07-01 | 2022-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499000 | 100% | 1499000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2908 | Sports Development | Purchase of uniforms and other sport equipment- Nyakio | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Kinangop | Nyakio |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 499800 | 100% | 499800 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2909 | Sports Development | Purchase of uniforms and other sport equipment- Weru | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Oljoro Orok | Weru |  | Productive | 2021-07-01 | 2022-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1994000 | 100% | 1994000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2910 | Sports Development | Purchase of uniforms and other sport equipment- Rurii | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Olkalou | rurii |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 448800 | 100% | 448800 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2911 | Sports Development | Purchase of uniforms and other sport equipment- Njabini | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Kinangop | Njabini |  | Productive | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999000 | 100% | 999000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2912 | Sports Development | Purchase of uniforms and other sport equipment- Engineer | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Kinangop | Engineer |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 499995 | 100% | 499995 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2913 | Sports Development | Purchase of uniforms and other sport equipment- Wanjohi | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Kipipiri | Wanjohi |  | Productive | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2914 | Sports Development | Purchase of uniforms and other sport equipment- Karau | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Olkalou | Karau |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 499950 | 100% | 499950 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2915 | Sports Development | Purchase of uniforms and other sport equipment- Kanjuiri | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Olkalou | Kanjuiri |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 499500 | 100% | 499500 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2916 | Sports Development | Purchase of uniforms and other sport equipment- Kiriita | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Ndaragwa | Kiriita |  | Productive | 2021-07-01 | 2022-06-30 |  | 1900000 | 1900000 | 1900000 | CGN | N/A | 1900000 | N/A | 1899960 | 100% | 1899960 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2917 | Sports Development | Ndarangwa Central- Supply of assorted sports equipment-Upper | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Ndaragwa | Ndaragwa Central |  | Productive | 2021-07-01 | 2022-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1998900 | 100% | 1998900 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2918 | Sports Development | Ndarangwa Central -Supply of assorted sports equipment- Lower | Sports Development | procured and distributed sports uniform and equipment | 2211018 | Ndaragwa | Ndaragwa Central |  | Productive | 2021-07-01 | 2022-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2919 | Sports Development | KYSA teams selection | Sports Development | KYSA games selection events | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 583000 | 72.88% | 583000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athletes turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2920 | Sports Development | KYSA games | Promotion of sports participation and competitiveness. | KYSA game events | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 5000000 | 5000000 | 5000000 | CGN | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athletes turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2921 | Sports Development | Governor's tournament | Promotion of sports participation and competitiveness. | Governors tournament events | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 1200000 | 1200000 | 1200000 | CGN | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athletes turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2922 | Sports Development | Cross country games | Promotion of sports participation and competitiveness. | Cross country games | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 970000 | 97% | 970000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athletes turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2923 | Sports Development | Under 20 athletics | Promotion of sports participation and competitiveness. | Under 20 athletics | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 700000 | 700000 | 700000 | CGN | N/A | 700000 | N/A | 700000 | 100% | 700000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athletes turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2924 | Sports Development | Track and field events | Promotion of sports participation and competitiveness. | Track and field events | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athletes turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2925 | Sports Development | FKF LEAGUE | Promotion of sports participation and competitiveness. | Participation in FKF events | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athletes turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2926 | Sports Development | Other championship (Darts, Wrestling,Tae kwodo and Pool) | Promotion of sports participation and competitiveness. | Participation in various discipline championship | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athletes turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2927 | Sports Development | Capacity building for sports support personnel | Sports Development | Capacity building forums | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 | N/A | 300000 | 100% | 300000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athletes turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2928 | Sporting infrastructure development and upgrade | Construction of concrete Running track with concrete at Olkalou Stadium | Sports Development | Running track | 3110504 | Olkalou | Kaimbaga |  | Productive | 2021-07-01 | 2022-06-30 |  | 14500000 | 14500000 | 14500000 | CGN | N/A | 14500000 | N/A | 2127200 | 14.67% | 2127200 | 0 | 12323800 | Stalled | 30% | 30% | Contractor deserted site | 2021/2022 | 6months | 12372800 | No | Complete | financial-Wearing out of the running track,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | Construction of drainage systems to avert floods;construction of sewerline for disposal of foul water and waste | Yes | Preparation of BoQ was done as per the recommendations in the report | There is a proposal for Completion of the project by the Department of Defence
YOUTH | 2929 | Sporting infrastructure development and upgrade | Olkalou Stadium - public toilet | Sports Development | Public toilet | 3110504 | Olkalou | Kaimbaga |  | Productive | 2021-07-01 | 2022-06-30 |  | 6000000 | 6000000 | 6000000 | CGN | N/A | 6000000 | N/A | 566810 | 9.447% | 566810 | 0 | 5433190 | Stalled | 15% | 15% | Contractor deserted site | 2021/2022 | 6months | 5433190 | No | Complete | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Yes | Construction of drainage systems to avert floods;construction of sewerline for disposal of foul water and waste | Yes | Preparation of BoQ was done as per the recommendations in the report | There is a proposal for Completion of the project by the Department of Defence
YOUTH | 2930 | Sporting infrastructure development and upgrade | Rehabilitation of Ndunyu Njeru stadium wall | Sports Development | Rehabilitation of stadium | 3110504 | Kinangop | N.Kinangop |  | Productive | 2021-07-01 | 2022-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1997119 | 100% | 1997119 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the wall,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2931 | Sporting infrastructure development and upgrade | grading of Muoroto playground | Sports Development | Graded stadium | 3110504 | Ndaragwa | Kiriita |  | Productive | 2021-07-01 | 2022-06-30 |  | 1800000 | 1800000 | 1800000 | CGN | N/A | 1800000 | N/A | 1799976 | 100% | 1799976 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2932 | Sporting infrastructure development and upgrade | leveling of Koinange playground | Sports Development | leveled stadium | 3110504 | Kinangop | Githabai |  | Productive | 2021-07-01 | 2022-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499976 | 100% | 1499976 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2933 | Sporting infrastructure development and upgrade | Construction of 3 door toilet and urinal at Wakirogo playing ground | Sports Development | Constructed toilet | 3110504 | Kipipiri | Wanjohi |  | Productive | 2019-07-01 | 2020-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999925 | 100% | 999925 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the toilet,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2934 | Sporting infrastructure development and upgrade | Shamata field dias | Sports Development | field Dias | 3110504 | Ndaragwa | Shamata |  | Productive | 2021-07-01 | 2022-06-30 |  | 3000000 | 3000000 | 3000000 | CGN | N/A | 3000000 | N/A | 2996352 | 100% | 2996352 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the Dias,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2935 | Youth Support | Youth Company registration and training | Youth empowerment | Registered youth companies | 2210714 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low youth turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2936 | Youth Support | Youth Capacity building and development | Youth empowerment | Youth training forums | 2210799 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 1100000 | 1100000 | 1100000 | CGN | N/A | 1100000 | N/A | 1100000 | 100% | 1100000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low youth turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2937 | Youth Support | Clinics for youth empowerment equipment (Business Skills training) | Youth empowerment | Youth training forums | 2210712 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low youth turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2938 | Youth Support | Purchase of Specialised Plant, Equipment & Machines- (Including greenhouses, posho mills, carwash machines, incubators, certified seeds, Selection Hauler, Saloon and Barber equipment in various wards etc) | Youth empowerment | procured and distributed youth equipment | 3111120 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1999800 | 100% | 1999800 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2939 | Youth Support | Equipping Miharati youth empowerment center | Youth empowerment | procured and distributed youth equipment | 3111120 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2940 | Youth Support | Kiriita- Support to youth groups with assorted sports equipments | Youth empowerment | procured and distributed youth equipment | 3111120 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 1900000 | 1900000 | 1900000 | CGN | N/A | 1900000 | N/A | 1899960 | 100% | 1899960 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2941 | Youth Support | Kiriita- Support to youth groups with incubators, backup generators and supply of eggs | Youth empowerment | procured and distributed youth equipment | 3111120 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 1800000 | 1800000 | 1800000 | CGN | N/A | 1800000 | N/A | 1800000 | 100% | 1800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2942 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths ( 1No. Complete set Public address system) - Njabini | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Njabini |  | Productive | 2021-07-01 | 2022-06-30 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 | N/A | 299980 | 100% | 299980 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2943 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths ( 1No. Complete set Public address system including generator) - Shamata | Youth empowerment | procured and distributed youth equipment | 3111120 | Ndaragwa | Shamata |  | Productive | 2021-07-01 | 2022-06-30 |  | 1900000 | 1900000 | 1900000 | CGN | N/A | 1900000 | N/A | 1879980 | 100% | 1879980 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2944 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths - Nyakio | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Nyakio |  | Productive | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999999 | 100% | 999999 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2945 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths - Engineer | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Engineer |  | Productive | 2021-07-01 | 2022-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 799990 | 100% | 799990 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2946 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths - Gathaara | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Gathaara |  | Productive | 2021-07-01 | 2022-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 799500 | 100% | 799500 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2947 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths - Murungaru | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Murungaru |  | Productive | 2021-07-01 | 2022-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1999999 | 100% | 1999999 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2948 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths- (2No. concrete Mixers and vibrators) Wanjohi | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Wanjohi |  | Productive | 2021-07-01 | 2022-06-30 |  | 1200000 | 1200000 | 1200000 | CGN | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2949 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery - Gatuikaini Bodaboda group (1No. public address system) Wanjohi | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Wanjohi |  | Productive | 2021-07-01 | 2022-06-30 |  | 400000 | 400000 | 400000 | CGN | N/A | 400000 | N/A | 399960 | 100% | 399960 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2950 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths ( 2 No. incubators- Wanjohi | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Wanjohi |  | Productive | 2021-07-01 | 2022-06-30 |  | 250000 | 250000 | 250000 | CGN | N/A | 250000 | N/A | 250000 | 100% | 250000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2951 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths ( 2 No. carwash machine -Muteng'uri and Jiret boda boda youth groups)- Wanjohi | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Wanjohi |  | Productive | 2021-07-01 | 2022-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2952 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths- Kipipiri | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Kipipiri |  | Productive | 2021-07-01 | 2022-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 700000 | 87.5% | 700000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2953 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths- Githioro | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Githioro |  | Productive | 2021-07-01 | 2022-06-30 |  | 400000 | 400000 | 400000 | CGN | N/A | 1000000 | N/A | 999326 | 100% | 999326 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2954 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths - Kanjuiri | Youth empowerment | procured and distributed youth equipment | 3111120 | Olkalou | Kanjuiri |  | Productive | 2021-07-01 | 2022-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2955 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths- Mirangine | Youth empowerment | procured and distributed youth equipment | 3111120 | Olkalou | Mirangine |  | Productive | 2021-07-01 | 2022-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1999850 | 100% | 1999850 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2956 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths - Charagita | Youth empowerment | procured and distributed youth equipment | 3111120 | Oljoro Orok | Charagita |  | Productive | 2021-07-01 | 2022-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 499800 | 100% | 499800 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2957 | Youth Support | Purchase of 1No. Merry go-round swing Karau | Youth empowerment | procured and distributed youth equipment | 3111120 | Olkalou | Karau |  | Productive | 2021-07-01 | 2022-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1499500 | 100% | 1499500 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No risk | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2958 | Youth Support | Purchase of (Hair Salon/Barber Shop equipment)- Karau | Youth empowerment | procured and distributed youth equipment | 3111120 | Olkalou | Karau |  | Productive | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999900 | 100% | 999900 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2959 | Youth Support | Purchase of tent -Karau | Youth empowerment | procured and distributed youth equipment | 3111120 | Olkalou | Karau |  | Productive | 2021-07-01 | 2022-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No risk | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2960 | Youth Support | County Talent Search Event | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2961 | Youth Support | Talent training and development | Talent search, nurturing and promotion | Artists training forums | 2211399 | Countywide | Countywide |  | Productive | 2021-07-01 | 2022-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2962 | Arts development | Sub-County Talent Search events | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2963 | Arts development | Talent search- Shamata ward | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 600000 | 600000 | 600000 | CGN | N/A | 600000 | N/A | 600000 | 100% | 600000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2964 | Arts development | Talent training and development | Talent search, nurturing and promotion | Talent training forums | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2965 | Sports development | Purchase of uniforms and other sport equipment for county teams | Sports Development | Purchased and distributed sports equipment and uniform | 2211016 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2966 | Sports development | Purchase of uniforms and other sport equipment- Magumu | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Kinangop | Magumu |  | Productive | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2967 | Sports development | Purchase of uniforms and other sport equipment- Kanjuiri | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Olkalou | Kanjuiri |  | Productive | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2968 | Sports development | Purchase of uniforms and other sport equipment- Kipipiri | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Kipipiri | Kipipiri |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2969 | Sports development | Purchase of uniforms and other sport equipment- Njabini | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Kingop | Njabini |  | Productive | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2970 | Sports development | Purchase of uniforms and other sport equipment- Githioro | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Kipipiri | Githioro |  | Productive | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2971 | Sports development | Purchase of uniforms and other sport equipment- Karau | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Olkalou | Karau |  | Productive | 2022-07-01 | 2023-06-30 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 | N/A | 300000 | 100% | 300000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2972 | Sports development | Purchase of uniforms and other sport equipment- Kaimbaga | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Olkalou | Kaimbaga |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2973 | Sports development | Purchase of uniforms and other sport equipment- Engineer | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Kinangop | Engineer |  | Productive | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2974 | Sports development | Purchase of uniforms and other sport equipment- Leshau Pondo | Sports Development | Purchased and distributed sports equipment and uniform | 2211018 | Ndaragwa | leshau pondo |  | Productive | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2975 | Sports development | KYSA teams selection | Promotion of sports participation and competitiveness. | KYSA selection events | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 1350000 | 1350000 | 1350000 | CGN | N/A | 1350000 | N/A | 1350000 | 100% | 1350000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2976 | Sports development | KYSA games | Promotion of sports participation and competitiveness. | KYSA game events | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 5000000 | 5000000 | 5000000 | CGN | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2977 | Sports development | Cross country games | Promotion of sports participation and competitiveness. | Cross country games | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2978 | Sports development | Under 20 athletics | Promotion of sports participation and competitiveness. | Under 20 athletics | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2979 | Sports development | Track and field events | Promotion of sports participation and competitiveness. | Track and field events | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2980 | Sports development | FKF LEAGUE | Promotion of sports participation and competitiveness. | Partcipation in FKF events | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2981 | Sports development | Other championship (Darts, Wrestling,Tae kwodo and Pool) | Promotion of sports participation and competitiveness. | participation in other discplines championship | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2982 | Sports development | Football and volleyball tournament-Leshau Pondo | Promotion of sports participation and competitiveness. | Football and volleyball tournaments | 2211399 | Ndaragwa | leshau pondo |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2983 | Sports development | Capacity building for sports support personnel | Sports Development | Capacity building forums | 2211399 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 180000 | 180000 | 180000 | CGN | N/A | 180000 | N/A | 180000 | 100% | 180000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2984 | Youth Support | Youth groups formation and training | Youth empowerment | Youth training forums | 2210714 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 | N/A | 300000 | 100% | 300000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Youth turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2985 | Youth Support | Youth Capacity building and development | Youth empowerment | Youth training forums | 2210799 | Countywide | Countywide |  | Productive | 2022-07-01 | 2023-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Low Youth turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 2986 | Youth Support | Purchase of Specialised Plant, Equipment & Machines for youth groups- Concrete Mixer Shamata- Wafici-ini Masonry Self Help Group | Youth empowerment | procured and distributed youth equipment | 3111120 | Ndaragwa | Shamata |  | Productive | 2022-07-01 | 2023-06-30 |  | 400000 | 400000 | 400000 | CGN | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2987 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youth groups (2. No. complete set public address systems and Carwash machines )- Magumu Ward | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Magumu |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999100 | 100% | 999100 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2988 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youth groups - North Kinangop Ward | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | N.Kinangop |  | Productive | 2022-07-01 | 2023-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2989 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youth groups - Kipipiri Ward | Youth empowerment | procured and distributed youth equipment | 3111120 | Kipipiri | Kipipiri |  | Productive | 2022-07-01 | 2023-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2990 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths - Engineer | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Engineer |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 999950 | 100% | 999950 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2991 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths - Njabini | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Njabini |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 959699 | 100% | 959699 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2992 | Youth Support | Shamata - Purchase of Specialised Plant, Equipment & Machinery for youths (Musical instruments for Mwihoti youth group) | Youth empowerment | procured and distributed youth equipment | 3111120 | Ndaragwa | Shamata |  | Productive | 2022-07-01 | 2023-06-30 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 | N/A | 300000 | 100% | 300000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2993 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths - Gathaara | Youth empowerment | procured and distributed youth equipment | 3111120 | Kinangop | Gathaara |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2994 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery - ( 5No. Motor bikes)- Leshau Pondo | Youth empowerment | procured and distributed youth equipment | 3111120 | Ndaragwa | leshau pondo |  | Productive | 2022-07-01 | 2023-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2995 | Youth Support | Purchase of Specialised Plant, Equipment & Machinery for youths- 5No. 2No.Welding Machines, 2No. Incubators, 1No. Powersaw (Husqvarna)-Mirangine | Youth empowerment | procured and distributed youth equipment | 3111120 | Olkalou | Mirangine |  | Productive | 2022-07-01 | 2023-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2996 | Youth Support | Purchase of Specialised Plant, Equipment & Machines- Public address system and generator - Leshau-Pondo- FY 2020-21 | Youth empowerment | procured and distributed youth equipment | 3111120 | Ndaragwa | leshau pondo |  | Productive | 2022-07-01 | 2023-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 499300 | 100% | 499300 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2997 | Sports developm ent | Purchase of uniforms and other sport equipment- Githabai Ward | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Kinangop | Githabai |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 0 | 0% | 0 | 499675 | 499675 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2998 | Sports developm ent | Purchase of uniforms and other sport equipment- Nyakio Ward | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Kinangop | Nyakio |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 0 | 0% | 0 | 498695 | 498695 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 2999 | Sports developm ent | Purchase of uniforms and other sport equipment- Njabini Ward | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Kinangop | Njabini |  | Productive | 2023-07-01 | 2024-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 0 | 0% | 0 | 998434 | 998434 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3000 | Sports developm ent | Purchase of uniforms and other sport equipment- Gathaara Ward | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Kinangop | Gathaara |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 0 | 0% | 0 | 499454 | 499454 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3001 | Sports developm ent | Sports Tournament- Gathaara Ward | Sports Development | Sports tournaments | 2211018 | Kinangop | Gathaara |  | Productive | 2023-07-01 | 2024-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3002 | Sports developm ent | Purchase of uniforms and other sport equipment- Murungaru | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Kinangop | Murungaru |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 0 | 0% | 0 | 499980 | 499980 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3003 | Sports developm ent | Purchase of uniforms and other sport equipment- Githioro | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Kipipiri | Githioro |  | Productive | 2023-07-01 | 2024-06-30 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 | N/A | 300000 | 100% | 300000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3004 | Sports developm ent | Purchase of uniforms and other sport equipment- Charagita | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Oljoro Orok | Charagita |  | Productive | 2023-07-01 | 2024-06-30 |  | 1200000 | 1200000 | 1200000 | CGN | N/A | 1200000 | N/A | 0 | 0% | 0 | 1194476 | 1194476 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3005 | Sports developm ent | Purchase of uniforms and other sport equipment- Kipipiri | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Kipipiri | Kipipiri |  | Productive | 2023-07-01 | 2024-06-30 |  | 400000 | 400000 | 400000 | CGN | N/A | 400000 | N/A | 0 | 0% | 0 | 400000 | 400000 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3006 | Sports developm ent | Purchase of uniforms and other sport equipment- Rurii | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Olkalou | Rurii |  | Productive | 2023-07-01 | 2024-06-30 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 | N/A | 0 | 0% | 0 | 300000 | 300000 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3007 | Sports developm ent | Purchase of uniforms and other sport equipment- Wanjohi | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Kipipiri | Wanjohi |  | Productive | 2023-07-01 | 2024-06-30 |  | 750000 | 750000 | 750000 | CGN | N/A | 750000 | N/A | 748800 | 100% | 748800 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3008 | Sports developm ent | Purchase of uniforms and other sport equipment- Ndaragwa Central | Sports Development | Purchased and distributed sports equiment and uniform | 2211018 | Ndaragwa | Ndaragwa Central |  | Productive | 2023-07-01 | 2024-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 0 | 0% | 0 | 1489890 | 1489890 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3009 | Sports developm ent | Cross country games | Promotion of sports participation and competitiveness. | Cross country games | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3010 | Sports developm ent | Under 20 athletics | Promotion of sports participation and competitiveness. | Under 20 athletics | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3011 | Sports developm ent | Track and field events | Promotion of sports participation and competitiveness. | Track and field events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 3000000 | 3000000 | 3000000 | CGN | N/A | 3000000 | N/A | 405000 | 100% | 405000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3012 | Sports developm ent | FKF LEAGUE | Promotion of sports participation and competitiveness. | Participation on FKF sports events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 1200000 | 1200000 | 1200000 | CGN | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3013 | Sports developm ent | Other championship (volleyball league) | Promotion of sports participation and competitiveness. | Participation on volleyball sports events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 | N/A | 50000 | 100% | 50000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3014 | Sports developm ent | Indoor games support (Darts, Wrestling,Tae kwodo, Boxing, table tennis,Pool) | Promotion of sports participation and competitiveness. | Indoor games events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3015 | Sports developm ent | Sports for PWD's | Promotion of sports participation and competitiveness. | PWD sports events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 845000 | 100% | 845000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3016 | Sports developm ent | Sports talent support ( Kahuho Primary - 0.25m, Mukungi Primary - 0.25m) | Promotion of sports participation and competitiveness. | Sports events | 2211399 | Kipipiri | Githioro |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No risk | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3017 | Sports developm ent | Talanta Hela (Sports talent nurturing, in collaboration with the National Government) | Promotion of sports participation and competitiveness. | Talanta Hela events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 2500000 | 2500000 | 2500000 | CGN | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3018 | Sports developm ent | Kiriita Ward Sports league tournament | Promotion of sports participation and competitiveness. | Ward sports league tournament | 2211399 | Ndaragwa | Kiriita |  | Productive | 2023-07-01 | 2024-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3019 | Sports developm ent | Kipipiri Ward Sports league tournament | Promotion of sports participation and competitiveness. | Ward sports league tournament | 2211399 | Kipipiri | Kipipiri |  | Productive | 2023-07-01 | 2024-06-30 |  | 600000 | 600000 | 600000 | CGN | N/A | 600000 | N/A | 600000 | 100% | 600000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3020 | Sports developm ent | Magumu Ward- Ward Sports league tournament | Promotion of sports participation and competitiveness. | Ward sports league tournament | 2211399 | Kinangop | Magumu |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3021 | Sports developm ent | Githioro Ward Sports league tournament | Promotion of sports participation and competitiveness. | Ward sports league tournament | 2211399 | Kipipiri | Githioro |  | Productive | 2023-07-01 | 2024-06-30 |  | 400000 | 400000 | 400000 | CGN | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3022 | Sports developm ent | Murungaru Ward Sports league tournament | Promotion of sports participation and competitiveness. | Ward sports league tournament | 2211399 | Kinangop | Murungaru |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3023 | Sports developm ent | Governor's tournament (wards Play Offs, Sub-counties Leagues, and county Finalists League for All Disciplines) | Promotion of sports participation and competitiveness. | Governors tournament events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 11000000 | 11000000 | 11000000 | CGN | N/A | 11000000 | N/A | 6005092 | 54.59% | 6005092 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3024 | Sporting infrastructure development and upgrade | Upgrading Mutanga Stadium- Kiriita | Sports Development | Rehabilitation of Mutanga stadium(Erection of goal post ,backfilling,fence repair,drainage system) | 3110504 | Ndaragwa | Kiriita |  | Productive | 2023-07-01 | 2024-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 0 | 0% | 0 | 999969 | 999969 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3025 | Sporting infrastructure development and upgrade | Grading of Koinange and Ngoyo-Miti iri playgound | Sports Development | Grading of stadium | 3110504 | Kinangop | Githabai |  | Productive | 2023-07-01 | 2024-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 0 | 0% | 0 | 1497589 | 1497589 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3026 | Youth support | Civic education on emerging issues / youth skills and capacity development | Youth empowerment | Youth training forums | 2210712 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 350000 | 100% | 350000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Youth turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3027 | Youth support | Support for new youth enterprise (Music instruments and cameras) -Njabini | Youth empowerment | procured and distributed youth equipment | 3111100 | Kinangop | Njabini |  | Productive | 2023-07-01 | 2024-06-30 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 | N/A | 739230 | 100% | 739230 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3028 | Youth support | Support for new youth enterprise (Kijiko, Munyaka and Kanyugi)- Engineer | Youth empowerment | procured and distributed youth equipment | 3111100 | Kinangop | Engineer |  | Productive | 2023-07-01 | 2024-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3029 | Youth support | Support for new youth enterprise - North Kinangop | Youth empowerment | procured and distributed youth equipment | 3111100 | Kinangop | N.Kinangop |  | Productive | 2023-07-01 | 2024-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3030 | Youth support | Support for new youth enterprise with Yoghurt making machine- Geta | Youth empowerment | procured and distributed youth equipment | 3111100 | Kipipiri | Geta |  | Productive | 2023-07-01 | 2024-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3031 | Youth support | Support for new youth enterprise (public address system)- Githioro | Youth empowerment | procured and distributed youth equipment | 3111100 | Kipipiri | Githioro |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3032 | Youth support | Support for new youth enterprise - Kipipiri | Youth empowerment | procured and distributed youth equipment | 3111100 | Kipipiri | kipipiri |  | Productive | 2023-07-01 | 2024-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3033 | Youth support | Support for new youth enterprise (Assorted kinyozi, Carwash, 2Public Address systems and salon equipment)- Karau | Youth empowerment | procured and distributed youth equipment | 3111100 | Olkalou | Karau |  | Productive | 2023-07-01 | 2024-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 1923942 | 100% | 1923942 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3034 | Youth support | Support for new youth enterprise (public address system)- Charagita | Youth empowerment | procured and distributed youth equipment | 3111100 | Oljoro Orok | Charagita |  | Productive | 2023-07-01 | 2024-06-30 |  | 600000 | 600000 | 600000 | CGN | N/A | 600000 | N/A | 600000 | 100% | 600000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No risk | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3035 | Youth support | Support for youths- Shamata | Youth empowerment | procured and distributed youth equipment | 3110704 | Ndaragwa | Shamata |  | Productive | 2023-07-01 | 2024-06-30 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3036 | Youth support | Support for youth enterprise - TOPUP SHG- Engineer | Youth empowerment | procured and distributed youth equipment | 3110704 | Kinangop | Engineer |  | Productive | 2023-07-01 | 2024-06-30 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 | N/A | 300000 | 100% | 300000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3037 | Youth support | Support for new youth enterprise (Assorted salon equipment) - Ndaragwa Central | Youth empowerment | procured and distributed youth equipment | 3111100 | Ndaragwa | Ndaragwa Central |  | Productive | 2023-07-01 | 2024-06-30 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3038 | Youth support | Tent Making Youth Empowerment Project at Oleliondo Cottage Industry (Formerly Oleliondo Market) | Youth empowerment | procured and distributed youth equipment | 3111100 | Kipipiri | Wanjohi |  | Productive | 2023-07-01 | 2024-06-30 |  | 3000000 | 3000000 | 3000000 | CGN | N/A | 3000000 | N/A | 0 | 0% | 3000000 | 2991800 | 2991800 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3039 | Arts development | Sub-County Talent Search events | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 1200000 | 1200000 | 1200000 | CGN | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3040 | Arts development | County Talent Search Event | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3041 | Arts development | Talent training and development | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2023-07-01 | 2024-06-30 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3042 | Sports development | Cross country games | Promotion of sports participation and competitiveness. | Cross country games | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 |  | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3043 | Sports development | Under 20 athletics | Promotion of sports participation and competitiveness. | Under 20 athletics | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 |  | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3044 | Sports development | Track and field events | Promotion of sports participation and competitiveness. | Track and field events | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 |  | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3045 | Sports development | FKF LEAGUE | Promotion of sports participation and competitiveness. | Participation in FKF events | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 |  | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3046 | Sports development | Procurement of Uniform and Sport Equipment | Promotion of sports participation and competitiveness. | Procured uniform and sports equipment | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3047 | Sports development | Governor's tournament | Promotion of sports participation and competitiveness. | Governors tournament events | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 6000000 | 6000000 | 6000000 | CGN | N/A | 6000000 |  | 6000000 | 100% | 6000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3048 | Sports development | Support for Nyandarua Karate club | Promotion of sports participation and competitiveness. | Participation in Karate Campionship | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 |  | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3049 | Sports development | Support for Tae Kwondo sport in Nyandarua | Promotion of sports participation and competitiveness. | Participation in Tae Kwondo Championship | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 700000 | 700000 | 700000 | CGN | N/A | 700000 |  | 700000 | 100% | 700000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3050 | Sports development | Support to boxing sport | Promotion of sports participation and competitiveness. | Athletes Participation in Championship | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Athlete turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3051 | Sports development | Purchase of Youth equipment | Promotion of sports participation and competitiveness. | Procured uniform and sports equipment | 2211031 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 |  | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3052 | Sporting infrastructure development and upgrade | Construction of murram running tracks - Ol jororok stadium | Promotion of sports participation and competitiveness. | Constructed running tracks | 3110504 | Oljoro Orok | Weru |  | Productive | 2024-07-20 | 2025-06-20 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 |  | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the running track,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3053 | Sporting infrastructure development and upgrade | Levelling and other works- new ground for the proposed Engineer stadium | Promotion of sports participation and competitiveness. | Leveling of Stadium and erection of goal post | 3110504 | Kinangop | Gathaara |  | Productive | 2024-07-20 | 2025-06-20 |  | 3000000 | 3000000 | 3000000 | CGN | N/A | 3000000 |  | 2897934 | 96.6% | 2897934 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3054 | Sporting infrastructure development and upgrade | Levelling and construction of 3-door toilet, drainage works and goal posts - Kianjata playing field | Promotion of sports participation and competitiveness. | Levelling , construction of 3-door toilet, drainage works and erection of goal posts | 3110504 | Oljoro Orok | Gatimu |  | Productive | 2024-07-20 | 2025-06-20 |  | 2500000 | 2500000 | 2500000 | CGN | N/A | 2500000 |  | 2425147 | 97.01% | 2425147 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance,Vandalism of goal posts | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3055 | Sporting infrastructure development and upgrade | Running tracks - Wakirogo stadium | Promotion of sports participation and competitiveness. | Constructed running tracks | 3110504 | Kipipiri | Wanjohi |  | Productive | 2024-07-20 | 2025-06-20 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 |  | 1395549 | 93.04% | 1395549 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the running track,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3056 | Sporting infrastructure development and upgrade | Dias construction - Ndunyu Njeru stadium | Promotion of sports participation and competitiveness. | Constructed dias | 3110504 | Kinangop | N.Kinangop |  | Productive | 2024-07-20 | 2025-06-20 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 |  | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the Dias,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3057 | Sporting infrastructure development and upgrade | Murungaru stadium- Levelling and goal posts | Promotion of sports participation and competitiveness. | Levelling and erection of goal posts | 3110504 | Kinangop | Murungaru |  | Productive | 2024-07-20 | 2025-06-20 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 |  | 1000000 | 100% | 995589 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-weeds growth thus,requiring allocation of funds for regular maintenance,Vandalism of goal posts | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3058 | Sporting infrastructure development and upgrade | Repair of Rurinja stadium perimeter wall | Promotion of sports participation and competitiveness. | Repair of Rurinja stadium perimeter wall | 3110504 | Kinangop | Njabini |  | Productive | 2024-07-20 | 2025-06-20 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 |  | 178371 | 89.19% | 178371 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | financial-Wearing out of the wall,thus requiring an allocation of funds for regular maintenance | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3059 | Sports development | Procurement and distribution of sports equipment | Promotion of sports participation and competitiveness. | procured and distributed sports uniform and equipment | 2211031 | Olkalou | Kimbaga |  | Productive | 2024-07-20 | 2025-06-20 |  | 200000 | 200000 | 200000 | CGN | N/A | 200000 |  | 200000 | 100% | 200000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3060 | Sports development | Procurement and distribution of sports equipment | Promotion of sports participation and competitiveness. | procured and distributed sports uniform and equipment | 2211018 | Kinangop | Engineer |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3061 | Sports development | Procurement and distribution of sports equipment | Promotion of sports participation and competitiveness. | procured and distributed sports uniform and equipment | 2211018 | Kinangop | Githabai |  | Productive | 2024-07-20 | 2025-06-20 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 |  | 300000 | 100% | 300000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3062 | Sports development | Procurement and distribution of sports equipment | Promotion of sports participation and competitiveness. | procured and distributed sports uniform and equipment | 2211018 | Kinangop | Njabini |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3063 | Sports development | Procurement and distribution of sports equipment | Promotion of sports participation and competitiveness. | procured and distributed sports uniform and equipment | 2211018 | Kipipiri | Githioro |  | Productive | 2024-07-20 | 2025-06-20 |  | 300000 | 300000 | 300000 | CGN | N/A | 300000 |  | 300000 | 100% | 300000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3064 | Sports development | Procurement and distribution of sports equipment | Promotion of sports participation and competitiveness. | procured and distributed sports uniform and equipment | 2211018 | Oljoro Orok | Charagita |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3065 | Sports development | Procurement and distribution of sports equipment | Promotion of sports participation and competitiveness. | procured and distributed sports uniform and equipment | 2211018 | Olkalou | Rurii |  | Productive | 2024-07-20 | 2025-06-20 |  | 400000 | 400000 | 400000 | CGN | N/A | 400000 |  | 400000 | 100% | 400000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Wearing out of uniform and sports equipment | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3066 | Youth training and capacity building | Training and certification of Youth | Promotion of sports participation and competitiveness. | Training and certification | 2210713 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 10000000 | 10000000 | 10000000 | CGN | N/A | 10000000 |  | 10000000 | 100% | 10000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No risk | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3067 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 3111100 | Olkalou | Kaimbaga |  | Productive | 2024-07-20 | 2025-06-20 |  | 700000 | 700000 | 700000 | CGN | N/A | 700000 |  | 700000 | 100% | 700000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3068 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 2211018 | Kinangop | Nyakio |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3069 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 3111100 | Kinangop | Njabini |  | Productive | 2024-07-20 | 2025-06-20 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 |  | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3070 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 3110701 | Kinangop | Gathaara |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3071 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 3111100 | Olkalou | Karau |  | Productive | 2024-07-20 | 2025-06-20 |  | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3072 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 3112299 | Kinangop | Engineer |  | Productive | 2024-07-20 | 2025-06-20 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 |  | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3073 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 3111100 | Olkalou | Karau |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3074 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 2211399 | Ndaragwa | Shamata |  | Productive | 2024-07-20 | 2025-06-20 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 |  | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3075 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 2211011 | Ndaragwa | Shamata |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3076 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 3111100 | Kinangop | Engineer |  | Productive | 2024-07-20 | 2025-06-20 |  | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 |  | 1500000 | 100% | 1500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3077 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 3111100 | Kipipiri | Wanjohi |  | Productive | 2024-07-20 | 2025-06-20 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 |  | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3078 | Youth support | Procurement and distribution of Youth equipment | Youth empowerment | Procured youth equipment | 3111100 | Ndaragwa | Ndaragwa Central |  | Productive | 2024-07-20 | 2025-06-20 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 |  | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Limited access to utilities e.g water,electricity | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Done to completion
YOUTH | 3079 | Arts development | Talent identification | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 900000 | 900000 | 900000 | CGN | N/A | 900000 |  | 900000 | 100% | 900000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3080 | Arts development | Talent identification | Talent search, nurturing and promotion | Talent search events | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 900000 | 900000 | 900000 | CGN | N/A | 900000 |  | 900000 | 100% | 900000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3081 | Arts development | Talent awarding | Talent search, nurturing and promotion | Talent Awards | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 900000 | 900000 | 900000 | CGN | N/A | 900000 |  | 900000 | 100% | 900000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3082 | Arts development | Talent training | Talent search, nurturing and promotion | Training and capacity building forums | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 800000 | 800000 | 800000 | CGN | N/A | 800000 |  | 800000 | 100% | 800000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3083 | Arts development | Talent training | Talent search, nurturing and promotion | Training and capacity building forums | 2211399 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 500000 | 500000 | 500000 | CGN | N/A | 500000 |  | 500000 | 100% | 500000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Continuous
YOUTH | 3084 | Arts development | Formulation of Arts policy | Talent search, nurturing and promotion | Arts policy | 2210802 | Countywide | Countywide |  | Productive | 2024-07-20 | 2025-06-20 |  | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 |  | 1000000 | 100% | 1000000 | 0 | 0 | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Financial-Low Artists turn out | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | No | No budget allocation,the department intends to incoorporate this aspect in Annual budgets | Ongoing
LANDS | 3085 | Preparation of physical and land use development plans for Rurii Trading Centre, Mufau Trading Centre, Kiriogo Trading Centre, Leshau Trading Centre, Mawingu Trading Centre, Njabini Town, Ol'Joro'Orok Town & Miharati Town | Preparation of physical and development land use plans for Rurii Trading Centre (Rurii Ward)Mufau Trading Centre (Wanjohi Ward), Kiriogo Trading Centre (Ndaragwa Central ward) Leshau Trading Centre (Leshau Pondo Ward), Mawingu Trading Centre (Karau ward), Njabini Town in Njabini ward, Ol'Joro'Orok Town in Weru Ward & Miharati Town in Kipipiri Ward | Preparation of up-to-date plan | Local Physical and Land Use Development Plans |  | Ol'kalou, Kipipiri, Ndaragwa, Oljoro'orok, Kinangop | Rurii, Wanjohi, Central, Leshau Pondo, Karau, Njabini, Weru, Kipipiri |  |  | 2020/21 | 2020/21 |  | 10000000 | 2.4M |  | CGN |  | 2400000 | [6 empty] | Ongoing | 90% complete for 3 centers of Mawingu, Miharati and Oljolorok | 50% for discontinued centers | Budgetary constraints | 23/24 | 6 Months |  | No | Complete | Uncontrolled development & Insecurity of tenure | It will be done once the plan is completed |  | It will be done once the plan is completed |  | No |  | Rurii Trading Centre (Rurii Ward) is part of the Municipalty whose planning at the moment was ongoing, The Department was able to proceed from the data collection phase for only 3 centers of Miharati, Mawingu and Oljolorok
LANDS | 3086 | Preparation of physical and land-use development Plans for 4 colonial dams (per sub county) | Preparation of physical and land-use development Plans for 4 colonial dams (per sub county) | Preparation of up-to-date plan | Local Physical and Land Use Development Plans |  | Ol'kalou, Kipipiri, Ndaragwa, Oljoro'orok, Kinangop | To be determined |  |  | 2022/23 | 2022/23 |  | 5000000 | 2M |  | CGN |  | 2000000 | [6 empty] | Stalled | 100% |  | Budgetary constraints | 23/24 |  |  | No | Complete | Grabbing | No |  |  |  | No |  | funds supplemented to other projects during 1st supplementary
LANDS | 3087 | Classification of miharati,magumu,Ol'jororok,Shamata,Njabini Urban centres | Classification of miharati,magumu,Ol'jororok,Shamata,Njabini Urban centres | Upgrading of towns | Conferment of level of centers |  | Kipipiri, Ndaragwa, Oljoro'orok, Kinangop | Njabini, Weru, Kipipiri |  |  | 2022/23 | 2022/23 |  | 10000000 | 1.5M |  | CGN |  | 1500000 | [6 empty] | Ongoing | 50% complete |  |  | 24/25 | 5Months |  | No | Complete | Lack of a framework for provision of essential services in each level of centers | It will be done once the plan is completed |  | It will be done once the plan is completed |  | No |  | Resolved to focus on assessing the centers within a subcounty context for ease of comparison (Commenced with Kinangop)
LANDS | 3088 | Preparation of physical and development land use plans for (Kasuku, Kwa Haraka, Ngorika, Rironi and Shamata) | Preparation of physical and development land use plans for (Kasuku, Kwa Haraka, Ngorika, Rironi and Shamata) | Preparation of up-to-date plan | Local Physical and Land Use Development Plans |  | Ol'kalou, Ndaragwa, Oljoro'orok, | Weru, Kanjuiri, Shamata |  |  | 2023/24 | 2023/24 |  | 5000000 | 1.5M |  | CGN |  | 1500000 | [6 empty] | Ongoing | 50% complete for Shamata & Ngorika | 100% for discontinued towns | Budgetary constraints | 24/25 | 8 Months |  | No | Complete | Uncontrolled development & Insecurity of tenure | It will be done once the plan is completed |  | It will be done once the plan is completed |  | No |  | With the inadequate budgetary allocation only plans for Shamata and Ngorika towns could be accommodated
LANDS | 3089 | Preparation of Municipal Plan for Mairo-Inya and Engineer municipality | Preparation of Municipal Plan for Engineer municipality |  | Integrated and Strategic Urban Development Plan |  | kinangop ndaragwa | Gathaara engineer ndaragwa central |  |  | 2024/25 | 2024/25 |  | 19000000 | 5M |  | CGN |  | 5000000 | [6 empty] | Stalled |  | 70% | Budgetary constraints | 23/24 | 6 Months |  | No | Complete | Discontinuation for KUSP II Funding due to failure to meet the minimum conditions for eligibility | It will be done once the plan is completed |  | It will be done once the plan is completed |  | No |  | Due to the inadequacy of the budgetary allocation Engineer Municipality was prioritised as it had been prequalified to KUSP II funding and the plan were part of the minimum requirements
LANDS | 3090 | Survey of Njabini Colonial Village | Survey of Njabini Colonial Village | Provide secure land tenure | Survey Plans and RIMs |  | Kinangop | Njabini | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3091 | Survey of Murungaru Colonial Village | Survey of Murungaru Colonial Village | Provide secure land tenure | Survey Plans and RIMs |  | Kinangop | Murungaru | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3092 | Survey of Magumu Colonial Village | Survey of Magumu Colonial Village | Provide secure land tenure | Survey Plans and RIMs |  | Kinangop | Magumu | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3093 | Survey of Githioro Colonial Village | Survey of Githioro Colonial Village | Provide secure land tenure | Survey Plans and RIMs |  | Kipipiri | Githioro | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3094 | Survey of Captain Township | Survey of Captain Township | Provide secure land tenure | Survey Plans and RIMs |  | Ol'Kalou | Kaimbaga | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3095 | Survey of Kambaa Colonial village | Survey of Kambaa Colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Ndaragwa | Ndaragwa | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3096 | Survey of Rurii Colonial village | Survey of Rurii Colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Ol'Kalou | Rurii | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3097 | Survey of Mbuyu Township | Survey of Mbuyu Township | Provide secure land tenure | Survey Plans and RIMs |  | Ndaragwa | Leshau | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3098 | Survey of Mukeu Colonial Village | Survey of Mukeu Colonial Village | Provide secure land tenure | Survey Plans and RIMs |  | Kinangop | Nyakio | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3099 | Survey of Nyairoko Colonial Village | Survey of Nyairoko Colonial Village | Provide secure land tenure | Survey Plans and RIMs |  | Ol'Kalou | Rurii | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3100 | Survey of Sofia Colonial Village | Survey of Sofia Colonial Village | Provide secure land tenure | Survey Plans and RIMs |  | Kipipiri | Kipipiri | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3101 | Survey of Wanjohi Colonial Village | Survey of Wanjohi Colonial Village | Provide secure land tenure | Survey Plans and RIMs |  | Kipipiri | Wanjohi | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3102 | Survey of Koinange colonial village | Survey of Koinange colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Kinangop | Githabai | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3103 | Survey of Kiriko colonial village | Survey of Kiriko colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Kipipiri | Githioro | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3104 | Survey of Kaheho Colonial village | Survey of Kaheho Colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Ndaragwa | Shamata | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3105 | Survey of Ngorika colonial village | Survey of Ngorika colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Ol'Kalou | Kanjuiri | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3106 | Survey of Heni colonial village | Survey of Heni colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Kinangop | Githabai | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3107 | Survey of Ngano colonial village | Survey of Ngano colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Ol-Joro-orok | Charagita | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3108 | Survey of Gathanji colonial village | Survey of Gathanji colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Ol-Joro-orok | Gathanji | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3109 | Survey of Huruma colonial village | Survey of Huruma colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Ol'Kalou | Kaimbaga | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3110 | Survey of Turkana colonial village | Survey of Turkana colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Ol'Kalou | Rurii | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3111 | Survey of Miharati Colonial village | Survey of Miharati Colonial village | Provide secure land tenure | Survey Plans and RIMs |  | Kipipiri | Kipipiri | [8 empty] | MoL | [8 empty] | Completed | [15 empty] | completed
LANDS | 3112 | Survey of Ol'KalounTownship | Survey of Ol'KalounTownship | Provide secure land tenure | Survey Plans and RIMs |  | Ol'Kalou | Kaimbaga | [8 empty] | CGN | [8 empty] | On-going | 90% | [14 empty] | On-going
LANDS | 3113 | Preparation of Topographical Maps of Ngorika and Shamata Townships | Preparation of Topographical Maps of Ngorika and Shamata Townships | Provide secure land tenure | Topographical Maps |  | Ol'Kalou and Ndaragwa | Kanjuiri and Shamata | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3114 | Preparation of Topographical Maps of Rurii, Michore, Kiriogo, Leshau, Mawingu, Njabini, Ol-Joro-Orok, Miharati, Kimbogo and Kianjogu Townships | Preparation of Topographical Maps of Rurii, Michore, Kiriogo, Leshau, Mawingu, Njabini, Ol-Joro-Orok, Miharati, Kimbogo and Kianjogu Townships | Protect public land | Topographical Maps |  | All | Rurii, Wanjohi, Ndaragwa, Leshau, Karau, Njabini, Weru, Kipipiri and Geta | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3115 | Survey of 20 colonial Dams | Survey of 20 colonial Dams | Provide secure land tenure | RIMs |  | All | Various | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3116 | Survey of Sabugo Colonial Village | Survey of Sabugo Colonial Village | Provide secure land tenure | Survey Plans and RIMs |  | Ol-Joro-orok | Charagita | [8 empty] | CGN | [8 empty] | Completed | [15 empty] | completed
LANDS | 3117 | Nya/Mawingu/5683 0.20ha. | [8 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 600000 | [10 empty] | complete
LANDS | 3118 | Purchase of land for Gathima ECDE | Nya/Ngorika/3374 0.2023ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 | [10 empty] | complete
LANDS | 3119 | Nya/Githioro/4585 0.405 | [8 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 | [10 empty] | complete
LANDS | 3120 | Purchase of land for Manyatta ECDE | Nya/ Kahuru/3205 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 1150000 | 1150000 | [10 empty] | complete
LANDS | 3121 | Purchase of land for Goodfall ECDE | Nya/Silibwet /5144 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3122 | Purchase of land for Munyaka Dispensary | Nya/Tulaga/1571 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 650000 | 650000 | [10 empty] | complete
LANDS | 3123 | Purchase of land for Geta livestock sale yard | Nya/647 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 2250000 | 2250000 | [10 empty] | complete
LANDS | 3124 | Purchase of land for Yaanga Community land | Nya/Njabini/6337 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 650000 | 650000 | [10 empty] | complete
LANDS | 3125 | Purchase of land for Mwireri Community Land | Nya/Ndemi/5627 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3126 | Purchase of land for Mwihangia Community Land | Nya/ Shamata/4251 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 680000 | 680000 | [10 empty] | complete
LANDS | 3127 | Purchase of land for Gichungo Dispensary | Nya/Ol kalou salient/ | [7 empty] | 2015-07-01 | 2016-06-01 |  | 2900000 | 2900000 | [10 empty] | complete
LANDS | 3128 | Nya/Njabini/4927 0.2003 ha | Nya/Njabini/4927 0.2003 ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 850000 | 850000 | [10 empty] | complete
LANDS | 3129 | Nya/Kitiri/5140 0.1074ha | Nya/Kitiri/5140 0.1074ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 | [10 empty] | complete
LANDS | 3130 | Nya/Muruaki /6227 0.0905 | Nya/Muruaki /6227 0.0905 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 380000 | 380000 | [10 empty] | complete
LANDS | 3131 | Nya/Muruaki /5159 0.043ha | Nya/Muruaki /5159 0.043ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 100000 | 100000 | [10 empty] | complete
LANDS | 3132 | Nya/Shamata/3544 0.1526ha | Nya/Shamata/3544 0.1526ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 300000 | 300000 | [10 empty] | complete
LANDS | 3133 | Nya/Shamata/3543 | Nya/Shamata/3543 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 235000 | 235000 | [10 empty] | complete
LANDS | 3134 | Nya/Turasha/877 0.2479 ha | Nya/Turasha/877 0.2479 ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 300000 | [10 empty] | complete
LANDS | 3135 | Nya/Malewa/820 0.350ha | Nya/Malewa/820 0.350ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 495000 | 495000 | [10 empty] | complete
LANDS | 3136 | Nya/Karati/3846 0.0479ha | Nya/Karati/3846 0.0479ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 260000 | 260000 | [10 empty] | complete
LANDS | 3137 | Nya/Muruaki/1044 0.45ha | Nya/Muruaki/1044 0.45ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 795000 | 795000 | [10 empty] | complete
LANDS | 3138 | Nya/Olkalou/2035 0.208ha | Nya/Olkalou/2035 0.208ha | [7 empty] | 2015-07-01 | 2016-06-01 |  | 400000 | 400000 | [10 empty] | complete
LANDS | 3139 | Nyandarua/Muruaki/2620 | Nyandarua/Muruaki/2620 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 255000 | 255000 | [10 empty] | complete
LANDS | 3140 | Nyandarua /Muruaki/2621 | Nyandarua /Muruaki/2621 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 180000 | 180000 | [10 empty] | complete
LANDS | 3141 | Nyandarua /Muruaki/720 | Nyandarua /Muruaki/720 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 215000 | 215000 | [10 empty] | complete
LANDS | 3142 | Nyandarua/Mkungi/5219 | Nyandarua/Mkungi/5219 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 120000 | 120000 | [10 empty] | complete
LANDS | 3143 | Nyandarua/Sabugo/4907 | Nyandarua/Sabugo/4907 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 397000 | 397000 | [10 empty] | complete
LANDS | 3144 | Nyandarua/Oljororoko west/575 | Nyandarua/Oljororoko west/575 | [7 empty] | 2015-07-01 | 2016-06-01 |  | 350000 | 345541 | [10 empty] | complete
LANDS | 3145 | Nyandarua/nyairoko/285 market land | Nyandarua/nyairoko/285 market land | [7 empty] | 2016-07-01 | 2017-06-01 |  | 2000000 | 2000000 | [10 empty] | complete
LANDS | 3146 | nyandarua/south kinangop/3309 kageraini market road | nyandarua/south kinangop/3309 kageraini market road | [7 empty] | 2016-07-01 | 2017-06-01 |  | 3350000 | 3350000 | [10 empty] | complete
LANDS | 3147 | nyandarua /sabugo/1207 ngano market land | nyandarua /sabugo/1207 ngano market land | [7 empty] | 2016-07-01 | 2017-06-01 |  | 3000000 | 3000000 | [10 empty] | complete
LANDS | 3148 | Nyandarua/ngorika/4113 | Nyandarua/ngorika/4113 | [7 empty] | 2016-07-01 | 2017-06-01 |  | 1150000 | 1150000 | [10 empty] | complete
LANDS | 3149 | nyandarua/tulaga/1571 | nyandarua/tulaga/1571 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 650000 | 650000 | [10 empty] | complete
LANDS | 3150 | nyandarua/silibwet/5144 | nyandarua/silibwet/5144 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3151 | nyandarua/njabini/6337 | nyandarua/njabini/6337 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 650000 | 650000 | [10 empty] | complete
LANDS | 3152 | nyandarua/ol kalo salient | nyandarua/ol kalo salient | [7 empty] | 2017-07-01 | 2018-06-01 |  | 2900000 | 2900000 | [10 empty] | complete
LANDS | 3153 | nyandarua/ndemi/5627 | nyandarua/ndemi/5627 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 900000 | 900000 | [10 empty] | complete
LANDS | 3154 | nyandarua/shamata/4251 | nyandarua/shamata/4251 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 925000 | [11 empty] | pending payment
LANDS | 3155 | nyandarua/mawingu/5683 | nyandarua/mawingu/5683 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 600000 | 600000 | [10 empty] | complete
LANDS | 3156 | nyandarua/kahuru/8362 | nyandarua/kahuru/8362 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 1150000 | 1150000 | [10 empty] | complete
LANDS | 3157 | nyandarua/melangine/4480 | nyandarua/melangine/4480 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 750000 | 750000 | [10 empty] | complete
LANDS | 3158 | nyandarua/ol kalou west/2220 | nyandarua/ol kalou west/2220 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 750000 | [11 empty] | pending payment
LANDS | 3159 | nyandarua/olarawai/4641 &nyandarua/olaragwai/6894 | nyandarua/olarawai/4641 &nyandarua/olaragwai/6894 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 5000000 | 5000000 | [10 empty] | complete
LANDS | 3160 | nyandarua/ngorika/3374 | nyandarua/ngorika/3374 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 500000 | [10 empty] | complete
LANDS | 3161 | nyandarua/githioro/4585 | nyandarua/githioro/4585 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 1000000 | [10 empty] | complete
LANDS | 3162 | nyandarua/ol kalou central/6681 | nyandarua/ol kalou central/6681 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 900000 | [11 empty] | pending payment
LANDS | 3163 | nyandarua/kitiri/3996&2844 | nyandarua/kitiri/3996&2844 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 2000000 | [10 empty] | complete
LANDS | 3164 | nyandarua/sabugo/4441&4460 | nyandarua/sabugo/4441&4460 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 1600000 | 1600000 | [10 empty] | complete
LANDS | 3165 | nyandarua/mutonyora/4592 | nyandarua/mutonyora/4592 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 1126000 | 1126000 | [10 empty] | complete
LANDS | 3166 | nyandarua/simbara/1006 | nyandarua/simbara/1006 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 1035000 | 1035000 | [10 empty] | complete
LANDS | 3167 | nyandarua/olaragwi6784&6785 | nyandarua/olaragwi6784&6785 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 1460000 | 1460000 | [10 empty] | complete
LANDS | 3168 | nyandarua/njabini/11169 | nyandarua/njabini/11169 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3169 | nyandarua/mawingu/4671 | nyandarua/mawingu/4671 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 510000 | [11 empty] | pending payment
LANDS | 3170 | nyandarua/geta/4576 | nyandarua/geta/4576 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 2250000 | 2250000 | [10 empty] | complete
LANDS | 3171 | nyandarua/mawingu/2755 | nyandarua/mawingu/2755 | [7 empty] | 2017-07-01 | 2018-06-01 |  | 580000 | 580000 | [10 empty] | complete
LANDS | 3172 | nyandarua/sabugo/2413 | nyandarua/sabugo/2413 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 12997460 | 12997460 | [10 empty] | complete
LANDS | 3173 | nyandarua/olaragwa/9110 | nyandarua/olaragwa/9110 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 7500000 | 7500000 | [10 empty] | complete
LANDS | 3174 | nyandarua/silibwet/2739 | nyandarua/silibwet/2739 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 600000 | 600000 | [10 empty] | complete
LANDS | 3175 | nyandarua/njabini/11444 | nyandarua/njabini/11444 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 550000 | 550000 | [10 empty] | complete
LANDS | 3176 | nyandarua/njabini/1445 | nyandarua/njabini/1445 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 550000 | 550000 | [10 empty] | complete
LANDS | 3177 | nyandarua/shamata/4562 | nyandarua/shamata/4562 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 400000 | [11 empty] | pending payment
LANDS | 3178 | nyandarua/nyairoko/229 | nyandarua/nyairoko/229 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | [11 empty] | pending payment
LANDS | 3179 | nyandarua/leshau karagoini blk2/515 | nyandarua/leshau karagoini blk2/515 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 450000 | 450000
LANDS | 3180 | nyandarua/njabini/4390 | nyandarua/njabini/4390 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 400000 | 400000
LANDS | 3181 | nyandarua/turasha/3312 | nyandarua/turasha/3312 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 80000 | [11 empty] | pending payment
LANDS | 3182 | nyandarua/ol kalou south/3327 | nyandarua/ol kalou south/3327 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | [11 empty] | pending payment
LANDS | 3183 | nyandarua/turasha/3313 | nyandarua/turasha/3313 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 80000 | [11 empty] | pending payment
LANDS | 3184 | nyandarua/njabini/7846 | nyandarua/njabini/7846 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3185 | nyandarua/nandarasi/360 | nyandarua/nandarasi/360 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 500 | 500 | [10 empty] | complete
LANDS | 3186 | nyandarua/turasha/3005 | nyandarua/turasha/3005 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 80000 | 80000 | [10 empty] | complete
LANDS | 3187 | nyandarua/turasha/3003 | nyandarua/turasha/3003 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 4700000 | 4700000 | [10 empty] | complete
LANDS | 3188 | nyandarua/ol kalou west/2321 | nyandarua/ol kalou west/2321 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 | [10 empty] | complete
LANDS | 3189 | nyandarua/leshau blk 2/827 | nyandarua/leshau blk 2/827 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 450000 | 450000 | [10 empty] | complete
LANDS | 3190 | nyandarua/kiriite shauri blk 1/2584 | nyandarua/kiriite shauri blk 1/2584 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 900000 | [10 empty] | complete
LANDS | 3191 | nyandarua/muruaki/2621 | nyandarua/muruaki/2621 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 180000 | 180000 | [10 empty] | complete
LANDS | 3192 | nyandarua/shamata/2159 | nyandarua/shamata/2159 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3193 | nyandarua/nandarasi/3635 | nyandarua/nandarasi/3635 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 550000 | 550000 | [10 empty] | complete
LANDS | 3194 | nyandarua/s. kinangop/474 | nyandarua/s. kinangop/474 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 660000 | 660000 | [10 empty] | complete
LANDS | 3195 | nyandarua/silanga/780 | nyandarua/silanga/780 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 3500000 | 3500000 | [10 empty] | complete
LANDS | 3196 | nyandarua/s. kinangop/4522 | nyandarua/s. kinangop/4522 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3197 | nyandarua/githioro/3586 | nyandarua/githioro/3586 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 460000 | [11 empty] | pending payment
LANDS | 3198 | nyandarua/njabini/99 | nyandarua/njabini/99 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 1716000 | 1716000 | [10 empty] | complete
LANDS | 3199 | nyandarua/njabini/12849 | nyandarua/njabini/12849 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 1250000 | 1250000 | [10 empty] | complete
LANDS | 3200 | nyandarua/turasha/578,588,579,580 | nyandarua/turasha/578,588,579,580 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 5588000 | 5588000 | [10 empty] | complete
LANDS | 3201 | nyandarua/s.kinangop/7328 | nyandarua/s.kinangop/7328 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 1200000 | [10 empty] | complete
LANDS | 3202 | nyandarua/karai/4501 | nyandarua/karai/4501 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 900000 | [10 empty] | complete
LANDS | 3203 | nyandarua/s.kinangop/5500 | nyandarua/s.kinangop/5500 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3204 | nyandarua/s.kinangop/1810 | nyandarua/s.kinangop/1810 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 650000 | 650000 | [10 empty] | complete
LANDS | 3205 | nyandarua/githioro/5593 | nyandarua/githioro/5593 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 | [10 empty] | complete
LANDS | 3206 | nyandarua/njabini/6906 | nyandarua/njabini/6906 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 550000 | 550000 | [10 empty] | complete
LANDS | 3207 | nyandarua/ol kalou/315 | nyandarua/ol kalou/315 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 | [10 empty] | complete
LANDS | 3208 | nyandarua/wanjohi/5 | nyandarua/wanjohi/5 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 5500000 | 5500000 | [10 empty] | complete
LANDS | 3209 | nyandarua/sabugo/8107 | nyandarua/sabugo/8107 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 350000 | 350000 | [10 empty] | complete
LANDS | 3210 | nyandarua/njabini/10713 | nyandarua/njabini/10713 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | [11 empty] | pending payment
LANDS | 3211 | LR NO 3777/822& 3777/832 | LR NO 3777/822& 3777/832 | [7 empty] | 2018-07-01 | 2019-06-01 |  | 7500000 | 7500000 | [10 empty] | complete
LANDS | 3212 | nyandarua/s.kinangop/7824 | nyandarua/s.kinangop/7824 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 | [10 empty] | complete
LANDS | 3213 | nyandarua/ngorika/4739 | nyandarua/ngorika/4739 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 530000 | [11 empty] | pending payment
LANDS | 3214 | nyandarua/s.kinangop/1810 | nyandarua/s.kinangop/1810 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 650000 | 650000 | [10 empty] | complete
LANDS | 3215 | nyandarua/olaragwi/814 | nyandarua/olaragwi/814 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | 1300000 | [10 empty] | complete
LANDS | 3216 | nyandarua/ngorika/698 | nyandarua/ngorika/698 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 950000 | 950000 | [10 empty] | complete
LANDS | 3217 | nyandarua/kiriitamairo inya blk2/2755 | nyandarua/kiriitamairo inya blk2/2755 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 | [10 empty] | complete
LANDS | 3218 | nyandarua/ol kalou south/1750 | nyandarua/ol kalou south/1750 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 1600000 | 1600000 | [10 empty] | complete
LANDS | 3219 | nyandarua/kiriita shauri blk 1/672 | nyandarua/kiriita shauri blk 1/672 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3220 | nyandarua/leshau mbuyu blk 2/7 | nyandarua/leshau mbuyu blk 2/7 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 | [10 empty] | complete
LANDS | 3221 | nyandarua/karati/2362 | nyandarua/karati/2362 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 895000 | 895000 | [10 empty] | complete
LANDS | 3222 | nyandarua/sabugo/4251 | nyandarua/sabugo/4251 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 400000 | 400000 | [10 empty] | complete
LANDS | 3223 | nyandarua/geta/4342 | nyandarua/geta/4342 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 550000 | 550000 | [10 empty] | complete
LANDS | 3224 | nyandarua/ol kalou central/5809 | nyandarua/ol kalou central/5809 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 1200000 | 1200000 | [10 empty] | complete
LANDS | 3225 | nyandarua/s,kinangop/13529 | nyandarua/s,kinangop/13529 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 | [10 empty] | complete
LANDS | 3226 | nyandarua/silanga/114 | nyandarua/silanga/114 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 150000 | 150000 | [10 empty] | complete
LANDS | 3227 | nyandarua/sabugo/3121 | nyandarua/sabugo/3121 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 150000 | 150000 | [10 empty] | complete
LANDS | 3228 | nyandarua/githioro/3833 | nyandarua/githioro/3833 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 1477700 | 1477700 | [10 empty] | complete
LANDS | 3229 | nyandarua/geta/620 | nyandarua/geta/620 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 | [10 empty] | complete
LANDS | 3230 | nyandarua/ol jororok salient/33165 | nyandarua/ol jororok salient/33165 | [7 empty] | 2019-07-01 | 2020-06-01 |  | 1200000 | 1200000 | [10 empty] | complete
LANDS | 3231 | nyandarua/ol jororok west/6357 | nyandarua/ol jororok west/6357 | [7 empty] | 2020-07-01 | 2021-06-01 |  | 1200000 | 1200000 | [10 empty] | complete
LANDS | 3232 | nyandarua/milangine/2804 | nyandarua/milangine/2804 | [7 empty] | 2020-07-01 | 2021-06-01 |  | 90000 | 90000 | [10 empty] | complete
LANDS | 3233 | nyandarua/kipipiri/5599 | nyandarua/kipipiri/5599 | [7 empty] | 2020-07-01 | 2021-06-01 |  | 680000 | 680000 | [10 empty] | complete
LANDS | 3234 | nyandarua/shamata/2782 | nyandarua/shamata/2782 | [7 empty] | 2020-07-01 | 2021-06-01 |  | 550000 | 275000 | [10 empty] | complete
LANDS | 3235 | nyandarua/njabini/12097 | nyandarua/njabini/12097 | [7 empty] | 2020-07-01 | 2021-06-01 |  | 1000000 | 700000 | [10 empty] | complete
LANDS | 3236 | nyandarua/kaimbaga/2733 | nyandarua/kaimbaga/2733 | [7 empty] | 2020-07-01 | 2021-06-01 |  | 500000 | 500000 | [10 empty] | complete
LANDS | 3237 | nyandarua/githiororo/3467&3467 | nyandarua/githiororo/3467&3467 | [7 empty] | 2020-07-01 | 2021-06-01 |  | 800000 | 800000 | [10 empty] | complete
LANDS | 3238 | nyandarua/ngorika/3916 | nyandarua/ngorika/3916 | [7 empty] | 2020-07-01 | 2021-06-01 |  | 300000 | [11 empty] | pending payment
LANDS | 3239 | nyandarua/s. kinangop/16892 | nyandarua/s. kinangop/16892 | [7 empty] | 2020-07-01 | 2021-06-01 |  | 550000 | 550000 | [10 empty] | complete
LANDS | 3240 | nyandarua/nandarasi/3423 | nyandarua/nandarasi/3423 | [7 empty] | 2021-06-01 | 2022-06-01 |  | 600000 | 600000 | [10 empty] | complete
LANDS | 3241 | nyandarua/s.kinangop/2804 | nyandarua/s.kinangop/2804 | [7 empty] | 2021-06-01 | 2022-06-01 |  | 4300000 | 4300000 | [10 empty] | complete
LANDS | 3242 | nyandarua/ol jororok/6402 | nyandarua/ol jororok/6402 | [7 empty] | 2021-06-01 | 2022-06-01 |  | 1998000 | [11 empty] | pending payment
LANDS | 3243 | nyandarua/njabini/416 | nyandarua/njabini/416 | [7 empty] | 2021-06-01 | 2022-06-01 |  | 570000 | [11 empty] | pending payment
LANDS | 3244 | nyandarua/muruaki/3217 | nyandarua/muruaki/3217 | [7 empty] | 2021-06-01 | 2022-06-01 |  | 300000 | [11 empty] | pending payment
LANDS | 3245 | nyandarua/mawingu/1973 | nyandarua/mawingu/1973 | [7 empty] | 2021-06-01 | 2022-06-01 |  | 517000 | 517000 | [10 empty] | complete
LANDS | 3246 | nyandarua/ol jororok west/4571 | nyandarua/ol jororok west/4571 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 1550000 | 1395000 | [10 empty] | complete
LANDS | 3247 | nyandarua/tulaga/12429 | nyandarua/tulaga/12429 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 400000 | 360000 | [10 empty] | complete
LANDS | 3248 | nyandarua/tulaga/8985 | nyandarua/tulaga/8985 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 400000 | 360000 | [10 empty] | complete
LANDS | 3249 | nyandarua/kiriita shauri blk 1/733 | nyandarua/kiriita shauri blk 1/733 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 900000 | [11 empty] | pending payment
LANDS | 3250 | nyandarua/karati/6706 | nyandarua/karati/6706 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 1400000 | 1400000 | [10 empty] | complete
LANDS | 3251 | nyandarua/shamata/281 | nyandarua/shamata/281 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 400000 | 360000 | [10 empty] | complete
LANDS | 3252 | nyandarua/mkungi/3737 | nyandarua/mkungi/3737 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 300000 | [11 empty] | pending payment
LANDS | 3253 | nyandarua/shamata/281 | nyandarua/shamata/281 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 400000 | 360000 | [10 empty] | complete
LANDS | 3254 | nyandarua/shamata/4905 | nyandarua/shamata/4905 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 250000 | 225000 | [10 empty] | complete
LANDS | 3255 | nyandarua/shamata/4906 | nyandarua/shamata/4906 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 250000 | 225000 | [10 empty] | complete
LANDS | 3256 | nyandarua/muruaki/9893 | nyandarua/muruaki/9893 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 540000 | [11 empty] | pending payment
LANDS | 3257 | nyandarua/sabugo/3236 | nyandarua/sabugo/3236 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 500000 | [11 empty] | pending payment
LANDS | 3258 | nyandarua/mkungi/3736 | nyandarua/mkungi/3736 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 300000 | [11 empty] | pending payment
LANDS | 3259 | nyandarua/olaragwi/4346 | nyandarua/olaragwi/4346 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 900000 | [11 empty] | pending payment
LANDS | 3260 | nyandarua/s.kinangop/4188 | nyandarua/s.kinangop/4188 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 600000 | [11 empty] | pending payment
LANDS | 3261 | nyandarua/ol kalou west/1231 | nyandarua/ol kalou west/1231 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 1000000 | [11 empty] | pending payment
LANDS | 3262 | nyandarua/turasha/2489 | nyandarua/turasha/2489 | [7 empty] | 2022-06-01 | 2023-06-01 |  | 250000 | [11 empty] | pending payment
LANDS | 3263 | Gathaara- Land for Public Use- Githima Community | purchase of land | Land acquisition | Public utility land |  | Kinangop | Gathaara |  |  | 2022-06-01 | 2023-06-01 |  | 400000 | [11 empty] | pending payment
LANDS | 3264 | Gathaara- Land for Public Use- Gachucha Community | purchase of land | Land acquisition | Public utility land |  | Kinangop | Gathaara |  |  | 2022-06-01 | 2023-06-01 |  | 400000 | [11 empty] | pending payment
LANDS | 3265 | Murungaru - Acquisition of land for access road - Muchorui | purchase of land | Land acquisition | Access road |  | Kinangop | murungaru |  |  | 2022-06-01 | 2023-06-01 |  | 1000000 | [11 empty] | pending payment
LANDS | 3266 | Murungaru - Acquisition of land for access road - Arthur/Kahia | purchase of land | Land acquisition | Access road |  | Kinangop | murungaru |  |  | 2022-06-01 | 2023-06-01 |  | 1000000 | [11 empty] | pending payment
LANDS | 3267 | Karau ward - Acquisition of land for Kianda community Development - cooperative - Mwaniki Kibathi Macharia | purchase of land | Land acquisition | public utility land |  | O l Kalou | karau |  |  | 2022-06-01 | 2023-06-01 |  | 2000000 | [11 empty] | pending payment
LANDS | 3268 | Mirangine- Acquisition of Land for social amenity- Gwa Kiongo Stadium | purchase of land | Land acquisition | stadium |  | Ol kalou | mirangine |  |  | 2023-06-01 | 2024-06-01 |  | 7000000 | [11 empty] | pending payment
LANDS | 3269 | Acquisition of Land for Nyandundo Borehole- Mirangine | purchase of land | Land acquisition | bore hole |  | Ol kalou | mirangine |  |  | 2023-06-01 | 2024-06-01 |  | 500000 | [11 empty] | pending payment
LANDS | 3270 | Leshau Pondo- Acquisition of for social amenities - Gachengo | purchase of land | Land acquisition | public utility land |  | ndaragwa | L. Pondo |  |  | 2023-06-01 | 2024-06-01 |  | 1000000 | [11 empty] | pending payment
LANDS | 3271 | Leshau Pondo- Acquisition of for social amenities- Kiboya | purchase of land | Land acquisition | public utility land |  | ndaragwa | L. Pondo |  |  | 2023-06-01 | 2024-06-01 |  | 1000000 | [11 empty] | pending payment
LANDS | 3272 | Rurii- Purchase of land for Rurii Gichungo social amenity | purchase of land | Land acquisition | public utility land |  | ol kalou | rurii |  |  | 2023-06-01 | 2024-06-01 |  | 1000000 | [11 empty] | pending payment
LANDS | 3273 | Rurii- Purchase of land for Umoja water Tank Rurii | purchase of land | Land acquisition | water tank land |  | ol kalou | rurii |  |  | 2023-06-01 | 2024-06-01 |  | 500000 | [11 empty] | pending payment
LANDS | 3274 | Gathanji- Njoro Borehore- Compensation for transfer to community | purchase of land | bore hole |  |  | ol jororok | gathanji |  |  | 2023-06-01 | 2024-06-01 |  | 1550000 | [11 empty] | pending payment
LANDS | 3275 | Kahuruko Market Access Road - N.Kinangop | purchase of land | Land acquisition | Access road |  | Kinangop | N. Kinangop |  |  | 2023-06-01 | 2024-06-01 |  | 2000000 | [11 empty] | ongoing-phased project
LANDS | 3276 | Githabai- Purchase of Githae access road land - Samuel Gachanja -Half acre | purchase of land | Land acquisition | Access road |  | Kinangop | githabai |  |  | 2023-06-01 | 2024-06-01 |  | 800000 | [11 empty] | process ongoing
LANDS | 3277 | Githabai- Purchase of Githae access road land - James Mbogoro -Quarter acre | purchase of land | Land acquisition | Access road |  | Kinangop | githabai |  |  | 2023-06-01 | 2024-06-01 |  | 400000 | [11 empty] | process ongoing
LANDS | 3278 | Purchase of land for access road - Nyakio ward | purchase of land | Land acquisition | Access road |  | Kinangop | nyakio |  |  | 2023-06-01 | 2024-06-01 |  | 1000000 | [11 empty] | process ongoing
LANDS | 3279 | Purchase of land for Norfolk ECDE-Njabini ward | purchase of land | Land acquisition | ECDE land |  | kinangop | njabini |  |  | 2023-06-01 | 2024-06-01 |  | 1000000 | [11 empty] | process ongoing
LANDS | 3280 | Purchase of land for Kamonde Mwihoko access road-Gathaara ward | purchase of land | Land acquisition | Access road |  | Kinangop | gathaara |  |  | 2023-06-01 | 2024-06-01 |  | 700000 | [11 empty] | process ongoing
LANDS | 3281 | Purchase of land for Rutuba Primary access Road-Geta ward | purchase of land | Land acquisition | Access road |  | kipipiri | geta |  |  | 2023-06-01 | 2024-06-01 |  | 700000 | [11 empty] | process ongoing
LANDS | 3282 | Purchase of land for water tower - Gathanji | purchase of land | Land acquisition | water tower land |  | ol jororok | gathanji |  |  | 2023-06-01 | 2024-06-01 |  | 800000 | [11 empty] | process ongoing
LANDS | 3283 | Purchase of land for Wamwai access road-Charagita ward | purchase of land | Land acquisition | Access road |  | ol kalou | charagita |  |  | 2023-06-01 | 2024-06-01 |  | 800000 | [11 empty] | process ongoing
LANDS | 3284 | Purchase of land for Waichere access road-Weru ward | purchase of land | Land acquisition | Access road |  | ol jororok | weru |  |  | 2023-06-01 | 2024-06-01 |  | 1000000 | [11 empty] | process ongoing
LANDS | 3285 | Purchase of land for Mbuyu access road-Leshau Pondo ward | purchase of land | Land acquisition | Access road |  | ndaragwa | L, Pondo |  |  | 2023-06-01 | 2024-06-01 |  | 700000 | 700000 | [10 empty] | process ongoing
LANDS | 3286 | Githioro Ward- Purchase of land for public utility- Gathiriga Community water project | purchase of land | Land acquisition | public utility land |  | kinangop | githioro |  |  | 2023-06-01 | 2024-06-01 |  | 800000 | 800000 | [10 empty] | process ongoing
LANDS | 3287 | Purchase of land for Divai access road-Leshau Pondo ward | purchase of land | Land acquisition | Access road |  | ndaragwa | L, Pondo |  |  | 2023-06-01 | 2025-06-01 |  | 700000 | 700000 | [10 empty] | process ongoing
LANDS | 3288 | Acquisition of land for expansion of Engineer hospital- Gathaara ward | purchase of land | Land acquisition | public utility land |  | kinangop | gathaara |  |  | 2024-06-01 | 2025-06-01 |  | 15000000 | 15000000 | [10 empty] | complete
LANDS | 3289 | Acquistion of land for Mairo-Inya Market- Kiriita Ward | purchase of land | Land acquisition | public utility land |  | ndaragwa | kiriita |  |  | 2024-06-01 | 2025-06-01 |  | 10000000 | 10000000 | [10 empty] | complete
LANDS | 3290 | Karau - Acquisition of Land for Kandeto ECDE | purchase of land | Land acquisition | public utility land |  | ol kalou | karau |  |  | 2024-06-01 | 2025-06-01 |  | 1200000 | 1200000 | [10 empty] | complete
LANDS | 3291 | Magumu Jua Kali Toilet Block | construction of Jua Kali Toilet Block | construction | public toilet |  | kinangop | magumu |  |  | 2015-07-01 | 2016-06-01 |  | 692496.8 | 692497 | [10 empty] | complete
LANDS | 3292 | Olkalou Urban Improvement phase I- Extension of shoulders, drain & walkway along roads A4 & B20 | construction of shoulders, drain & walkway | construction | shoulders, drain & walkway |  | ol kalou | karau |  |  | 2015-07-01 | 2016-06-01 |  | 5000000 | 4999925 | [10 empty] | complete
LANDS | 3293 | Septic tank at Bahati Estate | construction of Septic tank | construction | sceptic tank |  | ol kalou | karau |  |  | 2016-07-01 | 2017-06-01 |  | 2500000 | 2423472 | [10 empty] | complete
LANDS | 3294 | Drainage and walkways in Ndaragwa – Central ward | construction of Drainage and walkways | construction |  |  | ndaragwa | central |  |  | 2017-07-01 | 2018-06-01 |  | 2000000 | 1999521 | [10 empty] | complete
LANDS | 3295 | Construction of Lands Office | construction of ardhi house | construction | lands offices |  | ol kalou | kaimbaga |  |  | 2017-07-01 | 2018-06-01 |  | 100000000 | 83476917.6 | [10 empty] | complete
LANDS | 3296 | Engineer Drainage &walkways already done | construction of Drainage &walkways | construction | Drainage &walkways |  | kinangopgathaara |  |  |  | 2017-07-01 | 2018-06-01 |  | 2000000 | 1999492 | [10 empty] | complete
LANDS | 3297 | Drainage and walkways in Olkalou town – Karau ward | construction of Drainage &walkways | construction | Drainage &walkways |  | ol kalou | karau |  |  | 2017-07-01 | 2018-06-01 |  | 2000000 | 1990444 | [10 empty] | complete
LANDS | 3298 | Drainage and walkways in Miharati - kipipiri | construction of Drainage &walkways | construction | Drainage &walkways |  | kipipiri | kipipiri |  |  | 2017-07-01 | 2018-06-01 |  | 2000000 | 1990212 | [10 empty] | complete
LANDS | 3299 | Provision of Parking lots at Olkalou town for Revenue Enhancement – Karau Ward | construction of Parking lots | construction | Parking lots |  | ol kalou | karau |  |  | 2018-07-01 | 2019-06-01 |  | 3000000 | 2896000 | [10 empty] | complete
LANDS | 3300 | Towns designs upgrade and update | [8 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | [11 empty] | complete
LANDS | 3301 | Drainage and walkways in Ol jororok | construction of Drainage and walkways | construction | Drainage and walkways |  | ol jororok | weru |  |  | 2018-07-01 | 2019-06-01 |  | 1000000 | 999919.6 | [10 empty] | complete
LANDS | 3302 | Drainage and walkways in Ndaragwa | construction of Drainage and walkways | construction | Drainage and walkways |  | ndaragwa | central |  |  | 2018-07-01 | 2019-06-01 |  | 1000000 | 999873.36 | [10 empty] | complete
LANDS | 3303 | Drainage and walkways in Miharati | construction of Drainage and walkways | construction | Drainage and walkways |  | kipipiri | kipipiri |  |  | 2018-07-01 | 2019-06-01 |  | 1842000 | 1841000 | [10 empty] | complete
LANDS | 3304 | Drainage and walkways in Engineer | construction of Drainage and walkways | construction | Drainage and walkways |  | kinangop | gathaara |  |  | 2018-07-01 | 2019-06-01 |  | 1842000 | 1835642 | [10 empty] | complete
LANDS | 3305 | Engineer Town Parking lots | construction of Parking lots | construction | Parking lots |  | kinangop | gathaara |  |  | 2018-07-01 | 2019-06-01 |  | 8000000 | 7420752 | [10 empty] | complete
LANDS | 3306 | Olkalou Drainage system &Parking lots | construction of Drainage system &Parking lots | construction | Drainage system &Parking lots |  | ol kalou | karau |  |  | 2018-07-01 | 2019-06-01 |  | 14000000 | 13308680 | [10 empty] | complete
LANDS | 3307 | Gwakiongo Centre upgrade - KDSP | construction of cabros | construction | cabros |  | ol kalou | mirangine |  |  | 2019-07-01 | 2020-06-01 |  | 5000000 | 4920240 | [10 empty] | complete
LANDS | 3308 | Captain Centre upgrade- KDSP | construction of drainage | construction | drainage |  | ol kalou | kaimbaga |  |  | 2019-07-01 | 2020-06-01 |  | 2000000 | 1997565 | [10 empty] | complete
LANDS | 3309 | Mairo Inya Upgrade - KDSP | construction of cabros | construction |  |  | ndaragwa | kiriita |  |  | 2019-07-01 | 2020-06-01 |  | 5000000 | 4996350 | [10 empty] | complete
LANDS | 3310 | Kwa Haraka drainage - KDSP | construction of cabros | construction | cabros |  | kinangop | nyakio |  |  | 2019-07-01 | 2020-06-01 |  | 2000000 | 1998162 | [10 empty] | complete
LANDS | 3311 | Murungaru Drainage | construction of drainage | construction | drainage |  | kinangop | murungaru |  |  | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999845 | [10 empty] | complete
LANDS | 3312 | Nyakio- Upgrade of Kwa Haraka Town | construction of cabros | construction | cabros |  | kinangop | nyakio |  |  | 2023-06-01 | 2024-06-01 |  | 2000000 | [11 empty] | pending payment
LANDS | 3313 | Murungaru - Construction of drainage system -urban areas outside the municipalities | construction of drainage | construction | drainage |  | kinangop | murungaru |  |  | 2023-06-01 | 2024-06-01 |  | 2500000 | 2500000 | [10 empty] | complete
LANDS | 3314 | Kanjuiri Ward-Implementation of drainage works-Ngorika | construction of drainage | construction | drainage |  | ol kalou | kanjuiri |  |  | 2023-06-01 | 2024-06-01 |  | 1000000 | 1000000 | [10 empty] | pending payment
LANDS | 3315 | Kenya Informal settlement program(KISIP 2) | construction of roads and public lighting | construction | roads and public lighting |  | ol kalou | kaimbaga |  |  | 2023-06-01 | 2024-06-01 |  | 50000000 | 50000000 | [10 empty] | works ongoing
LANDS | 3316 | Kiriita Ward-Town upgrade and culverts | construction of drainage and culverts | construction | drainage and culverts |  | ndaragwa | kiriita |  |  | 2023-06-01 | 2024-06-01 |  | 2000000 | 2000000 | [10 empty] | pending payment
LANDS | 3317 | Upgrade of Kwa Haraka Town | construction of drainage | construction | drainage |  | kinangop | nyakio |  |  | 2024-06-01 | 2025-06-01 |  | 2000000 | 2000000 | [10 empty] | complete
LANDS | 3318 | Upgrade of Karangatha Trading Centre | construction of drainage | construction | drainage |  | kinangop | nyakio |  |  | 2024-06-01 | 2025-06-01 |  | 2000000 | 2000000 | [10 empty] | complete
LANDS | 3319 | Drainage works-magumu town- Magumu Ward | construction of drainage | construction | drainage |  | kinangop | magumu |  |  | 2024-06-01 | 2025-06-01 |  | 1000000 | 1000000 | [10 empty] | complete
LANDS | 3320 | Improvement of Municipal Access Rds-KUSP | construction of cabro roads | construction | cabro roads |  | ol kalou | karau |  |  | 2018/2019 | 2018/2019 |  | 26543400 | 26543400 | [10 empty] | complete
LANDS | 3321 | Solid Waste Mgt-KUSP | purchase of SWM equipment | procurement | SWM equipment |  | ol kalou | karau |  |  | 2018/2019 | 2018/2019 |  | 15000000 | 15000000 | [10 empty] | complete
LANDS | 3322 | Olkalou Drainage system &Parking lots-KUSP | construction of drainage &Parking lots- | construction | drainage &Parking lots- |  | ol kalou | karau |  |  | 2018/2019 | 2018/2019 |  | 40000000 | 40000000 | [10 empty] | complete
LANDS | 3323 | Construction of street lighting of Roads-KUSP | construction of street lighting | construction | street lighting |  | ol kalou | karau&kaimbaga |  |  | 2018/2019 | 2018/2019 |  | 20000000 | 20000000 | [10 empty] | complete
LANDS | 3324 | Upgrading of Market Stalls-KUSP | construction of Market Stalls | construction | Market Stalls |  | ol kalou | karau |  |  | 2018/2019 | 2018/2019 |  | 30000000 | 30000000 | [10 empty] | complete
LANDS | 3325 | Development of Engineering designs for Ol Kalou Municipality -KUSP | Development of Engineering designs | Designing | Engineering designs |  | ol kalou | karau |  |  | 2018/2019 | 2018/2019 |  | 4000000 | 4000000 | [10 empty] | complete
LANDS | 3326 | Upgrading of Municipality Roads to Motorable Level and Pavings Works-KUSP | construction of Roads & Pavings | construction | Roads & Pavings |  | ol kalou | karau |  |  | 2019/2020 | 2019/2020 |  | 50543400 | 50543400 | [10 empty] | complete
LANDS | 3327 | Construction of a Paving Block Plant-KUSP | Construction of a Paving Block Plant | construction | Paving Block Plant |  | ol kalou | kaimbaga |  |  | 2019/2020 | 2019/2020 |  | 35000000 | 35000000 | [10 empty] | complete
LANDS | 3328 | Rollover and Variations of the Proposed Estate Roads Improvement Parking lots and Water Drain in Olkalou Town AND the Proposed Construction of Modern Market, Installation of Solar Lighting and Solid Waste Management in Ol-kalou Town -KUSP | Construction of Estate Roads, Parking lots , drainage, Modern Market, solar street lightind and SWM | construction | Improvement of ol kalou town |  | ol kalou | karau&kaimbaga |  |  | 2019/2020 | 2019/2020 |  | 35000000 | 35000000 | [10 empty] | complete
LANDS | 3329 | Development of the Modern Municipal Cemetry, Abattoir, Drainage and Solid Waste Mgt, Beautification-KUSP | Construction of Cemetry, Abattoir, Drainage and Solid Waste Mgt, Beautification | construction | Cemetry, Abattoir, Drainage and Solid Waste Mgt, Beautification |  | ol kalou | karau&kaimbaga |  |  | 2019/2020 | 2019/2020 |  | 10000000 | 10000000 | [10 empty] | complete
LANDS | 3330 | Maintenance of Municipal KUSP Projects | maintenance of projects | maintenance | well maintained projects |  | ol kalou | karau&kaimbaga |  |  | 2019/2020 | 2019/2020 |  | 5000000 | 5000000 | [10 empty] | complete
LANDS | 3331 | Construction of Ol'Kalou Multipurpose Hall | Construction of Multipurpose Hall | construction | Multipurpose Hall |  | ol kalou | kaimbaga |  |  | 2021/2022 | 2022/2023 |  | 35000000 | 34122081 | [10 empty] | complete
LANDS | 3332 | Infrastructure upgrade works in informal settlement within urban setup- World Bank KISIP II | construction of roads and public lighting | construction | roads and public lighting |  | ol kalou | kaimbaga |  |  | 2022/2023 | 2022/2023 |  | 25000000 | [11 empty] | project ongoing
LANDS | 3333 | Roofing of Ol'Kalou Old market and associated work | Roofing of Ol'Kalou Old market | construction | Market |  | ol kalou | karau |  |  | 2022/2023 | 2022/2023 |  | 2000000 | 1995587 | [10 empty] | complete
LANDS | 3334 | Paving block Plant and cemetery 3 phase power connection | construction of Paving block Plant and cemetery | construction | Paving block Plant and cemetery |  | ol kalou | kaimbaga |  |  | 2022/2023 | 2022/2023 |  | 1900000 | 1900000 | [10 empty] | complete
LANDS | 3335 | Ol'Kalou town signages | installation of signages | construction | signages |  | ol kalou | karau |  |  | 2022/2023 | 2022/2023 |  | 300000 | 300000 | [10 empty] | complete
LANDS | 3336 | Olkalou market- installation of 6 metal gates and repainting | installation of gates and repainting | construction | gates and repainting |  | ol kalou | karau |  |  | 2022/2023 | 2022/2023 |  | 1200000 | 1200000 | [10 empty] | complete
LANDS | 3337 | Repair and Maintenance of the infrastrustural projects of the Municipality including KUSP projects, markets, parkings, drainage, pavements etc | Repair and Maintenance of projects | maintenance | well maintained projects |  | ol kalou | karau&kaimbaga |  |  | 2023/2024 | 2023/2024 |  | 2500000 | 2500000 | [10 empty] | complete
LANDS | 3338 | Roofing of Ol'Kalou Old market and associated work | Roofing of market | construction | roofed market |  | ol kalou | karau |  |  | 2023/2024 | 2023/2024 |  | 3000000 | 3000000 | [10 empty] | complete
LANDS | 3339 | Completion of Ol'Kalou Multipurpose Hall- Ol'Kalou Municipality | Completion of Ol'Kalou Multipurpose Hall | construction | Multipurpose Hal |  | ol kalou | kaimbaga |  |  | 2023/2024 | 2023/2024 |  | 5000000 | 4997266 | [10 empty] | complete
LANDS | 3340 | Construction of toilet-Tumaini | construction of toilet | construction | toilet |  | ol kalou | kanjuiri |  |  | 2023/2024 | 2023/2024 |  | 1500000 | 1500000 | [10 empty] | complete
LANDS | 3341 | Construction of toilet-kariamu | construction of toilet | construction | toilet |  | ol kalou | wanjohi |  |  | 2023/2024 | 2023/2024 |  | 1500000 | 1500000 | [10 empty] | complete
LANDS | 3342 | Tree planting for beautification and environmental management | Tree planting for beautification | environmental management | beautiful town |  | ol kalou | karau&kaimbaga |  |  | 2023/2024 | 2023/2024 |  | 1000000 | 999763 | [10 empty] | complete
LANDS | 3343 | Install 2 floodlights- Karau ward | installation of flood lights |  |  |  | ol kalou | karau |  |  | 2024/25 | 2024/2025 |  | 2800000 | 2800000 | [10 empty] | complete
LANDS | 3344 | Repair and Maintenance of the infrastrustural projects of the Municipality including KUSP projects, markets, parkings, pavements etc | Repair and Maintenance of projects |  |  |  | ol kalou | karau&kaimbaga |  |  | 2024/25 | 2024/2025 |  | 1000000 | 1000000 | [10 empty] | complete
LANDS | 3345 | Infrastructure upgrade within the municipality(drainage,walkways,beautification e.t.c) | construction of drainage,walkways,beautification | construction | Drainage works |  | kinangop | gathaara&engineer |  |  | 2023/2024 | 2023/2024 |  | 3000000 | 2996000 | [10 empty] | complete
LANDS | 3346 | Development of drainage system in Ndunyu Njeru-N.Kinangop ward | construction of drainage,walkways,beautification | construction | Drainage works |  | kinangop | N. kinangop |  |  | 2024/25 | 2024/2025 |  | 1500000 | 1500000 | [10 empty] | complete
LANDS | 3347 | Installation of 30M High floodlight- Ndaragwa Central | construction of drainage,walkways,beautification | construction | Drainage works |  | kinangop | Engineer |  |  | 2024/25 | 2024/2025 |  | 1500000 | 1500000 | [10 empty] | complete
LANDS | 3348 | Development of drainage system in Engineer town-Gathaara ward | construction of drainage,walkways,beautification | construction | Drainage works |  | kinangop | Gtahaara |  |  | 2024/25 | 2024/2025 |  | 1500000 | 1500000 | [10 empty] | complete
LANDS | 3349 | Development of drainage system in Ndinda-Murungaru ward | construction of drainage,walkways,beautification | construction | Drainage works |  | kinangop | Murungaru |  |  | 2024/25 | 2024/2025 |  | 1500000 | 1500000 | [10 empty] | complete
LANDS | 3350 | Infrastructure upgrade within the municipality(drainage,walkways,beautification e.t.c) | construction of drainage,walkways,beautification |  | construction | drainage,walkways,beautification | ndaragwa | kiriita&cental |  |  | 2023/2024 | 2023/2024 |  | 3000000 | 3000000 | [10 empty] | Pending payment
LANDS | 3351 | Unclogging of drainage structures/Culverts- Gatimu ward | construction of drainage structures | construction |  | drainage structures | ol jororok | gatimu |  |  | 2023/2024 | 2023/2024 |  | 500000 | 500000 | [10 empty] | Pending payment
LANDS | 3352 | Installation of 30M High floodlight- Ndaragwa Central | construction of drainage structures | construction |  | drainage structures | Ndaragwa | Ndaragwa Central |  |  | 2024/25 | 2024/2025 |  | 1400000 | 1400000 | [10 empty] | complete
LANDS | 3353 | Completion of drainage works - Headquarters | construction of drainage structures | construction |  | drainage structures | Ndaragwa | kiriita |  |  | 2024/25 | 2024/2025 |  | 4000000 | 4000000 | [10 empty] | complete
LANDS | 3354 | Development of drainage systems - Leshau Pondo | construction of drainage structures | construction |  | drainage structures | Ndaragwa | L. pondo |  |  | 2024/25 | 2024/2025 |  | 1400000 | 1400000
ROADS | 3355 | Wards Roads Work | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2013-07-01 | 2014-06-01 |  | 362000000 | 361083220 |  | C.G.N | [5 empty] | 361083220 |  |  | complete | 100%
ROADS | 3356 | Kariamu-Kaheho (Muthama Road) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2013-07-01 | 2014-06-01 |  | 64000000 | 44000000 |  | C.G.N | [5 empty] | 44000000 |  |  | complete | 100%
ROADS | 3357 | J-30 Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2013-07-01 | 2014-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3358 | Rurii –Matura-Passenga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2013-07-01 | 2014-06-01 |  | 9500000 | 8000000 |  | C.G.N | [5 empty] | 8000000 |  |  | complete | 100%
ROADS | 3359 | Aberdare-Mutongwe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2013-07-01 | 2014-06-01 |  | 2000000 | 850000 |  | C.G.N | [5 empty] | 850000 |  |  | complete | 100%
ROADS | 3360 | WANJURA- MUGOIRI, LAITA- GICHAKA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 625430 | 625430 |  | C.G.N | [5 empty] | 625430 |  |  | complete | 100%
ROADS | 3361 | MATINDIRI-GRADWEL RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 625430 | 625430 |  | C.G.N | [5 empty] | 625430 |  |  | complete | 100%
ROADS | 3362 | KONA-SIR-WAKINGURU RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 625430 | 625430 |  | C.G.N | [5 empty] | 625430 |  |  | complete | 100%
ROADS | 3363 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 625434 | 625434 |  | C.G.N | [5 empty] | 625434 |  |  | complete | 100%
ROADS | 3364 | KASUKU-KANGUI& OL'JORO-OROK TOWNS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 858000 | 858000 |  | C.G.N | [5 empty] | 858000 |  |  | complete | 100%
ROADS | 3365 | J-30-GITONGA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 441000 | 441000 |  | C.G.N | [5 empty] | 441000 |  |  | complete | 100%
ROADS | 3366 | KWA FORESTER- J-30 GITONGA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 222000 | 222000 |  | C.G.N | [5 empty] | 222000 |  |  | complete | 100%
ROADS | 3367 | KANYUGI-WISDOM RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 981410 | 981410 |  | C.G.N | [5 empty] | 981410 |  |  | complete | 100%
ROADS | 3368 | ASSORTED ROADS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 645400 | 645400 |  | C.G.N | [5 empty] | 645400 |  |  | complete | 100%
ROADS | 3369 | KAHURU-MURUAKI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 591000 | 591000 |  | C.G.N | [5 empty] | 591000 |  |  | complete | 100%
ROADS | 3370 | ENGINEER TOWNSHIP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3798114 | 3798114 |  | C.G.N | [5 empty] | 3798114 |  |  | complete | 100%
ROADS | 3371 | BOARDER-GEORGE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 298500 | 298500 |  | C.G.N | [5 empty] | 298500 |  |  | complete | 100%
ROADS | 3372 | CHUMA- KANYUGI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3504000 | 3504000 |  | C.G.N | [5 empty] | 3504000 |  |  | complete | 100%
ROADS | 3373 | RAITA,MUTARAKWA,KANAMBA,MUTONYORA,KITIRI,KAMUREMBO,JOEL RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1085000 | 1085000 |  | C.G.N | [5 empty] | 1085000 |  |  | complete | 100%
ROADS | 3374 | ENGINEER TOWNSHIP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2240000 | 2240000 |  | C.G.N | [5 empty] | 2240000 |  |  | complete | 100%
ROADS | 3375 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 300000 | 300000 |  | C.G.N | [5 empty] | 300000 |  |  | complete | 100%
ROADS | 3376 | C69- ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2020000 | 2020000 |  | C.G.N | [5 empty] | 2020000 |  |  | complete | 100%
ROADS | 3377 | LAIKIPIA UNIVERSITY-SUNFALL- GOOD FALL RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 815520 | 815520 |  | C.G.N | [5 empty] | 815520 |  |  | complete | 100%
ROADS | 3378 |  | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3002000 | 3002000 |  | C.G.N | [5 empty] | 3002000 |  |  | complete | 100%
ROADS | 3379 | KONA MBAYA- GATHANJI- BOIMAN RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 510784.46 | 510784.46 |  | C.G.N | [5 empty] | 510784.46 |  |  | complete | 100%
ROADS | 3380 | NGANATHA- HUHOINI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2634000 | 2634000 |  | C.G.N | [5 empty] | 2634000 |  |  | complete | 100%
ROADS | 3381 | KAHURUKO RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 510000 | 510000 |  | C.G.N | [5 empty] | 510000 |  |  | complete | 100%
ROADS | 3382 | KARIAMU- GICHUNGO AIPCEA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3383 | MUTAMAIYU-LEE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2484000 | 2484000 |  | C.G.N | [5 empty] | 2484000 |  |  | complete | 100%
ROADS | 3384 | MUNG'ETO-MUTAMAIYU | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1103400 | 1103400 |  | C.G.N | [5 empty] | 1103400 |  |  | complete | 100%
ROADS | 3385 | RAITA,MUTARAKWA,KANAMBA,MUTONYORA,KITIRI,JOEL RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 537000 | 537000 |  | C.G.N | [5 empty] | 537000 |  |  | complete | 100%
ROADS | 3386 | MUTAMAIYU-LEE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1952008 | 1952008 |  | C.G.N | [5 empty] | 1952008 |  |  | complete | 100%
ROADS | 3387 | KAHURU BLDG'-RAITA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 166800 | 166800 |  | C.G.N | [5 empty] | 166800 |  |  | complete | 100%
ROADS | 3388 | AIC-NORTH KINANGOP HOSP.RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 168000 | 168000 |  | C.G.N | [5 empty] | 168000 |  |  | complete | 100%
ROADS | 3389 | ENGINEER TOWNSHIP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 480,000,01 | 480,000,00 |  | C.G.N | [5 empty] | 480,000,00 |  |  | complete | 100%
ROADS | 3390 | BANI-TABOR-MUKANDA- MANYATTA-NUNGA-NJUNU-PRIMAROSA-LAKE VIEW RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2654452 | 2654452 |  | C.G.N | [5 empty] | 2654452 |  |  | complete | 100%
ROADS | 3391 | EQUATOR-SUERA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2649500 | 2649500 |  | C.G.N | [5 empty] | 2649500 |  |  | complete | 100%
ROADS | 3392 | NJIRU -KANGUU RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2575000 | 2575000 |  | C.G.N | [5 empty] | 2575000 |  |  | complete | 100%
ROADS | 3393 | RUNDA – CATHOLIC-SHUHUDIA- MUGO RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2400000 | 2400000 |  | C.G.N | [5 empty] | 2400000 |  |  | complete | 100%
ROADS | 3394 | MUHINDI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3395 | GIKINGI-BARAKA-EQUATOR-TABOR- KIANJATA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3460250 | 3460250 |  | C.G.N | [5 empty] | 3460250 |  |  | complete | 100%
ROADS | 3396 | RAMI-KARI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3397 | MUNGETHO KIBATHI-BANI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2925000 | 2925000 |  | C.G.N | [5 empty] | 2925000 |  |  | complete | 100%
ROADS | 3398 | GRADING WORKS IN VARIOUS ROADS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | complete | 100%
ROADS | 3399 | CONCRETE TUBE CULVERT | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2575000 | 2575000 |  | C.G.N | [5 empty] | 2575000 |  |  | complete | 100%
ROADS | 3400 | LABOUR INSTALLATION CULVERTS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 375000 | 375000 |  | C.G.N | [5 empty] | 375000 |  |  | complete | 100%
ROADS | 3401 | SUNSET-BARAKA-NGOMONGO-GIKINGI-GACHATHI- KIERU-EMANUEL-KAYOLE | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3500000 | 3500000 |  | C.G.N | [5 empty] | 3500000 |  |  | complete | 100%
ROADS | 3402 | KIANJATA-NJUNU RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3500000 | 3500000 |  | C.G.N | [5 empty] | 3500000 |  |  | complete | 100%
ROADS | 3403 | BANI-KISIMA KISIMA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3500000 | 3500000 |  | C.G.N | [5 empty] | 3500000 |  |  | complete | 100%
ROADS | 3404 | GACHUIRO-MWISHO-RAMI-PBK-MUNGETHO-T/ROSE-ORAIMUTIA-NGANO-SILAH | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 4958287.36 | 4958287.36 |  | C.G.N | [5 empty] | 4958287.36 |  |  | complete | 100%
ROADS | 3405 | HAWAGATUA,GETA KIAMBOGO-MARIMU RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2608620 | 2608620 |  | C.G.N | [5 empty] | 2608620 |  |  | complete | 100%
ROADS | 3406 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 366000 | 366000 |  | C.G.N | [5 empty] | 366000 |  |  | complete | 100%
ROADS | 3407 | RUMWE-DISPENSARY-MIHATO RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 108000 | 108000 |  | C.G.N | [5 empty] | 108000 |  |  | complete | 100%
ROADS | 3408 | KIANJOGU-KIAMBOGO NO.3 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 5615000 | 5615000 |  | C.G.N | [5 empty] | 5615000 |  |  | complete | 100%
ROADS | 3409 | GITHAE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 379800 | 379800 |  | C.G.N | [5 empty] | 379800 |  |  | complete | 100%
ROADS | 3410 | VARIOUS SECTIONS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2440750 | 2440750 |  | C.G.N | [5 empty] | 2440750 |  |  | complete | 100%
ROADS | 3411 | JUNCTION-GITHABAI-NYAKIO RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 4186000 | 4186000 |  | C.G.N | [5 empty] | 4186000 |  |  | complete | 100%
ROADS | 3412 | MUMUI-TURASHA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1482000 | 1482000 |  | C.G.N | [5 empty] | 1482000 |  |  | complete | 100%
ROADS | 3413 | BARA INYA-KOMU-JURA SEC SCH.RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2966865.5 | 2966865.5 |  | C.G.N | [5 empty] | 2966865.5 |  |  | complete | 100%
ROADS | 3414 | MUGUMO-INI ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 415959 | 415959 |  | C.G.N | [5 empty] | 415959 |  |  | complete | 100%
ROADS | 3415 | KIRIKO TRADING CNTR.-ITHAGU-GITHIORO RIRICHUA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1075000 | 1075000 |  | C.G.N | [5 empty] | 1075000 |  |  | complete | 100%
ROADS | 3416 | BARA ITHATU- MUKAMI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1038000 | 1038000 |  | C.G.N | [5 empty] | 1038000 |  |  | complete | 100%
ROADS | 3417 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 276000 | 276000 |  | C.G.N | [5 empty] | 276000 |  |  | complete | 100%
ROADS | 3418 | KAMANDE PRI SCH ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3920400 | 3920400 |  | C.G.N | [5 empty] | 3920400 |  |  | complete | 100%
ROADS | 3419 | MAHINGA BRIDGE – MUMBI ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 712800 | 712800 |  | C.G.N | [5 empty] | 712800 |  |  | complete | 100%
ROADS | 3420 | MATHATHI - MALFAN ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2138400 | 2138400 |  | C.G.N | [5 empty] | 2138400 |  |  | complete | 100%
ROADS | 3421 | RUMATHI ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 534600 | 534600 |  | C.G.N | [5 empty] | 534600 |  |  | complete | 100%
ROADS | 3422 | CASINO – GEN. NJOROGE ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 712800 | 712800 |  | C.G.N | [5 empty] | 712800 |  |  | complete | 100%
ROADS | 3423 | MIHUTI – KANDUTURA ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3207600 | 3207600 |  | C.G.N | [5 empty] | 3207600 |  |  | complete | 100%
ROADS | 3424 | MWIRERI – MALEWA ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 5078700 | 5078700 |  | C.G.N | [5 empty] | 5078700 |  |  | complete | 100%
ROADS | 3425 | KAGAA-MUKUNGI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2546200 | 2546200 |  | C.G.N | [5 empty] | 2546200 |  |  | complete | 100%
ROADS | 3426 | NGORIKA – CHAMUKA ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 789872 | 789872 |  | C.G.N | [5 empty] | 789872 |  |  | complete | 100%
ROADS | 3427 | KANJUIRI – KAREBE ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1978500 | 1978500 |  | C.G.N | [5 empty] | 1978500 |  |  | complete | 100%
ROADS | 3428 | NJIGAGA – KANJUIRI ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 987400 | 987400 |  | C.G.N | [5 empty] | 987400 |  |  | complete | 100%
ROADS | 3429 | NGORIKA TOWNSHIP DRAINAGE | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1854000 | 1854000 |  | C.G.N | [5 empty] | 1854000 |  |  | complete | 100%
ROADS | 3430 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 447800 | 447800 |  | C.G.N | [5 empty] | 447800 |  |  | complete | 100%
ROADS | 3431 | GITHIORO- RUTARA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 996000 | 996000 |  | C.G.N | [5 empty] | 996000 |  |  | complete | 100%
ROADS | 3432 | MUGUMO PRI. –KANYORO ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 220000 | 220000 |  | C.G.N | [5 empty] | 220000 |  |  | complete | 100%
ROADS | 3433 | SLAUGHTER HOUSE – QUARRY ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1315000 | 1315000 |  | C.G.N | [5 empty] | 1315000 |  |  | complete | 100%
ROADS | 3434 | OLKALOU QUARRY ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1695000 | 1695000 |  | C.G.N | [5 empty] | 1695000 |  |  | complete | 100%
ROADS | 3435 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 306000 | 306000 |  | C.G.N | [5 empty] | 306000 |  |  | complete | 100%
ROADS | 3436 | OL'KALOU- CATHOLIC-GACHUE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3450000 | 3450000 |  | C.G.N | [5 empty] | 3450000 |  |  | complete | 100%
ROADS | 3437 | OLKALOU TOWN ROADS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | complete | 100%
ROADS | 3438 | KARUGUTU- MUNGETHO ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1556427 | 1556427 |  | C.G.N | [5 empty] | 1556427 |  |  | complete | 100%
ROADS | 3439 | KAGOTHO-CAPTAIN RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1183500 | 1183500 |  | C.G.N | [5 empty] | 1183500 |  |  | complete | 100%
ROADS | 3440 | OL'KALOU JUNCTION- TUMAINI- MUCHEMI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1183500 | 1183500 |  | C.G.N | [5 empty] | 1183500 |  |  | complete | 100%
ROADS | 3441 | MIHARATI-MARKET RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 6000 | 6000 |  | C.G.N | [5 empty] | 6000 |  |  | complete | 100%
ROADS | 3442 | KIPIPIRI PRI.-KAMUHU-WATER TANK | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 66000 | 66000 |  | C.G.N | [5 empty] | 66000 |  |  | complete | 100%
ROADS | 3443 | FOREST ONE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2364000 | 2364000 |  | C.G.N | [5 empty] | 2364000 |  |  | complete | 100%
ROADS | 3444 | KAHURUKO-RUTUMO-KIGOGO | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1839000 | 1839000 |  | C.G.N | [5 empty] | 1839000 |  |  | complete | 100%
ROADS | 3445 | INSTALLATION OFCULVERTS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 180000 | 180000 |  | C.G.N | [5 empty] | 180000 |  |  | complete | 100%
ROADS | 3446 | GRAVELLING WORKS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2364000 | 2364000 |  | C.G.N | [5 empty] | 2364000 |  |  | complete | 100%
ROADS | 3447 | WAKIROGO STADIUM | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2100 | 2100 |  | C.G.N | [5 empty] | 2100 |  |  | complete | 100%
ROADS | 3448 | MUNYU-MUHINDI PRI | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 54500 | 54500 |  | C.G.N | [5 empty] | 54500 |  |  | complete | 100%
ROADS | 3449 | GITHUNGUCHU- KANDUMA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1475000 | 1475000 |  | C.G.N | [5 empty] | 1475000 |  |  | complete | 100%
ROADS | 3450 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 312000 | 312000 |  | C.G.N | [5 empty] | 312000 |  |  | complete | 100%
ROADS | 3451 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 360000 | 360000 |  | C.G.N | [5 empty] | 360000 |  |  | complete | 100%
ROADS | 3452 | KWA MILKA -FOREST RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1108500 | 1108500 |  | C.G.N | [5 empty] | 1108500 |  |  | complete | 100%
ROADS | 3453 | HEROS- WAKAHOTI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2825860 | 2825860 |  | C.G.N | [5 empty] | 2825860 |  |  | complete | 100%
ROADS | 3454 | MAYU-MTI MOJA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 994500 | 994500 |  | C.G.N | [5 empty] | 994500 |  |  | complete | 100%
ROADS | 3455 | SHAURI-KIANDA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 665393 | 665393 |  | C.G.N | [5 empty] | 665393 |  |  | complete | 100%
ROADS | 3456 | MUTHIGA CNTR.- MUTHIGA PRI.-NYAKINYUA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2376000 | 2376000 |  | C.G.N | [5 empty] | 2376000 |  |  | complete | 100%
ROADS | 3457 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 306000 | 306000 |  | C.G.N | [5 empty] | 306000 |  |  | complete | 100%
ROADS | 3458 | KAGOTHO- ROAD (KIENI | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3459 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 252000 | 252000 |  | C.G.N | [5 empty] | 252000 |  |  | complete | 100%
ROADS | 3460 | RAICHIRI-MAYU-MTI MOJA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3492000 | 3492000 |  | C.G.N | [5 empty] | 3492000 |  |  | complete | 100%
ROADS | 3461 | KIHINGI-NDOGINO(KIENI | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 857000 | 857000 |  | C.G.N | [5 empty] | 857000 |  |  | complete | 100%
ROADS | 3462 | MAYU JUNCTION-MTI MOJA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2273381.55 | 2273381.55 |  | C.G.N | [5 empty] | 2273381.55 |  |  | complete | 100%
ROADS | 3463 | JAPAN/MUTHIGA PRI.-NYAKINYUA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2640000 | 2640000 |  | C.G.N | [5 empty] | 2640000 |  |  | complete | 100%
ROADS | 3464 | KIHINGI-NDOGINO(KIENI | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1024580 | 1024580 |  | C.G.N | [5 empty] | 1024580 |  |  | complete | 100%
ROADS | 3465 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 315000 | 315000 |  | C.G.N | [5 empty] | 315000 |  |  | complete | 100%
ROADS | 3466 | DANJO-MUSYOKA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3600000.01 | 3600000 |  | C.G.N | [5 empty] | 3600000 |  |  | complete | 100%
ROADS | 3467 | MAKUNO-WANGAI | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1697080 | 1697080 |  | C.G.N | [5 empty] | 1697080 |  |  | complete | 100%
ROADS | 3468 | NYANDUNDO-GITHIMA & MATHAKWA PRI. RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1620100 | 1620100 |  | C.G.N | [5 empty] | 1620100 |  |  | complete | 100%
ROADS | 3469 | GRADING WORKS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | complete | 100%
ROADS | 3470 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 55300 | 55300 |  | C.G.N | [5 empty] | 55300 |  |  | complete | 100%
ROADS | 3471 | BARA NJERU,CCM-KIRIMA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1620100 | 1620100 |  | C.G.N | [5 empty] | 1620100 |  |  | complete | 100%
ROADS | 3472 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 84000 | 84000 |  | C.G.N | [5 empty] | 84000 |  |  | complete | 100%
ROADS | 3473 | MURUNGARU-MUGUMOINI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3201540 | 3201540 |  | C.G.N | [5 empty] | 3201540 |  |  | complete | 100%
ROADS | 3474 | KIROBI-KAHUHO RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2680200 | 2680200 |  | C.G.N | [5 empty] | 2680200 |  |  | complete | 100%
ROADS | 3475 | MURUNGARU TOWNSHIP ROADS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 408000 | 408000 |  | C.G.N | [5 empty] | 408000 |  |  | complete | 100%
ROADS | 3476 | NDUNYU NJERU- KITIRI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1672720 | 1672720 |  | C.G.N | [5 empty] | 1672720 |  |  | complete | 100%
ROADS | 3477 | NDUNYU NJERU MARKET-NANDARASI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3531132 | 3531132 |  | C.G.N | [5 empty] | 3531132 |  |  | complete | 100%
ROADS | 3478 | NDUNYU NJERU-MUHUTI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 550000 | 550000 |  | C.G.N | [5 empty] | 550000 |  |  | complete | 100%
ROADS | 3479 | NDUNYU NJERU-MUHUTI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1450000 | 1450000 |  | C.G.N | [5 empty] | 1450000 |  |  | complete | 100%
ROADS | 3480 | NDUNYU NJERU- KITIRI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2576088 | 2576088 |  | C.G.N | [5 empty] | 2576088 |  |  | complete | 100%
ROADS | 3481 | KAHURUKO-KARIMA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2643700 | 2643700 |  | C.G.N | [5 empty] | 2643700 |  |  | complete | 100%
ROADS | 3482 | GITITE ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3483 | KWABEKENYA-KIAMBARIKI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 859414 | 859414 |  | C.G.N | [5 empty] | 859414 |  |  | complete | 100%
ROADS | 3484 | NDUNYU NJERU,MUHUTI,MOSETI,KAHURUKO,KAREMA,KABAA,KIANDEGE RDS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3531132 | 3531132 |  | C.G.N | [5 empty] | 3531132 |  |  | complete | 100%
ROADS | 3485 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 280000 | 280000 |  | C.G.N | [5 empty] | 280000 |  |  | complete | 100%
ROADS | 3486 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 84000 | 84000 |  | C.G.N | [5 empty] | 84000 |  |  | complete | 100%
ROADS | 3487 | WIYUMIRIRIE- KIANDONGORO RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2900000 | 2900000 |  | C.G.N | [5 empty] | 2900000 |  |  | complete | 100%
ROADS | 3488 | GRADING WORKS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3489 | 81-SUBUKU HEALTH CNTR RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1050000 | 1050000 |  | C.G.N | [5 empty] | 1050000 |  |  | complete | 100%
ROADS | 3490 | NDARAGWA TOWN ACCESS RDS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 792000 | 792000 |  | C.G.N | [5 empty] | 792000 |  |  | complete | 100%
ROADS | 3491 | NDARAGWA- KAHUTHU RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2550000 | 2550000 |  | C.G.N | [5 empty] | 2550000 |  |  | complete | 100%
ROADS | 3492 | WIYUMIRIRIE- KIANDONGORO RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1610000 | 1610000 |  | C.G.N | [5 empty] | 1610000 |  |  | complete | 100%
ROADS | 3493 | SOIL-CHURIRI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1360112 | 1360112 |  | C.G.N | [5 empty] | 1360112 |  |  | complete | 100%
ROADS | 3494 | ABERDARE- MTONGWE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2851200 | 2851200 |  | C.G.N | [5 empty] | 2851200 |  |  | complete | 100%
ROADS | 3495 | MWIRIGI-MIMANO RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1979600 | 1979600 |  | C.G.N | [5 empty] | 1979600 |  |  | complete | 100%
ROADS | 3496 | NJABINI-KIARUTARA ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 37566832 | 37566832 |  | C.G.N | [5 empty] | 37566832 |  |  | complete | 100%
ROADS | 3497 | WARURUNGANA-KINAMBA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1825050 | 1825050 |  | C.G.N | [5 empty] | 1825050 |  |  | complete | 100%
ROADS | 3498 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 924000 | 924000 |  | C.G.N | [5 empty] | 924000 |  |  | complete | 100%
ROADS | 3499 | KCB-KARWANGI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2880000 | 2880000 |  | C.G.N | [5 empty] | 2880000 |  |  | complete | 100%
ROADS | 3500 | VARIOUS SECTIONS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1785250 | 1785250 |  | C.G.N | [5 empty] | 1785250 |  |  | complete | 100%
ROADS | 3501 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 924000 | 924000 |  | C.G.N | [5 empty] | 924000 |  |  | complete | 100%
ROADS | 3502 | YANGA-CHURIRI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1393907 | 1393907 |  | C.G.N | [5 empty] | 1393907 |  |  | complete | 100%
ROADS | 3503 | YANGA(BRIDGE | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3504 | KIHUNGURU-KAMAU-KOMU ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2394000 | 2394000 |  | C.G.N | [5 empty] | 2394000 |  |  | complete | 100%
ROADS | 3505 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 238000 | 238000 |  | C.G.N | [5 empty] | 238000 |  |  | complete | 100%
ROADS | 3506 | KAMAU-KOMU-RAGIO FOREST RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1199996 | 1199996 |  | C.G.N | [5 empty] | 1199996 |  |  | complete | 100%
ROADS | 3507 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 450000 | 450000 |  | C.G.N | [5 empty] | 450000 |  |  | complete | 100%
ROADS | 3508 | MUKIRI- KARATU RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 430200 | 430200 |  | C.G.N | [5 empty] | 430200 |  |  | complete | 100%
ROADS | 3509 | YANGA-GITONGA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1393907 | 1393907 |  | C.G.N | [5 empty] | 1393907 |  |  | complete | 100%
ROADS | 3510 | KIHUNGURU-KARANGATHA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3300000 | 3300000 |  | C.G.N | [5 empty] | 3300000 |  |  | complete | 100%
ROADS | 3511 | KARANGATHA-TOWN BODABODA SITE | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 25500 | 25500 |  | C.G.N | [5 empty] | 25500 |  |  | complete | 100%
ROADS | 3512 | RWANYAMBO PRI.- FOREST RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1229000 | 1229000 |  | C.G.N | [5 empty] | 1229000 |  |  | complete | 100%
ROADS | 3513 | GATHANGARI LOWER-YANGA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3514 | MIKINDU-KARIAMU RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 930921 | 930921 |  | C.G.N | [5 empty] | 930921 |  |  | complete | 100%
ROADS | 3515 | GITHUNGURI – STAGE ONE ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1151400 | 1151400 |  | C.G.N | [5 empty] | 1151400 |  |  | complete | 100%
ROADS | 3516 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 480000 | 480000 |  | C.G.N | [5 empty] | 480000 |  |  | complete | 100%
ROADS | 3517 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 450000 | 450000 |  | C.G.N | [5 empty] | 450000 |  |  | complete | 100%
ROADS | 3518 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 480000 | 480000 |  | C.G.N | [5 empty] | 480000 |  |  | complete | 100%
ROADS | 3519 | NGATIA-NGOTHO-MATURA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1980000 | 1980000 |  | C.G.N | [5 empty] | 1980000 |  |  | complete | 100%
ROADS | 3520 | GRADING WORKS | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | complete | 100%
ROADS | 3521 |  | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1414310 | 1414310 |  | C.G.N | [5 empty] | 1414310 |  |  | complete | 100%
ROADS | 3522 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 651000 | 651000 |  | C.G.N | [5 empty] | 651000 |  |  | complete | 100%
ROADS | 3523 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 369500 | 369500 |  | C.G.N | [5 empty] | 369500 |  |  | complete | 100%
ROADS | 3524 | KANJOGU PRI.-OLBOLOSAT RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 4042500 | 4042500 |  | C.G.N | [5 empty] | 4042500 |  |  | complete | 100%
ROADS | 3525 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 252000 | 252000 |  | C.G.N | [5 empty] | 252000 |  |  | complete | 100%
ROADS | 3526 | MUTHAMA-KAHEHO LOT 1 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 3990000 | 3990000 |  | C.G.N | [5 empty] | 3990000 |  |  | complete | 100%
ROADS | 3527 | MUHAKAINI-SIMBARA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1147500 | 1147500 |  | C.G.N | [5 empty] | 1147500 |  |  | complete | 100%
ROADS | 3528 | KARAI-KWANDAYA-MWIHANGIA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2996250 | 2996250 |  | C.G.N | [5 empty] | 2996250 |  |  | complete | 100%
ROADS | 3529 | SHAMATA- KAKA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 2996250 | 2996250 |  | C.G.N | [5 empty] | 2996250 |  |  | complete | 100%
ROADS | 3530 | SHAMATA- MUTHAMA-KAKA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1648000 | 1648000 |  | C.G.N | [5 empty] | 1648000 |  |  | complete | 100%
ROADS | 3531 | MUTHAMA-KAHEHO LOT 4 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1336700 | 1336700 |  | C.G.N | [5 empty] | 1336700 |  |  | complete | 100%
ROADS | 3532 | KARIAMU-MICHORE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 797211 | 797211 |  | C.G.N | [5 empty] | 797211 |  |  | complete | 100%
ROADS | 3533 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 396000 | 396000 |  | C.G.N | [5 empty] | 396000 |  |  | complete | 100%
ROADS | 3534 | MAGOMANO-NATHAN RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1156845 | 1156845 |  | C.G.N | [5 empty] | 1156845 |  |  | complete | 100%
ROADS | 3535 | KIAMBOGO-GATUKAINI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1311089 | 1311089 |  | C.G.N | [5 empty] | 1311089 |  |  | complete | 100%
ROADS | 3536 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 375000 | 375000 |  | C.G.N | [5 empty] | 375000 |  |  | complete | 100%
ROADS | 3537 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 480000 | 480000 |  | C.G.N | [5 empty] | 480000 |  |  | complete | 100%
ROADS | 3538 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 480000 | 480000 |  | C.G.N | [5 empty] | 480000 |  |  | complete | 100%
ROADS | 3539 | CULVERT INSTALLATION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1295666.4 | 1295666.4 |  | C.G.N | [5 empty] | 1295666.4 |  |  | complete | 100%
ROADS | 3540 | GATONDO-MITI ITANO RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1295666 | 1295666 |  | C.G.N | [5 empty] | 1295666 |  |  | complete | 100%
ROADS | 3541 | KASUKU-LESIRIKO | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | complete | 100%
ROADS | 3542 | MADARAKA-CHAKARELI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2014-07-01 | 2015-06-01 |  | 1675440 | 1675440 |  | C.G.N | [5 empty] | 1675440 |  |  | complete | 100%
ROADS | 3543 | Foot bridge Leshau pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3544 | Ndaragwa town Drainage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3545 | Forest Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3546 | Ndunduri nyonjoro road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3999440 |  | C.G.N | [5 empty] | 3999440 |  |  | complete | 100%
ROADS | 3547 | Ndunyu -njeru Stage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1498000 |  | C.G.N | [5 empty] | 1498000 |  |  | complete | 100%
ROADS | 3548 | Kiheo Ngova road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3549 | Kangui T-rose road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1123500 |  | C.G.N | [5 empty] | 1123500 |  |  | complete | 100%
ROADS | 3550 | Ngorika Cool Pasture road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1124970 |  | C.G.N | [5 empty] | 1124970 |  |  | complete | 100%
ROADS | 3551 | Bridges gichuru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3552 | Installation of Culvert at weru ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 600000 |  | C.G.N | [5 empty] | 600000 |  |  | complete | 100%
ROADS | 3553 | Kaimbaga -Kahinga-Mumbi bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | complete | 100%
ROADS | 3554 | Junction kahia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3555 | Engineer Town Gathara Drainage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 2996000 |  | C.G.N | [5 empty] | 2996000 |  |  | complete | 100%
ROADS | 3556 | Road works Gathara ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 1999296 |  | C.G.N | [5 empty] | 1999296 |  |  | complete | 100%
ROADS | 3557 | Equator mbunyu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3558 | Park view Bara inya Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1124800 |  | C.G.N | [5 empty] | 1124800 |  |  | complete | 100%
ROADS | 3559 | Kihara Ack Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1119340 |  | C.G.N | [5 empty] | 1119340 |  |  | complete | 100%
ROADS | 3560 | Cuba thiga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3561 | Kamahia Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1123828 |  | C.G.N | [5 empty] | 1123828 |  |  | complete | 100%
ROADS | 3562 | Kamba Gatimu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1863000 | 1863000 |  | C.G.N | [5 empty] | 1863000 |  |  | complete | 100%
ROADS | 3563 | Bridges Kanyi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3564 | Muthiga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1199960 | 1199960 |  | C.G.N | [5 empty] | 1199960 |  |  | complete | 100%
ROADS | 3565 | Karuang'i joyce road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3566 | Kioneki road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2697480 | 2697480 |  | C.G.N | [5 empty] | 2697480 |  |  | complete | 100%
ROADS | 3567 | Kangia PCEA Saba Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3568 | Warui Kahuhu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3569 | Ndunyu -njeru Drainage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 2938500 |  | C.G.N | [5 empty] | 2938500 |  |  | complete | 100%
ROADS | 3570 | Njabini Drainange | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3571 | PI-polytechnic wanjiku RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3572 | Kanyenyaini-Munyaka RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3573 | madaraka gibathi-equitor-githima-muhinde-heshima rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3574 | Kanyawa-karadi RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3575 | Mwendandadu -heni-karate RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3576 | Munyeki Road off OLK-NRB highway- expansion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 7583770 | 7583770 |  | C.G.N | [5 empty] | 7583770 |  |  | complete | 100%
ROADS | 3577 | Munyeki Road off OLK-NRB highway- drainage/culvert instalation(7 lines) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | complete | 100%
ROADS | 3578 | Rutumo-kahuru-ndemi RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3579 | Mairo Inya Drainange & sewarage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3580 | Kaimbaga Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3581 | HQ kirima Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3582 | Yanga Mbaka Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 6000000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | complete | 100%
ROADS | 3583 | Kihara -81 RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3584 | Roads maintainace(Fuel levy fund) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 44714122 | 44714122 |  | C.G.N | [5 empty] | 44714122 |  |  | complete | 100%
ROADS | 3585 | Bridges and Drainage works(fuel levy fund) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | complete | 100%
ROADS | 3586 | Roads 2000 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 73000000 | 73000000 |  | C.G.N | [5 empty] | 73000000 |  |  | complete | 100%
ROADS | 3587 | County Headquaters | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 32000000 | 32000000 |  | C.G.N | [5 empty] | 32000000 |  |  | complete | 100%
ROADS | 3588 | Completion of County Headquaters | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 20000000 | 20000000 |  | C.G.N | [5 empty] | 20000000 |  |  | complete | 100%
ROADS | 3589 | Kiambogo Gatuikaini Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3590 | Munge Dam Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | complete | 100%
ROADS | 3591 | Kihungi Ndurubu Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 6000000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | complete | 100%
ROADS | 3592 | Construction of Designated Parking Area-Major Towns | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | complete | 100%
ROADS | 3593 | Nguli Drainage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3594 | Juakali Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4500000 | 4500000 |  | C.G.N | [5 empty] | 4500000 |  |  | complete | 100%
ROADS | 3595 | Kirathimo Neema Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 6000000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | complete | 100%
ROADS | 3596 | Ex Finally Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | complete | 100%
ROADS | 3597 | Gachata RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3598 | Thirikwa rod | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3599 | Phase II Senior Kahuho bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3600 | Mbaruku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3601 | PIAS Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3602 | Tosha Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3603 | Kahura Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3604 | Kamiruri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3605 | Good fall Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3606 | Engineer centre roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | complete | 100%
ROADS | 3607 | Kamurembo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3608 | Kaboi- Kinja road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3609 | Sheba Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3610 | Gathaara Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3611 | Micibau Karadi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3612 | ATC rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3613 | Line Moja/kiajata road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3614 | Githutha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | complete | 100%
ROADS | 3615 | Churiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3616 | kinamba muthoga rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3617 | Dr githaiga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3618 | Tumaini Githure road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3619 | Muthui Miiri Wanjiku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | complete | 100%
ROADS | 3620 | Kamirita - Barabara Njeru road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3621 | Gichungo pri.- thitai road: | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3622 | Kihurure- loriondo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3623 | Mumbi- kieni wooden bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | complete | 100%
ROADS | 3624 | Kihurure- wambui bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3625 | Juakali roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | complete | 100%
ROADS | 3626 | Kihara- a.c.k road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3627 | Macharia- julius- mahee road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | complete | 100%
ROADS | 3628 | Rumathi pri. School- d-69 (ndemi) road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3629 | Ciira- chamuka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3630 | Ngorika- cool pasture road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3631 | Dairy- st. Monicah road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3632 | Nyaituga- kangathia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3633 | Njigaga – kanjuiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3634 | Karebe- kanjuiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3635 | Grading general | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 800000 | 600000 |  | C.G.N | [5 empty] | 600000 |  |  | complete | 100%
ROADS | 3636 | P.c.e.a –kagotho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3637 | Mundia estate roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100%
ROADS | 3638 | Kandeto road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | complete | 100%
ROADS | 3639 | Asorted roads in karau ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | complete | 100%
ROADS | 3640 | Olkalou roads estate upgrade | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3641 | Karau estate | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | complete | 100%
ROADS | 3642 | bridge – njonado road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3643 | ccm- kirima road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3644 | kamirita road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3645 | kamuyu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 800000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | complete | 100%
ROADS | 3646 | karungo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3647 | kibedera road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 600000 |  | C.G.N | [5 empty] | 600000 |  |  | complete | 100%
ROADS | 3648 | matunda road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3649 | mbora dam- head quarter road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3650 | mbora- njaaga- makurata road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3651 | muchemi dam road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3652 | muthui-miiri- wanjiku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | complete | 100%
ROADS | 3653 | nyandundo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | complete | 100%
ROADS | 3654 | p.i –polytechnic road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3655 | riverside- head quarter road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | complete | 100%
ROADS | 3656 | chema road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100%
ROADS | 3657 | Kahuruko-muikia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3658 | Kanyari bridge road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3659 | Kianduba- rigui road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | complete | 100%
ROADS | 3660 | Wakabout road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100%
ROADS | 3661 | Rurii-kirima – mukuru road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100%
ROADS | 3662 | Mairo-mugumo- kanyoro road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1200000 | 1200000 |  | C.G.N | [5 empty] | 1200000 |  |  | complete | 100%
ROADS | 3663 | Kwa Matu Wangombe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1133000 | 1080040 |  | C.G.N | [5 empty] | 1080040 |  |  | Completed | 100%
ROADS | 3664 | Munanda intake | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1133000 | 992060 |  | C.G.N | [5 empty] | 992060 |  |  | Completed | 100%
ROADS | 3665 | Juction Kangongo pry | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1133000 | 1076638 |  | C.G.N | [5 empty] | 1076638 |  |  | Completed | 100%
ROADS | 3666 | Mihato-Muracia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2300000 | 2273800 |  | C.G.N | [5 empty] | 2273800 |  |  | Completed | 100%
ROADS | 3667 | Kanjangiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 2996500 |  | C.G.N | [5 empty] | 2996500 |  |  | Completed | 100%
ROADS | 3668 | JOHN B-KAGUTHI | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2113200 | 2099679 |  | C.G.N | [5 empty] | 2099679 |  |  | Completed | 100%
ROADS | 3669 | JUCTION -ROTUMBA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2132000 | 2020600 |  | C.G.N | [5 empty] | 2020600 |  |  | Completed | 100%
ROADS | 3670 | Kamahia wa chege road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1123828 |  | C.G.N | [5 empty] | 1123828 |  |  | Completed | 100%
ROADS | 3671 | Chief mathenge ngoyo dam | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 969990 |  | C.G.N | [5 empty] | 969990 |  |  | Completed | 100%
ROADS | 3672 | Kabati Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 997820 |  | C.G.N | [5 empty] | 997820 |  |  | Completed | 100%
ROADS | 3673 | Ithonga wamuioko road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 400000 | 399480 |  | C.G.N | [5 empty] | 399480 |  |  | Completed | 100%
ROADS | 3674 | Kanyua maya road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1499100 |  | C.G.N | [5 empty] | 1499100 |  |  | Completed | 100%
ROADS | 3675 | Kambingu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Completed | 100%
ROADS | 3676 | Mahinnga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1156700 | 1156700 |  | C.G.N | [5 empty] | 1156700 |  |  | Completed | 100%
ROADS | 3677 | Gitwe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 945900 |  | C.G.N | [5 empty] | 945900 |  |  | Completed | 100%
ROADS | 3678 | Wendo Nursery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 530000 | 530000 |  | C.G.N | [5 empty] | 530000 |  |  | Completed | 100%
ROADS | 3679 | Kahuruko Ndemi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Completed | 100%
ROADS | 3680 | St peter githima gathiriga-gathiriga pry | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1492016 |  | C.G.N | [5 empty] | 1492016 |  |  | Completed | 100%
ROADS | 3681 | Tulasha –munoru feeder road,rugano,mukumi,harambee,ndashi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | Completed | 100%
ROADS | 3682 | Bara-ithano-wangui-kagaa-mbogo-kiriko-wanjugi,mwangaza feeder road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1492016 |  | C.G.N | [5 empty] | 1492016 |  |  | Completed | 100%
ROADS | 3683 | Kagia –p.c.e.a laini saba and tigoni kangondi (i) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1624750 | 1624750 |  | C.G.N | [5 empty] | 1624750 |  |  | Completed | 100%
ROADS | 3684 | Kagia –p.c.e.a laini saba and tigoni kangondi (ii) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1496350 | 1496350 |  | C.G.N | [5 empty] | 1496350 |  |  | Completed | 100%
ROADS | 3685 | Kangondi-kangondi nursery(guba) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1800000 | 1700000 |  | C.G.N | [5 empty] | 1700000 |  |  | Completed | 100%
ROADS | 3686 | Bara inya wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 550000 |  | C.G.N | [5 empty] | 550000 |  |  | Completed | 100%
ROADS | 3687 | Kihenjo –michore | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 598560 |  | C.G.N | [5 empty] | 598560 |  |  | Completed | 100%
ROADS | 3688 | Miti-itano-mubao | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 400000 | 380000 |  | C.G.N | [5 empty] | 380000 |  |  | Completed | 100%
ROADS | 3689 | Kagika –thingoro road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 570533 |  | C.G.N | [5 empty] | 570533 |  |  | Completed | 100%
ROADS | 3690 | Karema –forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 599000 |  | C.G.N | [5 empty] | 599000 |  |  | Completed | 100%
ROADS | 3691 | Rayeta kirogi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 404000 | 404000 |  | C.G.N | [5 empty] | 404000 |  |  | Completed | 100%
ROADS | 3692 | Wakaba muchori rayeta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 598000 |  | C.G.N | [5 empty] | 598000 |  |  | Completed | 100%
ROADS | 3693 | Kiracha-gachugia -road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 540000 |  | C.G.N | [5 empty] | 540000 |  |  | Completed | 100%
ROADS | 3694 | Macharia-njeru-mahee | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 700000 | 670533 |  | C.G.N | [5 empty] | 670533 |  |  | Completed | 100%
ROADS | 3695 | Park-view –bara inya | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1124800 |  | C.G.N | [5 empty] | 1124800 |  |  | Completed | 100%
ROADS | 3696 | Mwireri- kimuru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 570533 |  | C.G.N | [5 empty] | 570533 |  |  | Completed | 100%
ROADS | 3697 | C-69-cattle dip-idp | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 598560 |  | C.G.N | [5 empty] | 598560 |  |  | Completed | 100%
ROADS | 3698 | Magomano-juction –chebe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 498560 |  | C.G.N | [5 empty] | 498560 |  |  | Completed | 100%
ROADS | 3699 | Malewa -huherio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 598000 |  | C.G.N | [5 empty] | 598000 |  |  | Completed | 100%
ROADS | 3700 | Dn-kimuru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1166666 | 1166666 |  | C.G.N | [5 empty] | 1166666 |  |  | Completed | 100%
ROADS | 3701 | Magomano-nathan road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1166666 | 1166666 |  | C.G.N | [5 empty] | 1166666 |  |  | Completed | 100%
ROADS | 3702 | Miti-itano gatodo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1166666 | 1166666 |  | C.G.N | [5 empty] | 1166666 |  |  | Completed | 100%
ROADS | 3703 | Muruai Pry Sch location 4 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1200000 | 1118700 |  | C.G.N | [5 empty] | 1118700 |  |  | Completed | 100%
ROADS | 3704 | Ndaragwa town Drainage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 907200 |  | C.G.N | [5 empty] | 907200 |  |  | Completed | 100%
ROADS | 3705 | forest Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Completed | 100%
ROADS | 3706 | Ndururi - Nyonjoro | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3999440 |  | C.G.N | [5 empty] | 3999440 |  |  | Completed | 100%
ROADS | 3707 | Kamiruri 91 Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 995000 |  | C.G.N | [5 empty] | 995000 |  |  | Completed | 100%
ROADS | 3708 | Kahutha Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 1999990 |  | C.G.N | [5 empty] | 1999990 |  |  | Completed | 100%
ROADS | 3709 | Lowduor Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 1999193 |  | C.G.N | [5 empty] | 1999193 |  |  | Completed | 100%
ROADS | 3710 | Ngamini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 1999804 |  | C.G.N | [5 empty] | 1999804 |  |  | Completed | 100%
ROADS | 3711 | Ngurumo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 1999990 |  | C.G.N | [5 empty] | 1999990 |  |  | Completed | 100%
ROADS | 3712 | Kihara- 81 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3962500 |  | C.G.N | [5 empty] | 3962500 |  |  | Completed | 100%
ROADS | 3713 | Kiriogo- Kangawa | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 1800080 |  | C.G.N | [5 empty] | 1800080 |  |  | Completed | 100%
ROADS | 3714 | Kiriogo-Munada | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 1999804 |  | C.G.N | [5 empty] | 1999804 |  |  | Completed | 100%
ROADS | 3715 | Kamiruri-kihara and Kihara- kiriogo rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2193540 | 2193540 |  | C.G.N | [5 empty] | 2193540 |  |  | Completed | 100%
ROADS | 3716 | Ndaragwa boys Muti umwe | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2262000 | 2260418 |  | C.G.N | [5 empty] | 2260418 |  |  | Completed | 100%
ROADS | 3717 | Kirigo- Tafaria | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 900033 |  | C.G.N | [5 empty] | 900033 |  |  | Completed | 100%
ROADS | 3718 | Muruai Pry Sch- Murichu- Matuiku | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1200000 | 1118700 |  | C.G.N | [5 empty] | 1118700 |  |  | Completed | 100%
ROADS | 3719 | Nyarich Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 2986500 |  | C.G.N | [5 empty] | 2986500 |  |  | Completed | 100%
ROADS | 3720 | Equator- Mbuyu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3951540 |  | C.G.N | [5 empty] | 3951540 |  |  | Completed | 100%
ROADS | 3721 | muthiga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3125000 | 3114308 |  | C.G.N | [5 empty] | 3114308 |  |  | Completed | 100%
ROADS | 3722 | Wakabout road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 2993675 |  | C.G.N | [5 empty] | 2993675 |  |  | Completed | 100%
ROADS | 3723 | Raichiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1400000 | 1314886 |  | C.G.N | [5 empty] | 1314886 |  |  | Completed | 100%
ROADS | 3724 | Kwanjora Raod | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1494500 |  | C.G.N | [5 empty] | 1494500 |  |  | Completed | 100%
ROADS | 3725 | General grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2700000 | 2698275 |  | C.G.N | [5 empty] | 2698275 |  |  | Completed | 100%
ROADS | 3726 | Culverts Kamwana | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Completed | 100%
ROADS | 3727 | Muhuri Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  |  |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3728 | Ndogino Mahianyu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 402020 | 402020 |  | C.G.N | [5 empty] | 402020 |  |  | Completed | 100%
ROADS | 3729 | Mithamo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 164000 | 164000 |  | C.G.N | [5 empty] | 164000 |  |  | Completed | 100%
ROADS | 3730 | Ndiiri Catholic Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 294520 | 294520 |  | C.G.N | [5 empty] | 294520 |  |  | Completed | 100%
ROADS | 3731 | Gatero Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 726900 | 726900 |  | C.G.N | [5 empty] | 726900 |  |  | Completed | 100%
ROADS | 3732 | Mama Wanjau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Completed | 100%
ROADS | 3733 | Mukoe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 166000 | 166000 |  | C.G.N | [5 empty] | 166000 |  |  | Completed | 100%
ROADS | 3734 | Kwamuira road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 528800 | 528800 |  | C.G.N | [5 empty] | 528800 |  |  | Completed | 100%
ROADS | 3735 | Thirikwa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3999500 |  | C.G.N | [5 empty] | 3999500 |  |  | Completed | 100%
ROADS | 3736 | Pesi-Mastoo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  |  |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3737 | kanjogu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 800000 | 734430 |  | C.G.N | [5 empty] | 734430 |  |  | Completed | 100%
ROADS | 3738 | Kiambogo site road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  |  |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3739 | gakoe- Kirima road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 999980 |  | C.G.N | [5 empty] | 999980 |  |  | Completed | 100%
ROADS | 3740 | EX- Ndana road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 597200 |  | C.G.N | [5 empty] | 597200 |  |  | Completed | 100%
ROADS | 3741 | Wachira theuri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 499776 |  | C.G.N | [5 empty] | 499776 |  |  | Completed | 100%
ROADS | 3742 | AIPCA Kaheho calvert | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 400000 | 400000 |  | C.G.N | [5 empty] | 400000 |  |  | Completed | 100%
ROADS | 3743 | Ndaya- Muhiriga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 497600 |  | C.G.N | [5 empty] | 497600 |  |  | Completed | 100%
ROADS | 3744 | Karai-kirimanjaro-Gathurima rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  |  |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3745 | Ziwani C. Church Rd/ ritaya st | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 498000 |  | C.G.N | [5 empty] | 498000 |  |  | Completed | 100%
ROADS | 3746 | Pauline shauri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  |  |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3747 | Starehe- Ndothua | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 900000 | 899400 |  | C.G.N | [5 empty] | 899400 |  |  | Completed | 100%
ROADS | 3748 | P.C.E.A - Kahembe | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 999990 |  | C.G.N | [5 empty] | 999990 |  |  | Completed | 100%
ROADS | 3749 | Baari Pry Watabby/ Kahembe Dispensary | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1494062 |  | C.G.N | [5 empty] | 1494062 |  |  | Completed | 100%
ROADS | 3750 | Pioneer- Mutarakwa/ Mungetho AIPCA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 951184 |  | C.G.N | [5 empty] | 951184 |  |  | Completed | 100%
ROADS | 3751 | Robkam- Mahihu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 994311.6 |  | C.G.N | [5 empty] | 994311.6 |  |  | Completed | 100%
ROADS | 3752 | Kamotho, Kiaritha, Munada/ Mastoo Kwanjuki/Mungetho AIPCA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 999464 |  | C.G.N | [5 empty] | 999464 |  |  | Completed | 100%
ROADS | 3753 | Tarmac Riverbank Academy Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1490000 |  | C.G.N | [5 empty] | 1490000 |  |  | Completed | 100%
ROADS | 3754 | Nyumba Ithatu- mahihu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3500000 | 3419640 |  | C.G.N | [5 empty] | 3419640 |  |  | Completed | 100%
ROADS | 3755 | Mukoe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1600000 | 1600000 |  | C.G.N | [5 empty] | 1600000 |  |  | Completed | 100%
ROADS | 3756 | Kingori- Mwalimu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2400000 | 2399020.6 |  | C.G.N | [5 empty] | 2399020.6 |  |  | Completed | 100%
ROADS | 3757 | Mukwanjo- Mwoni Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 999990 |  | C.G.N | [5 empty] | 999990 |  |  | Completed | 100%
ROADS | 3758 | Gatina rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2200000 | 2199330 |  | C.G.N | [5 empty] | 2199330 |  |  | Completed | 100%
ROADS | 3759 | Mutongwe rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1681000 | 1681000 |  | C.G.N | [5 empty] | 1681000 |  |  | Completed | 100%
ROADS | 3760 | Muthiga rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1125000 |  | C.G.N | [5 empty] | 1125000 |  |  | Completed | 100%
ROADS | 3761 | Dr. Githaiga rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 869200 |  | C.G.N | [5 empty] | 869200 |  |  | Completed | 100%
ROADS | 3762 | Mucibau - Karandi rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 980995 |  | C.G.N | [5 empty] | 980995 |  |  | Completed | 100%
ROADS | 3763 | Karuang'I Joyce rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 598600 |  | C.G.N | [5 empty] | 598600 |  |  | Completed | 100%
ROADS | 3764 | ATC rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3994750 |  | C.G.N | [5 empty] | 3994750 |  |  | Completed | 100%
ROADS | 3765 | Holly Oak - Forest Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3950000 |  | C.G.N | [5 empty] | 3950000 |  |  | Completed | 100%
ROADS | 3766 | Kioneki rd(A) & (B) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2700000 | 2697400 |  | C.G.N | [5 empty] | 2697400 |  |  | Completed | 100%
ROADS | 3767 | Githutha - Gocho rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1298400 |  | C.G.N | [5 empty] | 1298400 |  |  | Completed | 100%
ROADS | 3768 | Line Moja - Kianjata forest rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 1961000 |  | C.G.N | [5 empty] | 1961000 |  |  | Completed | 100%
ROADS | 3769 | Karuang'I Joyce rd (A) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1124904 |  | C.G.N | [5 empty] | 1124904 |  |  | Completed | 100%
ROADS | 3770 | Kanyinyaini -Munyaka rd( Shilikisho rd) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3958600 |  | C.G.N | [5 empty] | 3958600 |  |  | Completed | 100%
ROADS | 3771 | Kanyawa - Karadi rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3999200 |  | C.G.N | [5 empty] | 3999200 |  |  | Completed | 100%
ROADS | 3772 | Kinamba - Muthoga rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Completed | 100%
ROADS | 3773 | Gravelling disilting of side drains | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 937312 |  | C.G.N | [5 empty] | 937312 |  |  | Completed | 100%
ROADS | 3774 | Njabini Drainage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  |  |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3775 | Kimathi rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1734000 | 1734000 |  | C.G.N | [5 empty] | 1734000 |  |  | Completed | 100%
ROADS | 3776 | Gravel Patching in various rds in Njabini (A) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 495000 |  | C.G.N | [5 empty] | 495000 |  |  | Completed | 100%
ROADS | 3777 | Gravel patching in Njabini ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 683650 | 683150 |  | C.G.N | [5 empty] | 683150 |  |  | Completed | 100%
ROADS | 3778 | Holly oak road (additional) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 750000 | 734500 |  | C.G.N | [5 empty] | 734500 |  |  | Completed | 100%
ROADS | 3779 | Kanyawa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 900000 | 899000 |  | C.G.N | [5 empty] | 899000 |  |  | Completed | 100%
ROADS | 3780 | Kioneki road (additional) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 270000 | 269480 |  | C.G.N | [5 empty] | 269480 |  |  | Completed | 100%
ROADS | 3781 | Karuang'i - Joyce road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 600000 | 598600 |  | C.G.N | [5 empty] | 598600 |  |  | Completed | 100%
ROADS | 3782 | AIC Church Njabini rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3600000 | 3543800 |  | C.G.N | [5 empty] | 3543800 |  |  | Completed | 100%
ROADS | 3783 | Curiri - Makena | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3200000 | 3200000 |  | C.G.N | [5 empty] | 3200000 |  |  | Completed | 100%
ROADS | 3784 | Kwa Jane road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Completed | 100%
ROADS | 3785 | Kimamira road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Completed | 100%
ROADS | 3786 | Kiahiti road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 999200 |  | C.G.N | [5 empty] | 999200 |  |  | Completed | 100%
ROADS | 3787 | Caroboise rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2600000 | 2600000 |  | C.G.N | [5 empty] | 2600000 |  |  | Completed | 100%
ROADS | 3788 | varios rds in the ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Completed | 100%
ROADS | 3789 | Kihara - ACK rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 1122200 |  | C.G.N | [5 empty] | 1122200 |  |  | Completed | 100%
ROADS | 3790 | Installation of culverts at Wakimbo town | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Completed | 100%
ROADS | 3791 | White House rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1700000 | 1655375 |  | C.G.N | [5 empty] | 1655375 |  |  | Completed | 100%
ROADS | 3792 | Jesa Glory Kwa njau rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 2084760 |  | C.G.N | [5 empty] | 2084760 |  |  | Completed | 100%
ROADS | 3793 | Guest rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1700000 |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3794 | St. Mary Sulmak | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 2245580 |  | C.G.N | [5 empty] | 2245580 |  |  | Completed | 100%
ROADS | 3795 | Warui - Kahuhu rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3796 | Heavy & Light Grading in Magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1499997 |  | C.G.N | [5 empty] | 1499997 |  |  | Completed | 100%
ROADS | 3797 | Gravel Patching in Various roads in Magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1499970 |  | C.G.N | [5 empty] | 1499970 |  |  | Completed | 100%
ROADS | 3798 | Jackline- Soko mjinga rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3500000 | 3496426 |  | C.G.N | [5 empty] | 3496426 |  |  | Completed | 100%
ROADS | 3799 | kahuho- Karuru rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 2000000 | 2498940 |  | C.G.N | [5 empty] | 2498940 |  |  | Completed | 100%
ROADS | 3800 | Karangatha Health Center | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3801 | Fretha - Gachugwa route 18 rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 2480950 |  | C.G.N | [5 empty] | 2480950 |  |  | Completed | 100%
ROADS | 3802 | Bara - Inya | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1133000 |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3803 | Mutarakwa - Ugunyu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 2997100 |  | C.G.N | [5 empty] | 2997100 |  |  | Completed | 100%
ROADS | 3804 | Cuba - Thiga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1125000 | 2099625 |  | C.G.N | [5 empty] | 2099625 |  |  | Completed | 100%
ROADS | 3805 | Michinda rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 300000 |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3806 | Karangatha town rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3807 | Bako - Munanda rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1497994 |  | C.G.N | [5 empty] | 1497994 |  |  | Completed | 100%
ROADS | 3808 | Karangatha - Kihunguru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 2488028 |  | C.G.N | [5 empty] | 2488028 |  |  | Completed | 100%
ROADS | 3809 | Ndogonye rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3810 | Haraka town rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Completed | 100%
ROADS | 3811 | Karangatha - Mukiri rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 500000 | 999200 |  | C.G.N | [5 empty] | 999200 |  |  | Completed | 100%
ROADS | 3812 | Gravelling disilting of side drains | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1000000 | 900176 |  | C.G.N | [5 empty] | 900176 |  |  | Completed | 100%
ROADS | 3813 | Wamithi- Kimani rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 2999960 |  | C.G.N | [5 empty] | 2999960 |  |  | Completed | 100%
ROADS | 3814 | Gathangari -Lower yaanga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3995960 |  | C.G.N | [5 empty] | 3995960 |  |  | Completed | 100%
ROADS | 3815 | Kamau Komu -Ragia Forest | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 3000000 | 2999960 |  | C.G.N | [5 empty] | 2999960 |  |  | Completed | 100%
ROADS | 3816 | Kiamba forest | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1133000 | 2256000 |  | C.G.N | [5 empty] | 2256000 |  |  | Completed | 100%
ROADS | 3817 | Wanjumura | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1133000 |  |  | C.G.N | [8 empty] | Completed | 100%
ROADS | 3818 | Yaanga - Haraka Gwatikira | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1499300 |  | C.G.N | [5 empty] | 1499300 |  |  | Completed | 100%
ROADS | 3819 | Mbiru road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 4000000 | 3999012 |  | C.G.N | [5 empty] | 3999012 |  |  | Completed | 100%
ROADS | 3820 | bodaboda culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 300000 | 299000 |  | C.G.N | [5 empty] | 299000 |  |  | Completed | 100%
ROADS | 3821 | Wamithi rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2015-07-01 | 2016-06-01 |  | 1500000 | 1499600 |  | C.G.N | [5 empty] | 1499600 |  |  | Completed | 100%
ROADS | 3822 | Kayole - catholic - gachathi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1930500 | 1929500 |  | C.G.N | [5 empty] | 1929500 |  |  | Complete | 100%
ROADS | 3823 | West gate road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1930500 | 1929500 |  | C.G.N | [5 empty] | 1929500 |  |  | Complete | 100%
ROADS | 3824 | Muringe - waitegi - macadamia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1930500 | 1929500 |  | C.G.N | [5 empty] | 1929500 |  |  | Complete | 100%
ROADS | 3825 | Boiman junction - ndonga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1930500 | 1929500 |  | C.G.N | [5 empty] | 1929500 |  |  | Complete | 100%
ROADS | 3826 | Kamunya - iria ini - kiige - major - equator | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2871000 |  | C.G.N | [5 empty] | 2871000 |  |  | Complete | 100%
ROADS | 3827 | Health centre - nunga - kianjata road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1978800 |  | C.G.N | [5 empty] | 1978800 |  |  | Complete | 100%
ROADS | 3828 | Catholic - manyatta - iria ini road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1930500 | 1929500 |  | C.G.N | [5 empty] | 1929500 |  |  | Complete | 100%
ROADS | 3829 | Muthama road-shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3500000 | 3497806 |  | C.G.N | [5 empty] | 3497806 |  |  | COMPLETE | 100%
ROADS | 3830 | Gicheha - swamp - kag road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1930500 | 1929500 |  | C.G.N | [5 empty] | 1929500 |  |  | Complete | 100%
ROADS | 3831 | Kanguu - mutaro -stone city road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2869600 |  | C.G.N | [5 empty] | 2869600 |  |  | Complete | 100%
ROADS | 3832 | Kibathi -kisima - equator road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2970000 | 2969900 |  | C.G.N | [5 empty] | 2969900 |  |  | Complete | 100%
ROADS | 3833 | Grading gatimu ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2400000 | 2399999 |  | C.G.N | [5 empty] | 2399999 |  |  | Complete | 100%
ROADS | 3834 | Culvert in gatimu ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2475000 | 2475000 |  | C.G.N | [5 empty] | 2475000 |  |  | Complete | 100%
ROADS | 3835 | Nyakariang’a – mutitu water project accessibility road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3375000 | 3375000 |  | C.G.N | [5 empty] | 3375000 |  |  | Complete | 100%
ROADS | 3836 | Wamurita – gathima road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2376000 | 2375920 |  | C.G.N | [5 empty] | 2375920 |  |  | Complete | 100%
ROADS | 3837 | Ngomongo-emmanuel – kasa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3000000 | 2899800 |  | C.G.N | [5 empty] | 2899800 |  |  | ongoing | 100%
ROADS | 3838 | Mirichu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 988100 |  | C.G.N | [5 empty] | 988100 |  |  | Complete | 100%
ROADS | 3839 | Frether gachungwa rt18 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1692149 | 1690500 |  | C.G.N | [5 empty] | 1690500 |  |  | Complete | 100%
ROADS | 3840 | Karangatha stage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 789600 | 789600 |  | C.G.N | [5 empty] | 789600 |  |  | Complete | 100%
ROADS | 3841 | Kahuho - wairegi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1434000 | 1434000 |  | C.G.N | [5 empty] | 1434000 |  |  | Complete | 100%
ROADS | 3842 | Mutarakwa (a,b,c&d) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1879500 |  | C.G.N | [5 empty] | 1879500 |  |  | Complete | 100%
ROADS | 3843 | Bongo-cuba-james mwaura road-nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1486505 |  | C.G.N | [5 empty] | 1486505 |  |  | COMPLETE | 100%
ROADS | 3844 | Assorted roads (karangatha bara inya and warugu - ndungu road) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2970000 | 2968600 |  | C.G.N | [5 empty] | 2968600 |  |  | Complete | 100%
ROADS | 3845 | Wamukundi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 494800 |  | C.G.N | [5 empty] | 494800 |  |  | Complete | 100%
ROADS | 3846 | Gaturu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 493500 |  | C.G.N | [5 empty] | 493500 |  |  | Complete | 100%
ROADS | 3847 | Wahothi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 999000 | 989100 |  | C.G.N | [5 empty] | 989100 |  |  | Complete | 100%
ROADS | 3848 | Haraka - yanga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1484700 |  | C.G.N | [5 empty] | 1484700 |  |  | Complete | 100%
ROADS | 3849 | Kageraini acess roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 400000 | 399000 |  | C.G.N | [5 empty] | 399000 |  |  | ongoing | 100%
ROADS | 3850 | Wa biriha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 820500 | 820500 |  | C.G.N | [5 empty] | 820500 |  |  | Complete | 100%
ROADS | 3851 | Wa munoru baridi - gikebe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2671000 | 2670000 |  | C.G.N | [5 empty] | 2670000 |  |  | Complete | 100%
ROADS | 3852 | Grading nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1880998 |  | C.G.N | [5 empty] | 1880998 |  |  | Complete | 100%
ROADS | 3853 | Joyce road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 988800 |  | C.G.N | [5 empty] | 988800 |  |  | Ongoing | 100%
ROADS | 3854 | ATC road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1880400 |  | C.G.N | [5 empty] | 1880400 |  |  | Complete | 100%
ROADS | 3855 | St peter's road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1484550 | 1484550 |  | C.G.N | [5 empty] | 1484550 |  |  | Complete | 100%
ROADS | 3856 | Profesa ngugi - gikungu road (coroboise) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1386000 | 1386000 |  | C.G.N | [5 empty] | 1386000 |  |  | Complete | 100%
ROADS | 3857 | Njabini - polytechnic road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1483600 |  | C.G.N | [5 empty] | 1483600 |  |  | Complete | 100%
ROADS | 3858 | Slaughter house road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1376000 | 1376000 |  | C.G.N | [5 empty] | 1376000 |  |  | Complete | 100%
ROADS | 3859 | Ha kamwere road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | Complete | 100%
ROADS | 3860 | Maritati - gichia | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1980000 |  | C.G.N | [5 empty] | 1980000 |  |  | Complete | 100%
ROADS | 3861 | Shirikisho | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1980000 |  | C.G.N | [5 empty] | 1980000 |  |  | Complete | 100%
ROADS | 3862 | Assorted roads works njabini kiburu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2376000 | 2376000 |  | C.G.N | [5 empty] | 2376000 |  |  | Complete | 100%
ROADS | 3863 | St paul warurungana | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 767542 | 766500 |  | C.G.N | [5 empty] | 766500 |  |  | Complete | 100%
ROADS | 3864 | Completion of kinamba warurungana road (from gikungu makena) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | Complete | 100%
ROADS | 3865 | Muigana kabutu - gachoka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1499900 |  | C.G.N | [5 empty] | 1499900 |  |  | Complete | 100%
ROADS | 3866 | Joyce miumano | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 989100 |  | C.G.N | [5 empty] | 989100 |  |  | Complete | 100%
ROADS | 3867 | Asorted roads completion of warurungana road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2970000 | 2970000 |  | C.G.N | [5 empty] | 2970000 |  |  | Complete | 100%
ROADS | 3868 | Kagiiki road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1879600 |  | C.G.N | [5 empty] | 1879600 |  |  | Complete | 100%
ROADS | 3869 | Kiriaho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1483800 |  | C.G.N | [5 empty] | 1483800 |  |  | Complete | 100%
ROADS | 3870 | Kagiri-junction road-gathara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1498500 |  | C.G.N | [5 empty] | 1498500 |  |  | COMPLETE | 100%
ROADS | 3871 | Miti iri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 989100 |  | C.G.N | [5 empty] | 989100 |  |  | Complete | 100%
ROADS | 3872 | Culvert installation in githabai ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | Complete | 100%
ROADS | 3873 | Haraka - gathuita road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2376000 | 2376000 |  | C.G.N | [5 empty] | 2376000 |  |  | Complete | 100%
ROADS | 3874 | Light & heavy grading in githabai ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 981600 |  | C.G.N | [5 empty] | 981600 |  |  | Complete | 100%
ROADS | 3875 | Kiririmbi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2178000 | 2177500 |  | C.G.N | [5 empty] | 2177500 |  |  | Complete | 100%
ROADS | 3876 | Forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1683000 | 1681600 |  | C.G.N | [5 empty] | 1681600 |  |  | Complete | 100%
ROADS | 3877 | Mariru road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 866250 | 864000 |  | C.G.N | [5 empty] | 864000 |  |  | Complete | 100%
ROADS | 3878 | Flyover centre - barabara tano - flyover ya juu - st martin road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2469100 | 2469100 |  | C.G.N | [5 empty] | 2469100 |  |  | Complete | 100%
ROADS | 3879 | Soko - mjinga - washington - river side | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1336500 | 1330800 |  | C.G.N | [5 empty] | 1330800 |  |  | Complete | 100%
ROADS | 3880 | Mutonyora road-magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1496214 |  | C.G.N | [5 empty] | 1496214 |  |  | ONGOING | 100%
ROADS | 3881 | Muguga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1138500 | 1137600 |  | C.G.N | [5 empty] | 1137600 |  |  | Complete | 100%
ROADS | 3882 | Mugambi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 955350 | 953800 |  | C.G.N | [5 empty] | 953800 |  |  | Complete | 100%
ROADS | 3883 | Mutonyora a | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 979000 | 979000 |  | C.G.N | [5 empty] | 979000 |  |  | Complete | 100%
ROADS | 3884 | Mutonyora b | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 950400 | 948000 |  | C.G.N | [5 empty] | 948000 |  |  | Complete | 100%
ROADS | 3885 | Mutonyora c | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 950400 | 921000 |  | C.G.N | [5 empty] | 921000 |  |  | Complete | 100%
ROADS | 3886 | Kenton culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 485100 | 484500 |  | C.G.N | [5 empty] | 484500 |  |  | Complete | 100%
ROADS | 3887 | Gitwe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 499483 | 498000 |  | C.G.N | [5 empty] | 498000 |  |  | Complete | 100%
ROADS | 3888 | Munyuini -magutu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 931960 |  | C.G.N | [5 empty] | 931960 |  |  | COMPLETE | 100%
ROADS | 3889 | Wendani magutu bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 497170 | 497170 |  | C.G.N | [5 empty] | 497170 |  |  | COMPLETE | 100%
ROADS | 3890 | Ihinga pry-malewa culvert | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 495000 |  | C.G.N | [5 empty] | 495000 |  |  | COMPLETE | 100%
ROADS | 3891 | Rutumo juction kahuruko | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 495000 |  | C.G.N | [5 empty] | 495000 |  |  | COMPLETE | 100%
ROADS | 3892 | Gitwe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 931200 |  | C.G.N | [5 empty] | 931200 |  |  | COMPLETE | 100%
ROADS | 3893 | Mahinga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 940500 |  | C.G.N | [5 empty] | 940500 |  |  | COMPLETE | 100%
ROADS | 3894 | Kagogo a | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 959500 |  | C.G.N | [5 empty] | 959500 |  |  | COMPLETE | 100%
ROADS | 3895 | Kagogo b | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 964260 |  | C.G.N | [5 empty] | 964260 |  |  | COMPLETE | 100%
ROADS | 3896 | Manunga kag road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 960667 |  | C.G.N | [5 empty] | 960667 |  |  | COMPLETE | 100%
ROADS | 3897 | Kirima irubu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 488800 |  | C.G.N | [5 empty] | 488800 |  |  | COMPLETE | 100%
ROADS | 3898 | Kona mbaya-manunga road-kipipiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1489592 |  | C.G.N | [5 empty] | 1489592 |  |  | COMPLETE | 100%
ROADS | 3899 | Ndurubu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 490550 |  | C.G.N | [5 empty] | 490550 |  |  | COMPLETE | 100%
ROADS | 3900 | Forest 1 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 490620 |  | C.G.N | [5 empty] | 490620 |  |  | COMPLETE | 100%
ROADS | 3901 | Machinery road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435500 | 1435500 |  | C.G.N | [5 empty] | 1435500 |  |  | COMPLETE | 100%
ROADS | 3902 | Wamuiko-nganga njau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 948480 |  | C.G.N | [5 empty] | 948480 |  |  | COMPLETE | 100%
ROADS | 3903 | Rereshua road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435500 | 1435150 |  | C.G.N | [5 empty] | 1435150 |  |  | COMPLETE | 100%
ROADS | 3904 | Rutumo pry ngura road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1386000 | 1386000 |  | C.G.N | [5 empty] | 1386000 |  |  | COMPLETE | 100%
ROADS | 3905 | No 3 kianjogu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1386000 | 1386000 |  | C.G.N | [5 empty] | 1386000 |  |  | COMPLETE | 100%
ROADS | 3906 | No 10 river wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 940500 |  | C.G.N | [5 empty] | 940500 |  |  | COMPLETE | 100%
ROADS | 3907 | No 15 river road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 938000 |  | C.G.N | [5 empty] | 938000 |  |  | COMPLETE | 100%
ROADS | 3908 | No 22 river road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1237500 | 1232440 |  | C.G.N | [5 empty] | 1232440 |  |  | COMPLETE | 100%
ROADS | 3909 | Kwa matu no 1 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435500 | 1428600 |  | C.G.N | [5 empty] | 1428600 |  |  | COMPLETE | 100%
ROADS | 3910 | Slaughter hse rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 950250 |  | C.G.N | [5 empty] | 950250 |  |  | COMPLETE | 100%
ROADS | 3911 | Kanteen-kirima road-geta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1250000 | 1224090 |  | C.G.N | [5 empty] | 1224090 |  |  | COMPLETE | 100%
ROADS | 3912 | Aic-geta town | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 957620 |  | C.G.N | [5 empty] | 957620 |  |  | COMPLETE | 100%
ROADS | 3913 | Gathuthi forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 959000 |  | C.G.N | [5 empty] | 959000 |  |  | COMPLETE | 100%
ROADS | 3914 | Kariani-kiambogo kanjagiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1386000 | 1385295 |  | C.G.N | [5 empty] | 1385295 |  |  | COMPLETE | 100%
ROADS | 3915 | No 30 rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 960000 |  | C.G.N | [5 empty] | 960000 |  |  | COMPLETE | 100%
ROADS | 3916 | Mibiriti river rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 958200 |  | C.G.N | [5 empty] | 958200 |  |  | COMPLETE | 100%
ROADS | 3917 | Waiyego forest | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 965250 |  | C.G.N | [5 empty] | 965250 |  |  | COMPLETE | 100%
ROADS | 3918 | Canteen kirima | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1224090 |  | C.G.N | [5 empty] | 1224090 |  |  | COMPLETE | 100%
ROADS | 3919 | 800 forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 799920 |  | C.G.N | [5 empty] | 799920 |  |  | COMPLETE | 100%
ROADS | 3920 | Wakarithi kiboi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 965400 |  | C.G.N | [5 empty] | 965400 |  |  | COMPLETE | 100%
ROADS | 3921 | Mawingo village | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 790000 | 788000 |  | C.G.N | [5 empty] | 788000 |  |  | COMPLETE | 100%
ROADS | 3922 | St peter road-githioro | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 752400 | 752400 |  | C.G.N | [5 empty] | 752400 |  |  | COMPLETE | 100%
ROADS | 3923 | Gakroba a & b | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 940500 |  | C.G.N | [5 empty] | 940500 |  |  | COMPLETE | 100%
ROADS | 3924 | Mbogani-prof.gatei road-githabai | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1000000 | 998700 |  | C.G.N | [5 empty] | 998700 |  |  | COMPLETE | 100%
ROADS | 3925 | Gathiriga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1788000 |  | C.G.N | [5 empty] | 1788000 |  |  | COMPLETE | 100%
ROADS | 3926 | Mumui feeder roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 935550 | 930000 |  | C.G.N | [5 empty] | 930000 |  |  | COMPLETE | 100%
ROADS | 3927 | Mwangaza-ririchua-gatika | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1237500 | 1236800 |  | C.G.N | [5 empty] | 1236800 |  |  | COMPLETE | 100%
ROADS | 3928 | Gathioro road githioro | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 475200 | 475200 |  | C.G.N | [5 empty] | 475200 |  |  | COMPLETE | 100%
ROADS | 3929 | Harambee and bara inya rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2000000 | 1958200 |  | C.G.N | [5 empty] | 1958200 |  |  | COMPLETE | 100%
ROADS | 3930 | Mwangaza feeder roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 564300 | 560400 |  | C.G.N | [5 empty] | 560400 |  |  | COMPLETE | 100%
ROADS | 3931 | Rurii a & b in githioro | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 942000 | 938620 |  | C.G.N | [5 empty] | 938620 |  |  | COMPLETE | 100%
ROADS | 3932 | Forest 2 road kagia pcea | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 937000 |  | C.G.N | [5 empty] | 937000 |  |  | COMPLETE | 100%
ROADS | 3933 | Mumui -migaa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 3934 | Tigoni -kangondi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 594000 | 590200 |  | C.G.N | [5 empty] | 590200 |  |  | COMPLETE | 100%
ROADS | 3935 | Parkview bara inya | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | COMPLETE | 100%
ROADS | 3936 | Assorted culvert wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | COMPLETE | 100%
ROADS | 3937 | Kahiga a to kahiga b | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1881000 |  | C.G.N | [5 empty] | 1881000 |  |  | COMPLETE | 100%
ROADS | 3938 | Kimuru road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | COMPLETE | 100%
ROADS | 3939 | Parkview bara inya phase ii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1881000 |  | C.G.N | [5 empty] | 1881000 |  |  | COMPLETE | 100%
ROADS | 3940 | Kagiri-kimuru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | COMPLETE | 100%
ROADS | 3941 | Wanjohi -rayeta-gatondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | NOT STARTED
ROADS | 3942 | General china ndemi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2425500 | 2425500 |  | C.G.N | [5 empty] | 2425500 |  |  | COMPLETE | 100%
ROADS | 3943 | Dn -kimuru-wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435500 | 1435500 |  | C.G.N | [5 empty] | 1435500 |  |  | COMPLETE | 100%
ROADS | 3944 | Magomano road phase ii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1881000 |  | C.G.N | [5 empty] | 1881000 |  |  | COMPLETE | 100%
ROADS | 3945 | Kona mbaya road-wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1481204 |  | C.G.N | [5 empty] | 1481204 |  |  | COMPLETE | 100%
ROADS | 3946 | Mubao kipipiri sec -wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | COMPLETE | 100%
ROADS | 3947 | Wanjohi girls- mubao-wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 965250 |  | C.G.N | [5 empty] | 965250 |  |  | COMPLETE | 100%
ROADS | 3948 | Gatukai-ini-jifiini | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 965250 |  | C.G.N | [5 empty] | 965250 |  |  | COMPLETE | 100%
ROADS | 3949 | Miti -itano gatondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 965250 |  | C.G.N | [5 empty] | 965250 |  |  | COMPLETE | 100%
ROADS | 3950 | Rironi town general grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 965250 |  | C.G.N | [5 empty] | 965250 |  |  | COMPLETE | 100%
ROADS | 3951 | Glory church-village | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 965250 | 965250 |  | C.G.N | [5 empty] | 965250 |  |  | COMPLETE | 100%
ROADS | 3952 | Gatondo rayeta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | COMPLETE | 100%
ROADS | 3953 | Kawa kawa kirima road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1930500 | 1928412 |  | C.G.N | [5 empty] | 1928412 |  |  | COMPLETE | 100%
ROADS | 3954 | Kasuku town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1930500 | 1911575 |  | C.G.N | [5 empty] | 1911575 |  |  | COMPLETE | 100%
ROADS | 3955 | Gathundia-matura junction-weru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2700000 | 2683277 |  | C.G.N | [5 empty] | 2683277 |  |  | COMPLETE | 100%
ROADS | 3956 | Extension of kahii karandi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2376000 | 2375742 |  | C.G.N | [5 empty] | 2375742 |  |  | COMPLETE | 100%
ROADS | 3957 | Extension of kimutiini-karandi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2376000 | 2375997 |  | C.G.N | [5 empty] | 2375997 |  |  | COMPLETE | 100%
ROADS | 3958 | Weru ward grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3366000 | 3360654 |  | C.G.N | [5 empty] | 3360654 |  |  | COMPLETE | 100%
ROADS | 3959 | Kangui oljorok town road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1386000 | 1385000 |  | C.G.N | [5 empty] | 1385000 |  |  | COMPLETE | 100%
ROADS | 3960 | Weru ward culvrts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 990000 |  | C.G.N | [5 empty] | 990000 |  |  | COMPLETE | 100%
ROADS | 3961 | Simba-pub-y road-weru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1750000 | 1723377 |  | C.G.N | [5 empty] | 1723377 |  |  | COMPLETE | 100%
ROADS | 3962 | C77-muthukumi road-gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1488048 |  | C.G.N | [5 empty] | 1488048 |  |  | COMPLETE | 100%
ROADS | 3963 | Mutanga - limui road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2839340 |  | C.G.N | [5 empty] | 2839340 |  |  | COMPLETE | 100%
ROADS | 3964 | Karago ini - nairobi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1869440 |  | C.G.N | [5 empty] | 1869440 |  |  | COMPLETE | 100%
ROADS | 3965 | Githungucu - chapalungu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1138500 | 1134288 |  | C.G.N | [5 empty] | 1134288 |  |  | COMPLETE | 100%
ROADS | 3966 | Wa kiriita (wa gateere) road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1138500 | 1137100 |  | C.G.N | [5 empty] | 1137100 |  |  | COMPLETE | 100%
ROADS | 3967 | Wakahot-karagoini road-kiriita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3000000 | 2991002 |  | C.G.N | [5 empty] | 2991002 |  |  | COMPLETE | 100%
ROADS | 3968 | Wang'ombe and muniu roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435500 | 1423180 |  | C.G.N | [5 empty] | 1423180 |  |  | COMPLETE | 100%
ROADS | 3969 | Githinjiro and maina roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1237500 | 1236350 |  | C.G.N | [5 empty] | 1236350 |  |  | COMPLETE | 100%
ROADS | 3970 | Mairo inya - maryland road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 488200 |  | C.G.N | [5 empty] | 488200 |  |  | COMPLETE | 100%
ROADS | 3971 | Baari a and b road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1877406 |  | C.G.N | [5 empty] | 1877406 |  |  | COMPLETE | 100%
ROADS | 3972 | Ziwani - mairo inya road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1178100 | 1176273 |  | C.G.N | [5 empty] | 1176273 |  |  | COMPELETE | 100%
ROADS | 3973 | Mairo inya town gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1089000 | 1089000 |  | C.G.N | [5 empty] | 1089000 |  |  | COMPELETE | 100%
ROADS | 3974 | Culverts installations in kiriita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1454005 | 1454005 |  | C.G.N | [5 empty] | 1454005 |  |  | COMPELETE | 100%
ROADS | 3975 | General grading in l. Pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2128500 | 2126120 |  | C.G.N | [5 empty] | 2126120 |  |  | COMPELETE | 100%
ROADS | 3976 | Footbridges in l. Pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 697483 | 696500 |  | C.G.N | [5 empty] | 696500 |  |  | COMPELETE | 100%
ROADS | 3977 | Itangi ini - precious academy road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1431017 | 1430615 |  | C.G.N | [5 empty] | 1430615 |  |  | COMPLETE | 100%
ROADS | 3978 | Waititu - college road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435500 | 1435200 |  | C.G.N | [5 empty] | 1435200 |  |  | COMPLETE | 100%
ROADS | 3979 | Ndivai - kwa daudi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2863860 |  | C.G.N | [5 empty] | 2863860 |  |  | COMPLETE | 100%
ROADS | 3980 | Kamukunji-kihingo road-l.pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2000000 | 1993518 |  | C.G.N | [5 empty] | 1993518 |  |  | COMPLETE | 100%
ROADS | 3981 | Kiandege-aberdare ttc road-l.pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3500000 | 3485916 |  | C.G.N | [5 empty] | 3485916 |  |  | COMPLETE | 100%
ROADS | 3982 | Muthiga pri - nyanyuki jnc road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1478810 |  | C.G.N | [5 empty] | 1478810 |  |  | COMPLETE | 100%
ROADS | 3983 | Kagondo - githinjiro - tarmac road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2126120 | 2126120 |  | C.G.N | [5 empty] | 2126120 |  |  | COMPLETE | 100%
ROADS | 3984 | Kamukunji - ndivai primary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3663000 | 3656500 |  | C.G.N | [5 empty] | 3656500 |  |  | COMPLETE | 100%
ROADS | 3985 | Karampton - laikipia border | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 982210 |  | C.G.N | [5 empty] | 982210 |  |  | COMPLETE | 100%
ROADS | 3986 | Gwa kung'u - kanyagia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2376000 | 2372167 |  | C.G.N | [5 empty] | 2372167 |  |  | COMPLETE | 100%
ROADS | 3987 | Karai road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 493900 |  | C.G.N | [5 empty] | 493900 |  |  | COMPLETE | 100%
ROADS | 3988 | Equator road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1490720 |  | C.G.N | [5 empty] | 1490720 |  |  | COMPLETE | 100%
ROADS | 3989 | Nyonjoro - uruku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2376000 | 2323530 |  | C.G.N | [5 empty] | 2323530 |  |  | COMPLETE | 100%
ROADS | 3990 | Kahutha - uruku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2826640 |  | C.G.N | [5 empty] | 2826640 |  |  | COMPLETE | 100%
ROADS | 3991 | Lodwar - mika road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1852290 |  | C.G.N | [5 empty] | 1852290 |  |  | COMPLETE | 100%
ROADS | 3992 | Cllr mwaniki road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1879900 |  | C.G.N | [5 empty] | 1879900 |  |  | COMPLETE | 100%
ROADS | 3993 | Kiandongoro - forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2376000 | 2365127 |  | C.G.N | [5 empty] | 2365127 |  |  | COMPLETE | 100%
ROADS | 3994 | Makereka-ngurumo road-ndaragwa | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1485322 |  | C.G.N | [5 empty] | 1485322 |  |  | COMPLETE | 100%
ROADS | 3995 | Murichu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1465520 |  | C.G.N | [5 empty] | 1465520 |  |  | COMPLETE | 100%
ROADS | 3996 | Magomano - ack road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1470200 |  | C.G.N | [5 empty] | 1470200 |  |  | COMPLETE | 100%
ROADS | 3997 | Gathariga (kiriogo) roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1484400 |  | C.G.N | [5 empty] | 1484400 |  |  | COMPLETE | 100%
ROADS | 3998 | Loc 4 - mla chake road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1454240 |  | C.G.N | [5 empty] | 1454240 |  |  | COMPLETE | 100%
ROADS | 3999 | Muruai (subuku centre) roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1868600 |  | C.G.N | [5 empty] | 1868600 |  |  | COMPLETE | 100%
ROADS | 4000 | Ngurumo - makereka | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 984500 |  | C.G.N | [5 empty] | 984500 |  |  | COMPLETE | 100%
ROADS | 4001 | Kiriha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1039500 | 1038600 |  | C.G.N | [5 empty] | 1038600 |  |  | COMPLETE | 100%
ROADS | 4002 | Ol bollosat road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 935200 |  | C.G.N | [5 empty] | 935200 |  |  | COMPLETE | 100%
ROADS | 4003 | Thirikwa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 935200 |  | C.G.N | [5 empty] | 935200 |  |  | COMPLETE | 100%
ROADS | 4004 | Simbara - kabere road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 930940 |  | C.G.N | [5 empty] | 930940 |  |  | COMPLETE | 100%
ROADS | 4005 | Muhiriga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 930000 |  | C.G.N | [5 empty] | 930000 |  |  | COMPLETE | 100%
ROADS | 4006 | Rurii-asis road-githioro | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1000000 | 997100 |  | C.G.N | [5 empty] | 997100 |  |  | COMPLETE | 100%
ROADS | 4007 | Ma stoo - ex daya road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 930050 |  | C.G.N | [5 empty] | 930050 |  |  | COMPLETE | 100%
ROADS | 4008 | Kaheho p.a.g church - ex daya | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 376200 | 370100 |  | C.G.N | [5 empty] | 370100 |  |  | COMPLETE | 100%
ROADS | 4009 | Wachira theuri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 465300 | 460200 |  | C.G.N | [5 empty] | 460200 |  |  | COMPLETE | 100%
ROADS | 4010 | Shamata health centre/aipca roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 663300 | 658200 |  | C.G.N | [5 empty] | 658200 |  |  | COMPLETE | 100%
ROADS | 4011 | Mwihang'ia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 396000 | 396000 |  | C.G.N | [5 empty] | 396000 |  |  | COMPLETE | 100%
ROADS | 4012 | Turuthi - gakoe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 938975 | 938975 |  | C.G.N | [5 empty] | 938975 |  |  | COMPLETE | 100%
ROADS | 4013 | Matindiri - wanjura - mugoiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1680320 | 1680320 |  | C.G.N | [5 empty] | 1680320 |  |  | COMPLETE | 100%
ROADS | 4014 | Ol joro orok jnc - wa gichuki & kibiro - gichaka dam roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1696100 | 1696100 |  | C.G.N | [5 empty] | 1696100 |  |  | COMPLETE | 100%
ROADS | 4015 | Mungai - kimama & mung'etho - mucheru roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1994245 | 1994245 |  | C.G.N | [5 empty] | 1994245 |  |  | COMPLETE | 100%
ROADS | 4016 | T rose - mugoya - bara njeru road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1680320 | 1680320 |  | C.G.N | [5 empty] | 1680320 |  |  | COMPLETE | 100%
ROADS | 4017 | Muchemi pry-kiriondo river road-charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2500000 | 2483328 |  | C.G.N | [5 empty] | 2483328 |  |  | COMPLETE | 100%
ROADS | 4018 | Kona-ngatho road-charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1491308 |  | C.G.N | [5 empty] | 1491308 |  |  | COMPLETE | 100%
ROADS | 4019 | General grading in charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2890200 | 2890200 |  | C.G.N | [5 empty] | 2890200 |  |  | COMPLETE | 100%
ROADS | 4020 | Culverts installations in charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1638680 | 1638680 |  | C.G.N | [5 empty] | 1638680 |  |  | COMPLETE | 100%
ROADS | 4021 | T rose - kangui road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1994245 | 1994245 |  | C.G.N | [5 empty] | 1994245 |  |  | COMPLETE | 100%
ROADS | 4022 | T rose - mithamo dam - obed jnc | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 997464 | 997464 |  | C.G.N | [5 empty] | 997464 |  |  | COMPLETE | 100%
ROADS | 4023 | Assorted roads gravel patching - charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1875920 | 1875920 |  | C.G.N | [5 empty] | 1875920 |  |  | COMPLETE | 100%
ROADS | 4024 | Pbk bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1782000 | 1773980 |  | C.G.N | [5 empty] | 1773980 |  |  | COMPLETE | 100%
ROADS | 4025 | Gachuiro road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 898000 |  | C.G.N | [5 empty] | 898000 |  |  | COMPLETE | 100%
ROADS | 4026 | Cool pasture road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 970200 |  | C.G.N | [5 empty] | 970200 |  |  | COMPLETE | 100%
ROADS | 4027 | Ngorika sec-catholic $ gen. Grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2920500 | 2910425 |  | C.G.N | [5 empty] | 2910425 |  |  | COMPLETE | 100%
ROADS | 4028 | Shakora -kiboko, kiriko-dairy & kagunda- thaba roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2772000 | 2770000 |  | C.G.N | [5 empty] | 2770000 |  |  | COMPLETE | 100%
ROADS | 4029 | Stadium-gathundia road-kanjuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1490322 |  | C.G.N | [5 empty] | 1490322 |  |  | COMPLETE | 100%
ROADS | 4030 | Dairy- githinjiro, winyumiririe-rutara & nyaituga- borehole roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3861000 | 3756200 |  | C.G.N | [5 empty] | 3756200 |  |  | COMPLETE | 100%
ROADS | 4031 | Nyaituga- bata & karebe roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3316500 | 3314500 |  | C.G.N | [5 empty] | 3314500 |  |  | COMPLETE | 100%
ROADS | 4032 | Ack - uhuru & njigaga- kanjuiri roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3762000 | 3742400 |  | C.G.N | [5 empty] | 3742400 |  |  | COMPLETE | 100%
ROADS | 4033 | General culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1287000 | 1279080 |  | C.G.N | [5 empty] | 1279080 |  |  | COMPLETE | 100%
ROADS | 4034 | Upgrade of stadium - gathundia & wanyororo roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2772000 | 2752200 |  | C.G.N | [5 empty] | 2752200 |  |  | COMPLETE | 100%
ROADS | 4035 | Baruku bridge- tumaini village | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1300000 | 1296700 |  | C.G.N | [5 empty] | 1296700 |  |  | COMPLETE | 100%
ROADS | 4036 | Miiri- wanjiku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2869190 |  | C.G.N | [5 empty] | 2869190 |  |  | COMPLETE | 100%
ROADS | 4037 | Culvert- munyamba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 493200 |  | C.G.N | [5 empty] | 493200 |  |  | COMPLETE | 100%
ROADS | 4038 | Murindati- mbora, makurata, mbora -hq road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2869600 |  | C.G.N | [5 empty] | 2869600 |  |  | COMPLETE | 100%
ROADS | 4039 | Mbora dam-ngungu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 493183 |  | C.G.N | [5 empty] | 493183 |  |  | COMPLETE | 100%
ROADS | 4040 | Kirima junction- boundary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 495000 | 490860 |  | C.G.N | [5 empty] | 490860 |  |  | COMPLETE | 100%
ROADS | 4041 | Muua bridge road-milangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2000000 | 1989632 |  | C.G.N | [5 empty] | 1989632 |  |  | COMPLETE | 100%
ROADS | 4042 | Tumaini-githure road-milangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2000000 | 1993506 |  | C.G.N | [5 empty] | 1993506 |  |  | COMPLETE | 100%
ROADS | 4043 | Kamuyu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1386000 | 1378420 |  | C.G.N | [5 empty] | 1378420 |  |  | COMPLETE | 100%
ROADS | 4044 | Matunda- ramana road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1881000 |  | C.G.N | [5 empty] | 1881000 |  |  | COMPLETE | 100%
ROADS | 4045 | Ngiri kenda - ramana road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1467600 |  | C.G.N | [5 empty] | 1467600 |  |  | COMPLETE | 100%
ROADS | 4046 | General grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2842290 |  | C.G.N | [5 empty] | 2842290 |  |  | COMPLETE | 100%
ROADS | 4047 | Nyandundo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435500 | 1433384 |  | C.G.N | [5 empty] | 1433384 |  |  | COMPLETE | 100%
ROADS | 4048 | Kibendera -riverside -ramana road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1990000 | 1941350 |  | C.G.N | [5 empty] | 1941350 |  |  | COMPLETE | 100%
ROADS | 4049 | Mathakwa-mbocho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1880400 |  | C.G.N | [5 empty] | 1880400 |  |  | COMPLETE | 100%
ROADS | 4050 | Gwa kiongo township | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4051 | Captain roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2376000 | 2370000 |  | C.G.N | [5 empty] | 2370000 |  |  | COMPLETE | 100%
ROADS | 4052 | Nyumba ndune kamakia jnr road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435500 | 1434920 |  | C.G.N | [5 empty] | 1434920 |  |  | COMPLETE | 100%
ROADS | 4053 | Muchemi -ndehi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 693000 | 691250 |  | C.G.N | [5 empty] | 691250 |  |  | COMPLETE | 100%
ROADS | 4054 | Kariuki-maeya- wajeff road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 693000 | 690100 |  | C.G.N | [5 empty] | 690100 |  |  | COMPLETE | 100%
ROADS | 4055 | Gituamba - gakenge road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1386000 | 1385500 |  | C.G.N | [5 empty] | 1385500 |  |  | COMPLETE | 100%
ROADS | 4056 | Bahati primary school road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 979600 |  | C.G.N | [5 empty] | 979600 |  |  | COMPLETE | 100%
ROADS | 4057 | Kandutura -idp -kabingu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1879960 |  | C.G.N | [5 empty] | 1879960 |  |  | COMPLETE | 100%
ROADS | 4058 | Malfan - mandegwa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 980000 |  | C.G.N | [5 empty] | 980000 |  |  | COMPLETE | 100%
ROADS | 4059 | Gatere teacher road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 594000 | 585000 |  | C.G.N | [5 empty] | 585000 |  |  | COMPLETE | 100%
ROADS | 4060 | Head quarter-kidowa road-kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2250000 | 2244925 |  | C.G.N | [5 empty] | 2244925 |  |  | COMPLETE | 100%
ROADS | 4061 | Mahinga box~culvert-kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 4500000 | 4498132 |  | C.G.N | [5 empty] | 4498132 |  |  | COMPLETE | 100%
ROADS | 4062 | Majoe primary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940000 | 930000 |  | C.G.N | [5 empty] | 930000 |  |  | COMPLETE | 100%
ROADS | 4063 | Mahii-baba gerald-watoni road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 949200 |  | C.G.N | [5 empty] | 949200 |  |  | COMPLETE | 100%
ROADS | 4064 | Mama githinji road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 396000 | 386028 |  | C.G.N | [5 empty] | 386028 |  |  | COMPLETE | 100%
ROADS | 4065 | Jerusalem estate roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 980376 |  | C.G.N | [5 empty] | 980376 |  |  | COMPLETE | 100%
ROADS | 4066 | Wabiriti -wakaweru road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 693000 | 683006 |  | C.G.N | [5 empty] | 683006 |  |  | COMPLETE | 100%
ROADS | 4067 | Site & service roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1386000 | 1382150 |  | C.G.N | [5 empty] | 1382150 |  |  | COMPLETE | 100%
ROADS | 4068 | Meja gikuri -kiumu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 988200 |  | C.G.N | [5 empty] | 988200 |  |  | COMPLETE | 100%
ROADS | 4069 | Pcea kiganjo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 693000 | 691720 |  | C.G.N | [5 empty] | 691720 |  |  | COMPLETE | 100%
ROADS | 4070 | Wamuritu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 693000 | 675500 |  | C.G.N | [5 empty] | 675500 |  |  | COMPLETE | 100%
ROADS | 4071 | Assorted roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 883412 | 881643 |  | C.G.N | [5 empty] | 881643 |  |  | COMPLETE | 100%
ROADS | 4072 | Mwari junction -gatitu -ack road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1138500 | 1136600 |  | C.G.N | [5 empty] | 1136600 |  |  | COMPLETE | 100%
ROADS | 4073 | Wakabuti road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1879402 |  | C.G.N | [5 empty] | 1879402 |  |  | COMPLETE | 100%
ROADS | 4074 | Mukurino -nguva- bosnia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1880127 |  | C.G.N | [5 empty] | 1880127 |  |  | COMPLETE | 100%
ROADS | 4075 | St. Thomas road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 955350 | 952250 |  | C.G.N | [5 empty] | 952250 |  |  | COMPLETE | 100%
ROADS | 4076 | Plot 10-st.thomas road-rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1491273 |  | C.G.N | [5 empty] | 1491273 |  |  | COMPLETE | 100%
ROADS | 4077 | Githunguri- stage one road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 955350 | 953400 |  | C.G.N | [5 empty] | 953400 |  |  | COMPLETE | 100%
ROADS | 4078 | Rurii- kidowa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1237000 | 1236600 |  | C.G.N | [5 empty] | 1236600 |  |  | COMPLETE | 100%
ROADS | 4079 | Ndinguri- passenga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1138000 | 1131280 |  | C.G.N | [5 empty] | 1131280 |  |  | COMPLETE | 100%
ROADS | 4080 | Gakoroba -mugumo a.i.p.c.a road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 955350 | 953000 |  | C.G.N | [5 empty] | 953000 |  |  | COMPLETE | 100%
ROADS | 4081 | Kinyumba -mairo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1138000 | 1130250 |  | C.G.N | [5 empty] | 1130250 |  |  | COMPLETE | 100%
ROADS | 4082 | Mbicu -rukia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 693000 | 691195 |  | C.G.N | [5 empty] | 691195 |  |  | COMPLETE | 100%
ROADS | 4083 | Kirima -kirima junction road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 396000 | 394941 |  | C.G.N | [5 empty] | 394941 |  |  | COMPLETE | 100%
ROADS | 4084 | Gachau - wairimu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 693000 | 693000 |  | C.G.N | [5 empty] | 693000 |  |  | COMPLETE | 100%
ROADS | 4085 | Mtwaa -keboi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 500000 | 497960 |  | C.G.N | [5 empty] | 497960 |  |  | COMPLETE | 100%
ROADS | 4086 | Rurii-matura junction road-rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3250000 | 3221706 |  | C.G.N | [5 empty] | 3221706 |  |  | COMPLETE | 100%
ROADS | 4087 | Passenger-matura road-rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 850000 | 843900 |  | C.G.N | [5 empty] | 843900 |  |  | COMPLETE | 100%
ROADS | 4088 | Rurii town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 396000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4089 | Rurii dispensary- bosnia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 594000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4090 | Passenga town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 297000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4091 | Kanyoro road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 297000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4092 | Junction - kahia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 988300 |  | C.G.N | [5 empty] | 988300 |  |  | COMPLETE | 100%
ROADS | 4093 | Hire of 20 tons truck | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2400750 | 2398200 |  | C.G.N | [5 empty] | 2398200 |  |  | COMPLETE | 100%
ROADS | 4094 | Speading and spreading and supervision | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2881000 |  |  | C.G.N
ROADS | 4095 | Hire of single drum vibratory roller | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2869000 |  | C.G.N | [5 empty] | 2869000 |  |  | COMPLETE | 100%
ROADS | 4096 | Hire of motor gradr | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2895500 | 2890000 |  | C.G.N | [5 empty] | 2890000 |  |  | COMPLETE | 100%
ROADS | 4097 | Ol'kalou-mwireri-ndemi road-karau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2000000 | 1976528 |  | C.G.N | [5 empty] | 1976528 |  |  | COMPLETE | 100%
ROADS | 4098 | Agrow jnr-dicece road-karau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2000000 | 1982292 |  | C.G.N | [5 empty] | 1982292 |  |  | COMPLETE | 100%
ROADS | 4099 | Conner road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 987200 |  | C.G.N | [5 empty] | 987200 |  |  | COMPLETE | 100%
ROADS | 4100 | Munyeki-gachwe road-karau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 5000000 | 4527828 |  | C.G.N | [5 empty] | 4527828 |  |  | ONGOING
ROADS | 4101 | Pioneer estate road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1675000 | 1665200 |  | C.G.N | [5 empty] | 1665200 |  |  | COMPLETE | 100%
ROADS | 4102 | General culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1480000 |  | C.G.N | [5 empty] | 1480000 |  |  | COMPLETE | 100%
ROADS | 4103 | Kandeto -chief road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1483800 |  | C.G.N | [5 empty] | 1483800 |  |  | COMPLETE | 100%
ROADS | 4104 | Assorted roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1910000 |  | C.G.N | [5 empty] | 1910000 |  |  | COMPLETE | 100%
ROADS | 4105 | Ndiro- mukuha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 940500 | 937650 |  | C.G.N | [5 empty] | 937650 |  |  | COMPLETE | 100%
ROADS | 4106 | Sunjui-laikipia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 985200 |  | C.G.N | [5 empty] | 985200 |  |  | COMPLETE | 100%
ROADS | 4107 | Igwa miti prim sch road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1475000 |  | C.G.N | [5 empty] | 1475000 |  |  | COMPLETE | 100%
ROADS | 4108 | Mutharia-boiman road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1472870 |  | C.G.N | [5 empty] | 1472870 |  |  | COMPLETE | 100%
ROADS | 4109 | Ex smith - mungethu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1811000 |  | C.G.N | [5 empty] | 1811000 |  |  | COMPLETE | 100%
ROADS | 4110 | Kamuriki- kamamu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 985530 |  | C.G.N | [5 empty] | 985530 |  |  | COMPLETE | 100%
ROADS | 4111 | Kahumi - wamuyu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435000 | 1430000 |  | C.G.N | [5 empty] | 1430000 |  |  | COMPLETE | 100%
ROADS | 4112 | Silibwet prim sch. Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1875000 |  | C.G.N | [5 empty] | 1875000 |  |  | COMPLETE | 100%
ROADS | 4113 | Shrine road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1445000 |  | C.G.N | [5 empty] | 1445000 |  |  | COMPLETE | 100%
ROADS | 4114 | Karai-thaitai road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 983060 |  | C.G.N | [5 empty] | 983060 |  |  | COMPLETE | 100%
ROADS | 4115 | Gituamba-gg road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1435500 | 1426830 |  | C.G.N | [5 empty] | 1426830 |  |  | COMPLETE | 100%
ROADS | 4116 | Wamiti-kahiato road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 983060 |  | C.G.N | [5 empty] | 983060 |  |  | COMPLETE | 100%
ROADS | 4117 | Wagura-mbaria road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 984900 |  | C.G.N | [5 empty] | 984900 |  |  | COMPLETE | 100%
ROADS | 4118 | Migaa-kiharo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 989000 |  | C.G.N | [5 empty] | 989000 |  |  | COMPLETE | 100%
ROADS | 4119 | Wagithiri-kamukunji | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485500 | 1479740 |  | C.G.N | [5 empty] | 1479740 |  |  | COMPLETE | 100%
ROADS | 4120 | Karuthu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 985200 |  | C.G.N | [5 empty] | 985200 |  |  | COMPLETE | 100%
ROADS | 4121 | Bahati-chamuka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 980500 |  | C.G.N | [5 empty] | 980500 |  |  | COMPLETE | 100%
ROADS | 4122 | Grading (assorted) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 985000 |  | C.G.N | [5 empty] | 985000 |  |  | COMPLETE | 100%
ROADS | 4123 | Njugi-kagiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2673000 | 2660000 |  | C.G.N | [5 empty] | 2660000 |  |  | COMPLETE | 100%
ROADS | 4124 | Fokp-mugumuini road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1138500 | 1130000 |  | C.G.N | [5 empty] | 1130000 |  |  | COMPLETE | 100%
ROADS | 4125 | Muchoroi-230 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1188000 | 1170000 |  | C.G.N | [5 empty] | 1170000 |  |  | COMPLETE | 100%
ROADS | 4126 | Kianjogu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1732200 | 1726880 |  | C.G.N | [5 empty] | 1726880 |  |  | COMPLETE | 100%
ROADS | 4127 | Grading (mukungi-mikaro) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1881000 | 1878100 |  | C.G.N | [5 empty] | 1878100 |  |  | COMPLETE | 100%
ROADS | 4128 | Grading (murungaru) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2860740 |  | C.G.N | [5 empty] | 2860740 |  |  | COMPLETE | 100%
ROADS | 4129 | Gachuiya-wambae road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1633500 | 1626595 |  | C.G.N | [5 empty] | 1626595 |  |  | COMPLETE | 100%
ROADS | 4130 | Kinja-rugara road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1188000 | 1180000 |  | C.G.N | [5 empty] | 1180000 |  |  | COMPLETE | 100%
ROADS | 4131 | Nduru-mugi road-murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1250000 | 1249325 |  | C.G.N | [5 empty] | 1249325 |  |  | COMPLETE | 100%
ROADS | 4132 | Ndungu-waroda road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1188000 | 1184000 |  | C.G.N | [5 empty] | 1184000 |  |  | COMPLETE | 100%
ROADS | 4133 | Culvert installation (assorted) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1534500 | 1530590 |  | C.G.N | [5 empty] | 1530590 |  |  | COMPLETE | 100%
ROADS | 4134 | Kariuki-wari | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1188000 | 1184000 |  | C.G.N | [5 empty] | 1184000 |  |  | COMPLETE | 100%
ROADS | 4135 | Joakim-njau road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 841500 | 834000 |  | C.G.N | [5 empty] | 834000 |  |  | COMPLETE | 100%
ROADS | 4136 | Matopeni road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1445000 | 1439000 |  | C.G.N | [5 empty] | 1439000 |  |  | COMPLETE | 100%
ROADS | 4137 | Culvert installation (murungaru) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1550000 | 1530500 |  | C.G.N | [5 empty] | 1530500 |  |  | COMPLETE | 100%
ROADS | 4138 | Ack-village road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2475000 | 2435100 |  | C.G.N | [5 empty] | 2435100 |  |  | COMPLETE | 100%
ROADS | 4139 | Simon-kanguyo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1956240 |  | C.G.N | [5 empty] | 1956240 |  |  | COMPLETE | 100%
ROADS | 4140 | Center-wanguku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3960000 | 3955000 |  | C.G.N | [5 empty] | 3955000 |  |  | COMPLETE | 100%
ROADS | 4141 | Completion of mbaruku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1979894 |  | C.G.N | [5 empty] | 1979894 |  |  | COMPLETE | 100%
ROADS | 4142 | Cuma-junction road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1955250 | 1925000 |  | C.G.N | [5 empty] | 1925000 |  |  | COMPLETE | 100%
ROADS | 4143 | Ngonyi-gathara road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2819000 |  | C.G.N | [5 empty] | 2819000 |  |  | COMPLETE | 100%
ROADS | 4144 | Culvert supply&installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 984000 |  | C.G.N | [5 empty] | 984000 |  |  | COMPLETE | 100%
ROADS | 4145 | Mutamaiyu-forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1973540 |  | C.G.N | [5 empty] | 1973540 |  |  | COMPLETE | 100%
ROADS | 4146 | Mbaruku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1945000 |  | C.G.N | [5 empty] | 1945000 |  |  | COMPLETE | 100%
ROADS | 4147 | Wutarakwa forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 931320 |  | C.G.N | [5 empty] | 931320 |  |  | COMPLETE | 100%
ROADS | 4148 | Kinja prim sch and njogoo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2850055 |  | C.G.N | [5 empty] | 2850055 |  |  | COMPLETE | 100%
ROADS | 4149 | Guard-gitite road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2850055 |  | C.G.N | [5 empty] | 2850055 |  |  | COMPLETE | 100%
ROADS | 4150 | Academy, posta, junction and engineer township roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1230000 | 1219200 |  | C.G.N | [5 empty] | 1219200 |  |  | COMPLETE | 100%
ROADS | 4151 | Iganjo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1580000 | 1571940 |  | C.G.N | [5 empty] | 1571940 |  |  | COMPLETE | 100%
ROADS | 4152 | Kinja township - kiboi junction | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2852505 |  | C.G.N | [5 empty] | 2852505 |  |  | COMPLETE | 100%
ROADS | 4153 | Raitha pry-habu mwaura road-gathara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1750000 | 1746798 |  | C.G.N | [5 empty] | 1746798 |  |  | COMPLETE | 100%
ROADS | 4154 | St pauls school | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 986000 |  | C.G.N | [5 empty] | 986000 |  |  | COMPLETE | 100%
ROADS | 4155 | Kagiri-lee junction road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 986500 |  | C.G.N | [5 empty] | 986500 |  |  | COMPLETE | 100%
ROADS | 4156 | Mutuini pri school | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2091600 | 1941290 |  | C.G.N | [5 empty] | 1941290 |  |  | COMPLETE | 100%
ROADS | 4157 | Culverts installation (assorted) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1980000 | 1944972 |  | C.G.N | [5 empty] | 1944972 |  |  | COMPLETE | 100%
ROADS | 4158 | Ciondo-charles luanga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2762948 |  | C.G.N | [5 empty] | 2762948 |  |  | COMPLETE | 100%
ROADS | 4159 | Kanyugi prim school | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2900000 | 2898492 |  | C.G.N | [5 empty] | 2898492 |  |  | COMPLETE | 100%
ROADS | 4160 | Engineer-cuma road-engineer | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2500000 | 2490097 |  | C.G.N | [5 empty] | 2490097 |  |  | COMPLETE | 100%
ROADS | 4161 | Engineer township-kahuru rd-engineer | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1500000 | 1483408 |  | C.G.N | [5 empty] | 1483408 |  |  | COMPLETE | 100%
ROADS | 4162 | Gondo thindi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1880000 | 1831200 |  | C.G.N | [5 empty] | 1831200 |  |  | COMPLETE | 100%
ROADS | 4163 | Baringo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1999800 | 1972530 |  | C.G.N | [5 empty] | 1972530 |  |  | COMPLETE | 100%
ROADS | 4164 | Wisdom-kanyugi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2200000 | 2170700 |  | C.G.N | [5 empty] | 2170700 |  |  | COMPLETE | 100%
ROADS | 4165 | Culverts&drain clearing (assorted) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 951860 |  | C.G.N | [5 empty] | 951860 |  |  | COMPLETE | 100%
ROADS | 4166 | Assorted road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2998000 | 1992040 |  | C.G.N | [5 empty] | 1992040 |  |  | COMPLETE | 100%
ROADS | 4167 | Kangutu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2871000 | 2843680 |  | C.G.N | [5 empty] | 2843680 |  |  | COMPLETE | 100%
ROADS | 4168 | Shemba-wajusu-nduati road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1400000 | 1315300 |  | C.G.N | [5 empty] | 1315300 |  |  | COMPLETE | 100%
ROADS | 4169 | Soweto-wairi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3890000 | 3864000 |  | C.G.N | [5 empty] | 3864000 |  |  | COMPLETE | 100%
ROADS | 4170 | Kwambekenya village road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 3167000 | 3164664 |  | C.G.N | [5 empty] | 3164664 |  |  | COMPLETE | 100%
ROADS | 4171 | D-369-kimwaki centre-rumui road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1483500 | 1478650 |  | C.G.N | [5 empty] | 1478650 |  |  | ON GOING
ROADS | 4172 | Kamukunji centre-rumui road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1472000 |  | C.G.N | [5 empty] | 1472000 |  |  | COMPLETE | 100%
ROADS | 4173 | Assorted roads (north kinangop) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1485000 | 1497600 |  | C.G.N | [5 empty] | 1497600 |  |  | COMPLETE | 100%
ROADS | 4174 | Gitite road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 988500 | 966460 |  | C.G.N | [5 empty] | 966460 |  |  | COMPLETE | 100%
ROADS | 4175 | Muhutii road-n.kinangop | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1250000 | 1245682 |  | C.G.N | [5 empty] | 1245682 |  |  | COMPLETE | 100%
ROADS | 4176 | D-369-kimwaki centre-nandarasi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1692000 | 1659787 |  | C.G.N | [5 empty] | 1659787 |  |  | COMPLETE | 100%
ROADS | 4177 | Culvert installation (karima-muthurwa road) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 553649 | 552900 |  | C.G.N | [5 empty] | 552900 |  |  | COMPLETE | 100%
ROADS | 4178 | Kahuruko-kimbo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 989000 | 986000 |  | C.G.N | [5 empty] | 986000 |  |  | COMPLETE | 100%
ROADS | 4179 | Wapaul-kitogo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 2276500 | 2267780 |  | C.G.N | [5 empty] | 2267780 |  |  | COMPLETE | 100%
ROADS | 4180 | Ndunyu njeru-mihuti road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1683000 | 1679000 |  | C.G.N | [5 empty] | 1679000 |  |  | COMPLETE | 100%
ROADS | 4181 | Kimwaki centre nandarasi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1385500 | 1654787 |  | C.G.N | [5 empty] | 1654787 |  |  | COMPLETE | 100%
ROADS | 4182 | Assorted roads in ndunyunjeru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 1584000 | 1577200 |  | C.G.N | [5 empty] | 1577200 |  |  | COMPLETE | 100%
ROADS | 4183 | Completion of gatimu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 990000 | 978600 |  | C.G.N | [5 empty] | 978600 |  |  | COMPLETE | 100%
ROADS | 4184 | John macharia bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2016-07-01 | 2017-06-01 |  | 6000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | COMPLETE | 100%
ROADS | 4185 | Karatasi wambaa and proseki | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4186 | Nyathuta bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 999595 |  | C.G.N | [5 empty] | 999595 |  |  | COMPLETE | 100%
ROADS | 4187 | John-jeshi road njabini kiburu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 700000 | 645575 |  | C.G.N | [5 empty] | 645575 |  |  | COMPLETE | 100%
ROADS | 4188 | Pilot wakiiru- road njabini kiburu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 921000 |  | C.G.N | [5 empty] | 921000 |  |  | COMPLETE | 100%
ROADS | 4189 | Pcea spring muthui-ben | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1100000 | 1097630 |  | C.G.N | [5 empty] | 1097630 |  |  | COMPLETE | 100%
ROADS | 4190 | Ibrahim/bernard road njabini kiburu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1997400 |  | C.G.N | [5 empty] | 1997400 |  |  | COMPLETE | 100%
ROADS | 4191 | Assorted road works kiburo m | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 515200 | 514000 |  | C.G.N | [5 empty] | 514000 |  |  | COMPLETE | 100%
ROADS | 4192 | Sasumua dam | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2963254 |  | C.G.N | [5 empty] | 2963254 |  |  | COMPLETE | 100%
ROADS | 4193 | Churiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2998948 |  | C.G.N | [5 empty] | 2998948 |  |  | COMPLETE | 100%
ROADS | 4194 | Kiburu road works kwa ngua road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 995100 |  | C.G.N | [5 empty] | 995100 |  |  | COMPLETE | 100%
ROADS | 4195 | Freepentecoastal restoration njabini kiburu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1400000 | 1382200 |  | C.G.N | [5 empty] | 1382200 |  |  | COMPLETE | 100%
ROADS | 4196 | Churiri bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 6000000 | 5000064 |  | C.G.N | [5 empty] | 5000064 |  |  | COMPLETE | 100%
ROADS | 4197 | Muruai-subuku road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1986384 |  | C.G.N | [5 empty] | 1986384 |  |  | COMPLETE | 100%
ROADS | 4198 | Other road works ndaragwa makereka kaniaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 989000 |  | C.G.N | [5 empty] | 989000 |  |  | COMPLETE | 100%
ROADS | 4199 | Off ndaragwa boys-leshau road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1564000 | 1558750 |  | C.G.N | [5 empty] | 1558750 |  |  | COMPLETE | 100%
ROADS | 4200 | 81 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1998780 |  | C.G.N | [5 empty] | 1998780 |  |  | COMPLETE | 100%
ROADS | 4201 | Maili kumi-ndaragwa boys road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2997556 |  | C.G.N | [5 empty] | 2997556 |  |  | COMPLETE | 100%
ROADS | 4202 | Subuku-kanyagia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2996867 |  | C.G.N | [5 empty] | 2996867 |  |  | COMPLETE | 100%
ROADS | 4203 | Mavekia-gatece-mungetho | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1700000 | 1698696 |  | C.G.N | [5 empty] | 1698696 |  |  | COMPLETE | 100%
ROADS | 4204 | Kimili-mugokoro-mugwe rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 996100 |  | C.G.N | [5 empty] | 996100 |  |  | COMPLETE | 100%
ROADS | 4205 | Mutanga forest wamathigara rd kiriita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 700000 | 580000 |  | C.G.N | [5 empty] | 580000 |  |  | COMPLETE | 100%
ROADS | 4206 | Nairobi pcea road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 336000 | 330000 |  | C.G.N | [5 empty] | 330000 |  |  | COMPLETE | 100%
ROADS | 4207 | Raithi rowa rd drainage and culvert installation kiriita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 515200 | 513201 |  | C.G.N | [5 empty] | 513201 |  |  | COMPLETE | 100%
ROADS | 4208 | Githinji pry gathumo rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 995280 |  | C.G.N | [5 empty] | 995280 |  |  | COMPLETE | 100%
ROADS | 4209 | Heroes-wakahot road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2500000 | 2499449 |  | C.G.N | [5 empty] | 2499449 |  |  | COMPLETE | 100%
ROADS | 4210 | Mairo-inya town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1997495.06 |  | C.G.N | [5 empty] | 1997495.06 |  |  | COMPLETE | 100%
ROADS | 4211 | Graduel- matindiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1515200 | 1490200 |  | C.G.N | [5 empty] | 1490200 |  |  | COMPLETE | 100%
ROADS | 4212 | Muchemi -kiriondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1050000 | 1042750 |  | C.G.N | [5 empty] | 1042750 |  |  | COMPLETE | 100%
ROADS | 4213 | Ngari -mugwero | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1060000 | 1034256 |  | C.G.N | [5 empty] | 1034256 |  |  | COMPLETE | 100%
ROADS | 4214 | Gichaka-rita-wakaba rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1115200 | 1089500 |  | C.G.N | [5 empty] | 1089500 |  |  | COMPLETE | 100%
ROADS | 4215 | Mung'etho-gachuiri rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 460000 | 458200 |  | C.G.N | [5 empty] | 458200 |  |  | COMPLETE | 100%
ROADS | 4216 | Kwa meja- nyairoko | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1300000 | 1298000 |  | C.G.N | [5 empty] | 1298000 |  |  | COMPLETE | 100%
ROADS | 4217 | Adams road & kimathi access road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3994267 |  | C.G.N | [5 empty] | 3994267 |  |  | COMPLETE | 100%
ROADS | 4218 | Olaimutia pry & mithamo dam road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3450000 | 3426435 |  | C.G.N | [5 empty] | 3426435 |  |  | COMPLETE | 100%
ROADS | 4219 | Graduel- matindiri phase ii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2100000 | 1993100 |  | C.G.N | [5 empty] | 1993100 |  |  | COMPLETE | 100%
ROADS | 4220 | Chameleon-mahehe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4221 | 230-gacharage road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2300000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4222 | Kwa meja bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4223 | Peter githiji-kwa meja bridge murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3100000 | 3004000 |  | C.G.N | [5 empty] | 3004000 |  |  | COMPLETE | 100%
ROADS | 4224 | Hasaba gathioro rd gravelling murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1100000 | 1099350 |  | C.G.N | [5 empty] | 1099350 |  |  | COMPLETE | 100%
ROADS | 4225 | Nyaruia miiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4226 | Mkungi-mikaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 499800 |  | C.G.N | [5 empty] | 499800 |  |  | COMPLETE | 100%
ROADS | 4227 | Murungaru-nduru-mugi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2943633.4 |  | C.G.N | [5 empty] | 2943633.4 |  |  | COMPLETE | 100%
ROADS | 4228 | Munanda-ngunyo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 | 1488825 |  | C.G.N | [5 empty] | 1488825 |  |  | COMPLETE | 100%
ROADS | 4229 | Gitonga wakarenge road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1270000 | 1268000 |  | C.G.N | [5 empty] | 1268000 |  |  | COMPLETE | 100%
ROADS | 4230 | Gakoroba-gitahi rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 966000 | 963700 |  | C.G.N | [5 empty] | 963700 |  |  | COMPLETE | 100%
ROADS | 4231 | St lucy nduthi road rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 968000 | 962800 |  | C.G.N | [5 empty] | 962800 |  |  | COMPLETE | 100%
ROADS | 4232 | Mbogua gachokia road rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 598000 | 597730 |  | C.G.N | [5 empty] | 597730 |  |  | COMPLETE | 100%
ROADS | 4233 | Wamathenge-gitonga rd (gravelling, culvert installation) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 996100 |  | C.G.N | [5 empty] | 996100 |  |  | COMPLETE | 100%
ROADS | 4234 | Railway- mukiri rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997900 |  | C.G.N | [5 empty] | 997900 |  |  | COMPLETE | 100%
ROADS | 4235 | Githunguri- stage 1 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 999250 |  | C.G.N | [5 empty] | 999250 |  |  | COMPLETE | 100%
ROADS | 4236 | Reli-rurii road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1998000 |  | C.G.N | [5 empty] | 1998000 |  |  | COMPLETE | 100%
ROADS | 4237 | Gitu kibaki | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 700000 | 698000 |  | C.G.N | [5 empty] | 698000 |  |  | COMPLETE | 100%
ROADS | 4238 | Rurii-st.francis-thitai ecd road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2998089 |  | C.G.N | [5 empty] | 2998089 |  |  | COMPLETE | 100%
ROADS | 4239 | Jeremia- mugetho) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1058400 | 1056400 |  | C.G.N | [5 empty] | 1056400 |  |  | COMPLETE | 100%
ROADS | 4240 | Kiruthu mutharia | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1220000 | 1206748 |  | C.G.N | [5 empty] | 1206748 |  |  | COMPLETE | 100%
ROADS | 4241 | Kwa mboga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1050000 | 1048325 |  | C.G.N | [5 empty] | 1048325 |  |  | COMPLETE | 100%
ROADS | 4242 | Ihigaini kahuruko | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1058400 | 1056090 |  | C.G.N | [5 empty] | 1056090 |  |  | COMPLETE | 100%
ROADS | 4243 | Mugetho- ngatho | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1058400 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4244 | Bahati- oljororok rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1058400 | 1055500 |  | C.G.N | [5 empty] | 1055500 |  |  | COMPLETE | 100%
ROADS | 4245 | Silibwet nursery-mungetho (boiman-huhoini) road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 7500000 | 6188078 |  | C.G.N | [5 empty] | 6188078 |  |  | COMPLETE | 100%
ROADS | 4246 | Kariamburi-ndungu nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997310 |  | C.G.N | [5 empty] | 997310 |  |  | COMPLETE | 100%
ROADS | 4247 | Mutarakwa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1140000 | 1017625 |  | C.G.N | [5 empty] | 1017625 |  |  | COMPLETE | 100%
ROADS | 4248 | Mishinda road nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 850000 | 849800 |  | C.G.N | [5 empty] | 849800 |  |  | COMPLETE | 100%
ROADS | 4249 | Kihunguru rd nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1030400 | 1025600 |  | C.G.N | [5 empty] | 1025600 |  |  | COMPLETE | 100%
ROADS | 4250 | Issaco-kiragu nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1030400 | 1020000 |  | C.G.N | [5 empty] | 1020000 |  |  | COMPLETE | 100%
ROADS | 4251 | Marraming of mukeu squater village access road nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1450000 | 1449500 |  | C.G.N | [5 empty] | 1449500 |  |  | COMPLETE | 100%
ROADS | 4252 | Michinda-karangatha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1996752 |  | C.G.N | [5 empty] | 1996752 |  |  | COMPLETE | 100%
ROADS | 4253 | Cheese primary-hagard road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 998338 |  | C.G.N | [5 empty] | 998338 |  |  | COMPLETE | 100%
ROADS | 4254 | Bongo-cuba-kahuho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2991887 |  | C.G.N | [5 empty] | 2991887 |  |  | COMPLETE | 100%
ROADS | 4255 | Legetet road leshau pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 700000 | 695000 |  | C.G.N | [5 empty] | 695000 |  |  | COMPLETE | 100%
ROADS | 4256 | Gwa kungu trading centre rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 700000 | 697000 |  | C.G.N | [5 empty] | 697000 |  |  | COMPLETE | 100%
ROADS | 4257 | Nyakingwa- gwa karoki rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1400000 | 1397000 |  | C.G.N | [5 empty] | 1397000 |  |  | COMPLETE | 100%
ROADS | 4258 | Nyanyuki road -pcea gwa kungu leshau pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 600000 | 583150 |  | C.G.N | [5 empty] | 583150 |  |  | COMPLETE | 100%
ROADS | 4259 | Kiandege shopping centre- aberdares teachers college leshau pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1400000 | 1353150 |  | C.G.N | [5 empty] | 1353150 |  |  | COMPLETE | 100%
ROADS | 4260 | Kiandege pry-kingi dam rd leshau pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 900000 | 894540 |  | C.G.N | [5 empty] | 894540 |  |  | COMPLETE | 100%
ROADS | 4261 | Kwa j- lawrence leshau pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 800000 | 795530 |  | C.G.N | [5 empty] | 795530 |  |  | COMPLETE | 100%
ROADS | 4262 | Equator-kamukunji road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2969904 |  | C.G.N | [5 empty] | 2969904 |  |  | COMPLETE | 100%
ROADS | 4263 | Gwa-kung'u road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 996486 |  | C.G.N | [5 empty] | 996486 |  |  | COMPLETE | 100%
ROADS | 4264 | Ndogino bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2500000 | 2499700 |  | C.G.N | [5 empty] | 2499700 |  |  | COMPLETE | 100%
ROADS | 4265 | Mukuria chegemufia access road githabai | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997800 |  | C.G.N | [5 empty] | 997800 |  |  | COMPLETE | 100%
ROADS | 4266 | Mijikenda - wakweli - kiahuko | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 999740 |  | C.G.N | [5 empty] | 999740 |  |  | COMPLETE | 100%
ROADS | 4267 | Tariban- ndumbi nursery road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1100000 | 1095800 |  | C.G.N | [5 empty] | 1095800 |  |  | COMPLETE | 100%
ROADS | 4268 | Pro gatei junction rd githabai | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 978680 | 972500 |  | C.G.N | [5 empty] | 972500 |  |  | COMPLETE | 100%
ROADS | 4269 | Pas wanjohi haraka road githabai | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 | 1498590 |  | C.G.N | [5 empty] | 1498590 |  |  | COMPLETE | 100%
ROADS | 4270 | Githabai boda boda | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 498530 |  | C.G.N | [5 empty] | 498530 |  |  | COMPLETE | 100%
ROADS | 4271 | Koinange karate kio road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1994855 |  | C.G.N | [5 empty] | 1994855 |  |  | COMPLETE | 100%
ROADS | 4272 | Junction githabai nyakio road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2996570 |  | C.G.N | [5 empty] | 2996570 |  |  | COMPLETE | 100%
ROADS | 4273 | Gathae rd githabai | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 610880 | 550000 |  | C.G.N | [5 empty] | 550000 |  |  | COMPLETE | 100%
ROADS | 4274 | Completion of kiririmbi rd githabai | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 463680 | 384300 |  | C.G.N | [5 empty] | 384300 |  |  | COMPLETE | 100%
ROADS | 4275 | Githabai nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3990071.14 |  | C.G.N | [5 empty] | 3990071.14 |  |  | COMPLETE | 100%
ROADS | 4276 | Haraka githabai nyakio road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3990071 |  | C.G.N | [5 empty] | 3990071 |  |  | COMPLETE | 100%
ROADS | 4277 | Matini ecd-mawingu (rurii-asis) road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 | 1498943 |  | C.G.N | [5 empty] | 1498943 |  |  | COMPLETE | 100%
ROADS | 4278 | Mawingu-ngara ciori road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4279 | Nazareth road shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2100000 | 2099716 |  | C.G.N | [5 empty] | 2099716 |  |  | COMPLETE | 100%
ROADS | 4280 | Gikano road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4281 | Other road works muthama road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  |  | 796000 |  | C.G.N | [5 empty] | 796000 |  |  | COMPLETE | 100%
ROADS | 4282 | Ndaraca- igiri-kiambogo-mihangia rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4283 | Thirikwa-ndargwa centre rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 951490 |  | C.G.N | [5 empty] | 951490 |  |  | COMPLETE | 100%
ROADS | 4284 | Ex- daya kirimanjaro rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 980223 |  | C.G.N | [5 empty] | 980223 |  |  | COMPLETE | 100%
ROADS | 4285 | Simbara secondary sch rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 925772 |  | C.G.N | [5 empty] | 925772 |  |  | COMPLETE | 100%
ROADS | 4286 | Shamata-muthaiga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1999942 |  | C.G.N | [5 empty] | 1999942 |  |  | COMPLETE | 100%
ROADS | 4287 | Muhiriga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2985753 |  | C.G.N | [5 empty] | 2985753 |  |  | COMPLETE | 100%
ROADS | 4288 | Kwabekenya dispensary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997200 |  | C.G.N | [5 empty] | 997200 |  |  | COMPLETE | 100%
ROADS | 4289 | Mbothe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 600000 | 595689 |  | C.G.N | [5 empty] | 595689 |  |  | COMPLETE | 100%
ROADS | 4290 | Kiria rd n.kinangop | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 700000 | 690150 |  | C.G.N | [5 empty] | 690150 |  |  | COMPLETE | 100%
ROADS | 4291 | Ballam-kwabekenya-kiambariki | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1600000 | 1597000 |  | C.G.N | [5 empty] | 1597000 |  |  | COMPLETE | 100%
ROADS | 4292 | Muiruri - gatimu rd gravelling n.kinagop | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 368000 | 304700 |  | C.G.N | [5 empty] | 304700 |  |  | COMPLETE | 100%
ROADS | 4293 | Kamba -kag church road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 550000 | 547000 |  | C.G.N | [5 empty] | 547000 |  |  | COMPLETE | 100%
ROADS | 4294 | Ezekiel-kitogo-kwa moses road culvert-gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 576000 | 571550 |  | C.G.N | [5 empty] | 571550 |  |  | COMPLETE | 100%
ROADS | 4295 | Baaram-karanja-macharia rd n.kinagop | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 600000 | 12 |  | C.G.N | [5 empty] | 12 |  |  | COMPLETE | 100%
ROADS | 4296 | Ndunyu njeru-kahuruko (muhutii) road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3994558 |  | C.G.N | [5 empty] | 3994558 |  |  | COMPLETE | 100%
ROADS | 4297 | Muhutii-kimwaki-kinja road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3991908 |  | C.G.N | [5 empty] | 3991908 |  |  | COMPLETE | 100%
ROADS | 4298 | C69 -bara inya gathaara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1700000 | 1680000 |  | C.G.N | [5 empty] | 1680000 |  |  | COMPLETE | 100%
ROADS | 4299 | Gathogo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1600000 | 1598600 |  | C.G.N | [5 empty] | 1598600 |  |  | COMPLETE | 100%
ROADS | 4300 | Guard rd gathaara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 515200 | 498000 |  | C.G.N | [5 empty] | 498000 |  |  | COMPLETE | 100%
ROADS | 4301 | Gachicha rd ,gathaara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1800000 | 1794000 |  | C.G.N | [5 empty] | 1794000 |  |  | COMPLETE | 100%
ROADS | 4302 | Ichangai- grace pry school | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 1065000 |  | C.G.N | [5 empty] | 1065000 |  |  | COMPLETE | 100%
ROADS | 4303 | Kirima-ngandu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2970569 |  | C.G.N | [5 empty] | 2970569 |  |  | COMPLETE | 100%
ROADS | 4304 | Fr.joseph baldo pry-kitiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3997603 |  | C.G.N | [5 empty] | 3997603 |  |  | COMPLETE | 100%
ROADS | 4305 | Mwenda andu - kabua | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1400000 | 1399875 |  | C.G.N | [5 empty] | 1399875 |  |  | COMPLETE | 100%
ROADS | 4306 | St philips- ciondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 | 1497920 |  | C.G.N | [5 empty] | 1497920 |  |  | COMPLETE | 100%
ROADS | 4307 | Raitha water tank-kahuru disp- kirathimo pry | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1800000 | 1793180 |  | C.G.N | [5 empty] | 1793180 |  |  | COMPLETE | 100%
ROADS | 4308 | Weru-njoma road-engineer | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 800000 | 780000 |  | C.G.N | [5 empty] | 780000 |  |  | COMPLETE | 100%
ROADS | 4309 | Ask st phillips | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997690 |  | C.G.N | [5 empty] | 997690 |  |  | COMPLETE | 100%
ROADS | 4310 | Engineer town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1983356 |  | C.G.N | [5 empty] | 1983356 |  |  | COMPLETE | 100%
ROADS | 4311 | Engineer-cuma road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2913061 |  | C.G.N | [5 empty] | 2913061 |  |  | COMPLETE | 100%
ROADS | 4312 | No.14 river road geta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 999776 |  | C.G.N | [5 empty] | 999776 |  |  | COMPLETE | 100%
ROADS | 4313 | Wagatoto forest -kagongo road works geta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997800 |  | C.G.N | [5 empty] | 997800 |  |  | COMPLETE | 100%
ROADS | 4314 | Marimu canteen road geta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1491200 | 1415000 |  | C.G.N | [5 empty] | 1415000 |  |  | COMPLETE | 100%
ROADS | 4315 | Kanduma rd geta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997265 |  | C.G.N | [5 empty] | 997265 |  |  | COMPLETE | 100%
ROADS | 4316 | Sophia ithagu rd -geta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997950 |  | C.G.N | [5 empty] | 997950 |  |  | COMPLETE | 100%
ROADS | 4317 | Bahati rd geta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 988204 |  | C.G.N | [5 empty] | 988204 |  |  | COMPLETE | 100%
ROADS | 4318 | Peak line road mikeu geta- gravelling geta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 999850 |  | C.G.N | [5 empty] | 999850 |  |  | COMPLETE | 100%
ROADS | 4319 | Kanjangiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2965992 |  | C.G.N | [5 empty] | 2965992 |  |  | COMPLETE | 100%
ROADS | 4320 | Bethuel rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 998100 |  | C.G.N | [5 empty] | 998100 |  |  | COMPLETE | 100%
ROADS | 4321 | Munanda-mugaki road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3989297 |  | C.G.N | [5 empty] | 3989297 |  |  | COMPLETE | 100%
ROADS | 4322 | Mikiri kaba wangaiyo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 991280 |  | C.G.N | [5 empty] | 991280 |  |  | COMPLETE | 100%
ROADS | 4323 | Magega-muthungu rd kipipiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 999803 |  | C.G.N | [5 empty] | 999803 |  |  | COMPLETE | 100%
ROADS | 4324 | Ngonyo rd kipipiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 995419 |  | C.G.N | [5 empty] | 995419 |  |  | COMPLETE | 100%
ROADS | 4325 | St john wathigo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 800000 | 799400 |  | C.G.N | [5 empty] | 799400 |  |  | COMPLETE | 100%
ROADS | 4326 | Wagikandi- kirima road kipipiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 993400 |  | C.G.N | [5 empty] | 993400 |  |  | COMPLETE | 100%
ROADS | 4327 | Manunga-kabingu rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 900000 | 896796 |  | C.G.N | [5 empty] | 896796 |  |  | COMPLETE | 100%
ROADS | 4328 | Manunga-hosea rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 800000 | 797900 |  | C.G.N | [5 empty] | 797900 |  |  | COMPLETE | 100%
ROADS | 4329 | Bondeni pry-st johns kipipiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3998960 |  | C.G.N | [5 empty] | 3998960 |  |  | COMPLETE | 100%
ROADS | 4330 | Mahinga ecd-miharati road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4331 | Miharati town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1999544 |  | C.G.N | [5 empty] | 1999544 |  |  | COMPLETE | 100%
ROADS | 4332 | Roadworks at karau(mawingu sec school) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1800000 | 1797072 |  | C.G.N | [5 empty] | 1797072 |  |  | COMPLETE | 100%
ROADS | 4333 | Culvets installation,drainage works, and mullaming (kagotho-captain road off nairobi highway -mood hotel road) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2400000 | 2390389 |  | C.G.N | [5 empty] | 2390389 |  |  | COMPLETE | 100%
ROADS | 4334 | Kandeto museveni road karau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 804800 | 804800 |  | C.G.N | [5 empty] | 804800 |  |  | COMPLETE | 100%
ROADS | 4335 | Nyairoko-kamukururo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1106000 | 1095469 |  | C.G.N | [5 empty] | 1095469 |  |  | COMPLETE | 100%
ROADS | 4336 | Other road works karau (estate rds) bahati canaan rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2980000 |  | C.G.N | [5 empty] | 2980000 |  |  | COMPLETE | 100%
ROADS | 4337 | Olkalou estates roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2944980 |  | C.G.N | [5 empty] | 2944980 |  |  | COMPLETE | 100%
ROADS | 4338 | Olkalou-quarry-mumbi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3994518 |  | C.G.N | [5 empty] | 3994518 |  |  | COMPLETE | 100%
ROADS | 4339 | Uhuru primary kanjuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1600000 | 1596550 |  | C.G.N | [5 empty] | 1596550 |  |  | COMPLETE | 100%
ROADS | 4340 | Dailry st monica rd kanjuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1900000 | 1886450 |  | C.G.N | [5 empty] | 1886450 |  |  | COMPLETE | 100%
ROADS | 4341 | Kio rd ,kanjuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 998064 |  | C.G.N | [5 empty] | 998064 |  |  | COMPLETE | 100%
ROADS | 4342 | Bata road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 994660 |  | C.G.N | [5 empty] | 994660 |  |  | COMPLETE | 100%
ROADS | 4343 | Ngorika kio road kanjuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997100 |  | C.G.N | [5 empty] | 997100 |  |  | COMPLETE | 100%
ROADS | 4344 | Dairy-wiyumiririe-kanjuiri shopping road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3500000 | 3467646 |  | C.G.N | [5 empty] | 3467646 |  |  | COMPLETE | 100%
ROADS | 4345 | Ngorika-ithigani road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4500000 | 4487600 |  | C.G.N | [5 empty] | 4487600 |  |  | COMPLETE | 100%
ROADS | 4346 | Tumaini-njigaga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2978601 |  | C.G.N | [5 empty] | 2978601 |  |  | COMPLETE | 100%
ROADS | 4347 | Mbaruk rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1997200 |  | C.G.N | [5 empty] | 1997200 |  |  | COMPLETE | 100%
ROADS | 4348 | Wanjora mugoiri bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4500000 | 4493584 |  | C.G.N | [5 empty] | 4493584 |  |  | COMPLETE | 100%
ROADS | 4349 | Tumaini township roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 | 1497000 |  | C.G.N | [5 empty] | 1497000 |  |  | COMPLETE | 100%
ROADS | 4350 | Gichuki-gathiaka rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1600000 | 1597750 |  | C.G.N | [5 empty] | 1597750 |  |  | COMPLETE | 100%
ROADS | 4351 | Mukanda mwamu road gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1999980 |  | C.G.N | [5 empty] | 1999980 |  |  | COMPLETE | 100%
ROADS | 4352 | Wakahia-iriaina- equator -iriyainin road gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 999865 |  | C.G.N | [5 empty] | 999865 |  |  | COMPLETE | 100%
ROADS | 4353 | Destination ngomongo road gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 900000 | 885366 |  | C.G.N | [5 empty] | 885366 |  |  | COMPLETE | 100%
ROADS | 4354 | Airstrip-bani-kibathi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 800000 | 799500 |  | C.G.N | [5 empty] | 799500 |  |  | COMPLETE | 100%
ROADS | 4355 | Equator primary-kwamucheru road gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1995896 |  | C.G.N | [5 empty] | 1995896 |  |  | COMPLETE | 100%
ROADS | 4356 | Kinyonzi-babajohn-wanyega road gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 999600 |  | C.G.N | [5 empty] | 999600 |  |  | COMPLETE | 100%
ROADS | 4357 | Gatimu jubilee,wamercy,wamaina,mutaro tube culvert | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1100000 | 1094000 |  | C.G.N | [5 empty] | 1094000 |  |  | COMPLETE | 100%
ROADS | 4358 | Gikingi-emmanuel-ngomongo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2999770 |  | C.G.N | [5 empty] | 2999770 |  |  | COMPLETE | 100%
ROADS | 4359 | Equator bani rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4360 | Mwereri bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 600000 | 598119 |  | C.G.N | [5 empty] | 598119 |  |  | COMPLETE | 100%
ROADS | 4361 | Gatimu-njono-kangugo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2400000 | 2392360 |  | C.G.N | [5 empty] | 2392360 |  |  | COMPLETE | 100%
ROADS | 4362 | Kahii irani rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1600000 | 1585530 |  | C.G.N | [5 empty] | 1585530 |  |  | COMPLETE | 100%
ROADS | 4363 | Inoro-ngufa rd weru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1980195 |  | C.G.N | [5 empty] | 1980195 |  |  | COMPLETE | 100%
ROADS | 4364 | Rd 49- gatitu pry | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 850000 | 848800 |  | C.G.N | [5 empty] | 848800 |  |  | COMPLETE | 100%
ROADS | 4365 | Madaraka kenji rd weru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1351035 | 1309245 |  | C.G.N | [5 empty] | 1309245 |  |  | COMPLETE | 100%
ROADS | 4366 | Kieni ack -gacheru dam rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 700000 | 699200 |  | C.G.N | [5 empty] | 699200 |  |  | COMPLETE | 100%
ROADS | 4367 | Kwa meja bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2994830 |  | C.G.N | [5 empty] | 2994830 |  |  | COMPLETE | 100%
ROADS | 4368 | Karandi sec school road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 | 1499880 |  | C.G.N | [5 empty] | 1499880 |  |  | COMPLETE | 100%
ROADS | 4369 | Kirima makara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 | 1492000 |  | C.G.N | [5 empty] | 1492000 |  |  | COMPLETE | 100%
ROADS | 4370 | Culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 497200 |  | C.G.N | [5 empty] | 497200 |  |  | COMPLETE | 100%
ROADS | 4371 | Connerstone-gatitu pry road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2500000 | 2496706 |  | C.G.N | [5 empty] | 2496706 |  |  | COMPLETE | 100%
ROADS | 4372 | Kasuku-kahingo pry | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2500000 | 2499649 |  | C.G.N | [5 empty] | 2499649 |  |  | COMPLETE | 100%
ROADS | 4373 | Bamboo- runda road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 400000 | 398000 |  | C.G.N | [5 empty] | 398000 |  |  | COMPLETE | 100%
ROADS | 4374 | Abbas -nene road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 600000 | 598550 |  | C.G.N | [5 empty] | 598550 |  |  | COMPLETE | 100%
ROADS | 4375 | Kimbuyu-setlight-flyover magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1020000 | 998225 |  | C.G.N | [5 empty] | 998225 |  |  | COMPLETE | 100%
ROADS | 4376 | Kagumo- githaiga- kamisha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1380000 | 1349000 |  | C.G.N | [5 empty] | 1349000 |  |  | COMPLETE | 100%
ROADS | 4377 | Ha musyoka john kagecha magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1030400 | 998800 |  | C.G.N | [5 empty] | 998800 |  |  | COMPLETE | 100%
ROADS | 4378 | Soko mjinga -mukeu-kenton fly over road magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4379 | Soko mjinga -mukeu-kenton fly over road magumu(phase ii) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1998000 |  | C.G.N | [5 empty] | 1998000 |  |  | COMPLETE | 100%
ROADS | 4380 | Dr.mathenge mwalimu clerk road kiburu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1100690 | 1092200 |  | C.G.N | [5 empty] | 1092200 |  |  | COMPLETE | 100%
ROADS | 4381 | Magumu town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1100690 | 1990560 |  | C.G.N | [5 empty] | 1990560 |  |  | COMPLETE | 100%
ROADS | 4382 | St.marys-mwendandu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1959332 |  | C.G.N | [5 empty] | 1959332 |  |  | COMPLETE | 100%
ROADS | 4383 | Mirangine bus park | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1996244 |  | C.G.N | [5 empty] | 1996244 |  |  | COMPLETE | 100%
ROADS | 4384 | Karungo rd mirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4385 | Other road worksmirangine (gwa kiongo village) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1964422 |  | C.G.N | [5 empty] | 1964422 |  |  | COMPLETE | 100%
ROADS | 4386 | Makutano -mbora rd mirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1030200 | 1020000 |  | C.G.N | [5 empty] | 1020000 |  |  | COMPLETE | 100%
ROADS | 4387 | Kibendera rd mirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1909000 | 1897625 |  | C.G.N | [5 empty] | 1897625 |  |  | COMPLETE | 100%
ROADS | 4388 | Tumaini waganamirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 530400 | 529050 |  | C.G.N | [5 empty] | 529050 |  |  | COMPLETE | 100%
ROADS | 4389 | Kamuyu gitare | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1030400 | 1028050 |  | C.G.N | [5 empty] | 1028050 |  |  | COMPLETE | 100%
ROADS | 4390 | Off-kabazi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1510000 | 1490020 |  | C.G.N | [5 empty] | 1490020 |  |  | COMPLETE | 100%
ROADS | 4391 | Kabazi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3980911 |  | C.G.N | [5 empty] | 3980911 |  |  | COMPLETE | 100%
ROADS | 4392 | Githima-gituamba police station road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1991755 |  | C.G.N | [5 empty] | 1991755 |  |  | COMPLETE | 100%
ROADS | 4393 | Kihuho dispensary rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1831539 |  | C.G.N | [5 empty] | 1831539 |  |  | COMPLETE | 100%
ROADS | 4394 | Haraka-matunda-gathiriga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2989233 |  | C.G.N | [5 empty] | 2989233 |  |  | COMPLETE | 100%
ROADS | 4395 | Kirima forest rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 | 1498780 |  | C.G.N | [5 empty] | 1498780 |  |  | COMPLETE | 100%
ROADS | 4396 | Bara jeru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1997380 |  | C.G.N | [5 empty] | 1997380 |  |  | COMPLETE | 100%
ROADS | 4397 | Ngaruiya miiri rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997000 |  | C.G.N | [5 empty] | 997000 |  |  | COMPLETE | 100%
ROADS | 4398 | Gituamba-kibendera road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 | 1488280 |  | C.G.N | [5 empty] | 1488280 |  |  | COMPLETE | 100%
ROADS | 4399 | Gwakiongo town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 2000000 | 1995049 |  | C.G.N | [5 empty] | 1995049 |  |  | COMPLETE | 100%
ROADS | 4400 | Other road works githioro | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 998600 |  | C.G.N | [5 empty] | 998600 |  |  | COMPLETE | 100%
ROADS | 4401 | Mumui turasha | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1200000 | 1198355 |  | C.G.N | [5 empty] | 1198355 |  |  | COMPLETE | 100%
ROADS | 4402 | Harmbee- munoru booster rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1300000 | 1194400 |  | C.G.N | [5 empty] | 1194400 |  |  | COMPLETE | 100%
ROADS | 4403 | Gatherega roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1800000 | 1298708 |  | C.G.N | [5 empty] | 1298708 |  |  | COMPLETE | 100%
ROADS | 4404 | St. Peters mawingu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1800000 | 1797400 |  | C.G.N | [5 empty] | 1797400 |  |  | COMPLETE | 100%
ROADS | 4405 | Mawingu-ngara ciori road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 4000000 | 3982703 |  | C.G.N | [5 empty] | 3982703 |  |  | COMPLETE | 100%
ROADS | 4406 | Matini ecd-mawingu (rurii-asis) road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4407 | Olkalou estates roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2995955.2 |  | C.G.N | [5 empty] | 2995955.2 |  |  | COMPLETE | 100%
ROADS | 4408 | Kiganjo gicharu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 986200 |  | C.G.N | [5 empty] | 986200 |  |  | COMPLETE | 100%
ROADS | 4409 | County assembly road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 550000 | 547356 |  | C.G.N | [5 empty] | 547356 |  |  | COMPLETE | 100%
ROADS | 4410 | Olkalou-ndemi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3500000 | 3482746 |  | C.G.N | [5 empty] | 3482746 |  |  | COMPLETE | 100%
ROADS | 4411 | Wamalcolm-pcea-kiganjo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1400000 | 1399620 |  | C.G.N | [5 empty] | 1399620 |  |  | COMPLETE | 100%
ROADS | 4412 | Thatai wa- gideon rd kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 600001 | 597950 |  | C.G.N | [5 empty] | 597950 |  |  | COMPLETE | 100%
ROADS | 4413 | Kariamu-kag rd,kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 497060 |  | C.G.N | [5 empty] | 497060 |  |  | COMPLETE | 100%
ROADS | 4414 | Kihurure rd , kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 488300 |  | C.G.N | [5 empty] | 488300 |  |  | COMPLETE | 100%
ROADS | 4415 | Kanju-forest rd- grading and gravelling kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 498162 |  | C.G.N | [5 empty] | 498162 |  |  | COMPLETE | 100%
ROADS | 4416 | Gikuri wa moni road kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 998700 |  | C.G.N | [5 empty] | 998700 |  |  | COMPLETE | 100%
ROADS | 4417 | Rumathi-wa jack-thuo rd- , kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 498000 |  | C.G.N | [5 empty] | 498000 |  |  | COMPLETE | 100%
ROADS | 4418 | Kandutura idp rd kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 474000 |  | C.G.N | [5 empty] | 474000 |  |  | COMPLETE | 100%
ROADS | 4419 | Other road works wanjohi(kahiga road) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1700000 | 1694985 |  | C.G.N | [5 empty] | 1694985 |  |  | COMPLETE | 100%
ROADS | 4420 | Other road works wanjohi (riverside mukuhi) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 993250 |  | C.G.N | [5 empty] | 993250 |  |  | COMPLETE | 100%
ROADS | 4421 | Branda road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 997920 |  | C.G.N | [5 empty] | 997920 |  |  | COMPLETE | 100%
ROADS | 4422 | Rironi-wanjohi rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 7500000 | 6547109 |  | C.G.N | [5 empty] | 6547109 |  |  | COMPLETE | 100%
ROADS | 4423 | Huhirio pry road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 998725 |  | C.G.N | [5 empty] | 998725 |  |  | COMPLETE | 100%
ROADS | 4424 | Mubas-mititano road wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1100000 | 1097630 |  | C.G.N | [5 empty] | 1097630 |  |  | COMPLETE | 100%
ROADS | 4425 | Culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 998000 |  | C.G.N | [5 empty] | 998000 |  |  | COMPLETE | 100%
ROADS | 4426 | Culvert to kahinga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 500000 | 499500 |  | C.G.N | [5 empty] | 499500 |  |  | COMPLETE | 100%
ROADS | 4427 | Mubao -gathima | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 1000000 | 999910 |  | C.G.N | [5 empty] | 999910 |  |  | COMPLETE | 100%
ROADS | 4428 |  | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  |  |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4429 | Construction of county executive offices (county's contribution) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 55400000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4430 | Routine and periodical roads maintainance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 20000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4431 | Development programmes coordination (national government support ) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 13926040 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4432 | Construction of fire station | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 3000000 | 2989946 |  | C.G.N | [5 empty] | 2989946 |  |  | COMPLETE | 100%
ROADS | 4433 | Construction of county executive offices (nationalgovernment's contribution) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 121000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4434 | Governors residence | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 10000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4435 | 25 boda boda sheds in all wards | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2017-07-01 | 2018-06-01 |  | 5000000 |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 4436 | Other Rd Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4437 | Soweto Ngumo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 1799256 |  | C.G.N | [5 empty] | 1799256 |  |  | COMPLETE | 100%
ROADS | 4438 | Mutini Musa Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | - | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4439 | Wajesus Lower Kingimeri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1900000 |  | C.G.N | [5 empty] | 1900000 |  |  | COMPLETE | 100%
ROADS | 4440 | Mutiini-Ndaranja Mbili Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4441 | Kagungo-Kagutu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4442 | Muriganio Outreach Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4443 | Ack St.Philip-Slope Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4444 | Opec-Washgton Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1900000 |  | C.G.N | [5 empty] | 1900000 |  |  | COMPLETE | 100%
ROADS | 4445 | Kamuyaka-Fourteen Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4446 | Culvert Installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 4447 | Routine Mainatmce | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 3500000 |  | C.G.N | [5 empty] | 3500000 |  |  | COMPLETE | 100%
ROADS | 4448 | Roads Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 100000 |  | C.G.N | [5 empty] | 100000 |  |  | COMPLETE | 100%
ROADS | 4449 | Gacoya-Gathara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4450 | Mwinjoyo -Fafu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4451 | Kiariahu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4452 | Main Kenja Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4453 | Gathogo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4454 | Junction Kinja Mutarakwa Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1395900 |  | C.G.N | [5 empty] | 1395900 |  |  | COMPLETE | 100%
ROADS | 4455 | C65 Kinja Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1300000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4456 | Gachoya Gathara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4457 | Ichangai-Kitogo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4458 | Isaac Iganjo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4459 | Ichangai-Kambaa | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4460 | Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 805500 | 805500 |  | C.G.N | [5 empty] | 805500 |  |  | COMPLETE | 100%
ROADS | 4461 | Boda Boda Sheds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 358000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4462 | Opening And Development Of Various New Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 250600 | 250600 |  | C.G.N | [5 empty] | 250600 |  |  | COMPLETE | 100%
ROADS | 4463 | Routine Maintenance-Drainage Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4464 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4465 | Kambi Mbau Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4466 | Kitiri Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4467 | Ndungu -Township Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4468 | North Kinangop Ward General Rd Maintaince | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4469 | Culvert Installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 805500 | 805500 |  | C.G.N | [5 empty] | 805500 |  |  | COMPLETE | 100%
ROADS | 4470 | Ndunyu Njeru-Nandarasi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4471 | Kitiri Rd (Phase 2) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4472 | Bodaboda Shed | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 358000 | 358000 |  | C.G.N | [5 empty] | 358000 |  |  | COMPLETE | 100%
ROADS | 4473 | Muhatiko-Mbekenya Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 875660 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4474 | Muhoti Primary Field-Leveling And Fencing | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4475 | Nandarasi-Kitriri Sublocation Assorted Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4476 | Kahuruko Centre Draining | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4477 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 4478 | Boundary -Munyugu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3385900 | 3385900 |  | C.G.N | [5 empty] | 3385900 |  |  | COMPLETE | 100%
ROADS | 4479 | Wanyeki-Garati Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1375060 |  | C.G.N | [5 empty] | 1375060 |  |  | COMPLETE | 100%
ROADS | 4480 | Darashaini-Makinya Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4481 | Assorted Rds(Sport Patching) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4482 | Kirarwa Flood Light | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4483 | Mukomeri-Kahuria-Mkungi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 6000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4484 | Kamirangi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4485 | Dam-Boundary Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4486 | Soweto-230 Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1250600 | 1250600 |  | C.G.N | [5 empty] | 1250600 |  |  | COMPLETE | 100%
ROADS | 4487 | Culvert Installations Murungaru Ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 913500 | 913500 |  | C.G.N | [5 empty] | 913500 |  |  | COMPLETE | 100%
ROADS | 4488 | Memo Bodaboda | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 250000 | 200000 |  | C.G.N | [5 empty] | 200000 |  |  | COMPLETE | 100%
ROADS | 4489 | Mikaro Floodlight | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4490 | Routine Maintance-Drainge Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4491 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4492 | Churiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4493 | Dr Kiarie-Ngurari Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4494 | Yokosuna-Mkurino Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4495 | Mwalimu Muchiri-Ngero Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 976378 |  | C.G.N | [5 empty] | 976378 |  |  | COMPLETE | 100%
ROADS | 4496 | Njunge Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 1200000 |  | C.G.N | [5 empty] | 1200000 |  |  | COMPLETE | 100%
ROADS | 4497 | Njau-Rwigi-Kamuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4498 | Pcea -Church Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4499 | Eddy-Kanyanjua-Kibuti Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4500 | Kcb-Karuangi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4501 | Nyathuta Kioneki Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 841268 |  | C.G.N | [5 empty] | 841268 |  |  | COMPLETE | 100%
ROADS | 4502 | St.Stephen Church | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 961000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4503 | Wakahiga Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 490000 |  | C.G.N | [5 empty] | 490000 |  |  | COMPLETE | 100%
ROADS | 4504 | Kianjata Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4505 | Boda Boda Sheds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 350000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4506 | Opening Up Development Of Various New Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 627260 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4507 | Routine Maintaince And Drainage Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4508 | Kigoro Road -Curver | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4509 | General Grading-300k, Compacting-300k And Gravelling-600k | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4510 | Floodlights(Yaaga,Cheese,Mukiri,Kagemi,Njuguini,And Barainya Shopping Centres) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1336950 |  | C.G.N | [5 empty] | 1336950 |  |  | COMPLETE | 100%
ROADS | 4511 | Fredha Road Gravel Patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 236182 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4512 | Upper Bongo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 832162 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4513 | Completion Of Kahuho Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4514 | Completion Of Kangano | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1300000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4515 | Kagongo Komu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4516 | Yaaga Kibirio Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4517 | Ndungu Kageraini Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 4518 | Kabue Nyamu-Cheese Bridge Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4519 | Kageraini-Bako-Forest Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4520 | Kahuho-Fretha Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4521 | Completion Of Wanjamira Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4522 | Completion Of Mukiri Karate Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4523 | Culverts Installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 805500 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4524 | Boda Boda Shed | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 350000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4525 | Opening Of New Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 250000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4526 | Routine Maintance And Drainage Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4527 | Completion Of Bongo-Muini Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 801100 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4528 | Gradinng Gravel Patching And Compacting Of Mukiri Karangatha Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 0 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4529 | Completion Of Shirikisho Landmark Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1300000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4530 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4531 | Aic Kangodo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 1845304 |  | C.G.N | [5 empty] | 1845304 |  |  | COMPLETE | 100%
ROADS | 4532 | John Wainaina-Ka Theuri Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4533 | Githae -Kiriahu-Heni Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4534 | Githabai-Kibuika-Haraka Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4535 | Kayole Wakagwa Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | COMPLETE | 100%
ROADS | 4536 | Ndegwa-Mwaura Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 950000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4537 | Soweto Kaungi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 950000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4538 | Koingae Townships Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4539 | Baba Mungai Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4540 | Ballast Making Machine-Koinage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4541 | Culverts Making Baloon(600mm)-Koinange | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4542 | Floodlights-Kalulu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | COMPLETE | 100%
ROADS | 4543 | Assorted Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4544 | Floodlights-Kwajoma | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1300000 | 1298000 |  | C.G.N | [5 empty] | 1298000 |  |  | COMPLETE | 100%
ROADS | 4545 | Heni-Kinungi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4546 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4547 | Magumu-Kibuyu-Flyover | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 2533730 |  | C.G.N | [5 empty] | 2533730 |  |  | COMPLETE | 100%
ROADS | 4548 | Gachurio Floodlight | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 250000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4549 | Gichuhi-Muchara Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4550 | Kamuhuru-Chege Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4551 | Flyover-Kenton Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4552 | Mc Dan Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 1984160 |  | C.G.N | [5 empty] | 1984160 |  |  | COMPLETE | 100%
ROADS | 4553 | Mutonyora B Borehole -Kazi Yao Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1192000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4554 | Soko Mjionga-Mukeu-Flyover Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1727400 |  | C.G.N | [5 empty] | 1727400 |  |  | COMPLETE | 100%
ROADS | 4555 | Flyover-Kenton Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1900000 |  | C.G.N | [5 empty] | 1900000 |  |  | COMPLETE | 100%
ROADS | 4556 | Culverts Installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4557 | Bodaboda Shed | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 358000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4558 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4559 | Gathure Rd Wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4560 | Wanjohi Barainya Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4561 | Magomaro-Nathan | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4562 | Mitihano-Kburuti Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4563 | Rironi-Wanjohi Road Completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4564 | Michore-Chebe Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4565 | Dn Kariamu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4566 | Ndemi Secondary -Polytechinic | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4567 | Kiangware Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4568 | Assorted Gravel Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4569 | Gatukaini-Mahiti Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4570 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4571 | Gichigi-Munanda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4572 | Machina-Wamaina | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4573 | Kahiga-Chief Mathenge Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4574 | Jj Davis-Blue City | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 1981570 |  | C.G.N | [5 empty] | 1981570 |  |  | COMPLETE | 100%
ROADS | 4575 | Munyu-Ini-Magutu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4576 | Rona – John Mbuka | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4577 | Forest J Wagoe | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4578 | Knyua –M Baki | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4579 | Assorted Culvert And Drainage Work | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4580 | Routine Maintenance-Drainage Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4581 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4582 | Ibrahim Road Turasha | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4583 | Konoike Road Turasha | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4584 | Kihumbu-Malewa River Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 5000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4585 | Gakoroba Ngekenya Road Mawingu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4586 | Itangi Kamuyu Road (Gathiriga) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4587 | Kwa Well | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4588 | El Mas- Rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4589 | Mahiga Meri Kago Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4590 | Mumui Bridge Kariara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1700000 | 1700000 |  | C.G.N | [5 empty] | 1700000 |  |  | COMPLETE | 100%
ROADS | 4591 | Tulasha Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4592 | Assorted Culvert And Drainage Work(Mawingu) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4593 | Routine Maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4594 | Ndimi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4595 | Wamahungu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4596 | Mountain Academay Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 950000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4597 | Muthama Kungu-Wahadi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 950000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4598 | Benendeto-Wandaka Karuiru Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 950000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4599 | Number 29 Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4600 | Number 21 Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4601 | Wabocho-Rumwe Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4602 | Kanjangiri Kariaini Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4603 | Zabloni Wambugu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4604 | Kariua Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 4605 | Wauno Rumue Primary Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4606 | Number 3 Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 5000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | COMPLETE | 100%
ROADS | 4607 | Kagongo Forest Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4608 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4609 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4610 | Munyeki-Ctholic-Chiefs Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4611 | Kianda- Munyeki Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4612 | Kgatifaru-Gikonyo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4613 | Kandeto-Kahia | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4614 | Baba Joe-Maina Kamanda | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 950000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4615 | Fundi-Thairu-Nyairoko | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 950000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4616 | Kiweru Rd Networdk | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4617 | Kingaa Nursery -Dispensary Sharom | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 300000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4618 | Uhuru-Mungetho-Gatarwa | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 1647268 |  | C.G.N | [5 empty] | 1647268 |  |  | COMPLETE | 100%
ROADS | 4619 | Kagotho -Captain Road (Along Railway Line -Off Nairobi Nyahururu-Mood Hotel -Gachwe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4620 | Kanyiriri Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4621 | Shemba-Ack-Full -Gospel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4622 | Kimani-Marechu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4623 | Emily-Joram Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4624 | Munyeki Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4625 | Construction Of Bridge Shoulders Vatican | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4626 | Vatican Estate Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 300000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4627 | Bahati Estate Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 300000 | 300000 |  | C.G.N | [5 empty] | 300000 |  |  | COMPLETE | 100%
ROADS | 4628 | Sokomoko Estate Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 300000 | 300000 |  | C.G.N | [5 empty] | 300000 |  |  | COMPLETE | 100%
ROADS | 4629 | Mundia Estates Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 300000 | 300000 |  | C.G.N | [5 empty] | 300000 |  |  | COMPLETE | 100%
ROADS | 4630 | Makenji Estate Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 400000 | 400000 |  | C.G.N | [5 empty] | 400000 |  |  | COMPLETE | 100%
ROADS | 4631 | Bankers Estate Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 400000 | 400000 |  | C.G.N | [5 empty] | 400000 |  |  | COMPLETE | 100%
ROADS | 4632 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4633 | Githabira Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4634 | Waiting Bay Ngorika Hc | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 300000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4635 | Kamau Shilling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4636 | Kangunda Base | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4637 | Nyaitunga-Kanjuiri Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 1299477 |  | C.G.N | [5 empty] | 1299477 |  |  | COMPLETE | 100%
ROADS | 4638 | Murindati-Bata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1300000 | 366000 |  | C.G.N | [5 empty] | 366000 |  |  | COMPLETE | 100%
ROADS | 4639 | Wiyumiririe-Nyaituga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4640 | Njigaga-Kangatha Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4641 | Sailinga Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4642 | Rutara Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 1200000 |  | C.G.N | [5 empty] | 1200000 |  |  | COMPLETE | 100%
ROADS | 4643 | St Monica Mahehu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4644 | Wiy-Githioro Rutara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4645 | Kanjau Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4646 | Nyaitunga -Kirathimo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4647 | Daily -Rutara Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4648 | Culvert Installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4649 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4650 | Bora Dam-Njaga-Makurata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 1397523 |  | C.G.N | [5 empty] | 1397523 |  |  | COMPLETE | 100%
ROADS | 4651 | Haraka-Mwarangu-Matunda | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4652 | Komu-Kanyotu -Makara Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 8000 |  | C.G.N | [5 empty] | 8000 |  |  | COMPLETE | 100%
ROADS | 4653 | Kabazi Rd Ramana | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1399800 |  | C.G.N | [5 empty] | 1399800 |  |  | COMPLETE | 100%
ROADS | 4654 | Polytechnic-Gachifara Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4655 | Kibendera Rd Completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4656 | Gathiriga-Matunda Pry Sch Rd Completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4657 | Muua Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4658 | Gwakiongo Town Gravel Patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | COMPLETE | 100%
ROADS | 4659 | Kwajessi Village | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 4660 | Gwakiongo Bus Park | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2400000 | 2399144 |  | C.G.N | [5 empty] | 2399144 |  |  | COMPLETE | 100%
ROADS | 4661 | Reoutine Maintaince And Drainage Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1700000 | 1700000 |  | C.G.N | [5 empty] | 1700000 |  |  | COMPLETE | 100%
ROADS | 4662 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4663 | Kariamu-Kag Completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4664 | Mumbi-Rahab Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4665 | Thitai-Wa Gideon Comp | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4666 | Kieni-Mathathi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4667 | Kiganjo-Pcea Road Culvert Installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4668 | Muthiga A&B | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4669 | Vuja Kio 2,3,4 Rd Bosskago-Gituga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4670 | Mrs Gathajo-Wutani Cattle Dips | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4671 | Wa Leneta Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4672 | A4 Junction-Kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4673 | Olkolou-Ndemi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 5000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4674 | Teachers Dam Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4675 | Major Njoroge Mutiga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4676 | Gichugo Dispensary-Thitai Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 4677 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4678 | Githunguri Kamanja Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4679 | Wakarenge-Stage 1 Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1700000 | 1204421 |  | C.G.N | [5 empty] | 1204421 |  |  | COMPLETE | 100%
ROADS | 4680 | Mutwa -Benard Rd-Gravelling And Culvert Installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4681 | Ack-Muraya Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 600000 |  | C.G.N | [5 empty] | 600000 |  |  | COMPLETE | 100%
ROADS | 4682 | Maina Wanjeru Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4683 | Thuku Solomon Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4684 | Peter Kihara Mbatia Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1236512 |  | C.G.N | [5 empty] | 1236512 |  |  | COMPLETE | 100%
ROADS | 4685 | Kiduba Kimanga Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4686 | Silanga-Muchwe- Norman | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4687 | Corner Ndinguri Stage 1 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4688 | Muchiri-Gitu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4689 | Manyatta Pri.-Wanjeru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4690 | Rurii-Pasenga Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4691 | Umoja-Junction-Kanyoro-Wachiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1300000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4692 | Mugumo Wabeth Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4693 | Routine Maintenance-Drainage Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 300000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4694 | Roadworks And Drainage In Rurii Town | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4695 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1045000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4696 | Boiman Ngatho Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1845000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4697 | Mungetho Ngatho Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 2652534 |  | C.G.N | [5 empty] | 2652534 |  |  | COMPLETE | 100%
ROADS | 4698 | Laban Idp Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1345000 | 1207950 |  | C.G.N | [5 empty] | 1207950 |  |  | COMPLETE | 100%
ROADS | 4699 | Kwa Mande Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1295000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4700 | Ihigaini Y Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1345000 | 1266748 |  | C.G.N | [5 empty] | 1266748 |  |  | COMPLETE | 100%
ROADS | 4701 | Jeremiah- Mungetho Extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1245000 | 1245000 |  | C.G.N | [5 empty] | 1245000 |  |  | COMPLETE | 100%
ROADS | 4702 | John-Philip-Migaa | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1345000 | 1345000 |  | C.G.N | [5 empty] | 1345000 |  |  | COMPLETE | 100%
ROADS | 4703 | Gathanji-Mutharia-Boiman Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4704 | Ihingaini Bidii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1245000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4705 | Forest Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1405000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4706 | Grading Along Various Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4707 | Ngoberi Jimmy Annan Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4708 | Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 770000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4709 | Boda Boda Sheds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 220000 | 219942 |  | C.G.N | [5 empty] | 219942 |  |  | COMPLETE | 100%
ROADS | 4710 | Opening And Development Of Various New Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 695000 | 695000 |  | C.G.N | [5 empty] | 695000 |  |  | COMPLETE | 100%
ROADS | 4711 | Routine Maintenance-Drainage Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4712 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 495422 |  | C.G.N | [5 empty] | 495422 |  |  | COMPLETE | 100%
ROADS | 4713 | Gikingi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4714 | St.Pauls-Kanguu Dispensary Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4715 | Baraka Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4716 | Riverside Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4717 | Gatimu-Muhindi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4718 | Kibathi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4719 | Equator-Ahiti Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4720 | Kianjata Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4721 | Various Road Works-Gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4722 | Nyakariang'a -Mutitu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4723 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 1198000 |  | C.G.N | [5 empty] | 1198000 |  |  | COMPLETE | 100%
ROADS | 4724 | Inoro-Ngufa Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1491841 |  | C.G.N | [5 empty] | 1491841 |  |  | COMPLETE | 100%
ROADS | 4725 | Culvert Installation Various Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 1971370 |  | C.G.N | [5 empty] | 1971370 |  |  | COMPLETE | 100%
ROADS | 4726 | Emergency Rd Works And Repair In Weru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4727 | Grading In Various Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4728 | Kasuku Kirimangai (Rd Garding And Gravel Patchining) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4729 | Museveni-Wuiguano Pry Sch Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4730 | Kirimangai-49 Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4731 | Kamotho Wagishe Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4732 | Chakareri-Iriani Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1764050 |  | C.G.N | [5 empty] | 1764050 |  |  | COMPLETE | 100%
ROADS | 4733 | Kasuku Town Rd Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4734 | Mugikunjo Inani Extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4735 | Kangui Moshu Hospital Hill | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4736 | Josline Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4737 | Drainage At Kasuku Town | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 4738 | Mwanda Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4739 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 4740 | Waiyobo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4741 | Kagema Kona Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1895310 |  | C.G.N | [5 empty] | 1895310 |  |  | COMPLETE | 100%
ROADS | 4742 | Ngatha -Mithamo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4743 | Mugoiri Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | COMPLETE | 100%
ROADS | 4744 | Gichaka-Kirimangai | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 4745 | Gachuiru-Mukenga Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4746 | Kwa-Writter | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4747 | Flora Kirioundo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 499950 |  | C.G.N | [5 empty] | 499950 |  |  | COMPLETE | 100%
ROADS | 4748 | Adams-Kimathi-Olaimutia Pry Road(Phase 2) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4749 | Gachuiro-Mwisho Wa Rami Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4750 | Gichure Oleimutia | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4751 | Mungetho Olemuitia | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4752 | Kimathi Steven Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4753 | Kangathia-Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4754 | Culvert Installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 853905 |  | C.G.N | [5 empty] | 853905 |  |  | COMPLETE | 100%
ROADS | 4755 | 54 Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4756 | Gichaka Village Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4757 | Kamkunji Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4758 | Emergency Gravel Patching( Long Rains ) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4759 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 231400 |  | C.G.N | [5 empty] | 231400 |  |  | COMPLETE | 100%
ROADS | 4760 | Gikano Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4761 | Mukunya Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4762 | Kanjau Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4763 | Pesi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4764 | Mitambo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4765 | Kilimanjaro-Ndaragwa Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4766 | Muhiriga Rd Completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1297341 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4767 | Mukaru Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4768 | Kihuha Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4769 | Mwihoti Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4770 | Olbolosat Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4771 | Shamata Township Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4772 | Wanjihia Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4773 | Other Rd Works-Culvert Installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4774 | Drainge Kaheho Town -Cabro Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | COMPLETE | 100%
ROADS | 4775 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 4776 | Additional Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 0 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4777 | Anderson -Mt Moriah | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4778 | Wa Dk Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 950000 | 950000 |  | C.G.N | [5 empty] | 950000 |  |  | COMPLETE | 100%
ROADS | 4779 | Kihingo -Kiracheri Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 4780 | Divai- Gawa Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4781 | Muthuma- Kingi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1300000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4782 | Equator-Kamukunji Rd Completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4783 | Pastor Lydiah -Muthenga Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4784 | Ndogino-Mathenji Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4785 | Gwa-Kungo-Slaughter House Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 1200000 |  | C.G.N | [5 empty] | 1200000 |  |  | COMPLETE | 100%
ROADS | 4786 | Kwanjora Aic -Dr.Kungu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4787 | Kanyiriri-Muthee Kibaara Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4788 | Karamton-Gawa Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 750000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4789 | Drainge Works Kwa Kungu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 750000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4790 | Bodaboda Sheds(Kamukuji ) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 358000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4791 | Culverts Installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 555550 | 837200 |  | C.G.N | [5 empty] | 837200 |  |  | COMPLETE | 100%
ROADS | 4792 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4793 | Additional Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4794 | Gakanga-Lodwar Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4795 | Muriichua Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4796 | Routine Maintanice | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4797 | Culvert Installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4798 | Ndururi-Uruku Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4799 | Gravelling Along Various Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4800 | Church Of Elohimu Murichu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4801 | Road In Ndaragwa Town | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | 1298000 |  | C.G.N | [5 empty] | 1298000 |  |  | COMPLETE | 100%
ROADS | 4802 | Roads In Kanyangia Trading Centre | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4803 | Ngamini Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 999565 |  | C.G.N | [5 empty] | 999565 |  |  | COMPLETE | 100%
ROADS | 4804 | Kabunaini Primary School Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4805 | Other Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 4806 | Kabaria-Gitonga Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 4807 | Nyumba Tatu-Kinjio Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4808 | Leget-Kadishiani Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 4809 | Mutnaga-Wamuyui Mienyere Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4810 | Githunguchu-Primary School Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4811 | Wakui-Kahinga Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 4812 | Wakuria -Mwema-Ndarathi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 4813 | Roadworks And Drainage- Mairo Inya Town | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 995700 |  | C.G.N | [5 empty] | 995700 |  |  | COMPLETE | 100%
ROADS | 4814 | Floodlights-Leshau, Ziwani And Kwa Iria | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4815 | Uhuru-Kivuika-Wafula | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 1200000 |  | C.G.N | [5 empty] | 1200000 |  |  | COMPLETE | 100%
ROADS | 4816 | Kimaru Special Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4817 | Karuga-Ruhio Rd,Mugamba -Chiura-Ndungata Rd,Kahembe Dispensary Rd,Mboci-Mahehu Rd,Waka Karagoini Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | COMPLETE | 100%
ROADS | 4818 | Kwa J Mathaia-Mboci Rod | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | COMPLETE | 100%
ROADS | 4819 | Wa-Mbaki-Wangombe | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 1200000 |  | C.G.N | [5 empty] | 1200000 |  |  | COMPLETE | 100%
ROADS | 4820 | Routine Maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4821 | Nominated Kirrita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  |  |  |  | C.G.N
ROADS | 4822 | Kiamuere-Mutitu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4823 | Baboo-Cemetry-Muitha-Kengetho | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4824 | Survey Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4825 | Bara Njeru Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4826 | Gware Kimende | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4827 | Githunguri Mukuri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4828 | Community Culvert Installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4829 | Kareko Gicharu(Rurii) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4830 | Joe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4831 | Gwakori Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4832 | Wamuhoho-Mwalimu Clerk Extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4833 | Captain Chege Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4834 | Mbae Ndirangu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4835 | Road Routine Maintenance Including Hire Of Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 7000000 | 3800000 |  | C.G.N | [5 empty] | 3800000 |  |  | COMPLETE | 100%
ROADS | 4836 | Muchiri-Kwa Chief-Kahiro Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | COMPLETE | 100%
ROADS | 4837 | Thindi- Makutano Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4838 | Ndima Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 800000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | COMPLETE | 100%
ROADS | 4839 | Culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4840 | Kanyugi-Wisdom Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4841 | Kang'utu- Gichigirira Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | COMPLETE | 100%
ROADS | 4842 | engineer bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4843 | Culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 4844 | Kagungo-kagutu rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 4845 | Muriganio Outreach road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4846 | ACK ST.philip-slope rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4847 | MUTIINI-NDARANJA MBILI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3994900 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4848 | kamunyaka-kijiko pry sch road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4849 | Engineer culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4850 | Cheese- Churii Bridge (KDSP) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4851 | Cheese- Churiri Road KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4852 | Weru- Nda ya Njogu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | COMPLETE | 100%
ROADS | 4853 | Neema Children's Home Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4854 | Munyaka Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4855 | Kambi Choka Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4856 | Mugotio Mashua Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 969980 |  | C.G.N | [5 empty] | 969980 |  |  | COMPLETE | 100%
ROADS | 4857 | Man U Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 800000 | 769579 |  | C.G.N | [5 empty] | 769579 |  |  | COMPLETE | 100%
ROADS | 4858 | Bridges Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4859 | mutiini-kagonga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4860 | Sam- tree | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4861 | Toyota Gachema Road- Heavy Grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4862 | Mugo- Kihiko gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4863 | Kwambiruri road - grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | COMPLETE | 100%
ROADS | 4864 | Padre road- Gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4865 | mwinjoyo -Fafu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4866 | c65 Kinja road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | COMPLETE | 100%
ROADS | 4867 | culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 805500 | 805500 |  | C.G.N | [5 empty] | 805500 |  |  | COMPLETE | 100%
ROADS | 4868 | gathara-mwinjoyo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4869 | engineer-mutarakwa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4870 | opening and development of various new roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 250600 | 250600 |  | C.G.N | [5 empty] | 250600 |  |  | COMPLETE | 100%
ROADS | 4871 | Routine maintenance-Drainage works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4872 | boda boda sheds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 358000 | 358000 |  | C.G.N | [5 empty] | 358000 |  |  | COMPLETE | 100%
ROADS | 4873 | sendemoto road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | COMPLETE | 100%
ROADS | 4874 | Magenya Road- Gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4875 | Gachicha Road- Gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 498277 |  | C.G.N | [5 empty] | 498277 |  |  | COMPLETE | 100%
ROADS | 4876 | Kanamba Road- grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4877 | Munyaka - St. Paul road- Grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4878 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4879 | Munyaka Dispensary Road grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4880 | Routine road maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4881 | Kinangop polytechnic road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4882 | Gichuki Gathenge Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999476 |  | C.G.N | [5 empty] | 999476 |  |  | COMPLETE | 100%
ROADS | 4883 | Highland Road- Grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4884 | Karima Road - Grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4885 | Kimbo Road - Grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4886 | North Kinangop- Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1750000 | 1750000 |  | C.G.N | [5 empty] | 1750000 |  |  | COMPLETE | 100%
ROADS | 4887 | routine maintenance using in house | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4888 | ndunyu njeru -muhutii road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4889 | culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 805500 | 478503 |  | C.G.N | [5 empty] | 478503 |  |  | COMPLETE | 100%
ROADS | 4890 | NDUNYU NJERU-NANDARASI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2499300 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4891 | KITIRI RD (PHASE 2) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2490009 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4892 | KITIRI PRY SCH ACCESS ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4893 | N. Kinangop- Completion of Gatimu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 998700 |  | C.G.N | [5 empty] | 998700 |  |  | COMPLETE | 100%
ROADS | 4894 | Muhatiko-Mbekenya rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 875660 | 875660 |  | C.G.N | [5 empty] | 875660 |  |  | COMPLETE | 100%
ROADS | 4895 | Kahuruko centre draining | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 4896 | ndunyu njeru catholic church road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2600000 | 2569030 |  | C.G.N | [5 empty] | 2569030 |  |  | COMPLETE | 100%
ROADS | 4897 | Grading and graveling Kariuki-Maeya-Wajeff road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 690100 | 690100 |  | C.G.N | [5 empty] | 690100 |  |  | COMPLETE | 100%
ROADS | 4898 | Operationalization of in-house plant | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4899 | Kitiri Sub-location assorted roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4900 | Ndunyu Nandarasi Secondary Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 218100 |  | C.G.N | [5 empty] | 218100 |  |  | COMPLETE | 100%
ROADS | 4901 | Kiambariki Sub-location assorted roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4902 | Ndunyu NjeruTown Assorted roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4903 | C69 tarmac-Ndunyu Njeru Catholic | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4904 | Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4905 | Spot patching lower Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2400000 | 509600 |  | C.G.N | [5 empty] | 509600 |  |  | COMPLETE | 100%
ROADS | 4906 | Njiku Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4907 | Gachagi Kanjoro Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1200000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4908 | Routine maintance-drainge works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4909 | Kamirangi rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4910 | kimuri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4911 | D391-kinangop ridge farm road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4912 | MUKOMERI-KAHURIA-MKUNGI RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3751047 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4913 | Murungaru Stadium Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4914 | Murungaru Mwaniki Nguyayi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4915 | Dam-boundary rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4916 | Culvert installations murungaru ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 913500 | 907292 |  | C.G.N | [5 empty] | 907292 |  |  | COMPLETE | 100%
ROADS | 4917 | Memo bodaboda | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 250000 | 250000 |  | C.G.N | [5 empty] | 250000 |  |  | COMPLETE | 100%
ROADS | 4918 | Assorted rds(sport patching) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4919 | Darashaini-makinya rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 4920 | Boundary -Munyugu rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3385900 | 3385551 |  | C.G.N | [5 empty] | 3385551 |  |  | COMPLETE | 100%
ROADS | 4921 | Village Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1200000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4922 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4923 | Spot patching upperer Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2100000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4924 | Road grading - Lower Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4925 | Road grading- Upper Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4926 | Ezekiel-Wangunini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4927 | Kirobi Mikaro Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4928 | Assorted roadworks | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4929 | Baba Muchiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4930 | Completion of Njung'e Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4931 | Completion of Wakahiga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4932 | Kianjata/Line Moja | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4933 | Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 4934 | Kanamba Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4935 | Githutha/Kibara maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4936 | Churiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4937 | Yokosuna-mkurino rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 994053 |  | C.G.N | [5 empty] | 994053 |  |  | COMPLETE | 100%
ROADS | 4938 | Njau-rwigi-Kamuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 4939 | St.stephen Church | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 961000 | 961000 |  | C.G.N | [5 empty] | 961000 |  |  | COMPLETE | 100%
ROADS | 4940 | karuangi-mbuthori road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3200000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4941 | Gatukaini Jabini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2498500 |  | C.G.N | [5 empty] | 2498500 |  |  | COMPLETE | 100%
ROADS | 4942 | kioneki pry sch-kiamweri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4943 | College Road Maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4944 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4945 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1100100 |  | C.G.N | [5 empty] | 1100100 |  |  | COMPLETE | 100%
ROADS | 4946 | Kingethere road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4947 | Gakure/Gitau/Dosa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999740 |  | C.G.N | [5 empty] | 999740 |  |  | COMPLETE | 100%
ROADS | 4948 | Warurungana road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4949 | Gikuyu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4950 | Muchibau sec road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4951 | Kimamira road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4952 | Spot patching Njabini Ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4953 | Coloboise Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4954 | Maritati Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4955 | Kanyumba Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 750000 | 750000 |  | C.G.N | [5 empty] | 750000 |  |  | COMPLETE | 100%
ROADS | 4956 | Assorted road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4957 | Expansion, gravel patching and | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4958 | Upper Gathangari Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | COMPLETE | 100%
ROADS | 4959 | Drainage works ,bush clearing along | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4960 | Mwangi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4961 | Completion of Mutarakwa Ndogo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4962 | John Kirata- Kiragu Manene Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | COMPLETE | 100%
ROADS | 4963 | Completion of upper Shirikisho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 800000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | COMPLETE | 100%
ROADS | 4964 | njoguini-wanjama road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4965 | kihunguru-wamithi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4966 | riverside -kageraini road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4967 | Completion of Bongo-muini rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 801100 | 801100 |  | C.G.N | [5 empty] | 801100 |  |  | COMPLETE | 100%
ROADS | 4968 | Opening of new roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 250000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4969 | Fredha road gravel patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 236182 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4970 | Nyakio Gathangari Cornellius Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4971 | Routine maintance and drainage works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4972 | Boda boda shed | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 350000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4973 | Nyakio-Karati-Gatitu- Sulmac Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 4974 | Kandutura-Canaan Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 4975 | Thiga road Nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4976 | KABUE NYAMU-CHEESE BRIDGE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2497900 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4977 | KAGERAINI-BAKO-FOREST RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4978 | KAHUHO-FRETHA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1993400 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4979 | Lower Yaanga Primary Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1450000 | 1450000 |  | C.G.N | [5 empty] | 1450000 |  |  | COMPLETE | 100%
ROADS | 4980 | Bara-Inya - Muniu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4981 | Landmark Shirikisho Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | COMPLETE | 100%
ROADS | 4982 | Completion of Kangano Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | COMPLETE | 100%
ROADS | 4983 | Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 805000 | 805000 |  | C.G.N | [5 empty] | 805000 |  |  | COMPLETE | 100%
ROADS | 4984 | Upper Kahuho Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 4985 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1600000 |  | C.G.N | [5 empty] | 1600000 |  |  | COMPLETE | 100%
ROADS | 4986 | Upper Bongo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 4987 | Haraka Dispensary Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1200000 | 1200000 |  | C.G.N | [5 empty] | 1200000 |  |  | COMPLETE | 100%
ROADS | 4988 | Haraka Catholic Rurii Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 4989 | Kagongo Komu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 4990 | Assorted routine maintenance works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | Complete | 100%
ROADS | 4991 | Spot patching Weru Ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 4992 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 4993 | Cheese- Bako Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 4994 | Assorted road works in Nyakio ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | Complete | 100%
ROADS | 4995 | wakweli-ngigi-kwa haraka rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 4996 | miti iri-kang'utu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 4997 | heni sec-shadow road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 4998 | kibuika haraha road (phase 2) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 4999 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5000 | Ballast making machine-Koinage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | Complete | 100%
ROADS | 5001 | Culverts making Baloon(600mm)-Koinange | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5002 | Githabai- Mishinda Kiunyu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 968800 |  | C.G.N | [5 empty] | 968800 |  |  | Complete | 100%
ROADS | 5003 | Munanda-ini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5004 | completion of mijikenda-wakweli rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5005 | faith hope-gathuita rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5006 | wangai -kirima rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5007 | kwa joma-tuliban rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5008 | assorted gravel patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5009 | routine maintenance using in house | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5010 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 957000 | 957000 |  | C.G.N | [5 empty] | 957000 |  |  | Complete | 100%
ROADS | 5011 | Operationalization of in-house plant | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5012 | & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  |  |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5013 | mukuru koinange-karati road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 5014 | Supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5015 | Muchorui Pry Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5016 | Extension of Soko-Mjinga- Mukeu- Flyover Extension Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5017 | Extension of Magumu- Kibuyu- Flyover Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5018 | Extension of Flyover- Kenton Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1650000 | 1650000 |  | C.G.N | [5 empty] | 1650000 |  |  | Complete | 100%
ROADS | 5019 | Culverts installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 5020 | Mutonyora B borehole -kazi yao rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1192000 | 1192000 |  | C.G.N | [5 empty] | 1192000 |  |  | Complete | 100%
ROADS | 5021 | Bodaboda shed | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 358000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5022 | Magumu-Kibuyu-Flyover | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2998120 |  | C.G.N | [5 empty] | 2998120 |  |  | Complete | 100%
ROADS | 5023 | wamurenga-brovason high sch road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5024 | GACHURIO-FLY OVER -KENTON RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3998700 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5025 | Muchorui Pry Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5026 | Teachers Corner- Bravason School | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | Complete | 100%
ROADS | 5027 | routine maintenance using in house | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5028 | Operationalization of in-house plant | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5029 | Gichuhi- Muchara/Kamahuru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2100000 | 2100000 |  | C.G.N | [5 empty] | 2100000 |  |  | Complete | 100%
ROADS | 5030 | Junction - Sasini Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 5031 | D.K Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5032 | Culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | Complete | 100%
ROADS | 5033 | Soko Mjinga- gravelling and compacting | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | Complete | 100%
ROADS | 5034 | Sasini- Mwalimu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 800000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | Complete | 100%
ROADS | 5035 | Assorted roadworks - gravel patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 5036 | Routine maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5037 | Gatukaini -Mahiti Road- gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5038 | Culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5039 | muchori road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | Complete | 100%
ROADS | 5040 | Grading and gravelling - Mwinyogondi -Ndemi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | Complete | 100%
ROADS | 5041 | Grading and gravelling -Mubau- Mbiriri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5042 | Gatukaini-Mahiti rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1994000 |  | C.G.N | [5 empty] | 1994000 |  |  | Complete | 100%
ROADS | 5043 | DN Kariamu rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1900000 | 1900000 |  | C.G.N | [5 empty] | 1900000 |  |  | Complete | 100%
ROADS | 5044 | Magomano-Nathan | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2400000 | 2399000 |  | C.G.N | [5 empty] | 2399000 |  |  | Complete | 100%
ROADS | 5045 | Various assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 850000 | 850000 |  | C.G.N | [5 empty] | 850000 |  |  | Complete | 100%
ROADS | 5046 | RIRONI-WANJOHI ROAD COMPLETION | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3973450 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5047 | Rironi Bridge Phase 1- Wanjohi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5048 | michore-chebe road(phase 2) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5049 | magomano pry sch road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5050 | MICHORE-CHEBE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2495667 | 2499300 |  | C.G.N | [5 empty] | 2499300 |  |  | Complete | 100%
ROADS | 5051 | Grading and gravelling -Jiret-Kirima - Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5052 | Gathure Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1900000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5053 | Wanjohi Bara-Inya culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 582043 | 582043 |  | C.G.N | [5 empty] | 582043 |  |  | Complete | 100%
ROADS | 5054 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5055 | Road routine maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | Complete | 100%
ROADS | 5056 | Githunguri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5057 | Rayetta -Gatondo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | Complete | 100%
ROADS | 5058 | Glando- Kiburuti Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5059 | Jericho MM Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 5060 | Assorted road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5061 | Gitwe Road Wambui Kagari | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1969020 |  | C.G.N | [5 empty] | 1969020 |  |  | Complete | 100%
ROADS | 5062 | Ha Wamwiko - Kiama road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5063 | Lereshwa polytechnic road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5064 | Mbogo Martini Njiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1469800 |  | C.G.N | [5 empty] | 1469800 |  |  | Complete | 100%
ROADS | 5065 | Cereal - Murera Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5066 | Kabati Wang'ondu- Harun Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5067 | Nduru Road- Culvert and grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5068 | Knyua –m baki | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1600000 | 1600000 |  | C.G.N | [5 empty] | 1600000 |  |  | Complete | 100%
ROADS | 5069 | Assorted Culvert and Drainage work | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5070 | society-manunga-kirima road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5071 | KAHIGA-CHIEF MATHENGE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3997324 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5072 | Forest J Wang'oe | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1900000 | 1900000 |  | C.G.N | [5 empty] | 1900000 |  |  | Complete | 100%
ROADS | 5073 | Rona - John Mbuka | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1700000 | 1700000 |  | C.G.N | [5 empty] | 1700000 |  |  | Complete | 100%
ROADS | 5074 | Munyu-ini - Magutu -JJ Davis culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 782042 | 781550 |  | C.G.N | [5 empty] | 781550 |  |  | Complete | 100%
ROADS | 5075 | Kanyua Githogoge Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5076 | Githioro ward- Forest Muriuki Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5077 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5078 | Grading and opening of new roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5079 | Golden Wendani Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5080 | Manunga Kabingu Road- Grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | Complete | 100%
ROADS | 5081 | Chege Kamau- Chege Mbuthia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5082 | Kona Mbaya Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5083 | Wa Joshua Road (Mumui) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | Complete | 100%
ROADS | 5084 | Gakoroba - Kigotho Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5085 | Kibuya Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5086 | Mbui Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5087 | Gitweku Road (Gathiriga) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5088 | Ibrahim road turasha | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 5089 | Konoike road turasha | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 5090 | Tulasha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5091 | Gakoroba ngekenya Road mawingu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 5092 | Itangi kamuyu Road (Gathiriga) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 5093 | Assorted Culvert and Drainage work(Mawingu) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5094 | Mbogoro Dam Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5095 | mumui-kariara road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5096 | matopeni-gathiriga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5097 | KIHUMBU-MALEWA RIVER RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3746100 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5098 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5099 | Gachuha Bridge-KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10093520 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5100 | Road routine maintenance -gravel patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 5101 | Mwangaza area- Dam Rd Grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5102 | Muthaiga Road-Grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5103 | Kwa Nuthu Road -Grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 600000 | 600000 |  | C.G.N | [5 empty] | 600000 |  |  | Complete | 100%
ROADS | 5104 | Kinyua - Gatumbi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5105 | Tigoni- Migaa- Wa Njenga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5106 | ward road works(Njenga cocacola- | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 6000000 | 5999999 |  | C.G.N | [5 empty] | 5999999 |  |  | Complete | 100%
ROADS | 5107 | No. 30 Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5108 | Ngatho- Kanini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5109 | Gathima- Karia-ini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5110 | Benendeto-wandaka karuiru rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 950000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5111 | Number 29 rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5112 | Kariua rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 950000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5113 | Culvert installation Works. | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 499952 | 499952 |  | C.G.N | [5 empty] | 499952 |  |  | Complete | 100%
ROADS | 5114 | number 3 bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 7412272 | 7412272 |  | C.G.N | [5 empty] | 7412272 |  |  | Complete | 100%
ROADS | 5115 | WABOCHO-RUMWE RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3995800 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5116 | ng'atho-beam road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5117 | Geta-Ithagu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5118 | Bethwel Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5119 | Ndimi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | Complete | 100%
ROADS | 5120 | Mountain Academy Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 950000 | 950000 |  | C.G.N | [5 empty] | 950000 |  |  | Complete | 100%
ROADS | 5121 | Muthama kungu-wahadi rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 950000 | 950000 |  | C.G.N | [5 empty] | 950000 |  |  | Complete | 100%
ROADS | 5122 | Operationalization of in-house plant | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5123 | Njarumi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5124 | Kianjogu Corner | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5125 | Completion of Wamahugu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5126 | Sos-Peter Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5127 | Musa Councillor Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5128 | Roda road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5129 | Muroki road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5130 | No. 22 Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5131 | Geta trading Centre | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5132 | Wa Mbote Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5133 | Mood Munyeki off road culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 400000 | 400000 |  | C.G.N | [5 empty] | 400000 |  |  | Complete | 100%
ROADS | 5134 | Nyairoko Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5135 | Kiweru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5136 | Beatrice Road-Kerusoi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5137 | Maina Kamanda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5138 | Geoffrey Site Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5139 | Baba Mukunya Road- Kirimaini | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5140 | Muri Road- School Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5141 | Mawingu-Pyrethrum-Pastor Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5142 | Karugutu-Nyawakwe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5143 | Nyairoko -Fr. Rufus Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5144 | Thaba- Assistant Chief Kirimaini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 300000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5145 | Bahati Estate | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5146 | Vatican Estate | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5147 | Makenji Estate | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5148 | Kingaa nursery -dispensary sharom | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 300000 | 300000 |  | C.G.N | [5 empty] | 300000 |  |  | Complete | 100%
ROADS | 5149 | gatibaru-njane road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5150 | kianda-kwa emily | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5151 | Munyeki-Catholic-Chiefs rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | Complete | 100%
ROADS | 5152 | Kianda- munyeki rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | Complete | 100%
ROADS | 5153 | gatifaru-gikonyo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5154 | Kagotho -Captain Road (Along railway line -off nairobi nyahururu-mood hotel -Gachwe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5155 | Shemba-ACK-FULL -GOSPEL | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5156 | Munyeki bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5157 | Construction of bridge shoulders vatican | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 100000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5158 | Soko- Moko estate | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5159 | Bankers Estate | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5160 | EMILY-JORAM RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1999950 | 1970000 |  | C.G.N | [5 empty] | 1970000 |  |  | COMPLETE | 100%
ROADS | 5161 | HEADQUARTER-BORA ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5162 | Munyeki Junction-Kianda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5163 | Quarry- Gatifaro Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5164 | Sariga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5165 | Grading gravelling works along Mood road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2390389 | 2390389 |  | C.G.N | [5 empty] | 2390389 |  |  | COMPLETE | 100%
ROADS | 5166 | Road routine maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5167 | Nyairoko- Kagaa Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 400000 | 400000 |  | C.G.N | [5 empty] | 400000 |  |  | COMPLETE | 100%
ROADS | 5168 | Chief Mwiga -Kago Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 350000 | 350000 |  | C.G.N | [5 empty] | 350000 |  |  | COMPLETE | 100%
ROADS | 5169 | Kandeto-Chief Kiruga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5170 | Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 300000 | 300000 |  | C.G.N | [5 empty] | 300000 |  |  | COMPLETE | 100%
ROADS | 5171 | Grading of various roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 350000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5172 | Willis Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 400000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5173 | Deliverance church road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5174 | Nderi- Marugu-Kinyi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5175 | Mwiri-nguku-borehole road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5176 | Vatican estate - Drainage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 200000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5177 | Dairy - Mahihu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5178 | Kanjuiri Bata Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5179 | Nguva Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1700000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5180 | Kirathimo- Murindati Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5181 | Shakora - Githere | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5182 | Culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5183 | Hon. Cecily- Kwa Njoroge Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5184 | Supply of murram | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 200000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5185 | PCEA Gathundia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5186 | nyaituga-kanjuiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5187 | chamuka-kasambara road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5188 | Vi-rutara road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5189 | Ngorika Township including Ngorika secondary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5190 | Joe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5191 | NJIGAGA-KANGATHIA ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3499955 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5192 | Sairinga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | 1200000 |  | C.G.N | [5 empty] | 1200000 |  |  | COMPLETE | 100%
ROADS | 5193 | Kamau-Shillingi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5194 | Kagunda base | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 5195 | Githabina | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 600000 | 600000 |  | C.G.N | [5 empty] | 600000 |  |  | COMPLETE | 100%
ROADS | 5196 | Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5197 | Wiyumiririe -Githioro Rutara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2200000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5198 | Nyaituga Kirathimo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5199 | 1No. Floodlight | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1350000 | 798070 |  | C.G.N | [5 empty] | 798070 |  |  | COMPLETE | 100%
ROADS | 5200 | Mahihu St. Monicah Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5201 | Mahuthu Kanjuiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 998800 |  | C.G.N | [5 empty] | 998800 |  |  | COMPLETE | 100%
ROADS | 5202 | Grading and gravelling Plot 11 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5203 | Gwa Kiongo Town - Cabro works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5204 | Makutano- Murindati Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5205 | Mwangi- Mjeshi- Karugo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5206 | Nyandondo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5207 | Bahati Forest Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5208 | Kamuyu- Forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5209 | Kwa Njaaga- Father Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5210 | Miiri Kamunge road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5211 | Assorted Drainage Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5212 | nyandundo-kanyotu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5213 | gituamba-makara road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5214 | kirima-forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5215 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5216 | MUUA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3950670 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5217 | Mirangine-Kwa Jesse Village Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5218 | Kware road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5219 | Various Culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2259700 | 2259700 |  | C.G.N | [5 empty] | 2259700 |  |  | COMPLETE | 100%
ROADS | 5220 | gwakiongo Town gravel patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5221 | polytechnic-Gachifara RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1753909 |  | C.G.N | [5 empty] | 1753909 |  |  | COMPLETE | 100%
ROADS | 5222 | Gathiriga A Matunda | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2496200 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5223 | Routine Maintaince and drainage works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1700000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5224 | Bora dam-njaga-makurata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3616780 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5225 | kwajessi village | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5226 | kabazi rd ramana | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5227 | Tumaini Githure rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 3615620 |  | C.G.N | [5 empty] | 3615620 |  |  | COMPLETE | 100%
ROADS | 5228 | Bora Hills - Mutitu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | COMPLETE | 100%
ROADS | 5229 | Boda boda sheds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5230 | Mathakwa kwa Haraka Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5231 | Kihuho kwa MOA bridge- KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4578543 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5232 | Wambao Gwa Kago Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 1406730 |  | C.G.N | [5 empty] | 1406730 |  |  | COMPLETE | 100%
ROADS | 5233 | Kwa Njaaga/Forest Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5234 | Githima Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1700000 | 1700000 |  | C.G.N | [5 empty] | 1700000 |  |  | COMPLETE | 100%
ROADS | 5235 | Assorted gravel works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2300000 | 2300000 |  | C.G.N | [5 empty] | 2300000 |  |  | COMPLETE | 100%
ROADS | 5236 | Assorted grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5237 | Routine maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5238 | Kiganjo A: 1,2,3,4 roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | COMPLETE | 100%
ROADS | 5239 | Kuria (CK)- Huruma road, Muriu- Kanyi-Kware road completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | COMPLETE | 100%
ROADS | 5240 | A4 junction-kaimbaga dispensary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5241 | captain town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5242 | kanjo-kwa mumbi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5243 | Kariamu Town Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 2969920 |  | C.G.N | [5 empty] | 2969920 |  |  | COMPLETE | 100%
ROADS | 5244 | Kinja Secondary Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5245 | mama gichohi-mp road, gichungo dispensary-thitai road, waleneta culverts, teacher dam culverts, kiganjo-PCEA culverts, kariamu-KAG completion, thitai wa gideon completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2958040 | 597950 |  | C.G.N | [5 empty] | 597950 |  |  | COMPLETE | 100%
ROADS | 5246 | Survey Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5247 | Gwakori rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5248 | kieni mathathi road & muthaiga A&B | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | COMPLETE | 100%
ROADS | 5249 | meja njoroge-mutuga road& mumbi rahab road and mrs gathogo- watoni road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 3998800 |  | C.G.N | [5 empty] | 3998800 |  |  | COMPLETE | 100%
ROADS | 5250 | Vuja Kio 2,3,4 Rd Bosskago-Gituga & mwireri roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 3969999 |  | C.G.N | [5 empty] | 3969999 |  |  | COMPLETE | 100%
ROADS | 5251 | Gravelling of roads in Kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5252 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5253 | JM Riverside Road and Canaan Completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 1105000 |  | C.G.N | [5 empty] | 1105000 |  |  | COMPLETE | 100%
ROADS | 5254 | Huruma Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5255 | Nyakinyua Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5256 | Riverside Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5257 | Mwireri Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5258 | Gichungo Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5259 | Kamau- Kiriga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5260 | Kinyumba-Mbichu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5261 | Nguba-Kamindu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5262 | Kiyuu-Githunguri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | COMPLETE | 100%
ROADS | 5263 | Wakarenge- Ng'ang'a Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5264 | Grading and gravelling - Mbugua- | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5265 | Mukugi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  |  |  |  | C.G.N | [8 empty] | COMPLETE | 100%
ROADS | 5266 | Mugumo- Tank Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5267 | Maran Mwisho Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5268 | KaMwega- Dam Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 800000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | COMPLETE | 100%
ROADS | 5269 | Shem - Njuru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5270 | Thuku Solomon Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 5271 | Githioro- Rurii kwa Mimi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5272 | Completion of Karuri Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1249325 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5273 | umoja pry road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5274 | mutwa -Benard rd-Gravelling and Culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5275 | Githunguri Kamanja RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5276 | manyatta pri.-wanjeru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 5277 | RURII-PASENGA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3996841 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5278 | MUKINDU PRY-DISPENSARY ROAD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1522607 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5279 | Kareko Gicharu(Rurii) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5280 | TOTAL | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 8212820 | 4019645 |  | C.G.N | [5 empty] | 4019645 |  |  | COMPLETE | 100%
ROADS | 5281 | Routine maintenance works -Drainage works, Wakarenge-Stage 1 culverts, Peter Kihara Mbatia Rd, | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2438040 | 2438040 |  | C.G.N | [5 empty] | 2438040 |  |  | COMPLETE | 100%
ROADS | 5282 | Plot 10 -St Thomas Road Junction- Culvert Installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5283 | ACK Muraya Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 5284 | Maina Wa Njeru Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 5285 | Kiduba Kimanga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5286 | Githunguri Mukurino | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5287 | Gware Kimende | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5288 | Gatitu Wairagu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5289 | Kimani Kabora Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5290 | James Mbatia Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1200000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5291 | Rurii Town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5292 | Passenga Town Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5293 | Matura Shopping Centre | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5294 | Githunguri Kwa Mondo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5295 | Wanjohi Nduhiu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5296 | Grading and gravelling various roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 850000 | 850000 |  | C.G.N | [5 empty] | 850000 |  |  | COMPLETE | 100%
ROADS | 5297 | Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1150000 | 1150000 |  | C.G.N | [5 empty] | 1150000 |  |  | COMPLETE | 100%
ROADS | 5298 | Mung'etho Township- Grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5299 | Kwa Ngara Township- Grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5300 | Grading various roads- Kwa Ngara Dam- Kiruthu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5301 | ihingaini bidii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1245000 | 1245000 |  | C.G.N | [5 empty] | 1245000 |  |  | COMPLETE | 100%
ROADS | 5302 | forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1405000 | 1405000 |  | C.G.N | [5 empty] | 1405000 |  |  | COMPLETE | 100%
ROADS | 5303 | Ihigaini Y Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1345000 | 1345000 |  | C.G.N | [5 empty] | 1345000 |  |  | COMPLETE | 100%
ROADS | 5304 | Grading along various roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | COMPLETE | 100%
ROADS | 5305 | Ngoberi Jimmy Annan Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5306 | culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 770000 | 770000 |  | C.G.N | [5 empty] | 770000 |  |  | COMPLETE | 100%
ROADS | 5307 | Gravelling Various Roads- Gituamba | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5308 | Gravelling Various Roads- Kwa | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5309 | mung'etho-jeremia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5310 | Gravelling Various Roads- Bara-Inya - | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5311 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5312 | Boiman- Ngatho Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1845000 | 1845000 |  | C.G.N | [5 empty] | 1845000 |  |  | COMPLETE | 100%
ROADS | 5313 | Karai Ithatu grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5314 | Kwa Meja grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5315 | Boiman Town grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1640000 | 1640000 |  | C.G.N | [5 empty] | 1640000 |  |  | COMPLETE | 100%
ROADS | 5316 | Chameleon Road grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1200000 |  | C.G.N | [5 empty] | 1200000 |  |  | COMPLETE | 100%
ROADS | 5317 | Extension Migaa Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | COMPLETE | 100%
ROADS | 5318 | Kiheo-Ihigaini Rd gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5319 | Chamuka IDP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5320 | Gikingi Location Roads maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5321 | Gatimu location Roads maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | COMPLETE | 100%
ROADS | 5322 | Kanguu/Kiwanja locations roads maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5323 | Equator-Ahiti Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1900000 |  | C.G.N | [5 empty] | 1900000 |  |  | COMPLETE | 100%
ROADS | 5324 | Kianjata Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5325 | Gikingi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1900000 |  | C.G.N | [5 empty] | 1900000 |  |  | COMPLETE | 100%
ROADS | 5326 | A4 junction-tabor hill road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5327 | Riverside Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5328 | Wamaina Bridge- Kanguu Gatimu (1200mm) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5329 | Various Road works-Gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5330 | Nyakariang'a -Mutitu rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5331 | Mugikunjo inani extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5332 | oljororok-primarosa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5333 | westgate-riverside estate roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5334 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5335 | Ngomongo (Ha Water) Double layer culvert bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2900000 | 2900000 |  | C.G.N | [5 empty] | 2900000 |  |  | COMPLETE | 100%
ROADS | 5336 | Upper Hill Jericho Rurii Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5337 | Njunu-Kanguu-Mabatini Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5338 | Assorted grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5339 | Gicheha Mukurino culvdert backfilling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5340 | Bani Bridge backfilling/ Approach culverts-Kabunda Tabor Hill Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1900000 | 1897620 |  | C.G.N | [5 empty] | 1897620 |  |  | COMPLETE | 100%
ROADS | 5341 | Mugikunjo Kwa Bison | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5342 | Wagioche - Iriani Extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5343 | Police Line Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5344 | Assorted Road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5345 | Kasuku Kirimangai (rd garding and gravel patchining) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5346 | kasuku-kichakani road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5347 | Muhindi Kenji Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 998159 |  | C.G.N | [5 empty] | 998159 |  |  | COMPLETE | 100%
ROADS | 5348 | museveni-wuiguano pry road (phase 2) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5349 | Assorted grading-Weru ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 2970000 |  | C.G.N | [5 empty] | 2970000 |  |  | COMPLETE | 100%
ROADS | 5350 | Kasuku town rd works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3100000 | 3086010 |  | C.G.N | [5 empty] | 3086010 |  |  | COMPLETE | 100%
ROADS | 5351 | Drainage at Kasuku Town | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 983000 |  | C.G.N | [5 empty] | 983000 |  |  | COMPLETE | 100%
ROADS | 5352 | gitura-olbolosat road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5353 | Gatitu Road drainage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5354 | Mwihoti Gathundia | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5355 | Weru -Kangui Town Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5356 | Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5357 | Kangui Moshu Hospital Hill | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1100000 | 1100000 |  | C.G.N | [5 empty] | 1100000 |  |  | COMPLETE | 100%
ROADS | 5358 | Assorted road grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5359 | Dream Hotel Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5360 | Dream Hotel Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | COMPLETE | 100%
ROADS | 5361 | Karandi Primary Road and drainage works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | COMPLETE | 100%
ROADS | 5362 | Kasuku Inooro Primary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5363 | Emergency road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5364 | Culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2018-07-01 | 2019-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5365 | Kamama Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5366 | Mbuthia Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5367 | Nyairoko Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 5368 | Gichure oleimutia | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5369 | Mungetho olemuitia | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5370 | 54 rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5371 | kamkunji rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5372 | Kangathia-rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 750000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5373 | Kenda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5374 | Thayu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999975 |  | C.G.N | [5 empty] | 999975 |  |  | COMPLETE | 100%
ROADS | 5375 | Gladwell Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3980050 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5376 | ADAMS-KIMATHI-OLAIMUTIA PRY ROAD(PHASE 2) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5377 | Charagita shopping Centre upgrade | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5378 | kangui-olaimutia pry school road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2354563 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5379 | kiriundu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5380 | Kwa Writter rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5381 | Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5382 | Gichaka Village Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5383 | Emergency gravel patching (Long | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5384 | Sabugo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5385 | Reuben Kiriundu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5386 | Gibson Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5387 | Runda Rd- Charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5388 | Sira road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5389 | Munga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5390 | Ngano Centre Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5391 | Mugoiri -Wamurugi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5392 | Mwisho wa Rami-Chief Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5393 | T-Rose Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5394 | Wa Mutungi- Victorio Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 438640 |  | C.G.N | [5 empty] | 438640 |  |  | COMPLETE | 100%
ROADS | 5395 | Mithami Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5396 | AIC Nyairoko Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5397 | Thayu Kimani Ngorongo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5398 | Ngomongo- Ngatho Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5399 | Captain Chege Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5400 | Grading and gravelling Karai road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5401 | Koro Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5402 | Kiambogo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5403 | Wa Gitahi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3967259 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5404 | KILIMANJARO-NDARAGWA RD | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5405 | kinuthia-mwihang'ia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | COMPLETE | 100%
ROADS | 5406 | Mukunya rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 800000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | COMPLETE | 100%
ROADS | 5407 | Kihuha rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | COMPLETE | 100%
ROADS | 5408 | Mwihoti rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2400000 | 2340000 |  | C.G.N | [5 empty] | 2340000 |  |  | COMPLETE | 100%
ROADS | 5409 | Shamata township rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | COMPLETE | 100%
ROADS | 5410 | Wanjihia Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5411 | Other rd works-Culvert Installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5412 | Drainge Kaheho town -Cabro works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 900000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5413 | Mitambo rd, | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5414 | Mukaru rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5415 | Olbolosat rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5416 | Gichuki road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5417 | Gichagi Pesi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5418 | Mastoo Magutu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5419 | Catholic Simbara Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5420 | Dam Gitare Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5421 | Gathurima Olbolosat road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5422 | Gakoe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5423 | Gachii Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5424 | Canary-Kabui Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5425 | Gitofu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5426 | Gikano road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5427 | Nazareth rooad | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | COMPLETE | 100%
ROADS | 5428 | Kimaru- Kiganda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 900000 | 900000 |  | C.G.N | [5 empty] | 900000 |  |  | COMPLETE | 100%
ROADS | 5429 | Mitambo rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5430 | Mukaru rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5431 | Olbolosat rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1040000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5432 | Grading upper Shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5433 | Pastor King'ara - Nyakinyua Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5434 | KAG - Mithuri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5435 | Aberdare Mahianyu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5436 | Wakaboat- Kieni Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5437 | Kwa Reuben - Kwa Njora Road Maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5438 | Kiandege - Shauri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | - | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5439 | Mbuyu Ndururi murraming-central | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5440 | kamukunji-kalamton road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5441 | Leshau Pondo- Mt. Moriah Kanyagia Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 555500 | 555500 |  | C.G.N | [5 empty] | 555500 |  |  | COMPLETE | 100%
ROADS | 5442 | Culverts installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 750000 | 750000 |  | C.G.N | [5 empty] | 750000 |  |  | COMPLETE | 100%
ROADS | 5443 | Karamton-gawa rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | COMPLETE | 100%
ROADS | 5444 | Muthama Kingi Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1200000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5445 | Kwa Njora AIC-Dr. Kung'u Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 300000 | 300000 |  | C.G.N | [5 empty] | 300000 |  |  | COMPLETE | 100%
ROADS | 5446 | Boda boda shed (Kamukunji) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2800000 | 2098892 |  | C.G.N | [5 empty] | 2098892 |  |  | COMPLETE | 100%
ROADS | 5447 | 8No. Floodlights (Kinadege, Shauri, Raicheri, Karamton, Kamukunji, Muthiga, Nyakinywa, Mithuuri) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5448 | Mama Kanyiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5449 | Mayu Primary Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5450 | Mtukufu Kahuho Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5451 | Nyakinyua- Gichinga Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5452 | Kihingo Raicheri Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5453 | Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5454 | Ngawa Divai Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5455 | Muthiga Nanyuki Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5456 | Assorted grading and gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | COMPLETE | 100%
ROADS | 5457 | Bush Clearing & grading Ndogino Mahianyu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3997224 |  | C.G.N | [5 empty] | 3997224 |  |  | COMPLETE | 100%
ROADS | 5458 | Grading and gravelling -Subuku- Chuma Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5459 | Grading and gravelling- Kanyagia | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5460 | Grading and gravelling- Ngamini | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5461 | Central Ward- Kahuho Secondary | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5462 | B21 junction-91 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | COMPLETE | 100%
ROADS | 5463 | Road in Ndaragwa town | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5464 | Muriichua rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 600000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5465 | Roads in Kanyangia trading centre | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5466 | Ngamini rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5467 | Kamburaini primary school rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 469986 | 469986 |  | C.G.N | [5 empty] | 469986 |  |  | COMPLETE | 100%
ROADS | 5468 | routine maintenance-gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 870000 | 870000 |  | C.G.N | [5 empty] | 870000 |  |  | COMPLETE | 100%
ROADS | 5469 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1869839 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5470 | ngurumo-makereka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5471 | Operationalization of in-house plant & machinery -KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 459184 | 459184 |  | C.G.N | [5 empty] | 459184 |  |  | COMPLETE | 100%
ROADS | 5472 | Church of Elohim culverts-Ndaragwa Ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1900000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5473 | Grading along various roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5474 | Wangui Bridge- KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5475 | Subego Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5476 | Gerald Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5477 | Subuku dispensary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5478 | Uruku-Wamung'ere | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5479 | Gakai Rural Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 670000 | 670000 |  | C.G.N | [5 empty] | 670000 |  |  | COMPLETE | 100%
ROADS | 5480 | Murichu Primary school Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5481 | Muti-umwe | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3700000 | 3700000 |  | C.G.N | [5 empty] | 3700000 |  |  | COMPLETE | 100%
ROADS | 5482 | Wama-ii- Wa-boat- Wakaba Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | COMPLETE | 100%
ROADS | 5483 | Fuel & Save Wakui Ziwani Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999591 |  | C.G.N | [5 empty] | 1999591 |  |  | COMPLETE | 100%
ROADS | 5484 | Mutanga- Kahembe PCEA | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | COMPLETE | 100%
ROADS | 5485 | MaryLand- Ndemi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 800000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | COMPLETE | 100%
ROADS | 5486 | Mung'etho Primary and Secondary School Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000225 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5487 | mbae-ndirangu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999800 |  | C.G.N | [5 empty] | 999800 |  |  | COMPLETE | 100%
ROADS | 5488 | Kiamuere-mutitu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5489 | wamuhoho-mwalimu clerk extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5490 | Leshau Ziwani Kwa-iria Floodlights | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3900000 | 3900000 |  | C.G.N | [5 empty] | 3900000 |  |  | COMPLETE | 100%
ROADS | 5491 | Kihembe dispensary road, Kionero Road, Chief Karago-ini Road, Full Gospel Mahihu Road & Starehe Bamboo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5492 | Living Love Children's Home Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5493 | mununga-njau road & karagoini water project access road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5494 | Matundura-Kahugu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 998100 |  | C.G.N | [5 empty] | 998100 |  |  | COMPLETE | 100%
ROADS | 5495 | Baringo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 998400 |  | C.G.N | [5 empty] | 998400 |  |  | COMPLETE | 100%
ROADS | 5496 | Brother M road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 999980 | 999980 |  | C.G.N | [5 empty] | 999980 |  |  | COMPLETE | 100%
ROADS | 5497 | Engineer Mugotio Mashua Rd- Engineer | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1799000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5498 | Engineer Munyaka Road and Man U | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5499 | Transformers- Engineer ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999935 |  | C.G.N | [5 empty] | 999935 |  |  | COMPLETE | 100%
ROADS | 5500 | Kingi Meri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499400 |  | C.G.N | [5 empty] | 1499400 |  |  | COMPLETE | 100%
ROADS | 5501 | Wakarega road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5502 | Itomboya Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 6000000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | COMPLETE | 100%
ROADS | 5503 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5504 | Gachicha Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5505 | Kanamba Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1498100 |  | C.G.N | [5 empty] | 1498100 |  |  | COMPLETE | 100%
ROADS | 5506 | Gathaara- Mung'etho Mutamaiyu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2998006 | 2998006 |  | C.G.N | [5 empty] | 2998006 |  |  | COMPLETE | 100%
ROADS | 5507 | Assorted roads Gathaara- Gravelling in munyaka dispensary,kamrembo shemba roads (Routine road maintenance) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1498287 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5508 | Padre road- Gravelling - Gathaara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2997288 | - |  | C.G.N | [5 empty] | - |  |  | COMPLETE | 100%
ROADS | 5509 | Gathaara- Kinja Secondary Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | COMPLETE | 100%
ROADS | 5510 | Wanjohi- Rironi Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2994890 | 2994890 |  | C.G.N | [5 empty] | 2994890 |  |  | COMPLETE | 100%
ROADS | 5511 | Chobe Floodlight-Engineer, Tigoni Floodlight- Githioro, Gachurio floodlights - Magumu and Kinja- Hospital floodlight Gathaara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2200000 | 2199600 |  | C.G.N | [5 empty] | 2199600 |  |  | COMPLETE | 100%
ROADS | 5512 | Wa Mihang'o Road- Gravelling and culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2496300 |  | C.G.N | [5 empty] | 2496300 |  |  | COMPLETE | 100%
ROADS | 5513 | Jesse- Mugo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999560 |  | C.G.N | [5 empty] | 999560 |  |  | COMPLETE | 100%
ROADS | 5514 | Munyaka- Hospital Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1700000 | 1699300 |  | C.G.N | [5 empty] | 1699300 |  |  | COMPLETE | 100%
ROADS | 5515 | Mutamaiyo Sec Road-Gravelling and Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | COMPLETE | 100%
ROADS | 5516 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | COMPLETE | 100%
ROADS | 5517 | Wa Paul Road- Gravelling and culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 876250 | 876250 |  | C.G.N | [5 empty] | 876250 |  |  | Complete | 100%
ROADS | 5518 | Kirima Massive Technologies (Road Improvement Works Along Ezekiel Kitogo Kwa Moses Road and Muiruri Gatimu Road In North Kinangop Ward)2017/18 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4800000 | 4799070 |  | C.G.N | [5 empty] | 4799070 |  |  | Complete | 100%
ROADS | 5519 | upgrade of ndunyu njeru stage-north kinangop ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3300000 | 3278733 |  | C.G.N | [5 empty] | 3278733 |  |  | Complete | 100%
ROADS | 5520 | North Kinangop assorted roadworks | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5521 | Road maintenance using County Road Machinery & Equipment (At least 35KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5522 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5523 | Kamirangi Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2791017 | 2760000 |  | C.G.N | [5 empty] | 2760000 |  |  | Complete | 100%
ROADS | 5524 | Njiku Road -Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2529300 |  | C.G.N | [5 empty] | 2529300 |  |  | Complete | 100%
ROADS | 5525 | Murungaru Ward - Murungaru Stadium Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 662400 | 276104 |  | C.G.N | [5 empty] | 276104 |  |  | Complete | 100%
ROADS | 5526 | Dam Boundary - Kamirangi Culvert Installation & Routine Maintenance Drainage - Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2321600 | 2321600 |  | C.G.N | [5 empty] | 2321600 |  |  | Complete | 100%
ROADS | 5527 | Kamirangi- Dam Boundary | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1997739 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5528 | Murungaru Ward- Ezekiel Wangunini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1968202 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5529 | Spot patching- Upper Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3997106 | 3997106 |  | C.G.N | [5 empty] | 3997106 |  |  | Complete | 100%
ROADS | 5530 | Assorted roadworks-Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1199000 | 327065 |  | C.G.N | [5 empty] | 327065 |  |  | Complete | 100%
ROADS | 5531 | Gachagi Kanjoro Road - Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1193300 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5532 | Village Road - Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1799155 | 1799154 |  | C.G.N | [5 empty] | 1799154 |  |  | Complete | 100%
ROADS | 5533 | Road grading - Lower Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1489432 | 1489432 |  | C.G.N | [5 empty] | 1489432 |  |  | Complete | 100%
ROADS | 5534 | Road grading- Upper Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 979955 |  | C.G.N | [5 empty] | 979955 |  |  | Complete | 100%
ROADS | 5535 | Karonjo Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2900000 | 2875680 |  | C.G.N | [5 empty] | 2875680 |  |  | Complete | 100%
ROADS | 5536 | Huho- Thira Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2400000 | 2400000 |  | C.G.N | [5 empty] | 2400000 |  |  | Complete | 100%
ROADS | 5537 | Mukomeri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2429510 |  | C.G.N | [5 empty] | 2429510 |  |  | Complete | 100%
ROADS | 5538 | Kiambaa-Nguyo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 7000000 | 7000000 |  | C.G.N | [5 empty] | 7000000 |  |  | Complete | 100%
ROADS | 5539 | Road maintenance using County Road Machinery & Equipment (At least 35KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5540 | Sasumwa Pry Sch Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5541 | Karatasi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5542 | Ngua Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 998000 |  | C.G.N | [5 empty] | 998000 |  |  | Complete | 100%
ROADS | 5543 | Nyaru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999880 |  | C.G.N | [5 empty] | 999880 |  |  | Complete | 100%
ROADS | 5544 | Jeshi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5545 | Kanamba Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 998468 |  | C.G.N | [5 empty] | 998468 |  |  | Complete | 100%
ROADS | 5546 | Kanyumba Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5547 | Mwalimu Mbugua road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999720 |  | C.G.N | [5 empty] | 999720 |  |  | Complete | 100%
ROADS | 5548 | Muthoga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499625 |  | C.G.N | [5 empty] | 1499625 |  |  | Complete | 100%
ROADS | 5549 | Ndabi/Wa Peter Road -Njabini | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5550 | Line Moja road- Njabini | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999475 |  | C.G.N | [5 empty] | 1999475 |  |  | Complete | 100%
ROADS | 5551 | Gravel Patching at Njabini and Nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1750000 | 1750000 |  | C.G.N | [5 empty] | 1750000 |  |  | Complete | 100%
ROADS | 5552 | 5 No. 13m height floodlight-njabini kiburu ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1996950 |  | C.G.N | [5 empty] | 1996950 |  |  | Complete | 100%
ROADS | 5553 | Njabini- Assorted Culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | Complete | 100%
ROADS | 5554 | Njabini- Assorted road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5555 | Njabini- Baba Muhoho Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 350000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5556 | 1 No. boda boda shed Kanyawa- Njabini | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999720 |  | C.G.N | [5 empty] | 999720 |  |  | Complete | 100%
ROADS | 5557 | Kihiu- Keneth Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5558 | Njabini Girls -Chief Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999010 |  | C.G.N | [5 empty] | 999010 |  |  | Complete | 100%
ROADS | 5559 | Gikuyu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1498000 |  | C.G.N | [5 empty] | 1498000 |  |  | Complete | 100%
ROADS | 5560 | Gatina Village road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999899 |  | C.G.N | [5 empty] | 999899 |  |  | Complete | 100%
ROADS | 5561 | Muthui Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5562 | Muraguri-Ibrahim road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999960 |  | C.G.N | [5 empty] | 999960 |  |  | Complete | 100%
ROADS | 5563 | Wakirigu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 997880 |  | C.G.N | [5 empty] | 997880 |  |  | Complete | 100%
ROADS | 5564 | Kanyi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999880 |  | C.G.N | [5 empty] | 999880 |  |  | Complete | 100%
ROADS | 5565 | John Jeshi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 499375 |  | C.G.N | [5 empty] | 499375 |  |  | Complete | 100%
ROADS | 5566 | Jose Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5567 | Kagunyi- Eddie Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 987150 |  | C.G.N | [5 empty] | 987150 |  |  | Complete | 100%
ROADS | 5568 | Kiahiti Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 9000000 | 9000000 |  | C.G.N | [5 empty] | 9000000 |  |  | Complete | 100%
ROADS | 5569 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1483830 |  | C.G.N | [5 empty] | 1483830 |  |  | Complete | 100%
ROADS | 5570 | kabue- Nyamu Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 5571 | Assorted road works-Nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999700 |  | C.G.N | [5 empty] | 999700 |  |  | Complete | 100%
ROADS | 5572 | Assorted Drainage Works and Bush Clearing(Labour Contracting) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5573 | Lower Mbiro road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | Complete | 100%
ROADS | 5574 | Barainya-Gachago rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5575 | Nyakio ward- Fencing of Haraka Ecde Centre | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5576 | Nyakio ward- 2No. Boda boda shed | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1175000 | 930000 |  | C.G.N | [5 empty] | 930000 |  |  | Complete | 100%
ROADS | 5577 | Nyakio ward- Fencing of Wachira Dam | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999680 |  | C.G.N | [5 empty] | 1999680 |  |  | Complete | 100%
ROADS | 5578 | Assorted roadworks-Nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1200000 | 1199880 |  | C.G.N | [5 empty] | 1199880 |  |  | Complete | 100%
ROADS | 5579 | Teacher Kimemia- Njoguini Road- Nyakio Ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2100000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5580 | Nyakio- 6No. Floodlight(Karate,Landmark, Bara-Inya, Haraka Dispensary Entrance, Lower Police Station, Kageraini) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1995987 |  | C.G.N | [5 empty] | 1995987 |  |  | Complete | 100%
ROADS | 5581 | Kangeraini Sec Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 990000 | 975000 |  | C.G.N | [5 empty] | 975000 |  |  | Complete | 100%
ROADS | 5582 | Nyakio ward- Gravelling Bara Inya Muniu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5583 | Fredha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2999970 |  | C.G.N | [5 empty] | 2999970 |  |  | Complete | 100%
ROADS | 5584 | Completion of lower Gathangiri Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5585 | Completion of kirangu Manene rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999740 |  | C.G.N | [5 empty] | 1999740 |  |  | Complete | 100%
ROADS | 5586 | Chief Mugo Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 5587 | Completion of Gatitu-Karate Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999675 |  | C.G.N | [5 empty] | 999675 |  |  | Complete | 100%
ROADS | 5588 | Assorted Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5589 | Muukiri Pry Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5590 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 6900000 | 6896623 |  | C.G.N | [5 empty] | 6896623 |  |  | Complete | 100%
ROADS | 5591 | Box culvert across Karati River along Kwa Senior Phase 2 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5592 | Ngigi-Muchedu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1498400 |  | C.G.N | [5 empty] | 1498400 |  |  | Complete | 100%
ROADS | 5593 | Githabai-Revered Jeremiah Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1298446 | 1298446 |  | C.G.N | [5 empty] | 1298446 |  |  | Complete | 100%
ROADS | 5594 | Ascom Networks Limited- (*Githabai high mast flood lights) FY 2016-17 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5595 | Phase 2 -Kwa Senior road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1469000 |  | C.G.N | [5 empty] | 1469000 |  |  | Complete | 100%
ROADS | 5596 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5597 | Mandiamba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1997360 |  | C.G.N | [5 empty] | 1997360 |  |  | Complete | 100%
ROADS | 5598 | Ngaruiya road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2499820 |  | C.G.N | [5 empty] | 2499820 |  |  | Complete | 100%
ROADS | 5599 | Turiban- Jubilee-Mastore-Kahara link roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5600 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2300000 | 2299994 |  | C.G.N | [5 empty] | 2299994 |  |  | Complete | 100%
ROADS | 5601 | Mutonyora Full Gospel Church road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499650 |  | C.G.N | [5 empty] | 1499650 |  |  | Complete | 100%
ROADS | 5602 | Magumu- Pastor Gideon Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 400000 | 400000 |  | C.G.N | [5 empty] | 400000 |  |  | Complete | 100%
ROADS | 5603 | 1 No. 13m height floodlight-Kenyatta Road-Magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2998000 | 2998000 |  | C.G.N | [5 empty] | 2998000 |  |  | Complete | 100%
ROADS | 5604 | Road routine maintenance -gravel patching- Magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 5605 | 1 No. 20M height Floodlight-Sasini in Magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999998 |  | C.G.N | [5 empty] | 1999998 |  |  | Complete | 100%
ROADS | 5606 | Gwa Turi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2499576 |  | C.G.N | [5 empty] | 2499576 |  |  | Complete | 100%
ROADS | 5607 | Dot Com Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499942 |  | C.G.N | [5 empty] | 1499942 |  |  | Complete | 100%
ROADS | 5608 | Lonana Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2996700 |  | C.G.N | [5 empty] | 2996700 |  |  | Complete | 100%
ROADS | 5609 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5610 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2999232 |  | C.G.N | [5 empty] | 2999232 |  |  | Complete | 100%
ROADS | 5611 | Branda Gatondo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2995467 |  | C.G.N | [5 empty] | 2995467 |  |  | Complete | 100%
ROADS | 5612 | Miti Itano Kirima Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5613 | Rironi Wa Nancy Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499994 |  | C.G.N | [5 empty] | 1499994 |  |  | Complete | 100%
ROADS | 5614 | Wanjohi- Rironi Ranges road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2469801 | 2469801 |  | C.G.N | [5 empty] | 2469801 |  |  | Complete | 100%
ROADS | 5615 | Wanjohi- Mwinyogondi -Ndemi Road improvement works and culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3900000 | 3897999 |  | C.G.N | [5 empty] | 3897999 |  |  | Complete | 100%
ROADS | 5616 | 3 No. 20M height floodlights- wanjohi ward- Gitei, Wanjohi Junction and Jillet | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1900000 | 1899600 |  | C.G.N | [5 empty] | 1899600 |  |  | Complete | 100%
ROADS | 5617 | Gathure Road -Wanjohi ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 400000 | 399278 |  | C.G.N | [5 empty] | 399278 |  |  | Complete | 100%
ROADS | 5618 | Bara-Inya Boda boda shed- Wanjohi ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2476009 | 2476008 |  | C.G.N | [5 empty] | 2476008 |  |  | Complete | 100%
ROADS | 5619 | Githunguri road- Wanjohi Ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2497712 |  | C.G.N | [5 empty] | 2497712 |  |  | Complete | 100%
ROADS | 5620 | Karima Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2498800 |  | C.G.N | [5 empty] | 2498800 |  |  | Complete | 100%
ROADS | 5621 | Kahiga- Koigi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 979800 |  | C.G.N | [5 empty] | 979800 |  |  | Complete | 100%
ROADS | 5622 | Satelight survey road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 925654 |  | C.G.N | [5 empty] | 925654 |  |  | Complete | 100%
ROADS | 5623 | Wenyenyeke WaKweri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 997050 |  | C.G.N | [5 empty] | 997050 |  |  | Complete | 100%
ROADS | 5624 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 11000000 | 11000000 |  | C.G.N | [5 empty] | 11000000 |  |  | Complete | 100%
ROADS | 5625 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499100 |  | C.G.N | [5 empty] | 1499100 |  |  | Complete | 100%
ROADS | 5626 | Gachugia-dadan-karua road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1495000 |  | C.G.N | [5 empty] | 1495000 |  |  | Complete | 100%
ROADS | 5627 | mikiri-kaba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5628 | Wa Boni Right- Ngururi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1994544 |  | C.G.N | [5 empty] | 1994544 |  |  | Complete | 100%
ROADS | 5629 | Father Paul Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1498615 |  | C.G.N | [5 empty] | 1498615 |  |  | Complete | 100%
ROADS | 5630 | warimia-wamartin road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | Complete | 100%
ROADS | 5631 | Ha Wamwiko - Kiama road -Kipipiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5632 | Lereshwa polytechnic road - Kipipiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 300000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5633 | Kipipiri ward- 1No. Boda boda sheds- Miharati | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 490000 |  | C.G.N | [5 empty] | 490000 |  |  | Complete | 100%
ROADS | 5634 | Nduru Road- Culvert and grading - Kipipiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 999120 |  | C.G.N | [5 empty] | 999120 |  |  | Complete | 100%
ROADS | 5635 | Chege Kamau - Chege Mbuthia - Kipipiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2932300 | 2932300 |  | C.G.N | [5 empty] | 2932300 |  |  | Complete | 100%
ROADS | 5636 | Gitweku Road (Gathiriga) and Mbogoro Dam Road Githioro ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1976400 | 1976400 |  | C.G.N | [5 empty] | 1976400 |  |  | Complete | 100%
ROADS | 5637 | Kipipiri- Golden Wendani Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2856886 | 2856886 |  | C.G.N | [5 empty] | 2856886 |  |  | Complete | 100%
ROADS | 5638 | Kipipiri Ward- karandi muthama road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5639 | forest one road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5640 | john mbuka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | 1799678 |  | C.G.N | [5 empty] | 1799678 |  |  | Complete | 100%
ROADS | 5641 | Assorted culverts and routine maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5642 | Kohora Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1418008 |  | C.G.N | [5 empty] | 1418008 |  |  | Complete | 100%
ROADS | 5643 | Wendo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5644 | Kariva Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2400000 | 2400000 |  | C.G.N | [5 empty] | 2400000 |  |  | Complete | 100%
ROADS | 5645 | Nairobi Range Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 5646 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999000 |  | C.G.N | [5 empty] | 1999000 |  |  | Complete | 100%
ROADS | 5647 | Gathiriga Kwa Njonge and Wa Gasheri Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2999300 |  | C.G.N | [5 empty] | 2999300 |  |  | Complete | 100%
ROADS | 5648 | upgrade of mawingu bus park-githioro ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1095000 | 1094745 |  | C.G.N | [5 empty] | 1094745 |  |  | Complete | 100%
ROADS | 5649 | Githioro ward 3 No. 13m height floodlight-Gathiriga, Ririshwa and Tigoni | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 999997 | 999997 |  | C.G.N | [5 empty] | 999997 |  |  | Complete | 100%
ROADS | 5650 | Tigoni- Migaa- Wa Njenga Road- Githioro | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 997650 | 982133 |  | C.G.N | [5 empty] | 982133 |  |  | Complete | 100%
ROADS | 5651 | Kinyua - Gatumbi Road - Githioro | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 967550 |  | C.G.N | [5 empty] | 967550 |  |  | Complete | 100%
ROADS | 5652 | Mumui Muchemi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 355000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5653 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 7500000 | 7500000 |  | C.G.N | [5 empty] | 7500000 |  |  | Complete | 100%
ROADS | 5654 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 979900 |  | C.G.N | [5 empty] | 979900 |  |  | Complete | 100%
ROADS | 5655 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 6136278 | 3888169 |  | C.G.N | [5 empty] | 3888169 |  |  | Complete | 100%
ROADS | 5656 | Geta ward road works(Njenga cocacola-1M) & bridge (mwakama-5M) in the ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3400000 | 3378723 |  | C.G.N | [5 empty] | 3378723 |  |  | Complete | 100%
ROADS | 5657 | Geta Ward- Number 3 Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2808824 | 2808824 |  | C.G.N | [5 empty] | 2808824 |  |  | Complete | 100%
ROADS | 5658 | Geta Ward- Benedeto - Wandaka Karuiru Road, Number 29 Road and - Kariua Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 999300 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5659 | Geta- Bethwel Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2999566 | 2986066 |  | C.G.N | [5 empty] | 2986066 |  |  | Complete | 100%
ROADS | 5660 | Geta- Kianjogu Corner rd, Geta- Completion of Wamahugu Road and No. 22 Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2800000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5661 | Geta- Ndimi Road, Mountain Academy Road and Muthama kungu-wahadi rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2998000 | 2998000 |  | C.G.N | [5 empty] | 2998000 |  |  | Complete | 100%
ROADS | 5662 | Geta- Njarumi Road, Muroki road and Wa Mbote Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1999650 | 1999650 |  | C.G.N | [5 empty] | 1999650 |  |  | Complete | 100%
ROADS | 5663 | Geta Trading Centre | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 997555 | 997555 |  | C.G.N | [5 empty] | 997555 |  |  | Complete | 100%
ROADS | 5664 | Geta Ward- 3No. Floodlights Geta (No.3, Councillor and Canteen) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499220 |  | C.G.N | [5 empty] | 1499220 |  |  | Complete | 100%
ROADS | 5665 | Geta- Baba Cocacola Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1600000 | 1600000 |  | C.G.N | [5 empty] | 1600000 |  |  | Complete | 100%
ROADS | 5666 | Kianjogu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1995248 |  | C.G.N | [5 empty] | 1995248 |  |  | Complete | 100%
ROADS | 5667 | No. 22 Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5668 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5669 | munyeki-chogi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5670 | kahia sec-tarma road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3999999 | 3984999 |  | C.G.N | [5 empty] | 3984999 |  |  | Complete | 100%
ROADS | 5671 | Karau- Munyeki Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1298000 | 1298000 |  | C.G.N | [5 empty] | 1298000 |  |  | Complete | 100%
ROADS | 5672 | Karau - Karugutu-Nyawakwe Road, Nyairoko -Fr. Rufus Road and Thaba- Assistant Chief Kirimaini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2998878 | 2998878 |  | C.G.N | [5 empty] | 2998878 |  |  | Complete | 100%
ROADS | 5673 | Karau- Bahati Estate, Vatican Estate, Makenji Estate, Soko- Moko estate, Bankers Estate and Maina Kamanda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 398400 | 398400 |  | C.G.N | [5 empty] | 398400 |  |  | Complete | 100%
ROADS | 5674 | Karau Ward- Mood Munyeki Off Road Culvert Works- Installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 100000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5675 | Karau- Construction of Shoulders for Vatican Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5676 | Karau Ward- Kagotho -Captain Road (Along railway line -off nairobi nyahururu- mood hotel -Gachwe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 180000 | 180000 |  | C.G.N | [5 empty] | 180000 |  |  | Complete | 100%
ROADS | 5677 | 1No. boda boda shed construction- Karau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1050000 | 1047020 |  | C.G.N | [5 empty] | 1047020 |  |  | Complete | 100%
ROADS | 5678 | 3No. Floodlight-Karau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1397900 |  | C.G.N | [5 empty] | 1397900 |  |  | Complete | 100%
ROADS | 5679 | Karau Ward 1No. Floodlight-Vatican Estate | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2984240 |  | C.G.N | [5 empty] | 2984240 |  |  | Complete | 100%
ROADS | 5680 | Karau- Munyeki Chiefs Office Kanduma- Baba Timo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5681 | Nyairoko Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 5682 | Nderi- Marugu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 496965 |  | C.G.N | [5 empty] | 496965 |  |  | Complete | 100%
ROADS | 5683 | kuresoi-beatrice road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 990461 |  | C.G.N | [5 empty] | 990461 |  |  | Complete | 100%
ROADS | 5684 | Grading various roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5685 | Kianda Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 997301 |  | C.G.N | [5 empty] | 997301 |  |  | Complete | 100%
ROADS | 5686 | Jamaa - St. Joseph- Slaughter House Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 800000 | 785237 |  | C.G.N | [5 empty] | 785237 |  |  | Complete | 100%
ROADS | 5687 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5600000 | 5600000 |  | C.G.N | [5 empty] | 5600000 |  |  | Complete | 100%
ROADS | 5688 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999344 |  | C.G.N | [5 empty] | 1999344 |  |  | Complete | 100%
ROADS | 5689 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499692 |  | C.G.N | [5 empty] | 1499692 |  |  | Complete | 100%
ROADS | 5690 | Kiambururu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3399107 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5691 | Kanjuiri- Wiyumiririe -Githioro Rutara and Nyaituga Kirathimo Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 999940 | 999940 |  | C.G.N | [5 empty] | 999940 |  |  | Complete | 100%
ROADS | 5692 | Joe Road - Kanjuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | Complete | 100%
ROADS | 5693 | Kanjuiri Warari- Wandati- Wakos- AIPCA Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 698534 |  | C.G.N | [5 empty] | 698534 |  |  | Complete | 100%
ROADS | 5694 | Kanjuiri-Completion of Plot 11 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1699260 | 1699260 |  | C.G.N | [5 empty] | 1699260 |  |  | Complete | 100%
ROADS | 5695 | Kanjuiri- Nguva Road Kanjuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 399980 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5696 | Kanjuiri- Ngorika Health Centre | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  |  |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5697 | waiting Bay | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2997858 | 2997858 |  | C.G.N | [5 empty] | 2997858 |  |  | Complete | 100%
ROADS | 5698 | Kanjuiri- St Monicah Kanjuiri & Plot 11 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1799970 | 1799970 |  | C.G.N | [5 empty] | 1799970 |  |  | Complete | 100%
ROADS | 5699 | Kanjuiri Ward- Shakora Githere Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1600000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5700 | Njigaga road gravel patching- Kanjuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 5701 | 4 No. 13m height floodlight(Wiyumiririe, Tumaini(Makuti), Nyaituga and Thaba-kanjuiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1640000 | 1629984 |  | C.G.N | [5 empty] | 1629984 |  |  | Complete | 100%
ROADS | 5702 | Drainage works Ngorika shopping Centre-kanjuiri ridge ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499522 |  | C.G.N | [5 empty] | 1499522 |  |  | Complete | 100%
ROADS | 5703 | Wiyumiririe borehole road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 989201 |  | C.G.N | [5 empty] | 989201 |  |  | Complete | 100%
ROADS | 5704 | Gathimiro-Gathima-Kwa Ngandi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5705 | Rutara Primary Githioro Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 985328 |  | C.G.N | [5 empty] | 985328 |  |  | Complete | 100%
ROADS | 5706 | Kang'athia Sailinga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5707 | PCEA Kung'u Dam Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5708 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | 2982360 |  | C.G.N | [5 empty] | 2982360 |  |  | Complete | 100%
ROADS | 5709 | Assorted ward road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 5710 | Gichungo roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | 2922578 |  | C.G.N | [5 empty] | 2922578 |  |  | Complete | 100%
ROADS | 5711 | Kiganjo Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2990000 | 2990000 |  | C.G.N | [5 empty] | 2990000 |  |  | Complete | 100%
ROADS | 5712 | Kaimbaga- Mwireri roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3999970 | 3057920 |  | C.G.N | [5 empty] | 3057920 |  |  | Complete | 100%
ROADS | 5713 | Kaimbaga - AIC Uhuru Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3999769 | 1945500 |  | C.G.N | [5 empty] | 1945500 |  |  | Complete | 100%
ROADS | 5714 | Kiganjo-Kiama-Charles-Gicheha Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3999793 |  | C.G.N | [5 empty] | 3999793 |  |  | Complete | 100%
ROADS | 5715 | Kaimbaga - Captain Road works - Emergency Fund | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2989000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5716 | Kaimbaga- JM Riverside Road Canaan Completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1460000 | 1460000 |  | C.G.N | [5 empty] | 1460000 |  |  | Complete | 100%
ROADS | 5717 | 4 No. Floodlights Kaimbaga (Site and Huruma) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1499800 | 1499248 |  | C.G.N | [5 empty] | 1499248 |  |  | Complete | 100%
ROADS | 5718 | Kaimbaga- Vunja Kiu road completion | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 998250 | 998250 |  | C.G.N | [5 empty] | 998250 |  |  | Complete | 100%
ROADS | 5719 | Kaimbaga- Wa Marika stage to Mwalimu Mbuthi off Karugutu Road Ruriundo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3280799 | 3280799 |  | C.G.N | [5 empty] | 3280799 |  |  | Complete | 100%
ROADS | 5720 | Kaimbaga- Muthiani Gichungo Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 30000000 | 30000000 |  | C.G.N | [5 empty] | 30000000 |  |  | Complete | 100%
ROADS | 5721 | county headqurters( county contribution) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 50000000 | 50000000 |  | C.G.N | [5 empty] | 50000000 |  |  | Complete | 100%
ROADS | 5722 | county headqurters( national contribution) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5723 | Kamakia Gachau Road- Kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5724 | Kandutura roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | 4999500 |  | C.G.N | [5 empty] | 4999500 |  |  | Complete | 100%
ROADS | 5725 | Rumathi Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5726 | Kieni Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5727 | Bahati roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 5000000 | 4998725 |  | C.G.N | [5 empty] | 4998725 |  |  | Complete | 100%
ROADS | 5728 | Mihute roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5729 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5730 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5731 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5732 | Assorted Drainange Works - Mirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1411633 | 1411633 |  | C.G.N | [5 empty] | 1411633 |  |  | Complete | 100%
ROADS | 5733 | 4 No. 13m height floodlight-mirangine ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 350000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5734 | 1 No. boda boda shed- mirangine ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3799600 | 3799600 |  | C.G.N | [5 empty] | 3799600 |  |  | Complete | 100%
ROADS | 5735 | Mirangine - Makutano- Murindati Road and Wa mbao Gwa kago road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 499751 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5736 | Mirangine Bodaboda sheds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1999919 | 1999919 |  | C.G.N | [5 empty] | 1999919 |  |  | Complete | 100%
ROADS | 5737 | Mirangine ward- Kwa Njaga forest road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5738 | Gwa Kahia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3996116 |  | C.G.N | [5 empty] | 3996116 |  |  | Complete | 100%
ROADS | 5739 | Githima roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3290000 | 3288900 |  | C.G.N | [5 empty] | 3288900 |  |  | Complete | 100%
ROADS | 5740 | Kihuho roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2997620 |  | C.G.N | [5 empty] | 2997620 |  |  | Complete | 100%
ROADS | 5741 | Mutitu Micharage roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5742 | Mirangine Ward- Gwa Kiongo Cabro works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 517500 |  | C.G.N | [5 empty] | 517500 |  |  | Complete | 100%
ROADS | 5743 | Assorted grading-Mirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5744 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5745 | nguva-ndegwa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1478598 |  | C.G.N | [5 empty] | 1478598 |  |  | Complete | 100%
ROADS | 5746 | Stage 1-Nderi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5747 | Mbichu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5748 | Ng'ang'a- Kauru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5749 | Kanduba School Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3994000 | 3994000 |  | C.G.N | [5 empty] | 3994000 |  |  | Complete | 100%
ROADS | 5750 | Rurii- Grading and gravelling - Mbugua-Mukugi Road, Kamau- Kiriga Road and Kinyumba-Mbichu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3200000 | 3200000 |  | C.G.N | [5 empty] | 3200000 |  |  | Complete | 100%
ROADS | 5751 | Rurii- Kimani Kabora Road, James Mbatia Road, Gatitu Wairagu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2998000 | 2998000 |  | C.G.N | [5 empty] | 2998000 |  |  | Complete | 100%
ROADS | 5752 | Rurii- Passenga Town Roads, Matura Shopping Centre and Wanjohi Nduhiu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1498000 | 1498000 |  | C.G.N | [5 empty] | 1498000 |  |  | Complete | 100%
ROADS | 5753 | Rurii- Haraka Catholic | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999997 |  | C.G.N | [5 empty] | 1999997 |  |  | Complete | 100%
ROADS | 5754 | Rurii-Reli-Mukiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 471970 |  | C.G.N | [5 empty] | 471970 |  |  | Complete | 100%
ROADS | 5755 | Rurii ward- Plot 10 -St Thomas Road Junction- | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  |  |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5756 | Culvert Installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | Complete | 100%
ROADS | 5757 | 2 No. boda boda sheds-Silanga and Bosnia- Rurii ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5758 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5759 | Ndarua- Charity Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5760 | Gitau Githariko road- Grading, gravelling and culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5761 | Ngware- Kimende Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | 484000 |  | C.G.N | [5 empty] | 484000 |  |  | Complete | 100%
ROADS | 5762 | Githariko Estate Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 750000 | 750000 |  | C.G.N | [5 empty] | 750000 |  |  | Complete | 100%
ROADS | 5763 | Kihonge Estate road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5764 | Plot 10 grading, gravelling and drainage works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 8000000 | 8000000 |  | C.G.N | [5 empty] | 8000000 |  |  | Complete | 100%
ROADS | 5765 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2499069 |  | C.G.N | [5 empty] | 2499069 |  |  | Complete | 100%
ROADS | 5766 | Laban-IDP Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3800000 | 3770000 |  | C.G.N | [5 empty] | 3770000 |  |  | Complete | 100%
ROADS | 5767 | Gathanji road (FY 2016-17) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | Complete | 100%
ROADS | 5768 | 2 No. 13m height floodlight-Gituamba and Ihiga-ini- Gathanji ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1498007 |  | C.G.N | [5 empty] | 1498007 |  |  | Complete | 100%
ROADS | 5769 | Gikonyo-Andrew Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5770 | Pivot road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 980000 | 980000 |  | C.G.N | [5 empty] | 980000 |  |  | Complete | 100%
ROADS | 5771 | Kosovo Forest Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5772 | Emergency road maintenance works-Spot patching and grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5773 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 13000000 | 8092853 |  | C.G.N | [5 empty] | 8092853 |  |  | Complete | 100%
ROADS | 5774 | Ol-Joro-Orok-Kanguu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5775 | Gatimu assorted grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 350000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5776 | 1No. Floodlight-Runda-Gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2994004 | 2210500 |  | C.G.N | [5 empty] | 2210500 |  |  | Complete | 100%
ROADS | 5777 | Gatimu- Kanguu/Kiwanja locations roads maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3396567 | 3396567 |  | C.G.N | [5 empty] | 3396567 |  |  | Complete | 100%
ROADS | 5778 | Gatimu- Gikingi Road and Upper Hill Jericho Rurii Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2979978 |  | C.G.N | [5 empty] | 2979978 |  |  | Complete | 100%
ROADS | 5779 | Assorted road works- Gatimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1497944 |  | C.G.N | [5 empty] | 1497944 |  |  | Complete | 100%
ROADS | 5780 | Wa Mercy Bridge-Kanguu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | Complete | 100%
ROADS | 5781 | Road maintenance using County Road Machinery & Equipment (At least 12KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1497008 |  | C.G.N | [5 empty] | 1497008 |  |  | Complete | 100%
ROADS | 5782 | Matura Secondary Sch Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2987531 |  | C.G.N | [5 empty] | 2987531 |  |  | Complete | 100%
ROADS | 5783 | Inooro Wa Giita Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 5784 | Ol-Joro-Orok Catholic Itegi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3998810 |  | C.G.N | [5 empty] | 3998810 |  |  | Complete | 100%
ROADS | 5785 | Gatumbiro Pry -Wa Gichenga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1099930 | 1099930 |  | C.G.N | [5 empty] | 1099930 |  |  | Complete | 100%
ROADS | 5786 | Weru Ward- Kangui Moshu Hospital Hill | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 998160 | 998159 |  | C.G.N | [5 empty] | 998159 |  |  | Complete | 100%
ROADS | 5787 | Weru Ward- Muhindi Kenji Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1951644 | 1921644 |  | C.G.N | [5 empty] | 1921644 |  |  | Complete | 100%
ROADS | 5788 | Weru Ward- Mugikunjo Kwa Bison | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5789 | Weru Ward - Kangui Town upgrade | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1999595 |  | C.G.N | [5 empty] | 1999595 |  |  | Complete | 100%
ROADS | 5790 | Weru Ward-Drainage and Culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1496200 | 1496200 |  | C.G.N | [5 empty] | 1496200 |  |  | Complete | 100%
ROADS | 5791 | Weru Karandi drainage works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1088367 | 1088367 |  | C.G.N | [5 empty] | 1088367 |  |  | Complete | 100%
ROADS | 5792 | Weru- Drainage at Kasuku Town | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1997901 | 1997901 |  | C.G.N | [5 empty] | 1997901 |  |  | Complete | 100%
ROADS | 5793 | Weru Ward Wagioche - Iriani Extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5794 | Weru-Gathima Nursery Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 5795 | Gatitu Pry -Mwanda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5796 | Wa Gioshe Road extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5797 | Police line Road Extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2499975 |  | C.G.N | [5 empty] | 2499975 |  |  | Complete | 100%
ROADS | 5798 | Kahii Iria-ini Extension Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1979984 |  | C.G.N | [5 empty] | 1979984 |  |  | Complete | 100%
ROADS | 5799 | Kahiro Kimana- Bush Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5800 | Kimana Quarry Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1498500 |  | C.G.N | [5 empty] | 1498500 |  |  | Complete | 100%
ROADS | 5801 | Waruiru drainage-Weru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5802 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499979 |  | C.G.N | [5 empty] | 1499979 |  |  | Complete | 100%
ROADS | 5803 | Waweru Mugo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5804 | Mugweru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5805 | Akurino Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1996994 |  | C.G.N | [5 empty] | 1996994 |  |  | Complete | 100%
ROADS | 5806 | Nyairoko Primary Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3239144 | 3239144 |  | C.G.N | [5 empty] | 3239144 |  |  | Complete | 100%
ROADS | 5807 | Charagita- Mbuthia Road, Nyairoko Road and Kenda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1989816 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5808 | Charagita- Culvert works & culvert installations | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1495650 | 1495650 |  | C.G.N | [5 empty] | 1495650 |  |  | Complete | 100%
ROADS | 5809 | Charagita - Kamama Road, Thayu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1499339 |  | C.G.N | [5 empty] | 1499339 |  |  | Complete | 100%
ROADS | 5810 | Charagita- Wanjura Village road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 979978 |  | C.G.N | [5 empty] | 979978 |  |  | Complete | 100%
ROADS | 5811 | Muchiri Kabaiko rd-Charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1050000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5812 | Boda boda sheds Charagita 3No. (Wanjura, Nyairoko, Ngatha) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2498640 | 2498640 |  | C.G.N | [5 empty] | 2498640 |  |  | Complete | 100%
ROADS | 5813 | Charagita- Mithami Road, Ngano Centre Road, Mugoiri -Wamurugi Road, T-Rose Road and Wa Mutungi- Victorio Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2984239 | 2984239 |  | C.G.N | [5 empty] | 2984239 |  |  | Complete | 100%
ROADS | 5814 | Charagita- AIC Nyairoko Road, Thayu Kimani Ngorongo Rd and Ngomongo- Ngatho Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2999978 | 2999978 |  | C.G.N | [5 empty] | 2999978 |  |  | Complete | 100%
ROADS | 5815 | Charagita- Mwisho Wa Rami - Chief Road and Charagita Shopping Centre | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2075400 | 2075400 |  | C.G.N | [5 empty] | 2075400 |  |  | Complete | 100%
ROADS | 5816 | Matindiri Floodlight Charagita and 2No.Floodlights -Charagita (Corner & Nyairoko ) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1996749 |  | C.G.N | [5 empty] | 1996749 |  |  | Complete | 100%
ROADS | 5817 | Gichure Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1994297 |  | C.G.N | [5 empty] | 1994297 |  |  | Complete | 100%
ROADS | 5818 | Destiny Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2496695 |  | C.G.N | [5 empty] | 2496695 |  |  | Complete | 100%
ROADS | 5819 | Kibiru Meja Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5820 | Gatama Road- Charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2500000 | 2466400 |  | C.G.N | [5 empty] | 2466400 |  |  | Complete | 100%
ROADS | 5821 | Nyairoko Gishaka road- Charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2300000 | 2290000 |  | C.G.N | [5 empty] | 2290000 |  |  | Complete | 100%
ROADS | 5822 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5823 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3999735 |  | C.G.N | [5 empty] | 3999735 |  |  | Complete | 100%
ROADS | 5824 | Upper Shamata Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3979996 |  | C.G.N | [5 empty] | 3979996 |  |  | Complete | 100%
ROADS | 5825 | Olbollosat Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3998985 |  | C.G.N | [5 empty] | 3998985 |  |  | Complete | 100%
ROADS | 5826 | Mwihoko Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3000000 | 2936886 |  | C.G.N | [5 empty] | 2936886 |  |  | Complete | 100%
ROADS | 5827 | Upper Karandi roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1400000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 5828 | Shamata- Gichagi Pesi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5829 | Shamata- Kiambogo Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 869726 | 869726 |  | C.G.N | [5 empty] | 869726 |  |  | Complete | 100%
ROADS | 5830 | Mitambo road in Shamata ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3997880 |  | C.G.N | [5 empty] | 3997880 |  |  | Complete | 100%
ROADS | 5831 | Simbara roads- Shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3998692 |  | C.G.N | [5 empty] | 3998692 |  |  | Complete | 100%
ROADS | 5832 | Kangocho Roads Shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3998372 |  | C.G.N | [5 empty] | 3998372 |  |  | Complete | 100%
ROADS | 5833 | Warukira roads Shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1800000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5834 | Gitaraga Road Phase II- Shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 641128 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5835 | Shamata- Solar powered town lighting | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3769860 | 3739860 |  | C.G.N | [5 empty] | 3739860 |  |  | Complete | 100%
ROADS | 5836 | Shamata-Captain Chege & Karai Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1040000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5837 | Grading upper Shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5838 | Shamata playing ground dias | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5839 | Transformers- Shamata ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1500000 | 1478760 |  | C.G.N | [5 empty] | 1478760 |  |  | Complete | 100%
ROADS | 5840 | Shamata- Ndemi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3997580 |  | C.G.N | [5 empty] | 3997580 |  |  | Complete | 100%
ROADS | 5841 | Kirimanjaro roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2600000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5842 | Shamata Central roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5843 | Kiriha Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5844 | Assorted culverts for Olbollosat Youths | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1989996 |  | C.G.N | [5 empty] | 1989996 |  |  | Complete | 100%
ROADS | 5845 | Assorted grading-Shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 11000000 | 11000000 |  | C.G.N | [5 empty] | 11000000 |  |  | Complete | 100%
ROADS | 5846 | Road maintenance using County Road Machinery & Equipment (At least 26KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1300000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5847 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5848 | Assorted bush clearing | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5849 | Muthaa- Mithuri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5850 | Kieni -Kihingo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2187329 | 1293480 |  | C.G.N | [5 empty] | 1293480 |  |  | Complete | 100%
ROADS | 5851 | Leshau Pondo Ward- 8No. Floodlights (Kiandege, Shauri, Raicheri, Karamton, Kamukunji, Muthiga, Nyakinywa, Mithuuri) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1999333 | 1999333 |  | C.G.N | [5 empty] | 1999333 |  |  | Complete | 100%
ROADS | 5852 | Leshau Pondo improvement of Mayu pri road & Ngawa Divai road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 380000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5853 | Lesha pondo -Umoja Mbuyu floodlight | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 700000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5854 | 2 No. boda boda shed -Equator and Umoja Mbuyu -leshau pondo ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5855 | KAG Mbuyu Extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5856 | Ngawa Gichohi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 988549 |  | C.G.N | [5 empty] | 988549 |  |  | Complete | 100%
ROADS | 5857 | Assorted road grading- Leshau Pond | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 978549 |  | C.G.N | [5 empty] | 978549 |  |  | Complete | 100%
ROADS | 5858 | Dan Hoseah Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5859 | Kiruhi Mrs. Ngari Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 979614 |  | C.G.N | [5 empty] | 979614 |  |  | Complete | 100%
ROADS | 5860 | Bulldozer Hire -Levelling works: Meja Dam Hill and Ndogino Mathanji Hill | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 979978 |  | C.G.N | [5 empty] | 979978 |  |  | Complete | 100%
ROADS | 5861 | Mathanji Karunda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 972877 |  | C.G.N | [5 empty] | 972877 |  |  | Complete | 100%
ROADS | 5862 | Karamton Mayu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 9999538 |  | C.G.N | [5 empty] | 9999538 |  |  | Complete | 100%
ROADS | 5863 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4200000 | 4200000 |  | C.G.N | [5 empty] | 4200000 |  |  | Complete | 100%
ROADS | 5864 | Wangui Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 4000000 | 3999000 |  | C.G.N | [5 empty] | 3999000 |  |  | Complete | 100%
ROADS | 5865 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5866 | Assorted grading works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 279000 | 273527 |  | C.G.N | [5 empty] | 273527 |  |  | Complete | 100%
ROADS | 5867 | Ndaragwa Central - Excavation, Loading Supply Of Gravel Materials (Emergency Fund)- | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2205000 | 1938333 |  | C.G.N | [5 empty] | 1938333 |  |  | Complete | 100%
ROADS | 5868 | Ndaragwa Central - Supply and Delivery of Gravel Materials (Emergency Fund) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 730104 | 730104 |  | C.G.N | [5 empty] | 730104 |  |  | Complete | 100%
ROADS | 5869 | Ndaragwa Central - Supply, Delivery and Spreading Of Gravel (Emergency Fund) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 995310 | 995310 |  | C.G.N | [5 empty] | 995310 |  |  | Complete | 100%
ROADS | 5870 | Ndaragwa Central - MC ROAD - | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3995249 | 3995249 |  | C.G.N | [5 empty] | 3995249 |  |  | Complete | 100%
ROADS | 5871 | Ndaragwa Central -Uruku-Wamung'ere and Grading and gravelling- Ngamini | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1996350 |  | C.G.N | [5 empty] | 1996350 |  |  | Complete | 100%
ROADS | 5872 | Kiruthu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 9990689 |  | C.G.N | [5 empty] | 9990689 |  |  | Complete | 100%
ROADS | 5873 | Road maintenance using County Road Machinery & Equipment (At least 24KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5874 | Drainage works and bush clearing (labour contracting) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2000000 | 1992380 |  | C.G.N | [5 empty] | 1992380 |  |  | Complete | 100%
ROADS | 5875 | Culverts installations (labour contracting) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 13000000 | 13000000 |  | C.G.N | [5 empty] | 13000000 |  |  | Complete | 100%
ROADS | 5876 | Road maintenance using County Road Machinery & Equipment (At least 36KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 146215617 | 146215617 |  | C.G.N | [5 empty] | 146215617 |  |  | Complete | 100%
ROADS | 5877 | road maintenance fuel levy fund | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2100000 | 2100000 |  | C.G.N | [5 empty] | 2100000 |  |  | Complete | 100%
ROADS | 5878 | 6No. 13m height floodlight-Ndaragwa Central | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 2100000 | 2100000 |  | C.G.N | [5 empty] | 2100000 |  |  | Complete | 100%
ROADS | 5879 | 6 No. 13m height floodlight- kiriita ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 797211 | 797211 |  | C.G.N | [5 empty] | 797211 |  |  | Complete | 100%
ROADS | 5880 | Stelny Enterprises Ltd (Road Work) 2014/2015 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 460800 | 460800 |  | C.G.N | [5 empty] | 460800 |  |  | Complete | 100%
ROADS | 5881 | Votex Ltd (Road Work) 2013/2014 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5882 | Kanyagia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 10000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 5883 | Governor’s Residence | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5884 | Suguroi Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 3300000 | 3300000 |  | C.G.N | [5 empty] | 3300000 |  |  | Complete | 100%
ROADS | 5885 | Rironi Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 614400 | 614400 |  | C.G.N | [5 empty] | 614400 |  |  | Complete | 100%
ROADS | 5886 | Votex Ltd (Road Work) 2013/2014 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2019-07-01 | 2020-06-01 |  | 426000 | 426000 |  | C.G.N | [5 empty] | 426000 |  |  | Complete | 100%
ROADS | 5887 | Lendabu Engineering (Road Work) 2013/2014 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 1628872 | 1628870 |  | C.G.N | [5 empty] | 1628870 |  |  | Complete | 100%
ROADS | 5888 | Lexcon Civil Contractors culvets works (Road improvement) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 997300 | 997300 |  | C.G.N | [5 empty] | 997300 |  |  | Complete | 100%
ROADS | 5889 | Dafred Kenya Ltd (Gravel Patching ) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5890 | Nyahururu Services Station | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 576000 | 576000 |  | C.G.N | [5 empty] | 576000 |  |  | Complete | 100%
ROADS | 5891 | Cenrift Cons (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 5155968 | 5155968 |  | C.G.N | [5 empty] | 5155968 |  |  | Complete | 100%
ROADS | 5892 | Pitbul Agencies Ltd (Construction of Branda Bridge) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 1817600 | 1817600 |  | C.G.N | [5 empty] | 1817600 |  |  | Complete | 100%
ROADS | 5893 | Mercy Technology (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 1257000 | 1257000 |  | C.G.N | [5 empty] | 1257000 |  |  | Complete | 100%
ROADS | 5894 | Peter M Murage (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 910000 | 910000 |  | C.G.N | [5 empty] | 910000 |  |  | Complete | 100%
ROADS | 5895 | Peter M Murage (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 590200 | 590200 |  | C.G.N | [5 empty] | 590200 |  |  | Complete | 100%
ROADS | 5896 | Procivil Engineering (Gravelling) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | Complete | 100%
ROADS | 5897 | Procivil Engineering (wagathuru bridge) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 534000 | 534000 |  | C.G.N | [5 empty] | 534000 |  |  | Complete | 100%
ROADS | 5898 | Randunya Ent (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 799200 | 799200 |  | C.G.N | [5 empty] | 799200 |  |  | Complete | 100%
ROADS | 5899 | Seaman Contractors Ltd (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 3886000 | 3886000 |  | C.G.N | [5 empty] | 3886000 |  |  | Complete | 100%
ROADS | 5900 | Seaman Building And Contractors | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 6000000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | Complete | 100%
ROADS | 5901 | Thumbi Company Ltd (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 403200 | 403200 |  | C.G.N | [5 empty] | 403200 |  |  | Complete | 100%
ROADS | 5902 | Jacksipho Co Ltd (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 2920000 | 2920000 |  | C.G.N | [5 empty] | 2920000 |  |  | Complete | 100%
ROADS | 5903 | Top Performance International (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 716800 | 716800 |  | C.G.N | [5 empty] | 716800 |  |  | Complete | 100%
ROADS | 5904 | Samson W Mwaura (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 303600 | 303600 |  | C.G.N | [5 empty] | 303600 |  |  | Complete | 100%
ROADS | 5905 | Cifra Contractors (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 785421 | 785421 |  | C.G.N | [5 empty] | 785421 |  |  | Complete | 100%
ROADS | 5906 | Danphel Enterprises | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 924000 | 924000 |  | C.G.N | [5 empty] | 924000 |  |  | Complete | 100%
ROADS | 5907 | Anga Bewan (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 530000 | 530000 |  | C.G.N | [5 empty] | 530000 |  |  | Complete | 100%
ROADS | 5908 | Framu Contractors (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 890 | 890 |  | C.G.N | [5 empty] | 890 |  |  | Complete | 100%
ROADS | 5909 | Framu Contractors (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5910 | Dorak Co Ltd (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 1811000 | 1811000 |  | C.G.N | [5 empty] | 1811000 |  |  | Complete | 100%
ROADS | 5911 | Gounzhaou Construction Company (Grading And Gravelling. Ex smith road) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 28869585 | 28869585 |  | C.G.N | [5 empty] | 28869585 |  |  | Complete | 100%
ROADS | 5912 | Fuel Levy Unspent Balances - FY 2019/20 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 10093520 | 10093520 |  | C.G.N | [5 empty] | 10093520 |  |  | Complete | 100%
ROADS | 5913 | Gachuha Bridge - KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 4578543 | 4578543 |  | C.G.N | [5 empty] | 4578543 |  |  | Complete | 100%
ROADS | 5914 | Kihuho Kwa MOA Bridge - KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 5915 | Wangui Bridge - KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 5916 | Cheese Churiri - Bridge - KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 4000000 | 3810039 |  | C.G.N | [5 empty] | 3810039 |  |  | Complete | 100%
ROADS | 5917 | Cheese Churiri - Road- KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 30000000 | 30000000 |  | C.G.N | [5 empty] | 30000000 |  |  | Complete | 100%
ROADS | 5918 | In House Machinery - KDSP | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 84000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 5919 | Paul Kababii (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 230400 | 230400 |  | C.G.N | [5 empty] | 230400 |  |  | Complete | 100%
ROADS | 5920 | Roch Mamet (Road Work) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 998025 | 998025 |  | C.G.N | [5 empty] | 998025 |  |  | Complete | 100%
ROADS | 5921 | Kirobi Mikaro Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 3861000 | 3861000 |  | C.G.N | [5 empty] | 3861000 |  |  | Complete | 100%
ROADS | 5922 | Ascom Networks Limited- (*Runda, Mathare and NIST high mast flood lights) FY 2016-17 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2020-07-01 | 2021-06-01 |  | 1800000 | 1766888 |  | C.G.N | [5 empty] | 1766888 |  |  | Complete | 100%
ROADS | 5923 | Gathairu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1800000 | 1731535 |  | C.G.N | [5 empty] | 1731535 |  |  | Complete | 100%
ROADS | 5924 | Lizbet Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 2469970 |  | C.G.N | [5 empty] | 2469970 |  |  | Complete | 100%
ROADS | 5925 | Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | Complete | 100%
ROADS | 5926 | Rurii road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1932115 |  | C.G.N | [5 empty] | 1932115 |  |  | Complete | 100%
ROADS | 5927 | Karaya Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1461827 |  | C.G.N | [5 empty] | 1461827 |  |  | Complete | 100%
ROADS | 5928 | Bamboo Village Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1900000 | 1869817 |  | C.G.N | [5 empty] | 1869817 |  |  | Complete | 100%
ROADS | 5929 | Wa Bonnie Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1468400 |  | C.G.N | [5 empty] | 1468400 |  |  | Complete | 100%
ROADS | 5930 | Wanjama-Kabuka road-Magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2700000 | 2700000 |  | C.G.N | [5 empty] | 2700000 |  |  | Complete | 100%
ROADS | 5931 | Mutonyora C- Wa Njeri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2300000 | 2300000 |  | C.G.N | [5 empty] | 2300000 |  |  | Complete | 100%
ROADS | 5932 | Kimani- Githua Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 10000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 5933 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 4958706 |  | C.G.N | [5 empty] | 4958706 |  |  | Complete | 100%
ROADS | 5934 | Rwanyambo Secondary- ACK Church road- Heavy grading, gravelling, compacting, drainage works culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5935 | Assorted grading, gravelling, bush clearing and drains maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5936 | Kimani Warima Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5937 | Githioro Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1429250 |  | C.G.N | [5 empty] | 1429250 |  |  | Complete | 100%
ROADS | 5938 | By pass road in nyakio ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 500000 | 499629 |  | C.G.N | [5 empty] | 499629 |  |  | Complete | 100%
ROADS | 5939 | Boda boda sheds construction Nyakio ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1969174 |  | C.G.N | [5 empty] | 1969174 |  |  | Complete | 100%
ROADS | 5940 | Haraka ECDE centre road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5941 | Upper mugo roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5942 | Gatitu Riverside link roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5943 | Completion of Lower Yaang'a and Church Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1974542 |  | C.G.N | [5 empty] | 1974542 |  |  | Complete | 100%
ROADS | 5944 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5945 | Cuba- Muni Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5946 | Completion of lower Kihunguru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5947 | Road maintenance using County's in-house Road Machinery & Equipment - Additional funding | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 2800000 |  | C.G.N | [5 empty] | 2800000 |  |  | Complete | 100%
ROADS | 5948 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 2438057 |  | C.G.N | [5 empty] | 2438057 |  |  | Complete | 100%
ROADS | 5949 | Wanyoike Road Gabions , backfilling, Mureith rural roads-4No. Culvert installations, Gabiuons works and Bnackfilling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5950 | Githabai ward - 1No. 13M High Floodmast | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 700000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5951 | Githabai- boda boda sheds construction- Joma and Karuru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 700000 | 699740 |  | C.G.N | [5 empty] | 699740 |  |  | Complete | 100%
ROADS | 5952 | Boda boda sheds construction Githabai | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5953 | Simba-Kangondo Roads and Gwa senior Bridge gabions and back filling works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 5954 | Gathuru-Kayole-Apostolic Church Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | Complete | 100%
ROADS | 5955 | Midland-Mboga Kiunyu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 2435946 |  | C.G.N | [5 empty] | 2435946 |  |  | Complete | 100%
ROADS | 5956 | Rural -wakahinga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 2435946 |  | C.G.N | [5 empty] | 2435946 |  |  | Complete | 100%
ROADS | 5957 | Gathanga-kahuho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3969052 |  | C.G.N | [5 empty] | 3969052 |  |  | Complete | 100%
ROADS | 5958 | Githuri road/Wassamuel Road -Kiambarambara Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1909184 |  | C.G.N | [5 empty] | 1909184 |  |  | Complete | 100%
ROADS | 5959 | Assorted Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3969930 |  | C.G.N | [5 empty] | 3969930 |  |  | Complete | 100%
ROADS | 5960 | Assorted road network-Nyakio(4KM) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3969940 |  | C.G.N | [5 empty] | 3969940 |  |  | Complete | 100%
ROADS | 5961 | Koinange village roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 10000000 | 10000000 |  | C.G.N | [5 empty] | 10000000 |  |  | Complete | 100%
ROADS | 5962 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5963 | Other Road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5964 | Dr. Mathenge Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5965 | Komu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5966 | Kabutu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 959106 |  | C.G.N | [5 empty] | 959106 |  |  | Complete | 100%
ROADS | 5967 | Kianjata Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 984460 |  | C.G.N | [5 empty] | 984460 |  |  | Complete | 100%
ROADS | 5968 | Kiambunda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5969 | Muchibau Secondary School Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 2939460 |  | C.G.N | [5 empty] | 2939460 |  |  | Complete | 100%
ROADS | 5970 | Assorted grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5971 | Gitari/Kibindo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1465494 |  | C.G.N | [5 empty] | 1465494 |  |  | Complete | 100%
ROADS | 5972 | Njoroge-Njihia road opposite Sasumwa Primary School | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5973 | Mufia-Ndothua Sec Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5974 | Fencing of Mtongwe ECDE land- Njabini | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5975 | Fencing of Kiandege ECDE Land- Njabini | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5976 | Njabini Ward- 1No. 13M High floodmast- Kabongo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5977 | Mwalimu Nyingi/Njihia Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1469940 |  | C.G.N | [5 empty] | 1469940 |  |  | Complete | 100%
ROADS | 5978 | Nyaru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 5979 | Wa Peter Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 958396 |  | C.G.N | [5 empty] | 958396 |  |  | Complete | 100%
ROADS | 5980 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1459893 |  | C.G.N | [5 empty] | 1459893 |  |  | Complete | 100%
ROADS | 5981 | Muhammed-Pastor Kariuki road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 5982 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5983 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2300000 | 2300000 |  | C.G.N | [5 empty] | 2300000 |  |  | Complete | 100%
ROADS | 5984 | Waoke road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1437158 |  | C.G.N | [5 empty] | 1437158 |  |  | Complete | 100%
ROADS | 5985 | Mwenje road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3100000 | 3100000 |  | C.G.N | [5 empty] | 3100000 |  |  | Complete | 100%
ROADS | 5986 | Padre Githabai road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1200000 | 1136699 |  | C.G.N | [5 empty] | 1136699 |  |  | Complete | 100%
ROADS | 5987 | Mwihoko pry road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3100000 | 3065300 |  | C.G.N | [5 empty] | 3065300 |  |  | Complete | 100%
ROADS | 5988 | Line Moja road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 5989 | Kariahu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2200000 | 2133112 |  | C.G.N | [5 empty] | 2133112 |  |  | Complete | 100%
ROADS | 5990 | Mutamaiyu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2100000 | 2100000 |  | C.G.N | [5 empty] | 2100000 |  |  | Complete | 100%
ROADS | 5991 | Ritho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2300000 | 1960565 |  | C.G.N | [5 empty] | 1960565 |  |  | Complete | 100%
ROADS | 5992 | Mortuary Raitha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5993 | Mwihoko U- road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 3977049 |  | C.G.N | [5 empty] | 3977049 |  |  | Complete | 100%
ROADS | 5994 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 5995 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1900000 | 1836003 |  | C.G.N | [5 empty] | 1836003 |  |  | Complete | 100%
ROADS | 5996 | Itomboya road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1800000 | 1800000 |  | C.G.N | [5 empty] | 1800000 |  |  | Complete | 100%
ROADS | 5997 | Kimotho - Kirathimo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5998 | Wagaya road Thindi- Engineer | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1800000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 5999 | Factory mamba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1800000 | 1739316 |  | C.G.N | [5 empty] | 1739316 |  |  | Complete | 100%
ROADS | 6000 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1939395 |  | C.G.N | [5 empty] | 1939395 |  |  | Complete | 100%
ROADS | 6001 | Kimemia- Wamari road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 4396225 |  | C.G.N | [5 empty] | 4396225 |  |  | Complete | 100%
ROADS | 6002 | Kingimeri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6003 | Kamunyaka b/h road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6004 | Makutano- Kahuru road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 4217625 |  | C.G.N | [5 empty] | 4217625 |  |  | Complete | 100%
ROADS | 6005 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6006 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6007 | Assorted grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 4931821 |  | C.G.N | [5 empty] | 4931821 |  |  | Complete | 100%
ROADS | 6008 | Assorted gravelling- Kiambariki | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6009 | Assorted gravelling - Kitiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 750000 | 749248 |  | C.G.N | [5 empty] | 749248 |  |  | Complete | 100%
ROADS | 6010 | North Kinangop- 2No. Boda boda sheds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 150000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6011 | North Kinangop- Ndunyu Njeru street lighting | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3500000 | 3467351 |  | C.G.N | [5 empty] | 3467351 |  |  | Complete | 100%
ROADS | 6012 | Assorted gravelling - Nandarasi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6013 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6014 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 6015 | Kianjogu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1939977 |  | C.G.N | [5 empty] | 1939977 |  |  | Complete | 100%
ROADS | 6016 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 2969265 |  | C.G.N | [5 empty] | 2969265 |  |  | Complete | 100%
ROADS | 6017 | CDF-Hianyu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2600000 | 2567141 |  | C.G.N | [5 empty] | 2567141 |  |  | Complete | 100%
ROADS | 6018 | C69-Muchere road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 6019 | Kwa rigu road-Grading & Gravelling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 6020 | Kahuho shamata road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 200000 | 199482 |  | C.G.N | [5 empty] | 199482 |  |  | Complete | 100%
ROADS | 6021 | Culvert installation (Njiku culvert) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 2465334 |  | C.G.N | [5 empty] | 2465334 |  |  | Ongoing
ROADS | 6022 | Top life-Githaraba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 3038000 |  | C.G.N | [5 empty] | 3038000 |  |  | Complete | 100%
ROADS | 6023 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  |  |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6024 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3967508 |  | C.G.N | [5 empty] | 3967508 |  |  | Complete | 100%
ROADS | 6025 | Kianjogu, Mundoro, churches roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4250000 | 4250000 |  | C.G.N | [5 empty] | 4250000 |  |  | Ongoing
ROADS | 6026 | Geta ward- Market stall | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1967633 |  | C.G.N | [5 empty] | 1967633 |  |  | Ongoing
ROADS | 6027 | No 10 road-Geta | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 4998186 |  | C.G.N | [5 empty] | 4998186 |  |  | Complete | 100%
ROADS | 6028 | Geta ward- Cabro works Geta stage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3963917 |  | C.G.N | [5 empty] | 3963917 |  |  | Complete | 100%
ROADS | 6029 | Gathuthi, Munanda, Bethieli, Waiyego roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3969840 |  | C.G.N | [5 empty] | 3969840 |  |  | Ongoing
ROADS | 6030 | Rumwe, Muthama, Runanu Kung'u, Dispensary roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3963262 |  | C.G.N | [5 empty] | 3963262 |  |  | Complete | 100%
ROADS | 6031 | Kamucibi, Kiriani roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3961800 |  | C.G.N | [5 empty] | 3961800 |  |  | Complete | 100%
ROADS | 6032 | Mutungu Willy Nyutu, Mihato tank, Wamuceru roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3965112 |  | C.G.N | [5 empty] | 3965112 |  |  | Complete | 100%
ROADS | 6033 | Kagongo roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6034 | Canteen Marimu B roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6035 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Ongoing
ROADS | 6036 | Road maintenance using County's in-house Road Machinery & Equipment - Additional funding | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 4698094 |  | C.G.N | [5 empty] | 4698094 |  |  | Ongoing
ROADS | 6037 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1600000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6038 | Gachuha road acess - Flagship | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 750000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6039 | Assorted Curlverts- 5 Lines | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 4936020 |  | C.G.N | [5 empty] | 4936020 |  |  | Complete | 100%
ROADS | 6040 | Gordon wendani road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6041 | Karua road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1966360 |  | C.G.N | [5 empty] | 1966360 |  |  | Complete | 100%
ROADS | 6042 | Ha wambui - gitwe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 3938032 |  | C.G.N | [5 empty] | 3938032 |  |  | Complete | 100%
ROADS | 6043 | Wamalitha - kanyari road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6044 | Forest one wangoe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2300000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6045 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6046 | Wanjohi-Kiamboga boda boda shed | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3900000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6047 | Wanjohi ward- 3No. 20M High Floodmast (Kiamboga, Jericho and Wanjohi mixed sec sch) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 10000000 | 2825000 |  | C.G.N | [5 empty] | 2825000 |  |  | Complete | 100%
ROADS | 6048 | Road maintenance using County's in-house Road Machinery & Equipment for Lereshwa, Malewa and Kipipiri location roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3500000 | 3469236 |  | C.G.N | [5 empty] | 3469236 |  |  | Complete | 100%
ROADS | 6049 | DN- Kimuru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 2469360 |  | C.G.N | [5 empty] | 2469360 |  |  | Complete | 100%
ROADS | 6050 | Sky High-IDP Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5900000 |  |  | C.G.N | [8 empty] | 0
ROADS | 6051 | Kipipiri Ward- Installation of solar panel floodlights | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 4934305 |  | C.G.N | [5 empty] | 4934305 |  |  | Complete | 100%
ROADS | 6052 | Mira B- Kaihu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6053 | Kimuru - Catholic Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2550000 | 2550000 |  | C.G.N | [5 empty] | 2550000 |  |  | Complete | 100%
ROADS | 6054 | Road maintenance using County's in-house Road Machinery & Equipment - Additional funding | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 7000000 | 7000000 |  | C.G.N | [5 empty] | 7000000 |  |  | Complete | 100%
ROADS | 6055 | Road maintenance using County's in-house Road Machinery & Equipment for Lereshwa, Malewa and Kipipiri location roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 |  |  | C.G.N | [8 empty] | Ongoing
ROADS | 6056 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3952571 |  | C.G.N | [5 empty] | 3952571 |  |  | Ongoing
ROADS | 6057 | Gituamba B roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2600000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6058 | Kaimbaga- Kiganjo 2No. 20M High floodmasts (Muthaiga and Chief Camp) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6059 | Aberdare school to gwa kibe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2599500 |  |  | C.G.N | [8 empty] | Ongoing
ROADS | 6060 | Mahinga roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2799999 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6061 | Koinange roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3280000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6062 | Jua kali roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6063 | Simba Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 7511261 | 7511261 |  | C.G.N | [5 empty] | 7511261 |  |  | Complete | 100%
ROADS | 6064 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6065 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2460000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6066 | 7 No. Floodlights - Karau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2560000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6067 | 7 No. Floodlights - Karau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1300000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6068 | Assorted grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6069 | Olkalou vatican karau | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 2793800 |  | C.G.N | [5 empty] | 2793800 |  |  | Ongoing
ROADS | 6070 | Assorted gravelling and spot patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 2331866 |  | C.G.N | [5 empty] | 2331866 |  |  | Complete | 100%
ROADS | 6071 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 6072 | Ha Mukurino-Kahungu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6073 | Ha Mathenge- Kiboi Road- Murraming, Bush Clearing, drain maintenance and culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6074 | Ngware-Kimende road-Rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 2439926 |  | C.G.N | [5 empty] | 2439926 |  |  | Complete | 100%
ROADS | 6075 | Rurii- Manyatta Primary- Mithia Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 500000 | 1439069 |  | C.G.N | [5 empty] | 1439069 |  |  | Complete | 100%
ROADS | 6076 | Rurii-Mbugua-Mukugi Road -Drainange and culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6077 | Rurii- Wa Shiru- Mama Luis off Mutharaba road- grading, gravelling, drainage and culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1469832 |  | C.G.N | [5 empty] | 1469832 |  |  | Ongoing
ROADS | 6078 | Ranges-mondo road-rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1300000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6079 | Rurii- Matura 13 M Floodlight | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6080 | Mazeras-Thitai Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6081 | Kigera- Mugumo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1461008 |  | C.G.N | [5 empty] | 1461008 |  |  | Complete | 100%
ROADS | 6082 | Kimang'a Wamuti Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6083 | Gakoroba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1409080 |  | C.G.N | [5 empty] | 1409080 |  |  | Ongoing
ROADS | 6084 | Kairianja - Munanda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1959128 |  | C.G.N | [5 empty] | 1959128 |  |  | Complete | 100%
ROADS | 6085 | Manyata -Kanyari road- grading, gravelling and construction of gabbions | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6086 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6087 | Matura Stage 1- Magomano Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 8000000 | 3552500 |  | C.G.N | [5 empty] | 3552500 |  |  | Complete | 100%
ROADS | 6088 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1800000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6089 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 800000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | Complete | 100%
ROADS | 6090 | Assorted spot patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | Complete | 100%
ROADS | 6091 | New Light Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6092 | Gakuyo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6093 | Baraka Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1300000 | 1300000 |  | C.G.N | [5 empty] | 1300000 |  |  | Complete | 100%
ROADS | 6094 | Tumaini Centre Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6095 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6096 | Makara Rds | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6097 | Kibendera Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1750000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6098 | Gwa Komu Road-Mirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6099 | Mirangine- 3No. 7M High Floodlights | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6100 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Ongoing
ROADS | 6101 | Assorted gravel patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6102 | Kanyingi-Slow down Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6103 | Micharage Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 8000000 | 8000000 |  | C.G.N | [5 empty] | 8000000 |  |  | Complete | 100%
ROADS | 6104 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3942242 |  | C.G.N | [5 empty] | 3942242 |  |  | Complete | 100%
ROADS | 6105 | Gachagi-Olbolosat Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 2461675 |  | C.G.N | [5 empty] | 2461675 |  |  | Complete | 100%
ROADS | 6106 | Wairua-Kamaina Primary Rd | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3942924 |  | C.G.N | [5 empty] | 3942924 |  |  | Complete | 100%
ROADS | 6107 | 49 Kawakawa-Muchu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Ongoing
ROADS | 6108 | Gacheru Dam Extension-Weru ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6109 | Wakahiu-Mutahi road-Weru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 2955254 |  | C.G.N | [5 empty] | 2955254 |  |  | Complete | 100%
ROADS | 6110 | Weru Secondary-Gachengo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3960185 |  | C.G.N | [5 empty] | 3960185 |  |  | Complete | 100%
ROADS | 6111 | Kareithi-Kahii Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6112 | Kware-Catholic Extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3947992 |  | C.G.N | [5 empty] | 3947992 |  |  | Complete | 100%
ROADS | 6113 | Gachigo-Pastor Karaba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  |  | 1939734 |  | C.G.N | [5 empty] | 1939734 |  |  | Complete | 100%
ROADS | 6114 | Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6115 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6116 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 2966484 |  | C.G.N | [5 empty] | 2966484 |  |  | Complete | 100%
ROADS | 6117 | Gathatwa Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 4933098 |  | C.G.N | [5 empty] | 4933098 |  |  | Complete | 100%
ROADS | 6118 | Charagita - Githinjiro Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6119 | Matindiri- Kibau Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6120 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 6121 | Muchemi-King'ori Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 4403260 |  | C.G.N | [5 empty] | 4403260 |  |  | Complete | 100%
ROADS | 6122 | Assorted bush clearing and drainage works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6123 | Hudson Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6124 | Gichura Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6125 | Munga School | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6126 | Wanderi- Munga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 6127 | Nett Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6128 | Extension of Ngatho Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6129 | Kwa Mboga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6130 | Waici Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6131 | Nguva Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1433375 |  | C.G.N | [5 empty] | 1433375 |  |  | Complete | 100%
ROADS | 6132 | Munandaini road-Gathanji | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6133 | Gituamba huhoini road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6134 | Gituamba Laikipia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1800000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6135 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6136 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6137 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3500000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6138 | Assorted grading works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1800000 | 1769589 |  | C.G.N | [5 empty] | 1769589 |  |  | Complete | 100%
ROADS | 6139 | Assorted spot patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1939237 |  | C.G.N | [5 empty] | 1939237 |  |  | Complete | 100%
ROADS | 6140 | Muhindi-equator-kisima kibathi-madaraka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6141 | Kibathi-madaraka roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2700000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6142 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6143 | Nyakariang'a tyre-Tank Dam-Pator ben road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6144 | Mutharia-gathiru-culvert gicheha road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6145 | Matron-kabunjo-prison road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1928923 |  | C.G.N | [5 empty] | 1928923 |  |  | Complete | 100%
ROADS | 6146 | Njunu-kanguu primary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1962150 |  | C.G.N | [5 empty] | 1962150 |  |  | Complete | 100%
ROADS | 6147 | Pub- Muembu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6148 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2500000 | 3928784 |  | C.G.N | [5 empty] | 3928784 |  |  | Complete | 100%
ROADS | 6149 | Ziwani roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6150 | Baari roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6151 | Mairo-Inya - Starehe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6152 | Karagoini roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6153 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6154 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 4782300 |  | C.G.N | [5 empty] | 4782300 |  |  | Complete | 100%
ROADS | 6155 | Kiandege secondary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6156 | Mama Nyika Kabera road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6157 | Shauri mc road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6158 | Mwalimu Weru road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 967260 |  | C.G.N | [5 empty] | 967260 |  |  | Complete | 100%
ROADS | 6159 | Aspen-Gachego road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 967784 |  | C.G.N | [5 empty] | 967784 |  |  | Complete | 100%
ROADS | 6160 | Muthega-Pastor Lydia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 375000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6161 | Bodaboda shed construction in leshau pondo ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6162 | 13 No. Floodlights connection to electricity-Leshau Pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1468505 |  | C.G.N | [5 empty] | 1468505 |  |  | Complete | 100%
ROADS | 6163 | Passaka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1425460 |  | C.G.N | [5 empty] | 1425460 |  |  | Complete | 100%
ROADS | 6164 | Ndivai dispensary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 | 1436164 |  | C.G.N | [5 empty] | 1436164 |  |  | Complete | 100%
ROADS | 6165 | Gwa Kungu town roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 6166 | Mt. Moriah road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6167 | Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1000000 | 2667560 |  | C.G.N | [5 empty] | 2667560 |  |  | Complete | 100%
ROADS | 6168 | Assorted grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6169 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6170 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6171 | Subego road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 4967744 |  | C.G.N | [5 empty] | 4967744 |  |  | Complete | 100%
ROADS | 6172 | Assorted grading works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6173 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 10000000 | 9999700 |  | C.G.N | [5 empty] | 9999700 |  |  | Complete | 100%
ROADS | 6174 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | - |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6175 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3967205 |  | C.G.N | [5 empty] | 3967205 |  |  | Complete | 100%
ROADS | 6176 | Mastoo roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6177 | Bodaboda shed construction in Shamata ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6178 | Shamata-kiambogo bodaboda shed | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6179 | Shamata ward - Solar lighting | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6180 | Joise road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3968900 |  | C.G.N | [5 empty] | 3968900 |  |  | Ongoing
ROADS | 6181 | Muhiriga roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3967368 |  | C.G.N | [5 empty] | 3967368 |  |  | Complete | 100%
ROADS | 6182 | Wangatafuthi roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6183 | Aeroplane road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | - |  | C.G.N | [5 empty] | - |  |  | Complete | 100%
ROADS | 6184 | Pesi roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3967810 |  | C.G.N | [5 empty] | 3967810 |  |  | Complete | 100%
ROADS | 6185 | Mwihoti roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3969190.4 |  | C.G.N | [5 empty] | 3969190.4 |  |  | Complete | 100%
ROADS | 6186 | Karimaini roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 4000000 | 3966244.4 |  | C.G.N | [5 empty] | 3966244.4 |  |  | Ongoing
ROADS | 6187 | Gikano roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6188 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2021-07-01 | 2022-06-01 |  | 2000000 | 1999055.13 |  | C.G.N | [5 empty] | 1999055.13 |  |  | Ongoing
ROADS | 6189 | George K Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1998003 |  | C.G.N | [5 empty] | 1998003 |  |  | Complete | 100%
ROADS | 6190 | Wa Njoroge Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1998514 |  | C.G.N | [5 empty] | 1998514 |  |  | Complete | 100%
ROADS | 6191 | Wa Paul Road- Light grading, gravelling, compacting and culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6192 | Magumu- Mutonyora C- Wa Njeri Road FY 2021-22 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6193 | Magumu- Kimani- Githua Road FY 2021-22 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2300000 | 1998639 |  | C.G.N | [5 empty] | 1998639 |  |  | Complete | 100%
ROADS | 6194 | Teacher's Corner Road- Magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1499749 |  | C.G.N | [5 empty] | 1499749 |  |  | Complete | 100%
ROADS | 6195 | Assorted culverts- Magumu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6196 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 1999413.6 |  | C.G.N | [5 empty] | 1999413.6 |  |  | Complete | 100%
ROADS | 6197 | Nyakio ward- Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 2998660 |  | C.G.N | [5 empty] | 2998660 |  |  | Complete | 100%
ROADS | 6198 | Nyakio ward- Assorted roadworks | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6199 | Nyakio- Lower Kahuho Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6200 | Nyakio ward- Cuba- Muni Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1999615.6 |  | C.G.N | [5 empty] | 1999615.6 |  |  | Complete | 100%
ROADS | 6201 | Nyakio- Kware road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6202 | Wa Mwihia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1400000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | Ongoing
ROADS | 6203 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 6000000 | 1999820 |  | C.G.N | [5 empty] | 1999820 |  |  | Ongoing
ROADS | 6204 | Wakarime Mishinda Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1990205 |  | C.G.N | [5 empty] | 1990205 |  |  | Complete | 100%
ROADS | 6205 | Njatha Midland Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 999280 |  | C.G.N | [5 empty] | 999280 |  |  | Complete | 100%
ROADS | 6206 | Mariko and Pastor Gideon Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 3999996 |  | C.G.N | [5 empty] | 3999996 |  |  | Complete | 100%
ROADS | 6207 | Wa Ngunjiri Roads network | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6208 | Kahang'i -Kiririmbi Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 1998862 |  | C.G.N | [5 empty] | 1998862 |  |  | Complete | 100%
ROADS | 6209 | Kagiiki- PN Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1499250 |  | C.G.N | [5 empty] | 1499250 |  |  | Complete | 100%
ROADS | 6210 | Heni Wanyoike Road- Spot patching/Maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 1997783 |  | C.G.N | [5 empty] | 1997783 |  |  | Complete | 100%
ROADS | 6211 | Njane and Kibuika Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1406039 |  | C.G.N | [5 empty] | 1406039 |  |  | Complete | 100%
ROADS | 6212 | Mbogani Primary School Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1406039 | 998779 |  | C.G.N | [5 empty] | 998779 |  |  | Complete | 100%
ROADS | 6213 | Assorted Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 1999295 |  | C.G.N | [5 empty] | 1999295 |  |  | Complete | 100%
ROADS | 6214 | Kahuho primary school road, Dam road and Kimani Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 3999802 |  | C.G.N | [5 empty] | 3999802 |  |  | Complete | 100%
ROADS | 6215 | Githabai Township Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6216 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 5000000 | 999820 |  | C.G.N | [5 empty] | 999820 |  |  | Complete | 100%
ROADS | 6217 | Shirikisho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 999496 |  | C.G.N | [5 empty] | 999496 |  |  | Complete | 100%
ROADS | 6218 | Theta road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 999900 |  | C.G.N | [5 empty] | 999900 |  |  | Ongoing
ROADS | 6219 | Mutongwe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 999799 |  | C.G.N | [5 empty] | 999799 |  |  | Complete | 100%
ROADS | 6220 | Dosa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6221 | Njabini-Ndabi/Wa Peter Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6222 | Njabini- Assorted culvert works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6223 | Njabini- Cheese Churiri - Bridge - KDSP Level II | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 999930.3 |  | C.G.N | [5 empty] | 999930.3 |  |  | Ongoing
ROADS | 6224 | Kamwiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 999550 |  | C.G.N | [5 empty] | 999550 |  |  | Complete | 100%
ROADS | 6225 | Kamwere road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 999659 |  | C.G.N | [5 empty] | 999659 |  |  | Complete | 100%
ROADS | 6226 | Assorted Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 999530 |  | C.G.N | [5 empty] | 999530 |  |  | Complete | 100%
ROADS | 6227 | Assorted Culverts-additional allocation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Ongoing
ROADS | 6228 | Pilot Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1400000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6229 | Gachomba/Churiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1200000 | 1499278 |  | C.G.N | [5 empty] | 1499278 |  |  | Complete | 100%
ROADS | 6230 | Kiandege road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1499230 |  | C.G.N | [5 empty] | 1499230 |  |  | Complete | 100%
ROADS | 6231 | Assorted road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 1499300 |  | C.G.N | [5 empty] | 1499300 |  |  | Complete | 100%
ROADS | 6232 | Kianjata Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6233 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 1998184 |  | C.G.N | [5 empty] | 1998184 |  |  | Complete | 100%
ROADS | 6234 | Gachwani road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 2499447 |  | C.G.N | [5 empty] | 2499447 |  |  | Complete | 100%
ROADS | 6235 | Gichinga Phyllis- Gichinga Wa Tabitha Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6236 | Karanga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1995508 |  | C.G.N | [5 empty] | 1995508 |  |  | Complete | 100%
ROADS | 6237 | SingleBoy- Meeni SingleBoy Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 899587 |  | C.G.N | [5 empty] | 899587 |  |  | Complete | 100%
ROADS | 6238 | Assorted culverts- Gathaara | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 900000 | 2998686 |  | C.G.N | [5 empty] | 2998686 |  |  | Complete | 100%
ROADS | 6239 | Guard- Gitite Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 1498483 |  | C.G.N | [5 empty] | 1498483 |  |  | Complete | 100%
ROADS | 6240 | F-Trading Centre - Keren Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 1998792 |  | C.G.N | [5 empty] | 1998792 |  |  | Complete | 100%
ROADS | 6241 | Gathara ward- Engineer town roads- | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 2998690 |  | C.G.N | [5 empty] | 2998690 |  |  | Complete | 100%
ROADS | 6242 | A.I.C - Hospital road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6243 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 2999850 |  | C.G.N | [5 empty] | 2999850 |  |  | Ongoing
ROADS | 6244 | Chobe - Quarry road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 2999599 |  | C.G.N | [5 empty] | 2999599 |  |  | Complete | 100%
ROADS | 6245 | Makutano- Machua Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 1649131 |  | C.G.N | [5 empty] | 1649131 |  |  | Complete | 100%
ROADS | 6246 | Assorted culverts- Engineer | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1650000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6247 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 2499005.19 |  | C.G.N | [5 empty] | 2499005.19 |  |  | Complete | 100%
ROADS | 6248 | Kiambariki Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6249 | North Kinangop- Kihingo Road in Kiambariki | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6250 | Gathaara - Kwa Shemba Wendani Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 2497472 |  | C.G.N | [5 empty] | 2497472 |  |  | Complete | 100%
ROADS | 6251 | Kitiri Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 994406 |  | C.G.N | [5 empty] | 994406 |  |  | Ongoing
ROADS | 6252 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 1999598 |  | C.G.N | [5 empty] | 1999598 |  |  | Complete | 100%
ROADS | 6253 | Kwa Balam Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6254 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 2996040 |  | C.G.N | [5 empty] | 2996040 |  |  | Ongoing
ROADS | 6255 | Manasseh - Wa Mburu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 1999396 |  | C.G.N | [5 empty] | 1999396 |  |  | Complete | 100%
ROADS | 6256 | Kamirangi - pry school road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1998798 |  | C.G.N | [5 empty] | 1998798 |  |  | Ongoing
ROADS | 6257 | Muchorui - Gacharage road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6258 | Rugara Dam Road- Hianyu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 998850 |  | C.G.N | [5 empty] | 998850 |  |  | Complete | 100%
ROADS | 6259 | Murungaru- Gathioro - Kienjero Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Ongoing
ROADS | 6260 | Spotpatching- Tank- Catholic Murungaru Pry Sch road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6261 | Assorted culverts- Murungaru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6262 | Assorted culverts- Murungaru FY 2020-21 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6263 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 2495949 |  | C.G.N | [5 empty] | 2495949 |  |  | Ongoing
ROADS | 6264 | A.I.C road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 2496215 |  | C.G.N | [5 empty] | 2496215 |  |  | Complete | 100%
ROADS | 6265 | Mountain academy road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 1149030 |  | C.G.N | [5 empty] | 1149030 |  |  | Complete | 100%
ROADS | 6266 | Gathanga- Njoya- Wandaka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1150000 | 1499444 |  | C.G.N | [5 empty] | 1499444 |  |  | Complete | 100%
ROADS | 6267 | Muhuko - Ndimi - Murugo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6268 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 499223 |  | C.G.N | [5 empty] | 499223 |  |  | Complete | 100%
ROADS | 6269 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6270 | Githioro- Gachuha Bridge - KDSP Level II | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 10093520 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6271 | Githioro ward - Jura - Bara-inya road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6272 | Githioro ward - Bara-inya Komu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 1999270 |  | C.G.N | [5 empty] | 1999270 |  |  | Complete | 100%
ROADS | 6273 | Mwangaza Kibe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1999075 |  | C.G.N | [5 empty] | 1999075 |  |  | Complete | 100%
ROADS | 6274 | Ririshwa- Mbui Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 2499882 |  | C.G.N | [5 empty] | 2499882 |  |  | Complete | 100%
ROADS | 6275 | Mwangaza - Muroki road works and drainage | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6276 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 5000000 | 1999829 |  | C.G.N | [5 empty] | 1999829 |  |  | Complete | 100%
ROADS | 6277 | Forest 1 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 999834 |  | C.G.N | [5 empty] | 999834 |  |  | Complete | 100%
ROADS | 6278 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 1998535 |  | C.G.N | [5 empty] | 1998535 |  |  | Complete | 100%
ROADS | 6279 | Miharati Gishagi PCEA Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 4759999 |  | C.G.N | [5 empty] | 4759999 |  |  | Complete | 100%
ROADS | 6280 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 5000000 | 2998322.4 |  | C.G.N | [5 empty] | 2998322.4 |  |  | Complete | 100%
ROADS | 6281 | Ndemi - Kahoro road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 1999606 |  | C.G.N | [5 empty] | 1999606 |  |  | Complete | 100%
ROADS | 6282 | Mubao - Kiroro road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1997434 |  | C.G.N | [5 empty] | 1997434 |  |  | Complete | 100%
ROADS | 6283 | Mahigaini - Kimunya road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 2499679.09 |  | C.G.N | [5 empty] | 2499679.09 |  |  |  | 100%
ROADS | 6284 | Ndemi- Mbekenya Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 2490931 |  | C.G.N | [5 empty] | 2490931 |  |  | Complete | 100%
ROADS | 6285 | Gatondo (Gitei) - Njue road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 1998399 |  | C.G.N | [5 empty] | 1998399 |  |  | Complete | 100%
ROADS | 6286 | Kahiga Road (Kang'aru ) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 999579 |  | C.G.N | [5 empty] | 999579 |  |  | Complete | 100%
ROADS | 6287 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 800000 |  | C.G.N | [5 empty] | 800000 |  |  | Complete | 100%
ROADS | 6288 | Road maintenance using County's in-house Road Machinery & Equipment-Rironi bridge backfilling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 800000 | 6297508 |  | C.G.N | [5 empty] | 6297508 |  |  | Complete | 100%
ROADS | 6289 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 6297508 | 1897147 |  | C.G.N | [5 empty] | 1897147 |  |  | Complete | 100%
ROADS | 6290 | Mwireri Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1900000 | 1994095 |  | C.G.N | [5 empty] | 1994095 |  |  | Complete | 100%
ROADS | 6291 | Withare roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1999446 |  | C.G.N | [5 empty] | 1999446 |  |  | Complete | 100%
ROADS | 6292 | Mwiyumia Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1999800 |  | C.G.N | [5 empty] | 1999800 |  |  | Complete | 100%
ROADS | 6293 | Gichungo Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 2398420.46 |  | C.G.N | [5 empty] | 2398420.46 |  |  | Complete | 100%
ROADS | 6294 | Ngoroba Kiganjo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2400000 | 999470.26 |  | C.G.N | [5 empty] | 999470.26 |  |  | Complete | 100%
ROADS | 6295 | Kaimbaga- Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 1999510 |  | C.G.N | [5 empty] | 1999510 |  |  | Complete | 100%
ROADS | 6296 | Site and service roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6297 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 1499890 |  | C.G.N | [5 empty] | 1499890 |  |  | Complete | 100%
ROADS | 6298 | Mariba- Shalom Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 6299 | Kanduma Bridge Munyeki | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6300 | Kagotho - Muiri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 800000 | 994887 |  | C.G.N | [5 empty] | 994887 |  |  | Complete | 100%
ROADS | 6301 | Munyeki Chief Emily Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 6302 | Wamuyu Mugo (Kagaa) Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 6303 | Kandete Chief Karua Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 500000 | 2370000 |  | C.G.N | [5 empty] | 2370000 |  |  | Ongoing
ROADS | 6304 | Kiburi Maresho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2370000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6305 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 5000000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6306 | Manyatta Umoja road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 999670.2 |  | C.G.N | [5 empty] | 999670.2 |  |  | Complete | 100%
ROADS | 6307 | Mukindu Dispensary Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 999267 |  | C.G.N | [5 empty] | 999267 |  |  | Complete | 100%
ROADS | 6308 | Kahuruko Mathia Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 599820 |  | C.G.N | [5 empty] | 599820 |  |  | Complete | 100%
ROADS | 6309 | Mathia- Gatuhi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 600000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6310 | Ali Road- Rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 999579 |  | C.G.N | [5 empty] | 999579 |  |  | Complete | 100%
ROADS | 6311 | Kabiu -Gachiengo (Mukuru) Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 999289.4 |  | C.G.N | [5 empty] | 999289.4 |  |  | Complete | 100%
ROADS | 6312 | Kairianja Gaturiro ( Mugathika) Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 990135 |  | C.G.N | [5 empty] | 990135 |  |  | Complete | 100%
ROADS | 6313 | Nguva B (Karwigi) Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 699270 |  | C.G.N | [5 empty] | 699270 |  |  | Complete | 100%
ROADS | 6314 | Kianduba (Gachanja) Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 700000 | 1998930 |  | C.G.N | [5 empty] | 1998930 |  |  | Complete | 100%
ROADS | 6315 | Kiriga Kuria Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 499840 |  | C.G.N | [5 empty] | 499840 |  |  | Complete | 100%
ROADS | 6316 | Gacau- wairimu | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 500000 | 499820 |  | C.G.N | [5 empty] | 499820 |  |  | Ongoing
ROADS | 6317 | Mwalimu Gachoka - Kimeria Lane | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 500000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6318 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6319 | Tumaini Gichagi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1800000 | 2499089 |  | C.G.N | [5 empty] | 2499089 |  |  | Complete | 100%
ROADS | 6320 | Rutara Wiyumiririe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 997345.68 |  | C.G.N | [5 empty] | 997345.68 |  |  | Complete | 100%
ROADS | 6321 | Kanjuiri- Karebe road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 1799862.42 |  | C.G.N | [5 empty] | 1799862.42 |  |  | Complete | 100%
ROADS | 6322 | Kanjau- Ndunduri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1800000 | 999729 |  | C.G.N | [5 empty] | 999729 |  |  | Complete | 100%
ROADS | 6323 | Wiyumiririe- Washanga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 1398671 |  | C.G.N | [5 empty] | 1398671 |  |  | Complete | 100%
ROADS | 6324 | Njigaga Road-Gravel Patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1400000 | 1498621 |  | C.G.N | [5 empty] | 1498621 |  |  | Complete | 100%
ROADS | 6325 | Other roadworks- | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 999878.29 |  | C.G.N | [5 empty] | 999878.29 |  |  | Complete | 100%
ROADS | 6326 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 999646.9 |  | C.G.N | [5 empty] | 999646.9 |  |  | Complete | 100%
ROADS | 6327 | Cecily - Kwa Njoroge road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 4100000 |  | C.G.N | [5 empty] | 4100000 |  |  | Complete | 100%
ROADS | 6328 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 5700000 | 3999478 |  | C.G.N | [5 empty] | 3999478 |  |  | Complete | 100%
ROADS | 6329 | Komu, Micharage, matunda and Nyandundo roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6330 | Mirangine- Kihuho Kwa MOA Bridge - KDSP Level II | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4578543 | 3190697 |  | C.G.N | [5 empty] | 3190697 |  |  | Complete | 100%
ROADS | 6331 | Mirangine- Makara, Kibendera Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4995765 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6332 | Mirangine- Gwa Kiongo Centre Upgrade - KDSP Level II | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 5000000 | 1999256 |  | C.G.N | [5 empty] | 1999256 |  |  | Complete | 100%
ROADS | 6333 | Assorted gravel patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | Complete | 100%
ROADS | 6334 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 500000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6335 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 1997376 |  | C.G.N | [5 empty] | 1997376 |  |  | Ongoing
ROADS | 6336 | Assorted culverts- Weru | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6337 | Assorted culverts- Weru- Additional allocation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1800000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6338 | Mzee Gatiba-Manuthia Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 4493515 |  | C.G.N | [5 empty] | 4493515 |  |  | Complete | 100%
ROADS | 6339 | Chakareli-Major Kunyiha- Kahingo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4500000 | 4985153 |  | C.G.N | [5 empty] | 4985153 |  |  | Ongoing
ROADS | 6340 | Sammy Ngozi- Munyu- Kamaina Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 5000000 | 4799119 |  | C.G.N | [5 empty] | 4799119 |  |  | Complete | 100%
ROADS | 6341 | Wa Ndira-Hinga- Karamuki Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4800000 | 3799317 |  | C.G.N | [5 empty] | 3799317 |  |  | Complete | 100%
ROADS | 6342 | Wa Muthii-Canaan-Quarry Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3800000 | 2997882 |  | C.G.N | [5 empty] | 2997882 |  |  | Complete | 100%
ROADS | 6343 | Martin- Wa Mungai- Iria-ini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 3799166 |  | C.G.N | [5 empty] | 3799166 |  |  | Complete | 100%
ROADS | 6344 | Wa Mwathi Matura Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3800000 | 2999898 |  | C.G.N | [5 empty] | 2999898 |  |  | Complete | 100%
ROADS | 6345 | Kagema Corner Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 1498689 |  | C.G.N | [5 empty] | 1498689 |  |  | Complete | 100%
ROADS | 6346 | Wanjurua- Mugoiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 3499742 |  | C.G.N | [5 empty] | 3499742 |  |  | Complete | 100%
ROADS | 6347 | Kamama Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3500000 | 1498638 |  | C.G.N | [5 empty] | 1498638 |  |  | Ongoing
ROADS | 6348 | Oleimutia Kabugi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6349 | Kwa lord Nyandundo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6350 | Ngano barrier road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2700000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6351 | Assorted roadworks using hired machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 5000000 | 1999298 |  | C.G.N | [5 empty] | 1999298 |  |  | Complete | 100%
ROADS | 6352 | Kimama Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1497477 |  | C.G.N | [5 empty] | 1497477 |  |  | Complete | 100%
ROADS | 6353 | Muchemi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 3676000 |  | C.G.N | [5 empty] | 3676000 |  |  | Complete | 100%
ROADS | 6354 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 3797883 |  | C.G.N | [5 empty] | 3797883 |  |  | Complete | 100%
ROADS | 6355 | Upper Gathanji Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3812995 | 3804615 |  | C.G.N | [5 empty] | 3804615 |  |  | Complete | 100%
ROADS | 6356 | Lower Gathanji Road Works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3812995 | 1999800 |  | C.G.N | [5 empty] | 1999800 |  |  | Complete | 100%
ROADS | 6357 | Chameleon - Bidii Gwa Chui Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 3300000 |  | C.G.N | [5 empty] | 3300000 |  |  | Complete | 100%
ROADS | 6358 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3300000 | 2999397 |  | C.G.N | [5 empty] | 2999397 |  |  | Complete | 100%
ROADS | 6359 | Gatimu ward- Assorted grading | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 1799264 |  | C.G.N | [5 empty] | 1799264 |  |  | Complete | 100%
ROADS | 6360 | Wa Mercy Junction Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1800000 | 1799588 |  | C.G.N | [5 empty] | 1799588 |  |  | Complete | 100%
ROADS | 6361 | AHITI Mathanji Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1800000 | 1799599 |  | C.G.N | [5 empty] | 1799599 |  |  | Ongoing
ROADS | 6362 | SDA Muthithe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1800000 | 2999932 |  | C.G.N | [5 empty] | 2999932 |  |  | Ongoing
ROADS | 6363 | Gatimu ward- Assorted gravel patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6364 | Kibathi - Madaraka Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Ongoing
ROADS | 6365 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 3999898 |  | C.G.N | [5 empty] | 3999898 |  |  | Ongoing
ROADS | 6366 | Wise Women road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 1998992 |  | C.G.N | [5 empty] | 1998992 |  |  | Ongoing
ROADS | 6367 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 2999800 |  | C.G.N | [5 empty] | 2999800 |  |  | Complete | 100%
ROADS | 6368 | Grading and compaction of various roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6369 | Kimara B road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 1600000 |  | C.G.N | [5 empty] | 1600000 |  |  | Complete | 100%
ROADS | 6370 | Gwa Kanyora - Witeithie road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1600000 | 3400000 |  | C.G.N | [5 empty] | 3400000 |  |  | Complete | 100%
ROADS | 6371 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3400000 | 1499270 |  | C.G.N | [5 empty] | 1499270 |  |  | Complete | 100%
ROADS | 6372 | Gachemi- Kagori Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 1498278 |  | C.G.N | [5 empty] | 1498278 |  |  | Complete | 100%
ROADS | 6373 | Iregi Kimotho Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 1999956 |  | C.G.N | [5 empty] | 1999956 |  |  | Complete | 100%
ROADS | 6374 | AIC- Munyeki Road- Leshau Pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1997529 |  | C.G.N | [5 empty] | 1997529 |  |  | Ongoing
ROADS | 6375 | Divai Secondary School Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1999461 |  | C.G.N | [5 empty] | 1999461 |  |  | Complete | 100%
ROADS | 6376 | ZU - Murenga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1994988 |  | C.G.N | [5 empty] | 1994988 |  |  | Complete | 100%
ROADS | 6377 | Gwa Kung'u Town Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 6378 | Assorted culverts- Leshau pondo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 6379 | Road maintenance using County's in-house Road Machinery & Equipment-additional allocation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6380 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 3912606 |  | C.G.N | [5 empty] | 3912606 |  |  | Ongoing
ROADS | 6381 | Kiandongoro Gatangi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 1499341 |  | C.G.N | [5 empty] | 1499341 |  |  | Complete | 100%
ROADS | 6382 | Mwangaza - Kaburo - Tafaria | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 1998343 |  | C.G.N | [5 empty] | 1998343 |  |  | Complete | 100%
ROADS | 6383 | Munanda- Mbakuri- Kirathe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 1999339 |  | C.G.N | [5 empty] | 1999339 |  |  | Complete | 100%
ROADS | 6384 | Kiriogo- WaMae Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 3832849 |  | C.G.N | [5 empty] | 3832849 |  |  | Complete | 100%
ROADS | 6385 | Gitare- Kihara Location Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 1899438 |  | C.G.N | [5 empty] | 1899438 |  |  | Complete | 100%
ROADS | 6386 | Murichu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1900000 | 1899456 |  | C.G.N | [5 empty] | 1899456 |  |  | Complete | 100%
ROADS | 6387 | Kahutha Polytechnic Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1900000 | 1897566 |  | C.G.N | [5 empty] | 1897566 |  |  | Complete | 100%
ROADS | 6388 | Munyu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1900000 | 1899874 |  | C.G.N | [5 empty] | 1899874 |  |  | Complete | 100%
ROADS | 6389 | Karandi- Gachobe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1900000 | 1899267 |  | C.G.N | [5 empty] | 1899267 |  |  | Complete | 100%
ROADS | 6390 | Kihara- Karima Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6391 | Kahutha No. 13 Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6392 | Subego Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 1000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6393 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 3499272 |  | C.G.N | [5 empty] | 3499272 |  |  | Complete | 100%
ROADS | 6394 | Shamata - Kaka Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3500000 | 3496259 |  | C.G.N | [5 empty] | 3496259 |  |  | Complete | 100%
ROADS | 6395 | Shamata - Kihuko Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3500000 | 3499064 |  | C.G.N | [5 empty] | 3499064 |  |  | Complete | 100%
ROADS | 6396 | Shamata - Rigathi Gachagua Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3500000 | 3497256 |  | C.G.N | [5 empty] | 3497256 |  |  | Complete | 100%
ROADS | 6397 | Shamata- Aberdare roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6398 | Pesi road Shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6399 | Road works- Jose road shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 3995120 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6400 | Shamata- Road maintenance using County's in-house Road Machinery & Equipment-Additional allocation- Park road(Pesi), Wambuku road and other roads in Shamata | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 2000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6401 | Road maintenance using County's in-house Road Machinery & Equipment | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2022-07-01 | 2023-06-01 |  | 4000000 | 7646980 |  | C.G.N | [5 empty] | 7646980 |  |  | Complete | 100%
ROADS | 6402 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 8000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6403 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1998930.4 |  | C.G.N | [5 empty] | 1998930.4 |  |  | Complete | 100%
ROADS | 6404 | Mutonyora C road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6405 | Kimotho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6406 | Kiambuthi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1999561 |  | C.G.N | [5 empty] | 1999561 |  |  | Complete | 100%
ROADS | 6407 | Konga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1999840.05 |  | C.G.N | [5 empty] | 1999840.05 |  |  | Complete | 100%
ROADS | 6408 | Wa Joseph road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6409 | Magumu - Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2999387 |  | C.G.N | [5 empty] | 2999387 |  |  | Complete | 100%
ROADS | 6410 | Magumu- Mutonyora C- Wa Njeri Road FY 2021-22 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Reallocated
ROADS | 6411 | Chege Mucheru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6412 | Wa Rundia Muiruri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1497554 |  | C.G.N | [5 empty] | 1497554 |  |  | Complete | 100%
ROADS | 6413 | Teachers Conner- Forest Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6414 | Road improvement and maintenance using county in-house roadwork machinery/Hired machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6415 | Nyakio Ward - Masharubu Karangatha Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6416 | Njoguini Bypass Bridge- Nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 10000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6417 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2999090.7 |  | C.G.N | [5 empty] | 2999090.7 |  |  | Complete | 100%
ROADS | 6418 | Wachira Karate Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6419 | Nyambura Nyamanu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 997884.04 |  | C.G.N | [5 empty] | 997884.04 |  |  | Complete | 100%
ROADS | 6420 | Assorted roadwork-Nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | Complete | 100%
ROADS | 6421 | Link Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6422 | Supply of gravel-Nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1999781.4 |  | C.G.N | [5 empty] | 1999781.4 |  |  | Complete | 100%
ROADS | 6423 | Assorted culvert installations- Nyakio | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6424 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6425 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6426 | Githabai Ward- Sheria Road - Ndothua | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 | 3499997.4 |  | C.G.N | [5 empty] | 3499997.4 |  |  | Complete | 100%
ROADS | 6427 | Mukuru-Mukabi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3500000 | 1499775 |  | C.G.N | [5 empty] | 1499775 |  |  | Complete | 100%
ROADS | 6428 | Emilio- mathu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6429 | Stone patching approach and recess- Gwa Senior brigde road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2400000 | 2499882.3 |  | C.G.N | [5 empty] | 2499882.3 |  |  | Complete | 100%
ROADS | 6430 | Kiriungi-Gichagi roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6431 | Ng'ang'a Gatu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6432 | Assorted culverts- Githabai | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6433 | Zakuru-Faithhope road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6434 | Repair of Wanyoike gabions and back filling | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6435 | Githabai - Assorted roads repairs (patching works) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 6417750 |  | C.G.N | [5 empty] | 6417750 |  |  | Complete | 100%
ROADS | 6436 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6437 | Njabini - Kinamba- Kanyenyaini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6438 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2493798 |  | C.G.N | [5 empty] | 2493798 |  |  | Complete | 100%
ROADS | 6439 | Makena Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | paid
ROADS | 6440 | Muigana Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 3999471 |  | C.G.N | [5 empty] | 3999471 |  |  | Complete | 100%
ROADS | 6441 | Assorted roads works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6442 | Shirikisho Road (Phase 2) | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 2498167.68 |  | C.G.N | [5 empty] | 2498167.68 |  |  | Complete | 100%
ROADS | 6443 | Line Moja Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6444 | Churiri Road- Spot patching | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 996744 |  | C.G.N | [5 empty] | 996744 |  |  | Complete | 100%
ROADS | 6445 | Kanyanjua/Ngorongo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6446 | Kiandege road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1399456 |  | C.G.N | [5 empty] | 1399456 |  |  | Complete | 100%
ROADS | 6447 | Pilot Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6448 | Spotpatching- Coloboise Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 999396 |  | C.G.N | [5 empty] | 999396 |  |  | Complete | 100%
ROADS | 6449 | Njabini Kiburu - Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6450 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6451 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 4499500.5 |  | C.G.N | [5 empty] | 4499500.5 |  |  | Complete | 100%
ROADS | 6452 | Ngugi Muno Norfolk road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 800000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6453 | Mwinjoyo Habu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2600000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6454 | Gichuki - Wanjau road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1100000 | 3499701.6 |  | C.G.N | [5 empty] | 3499701.6 |  |  | Complete | 100%
ROADS | 6455 | Muchema AIPCEA road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3500000 | 2799163.56 |  | C.G.N | [5 empty] | 2799163.56 |  |  | Complete | 100%
ROADS | 6456 | Nyanjui road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6457 | Kinja pry Njuri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6458 | Gathaara - Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1207475 | 4499601 |  | C.G.N | [5 empty] | 4499601 |  |  | Complete | 100%
ROADS | 6459 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4500000 | 3138546 |  | C.G.N | [5 empty] | 3138546 |  |  | Complete | 100%
ROADS | 6460 | Other road works-Hire of machinery - Engineer | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6461 | Ciondo- Chobe bridge Engineer | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4900000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6462 | Engineer Ward - Matundura Primary Sch Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 | 3659760 |  | C.G.N | [5 empty] | 3659760 |  |  | Complete | 100%
ROADS | 6463 | Brother M- Chobe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3700000 | 3993237 |  | C.G.N | [5 empty] | 3993237 |  |  | Complete | 100%
ROADS | 6464 | Wakarenjo Kigogo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4000000 | 3799843.21 |  | C.G.N | [5 empty] | 3799843.21 |  |  | Complete | 100%
ROADS | 6465 | Gatitu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3800000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6466 | Munanda-ini Kijiko Fourteen Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6467 | Forester Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6468 | Supply of quarry materials- Engineer | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 2799800 |  | C.G.N | [5 empty] | 2799800 |  |  | Complete | 100%
ROADS | 6469 | Floodlights installation 8 No.13M floodlights-Washington,Ciondo A and B, Citi, Soweto, Ha-Bei, Matundura and Thindi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2800000 | 3959436 |  | C.G.N | [5 empty] | 3959436 |  |  | Complete | 100%
ROADS | 6470 | Bishop Kairu -Mwendandu sec school road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4000000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | Complete | 100%
ROADS | 6471 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6472 | North Kinangop Ward -Karemeri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6473 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1999731.42 |  | C.G.N | [5 empty] | 1999731.42 |  |  | Complete | 100%
ROADS | 6474 | Kanja road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1996996.8 |  | C.G.N | [5 empty] | 1996996.8 |  |  | Complete | 100%
ROADS | 6475 | Assorted roadworks- Kiambariki | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 3498220 |  | C.G.N | [5 empty] | 3498220 |  |  | Complete | 100%
ROADS | 6476 | Assorted culverts- North Kinangop | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6477 | Assorted roadworks- Kitiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1997930.1 |  | C.G.N | [5 empty] | 1997930.1 |  |  | Complete | 100%
ROADS | 6478 | Assorted roadworks- Nandarasi | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2999056 |  | C.G.N | [5 empty] | 2999056 |  |  | Complete | 100%
ROADS | 6479 | Assorted Roadworks - Kitogo | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | Complete | 100%
ROADS | 6480 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6481 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6482 | Mburu T - Zacharia road Kahuho | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 3999647.4 |  | C.G.N | [5 empty] | 3999647.4 |  |  | Complete | 100%
ROADS | 6483 | Gatumbiriri road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6484 | Tank Wangunini - Wakaba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6485 | Githogororo stadium road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6486 | Murungaru-Assorted Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1995244.9 |  | C.G.N | [5 empty] | 1995244.9 |  |  | Complete | 100%
ROADS | 6487 | Wangunini- Kabeeri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2998629.4 |  | C.G.N | [5 empty] | 2998629.4 |  |  | Complete | 100%
ROADS | 6488 | KKY Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6489 | Spot patching Musari-Migwi- Githabai Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 3098036.82 |  | C.G.N | [5 empty] | 3098036.82 |  |  | Complete | 100%
ROADS | 6490 | Kahigi - Mathara road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1100000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6491 | John Boro-Migwi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6492 | Kang'ethe Ndeo farm road Kihumbu area | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6493 | Wanjiku Kang'ethe Ndarachaini road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1499850 |  | C.G.N | [5 empty] | 1499850 |  |  | Complete | 100%
ROADS | 6494 | Assorted culverts- Murungaru FY 2020-21 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | Complete | 100%
ROADS | 6495 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6496 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 3999082 |  | C.G.N | [5 empty] | 3999082 |  |  | Complete | 100%
ROADS | 6497 | Kagongo - John B road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6498 | Matangi - Githae - Kwa Matu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 1198670 |  | C.G.N | [5 empty] | 1198670 |  |  | Complete | 100%
ROADS | 6499 | No. 15 road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1200000 | 1999726.5 |  | C.G.N | [5 empty] | 1999726.5 |  |  | Complete | 100%
ROADS | 6500 | Murachia - Wandaka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2799120 |  | C.G.N | [5 empty] | 2799120 |  |  | Complete | 100%
ROADS | 6501 | Gwakanjora road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 800000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6502 | Geta - Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6503 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6504 | Githioro Ward - Ngomongo Road Ririchwa | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6505 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 3499064 |  | C.G.N | [5 empty] | 3499064 |  |  | Complete | 100%
ROADS | 6506 | Kiambi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6507 | Muriuki road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 2999860 |  | C.G.N | [5 empty] | 2999860 |  |  | Complete | 100%
ROADS | 6508 | Kangondi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6509 | Kanyiri Road Ririshwa | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6510 | KAG Jura Road extension | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1400000 | 1999875.2 |  | C.G.N | [5 empty] | 1999875.2 |  |  | Complete | 100%
ROADS | 6511 | Gathiriga-Gachuha road strip- concrete slab | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6512 | Githioro -Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6513 | Wa Lydia- Wa Njambi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6514 | Mwangaza - Wa Rugu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 | 1999922 |  | C.G.N | [5 empty] | 1999922 |  |  | Complete | 100%
ROADS | 6515 | Rusinga Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6516 | Gathiriga Road & Tigoni Migaa Road Maintenance | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6517 | Kipipiri Sch School road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6518 | Romba- Kirima Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6519 | Githige- Chobe Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2949000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6520 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6521 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 3999571 |  | C.G.N | [5 empty] | 3999571 |  |  | Complete | 100%
ROADS | 6522 | Kabati-Umoja KG Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6523 | Kabati- Umoja KG -Wanjau Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6524 | Rutumo Primary Sch Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6525 | Assorted culverts- Kipipiri | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6526 | Wanjohi ward -Githunguri- Wangige Ngando Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 | 1199150 |  | C.G.N | [5 empty] | 1199150 |  |  | Complete | 100%
ROADS | 6527 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6528 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2499708 |  | C.G.N | [5 empty] | 2499708 |  |  | Complete | 100%
ROADS | 6529 | Goko Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 | 2499321 |  | C.G.N | [5 empty] | 2499321 |  |  | Complete | 100%
ROADS | 6530 | Kahoro Michore Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 | 2497311 |  | C.G.N | [5 empty] | 2497311 |  |  | Complete | 100%
ROADS | 6531 | Mubau- Thing'oru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6532 | Mwireri - Kimuru Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6533 | Ngunyi- Kirogi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2300000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6534 | Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | Complete | 100%
ROADS | 6535 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6536 | Mathathi Bridge Repair- Kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 100000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6537 | Kaimbaga ward- Kieni Quarry Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6538 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2998488.5 |  | C.G.N | [5 empty] | 2998488.5 |  |  | Complete | 100%
ROADS | 6539 | Kieni roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6540 | Kihurure roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6541 | Junction - Kieni roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6542 | Kiganjo Quarry roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6543 | Kamande Roads -Kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4980000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6544 | Gachagi Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6545 | Thitai roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6546 | Kandutura roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1400000 |  | C.G.N | [5 empty] | 1400000 |  |  | Complete | 100%
ROADS | 6547 | Kaimbaga -Assorted Culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6548 | Rumathi Roads - Kaimbaga | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4999500 | 4225300 |  | C.G.N | [5 empty] | 4225300 |  |  | Complete | 100%
ROADS | 6549 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6550 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2198972 |  | C.G.N | [5 empty] | 2198972 |  |  | Complete | 100%
ROADS | 6551 | Karau ward- Emilly-WaMbugichi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6552 | Karau Ward- Kanduma Bridge | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 5000000 | 1497482 |  | C.G.N | [5 empty] | 1497482 |  |  | Complete | 100%
ROADS | 6553 | Kirimaini Nyairoko road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 2499784.4 |  | C.G.N | [5 empty] | 2499784.4 |  |  | Complete | 100%
ROADS | 6554 | Karugutu Gwa kung'u road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6555 | Jawakwe Kagaa road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1030000 |  | C.G.N | [5 empty] | 1030000 |  |  | Complete | 100%
ROADS | 6556 | Munyeki- Kwa Mashua Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1039900 | 2369617 |  | C.G.N | [5 empty] | 2369617 |  |  | Complete | 100%
ROADS | 6557 | Kiburi maresho road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2370000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6558 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6559 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1997721 |  | C.G.N | [5 empty] | 1997721 |  |  | Complete | 100%
ROADS | 6560 | Wami road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2999976.4 |  | C.G.N | [5 empty] | 2999976.4 |  |  | Complete | 100%
ROADS | 6561 | Gichinga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 1199169.4 |  | C.G.N | [5 empty] | 1199169.4 |  |  | Complete | 100%
ROADS | 6562 | Kuria kairu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2496577 |  | C.G.N | [5 empty] | 2496577 |  |  | Complete | 100%
ROADS | 6563 | Githunguri munanda road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6564 | Mukugi - Thiga road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 500000 | 999563 |  | C.G.N | [5 empty] | 999563 |  |  | Complete | 100%
ROADS | 6565 | Ali Road- Rurii | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1500000 |  | C.G.N | [5 empty] | 1500000 |  |  | Complete | 100%
ROADS | 6566 | Manyatta umoja road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6567 | Kanjuiri Ward- Tumaini Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 | 4225300 |  | C.G.N | [5 empty] | 4225300 |  |  | Complete | 100%
ROADS | 6568 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6569 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1999286.7 |  | C.G.N | [5 empty] | 1999286.7 |  |  | Complete | 100%
ROADS | 6570 | Uhuru ACK Church road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 3491414.1 |  | C.G.N | [5 empty] | 3491414.1 |  |  | Complete | 100%
ROADS | 6571 | Harambee Primary Sch road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6572 | Rutara- Dairy road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 2298723 |  | C.G.N | [5 empty] | 2298723 |  |  | Complete | 100%
ROADS | 6573 | Kang'athia road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1800000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6574 | Kanjuiri Range - Assorted culvert installation | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 500000 | 2199378 |  | C.G.N | [5 empty] | 2199378 |  |  | Complete | 100%
ROADS | 6575 | Mirangine Ward- Kamuyu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6576 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 8000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6577 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6578 | Assorted culverts- Mirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6579 | Bara Njeru - Kamunge Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6580 | Kangui Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6581 | Assorted bush clearing and drainage works- Mirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6582 | Assorted gravel patching- Mirangine | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6583 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 5500000 | 2199750 |  | C.G.N | [5 empty] | 2199750 |  |  | Complete | 100%
ROADS | 6584 | Weru ward -Completion of Kimuri- Matura Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6585 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 3999583 |  | C.G.N | [5 empty] | 3999583 |  |  | Complete | 100%
ROADS | 6586 | Junction- Gitira Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4000000 | 2997015 |  | C.G.N | [5 empty] | 2997015 |  |  | Complete | 100%
ROADS | 6587 | Michengi- Wa Gathua -Quarry Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 4999704.2 |  | C.G.N | [5 empty] | 4999704.2 |  |  | Complete | 100%
ROADS | 6588 | Nduati - WaGakenia Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 5000000 | 4999867 |  | C.G.N | [5 empty] | 4999867 |  |  | Complete | 100%
ROADS | 6589 | Culverts and Drainage- Weru Ward | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 5000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6590 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 | 2199523 |  | C.G.N | [5 empty] | 2199523 |  |  | Complete | 100%
ROADS | 6591 | Charagita Ward - Mathenge River Drive Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6592 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6593 | Chaina Road- Improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 8000000 | 2999862 |  | C.G.N | [5 empty] | 2999862 |  |  | Complete | 100%
ROADS | 6594 | Grading and compacting of assorted roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 2999182 |  | C.G.N | [5 empty] | 2999182 |  |  | Complete | 100%
ROADS | 6595 | T - Rose Kabugi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 1997343.6 |  | C.G.N | [5 empty] | 1997343.6 |  |  | Complete | 100%
ROADS | 6596 | Nyairoko Kibiro road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2999718 |  | C.G.N | [5 empty] | 2999718 |  |  | Complete | 100%
ROADS | 6597 | Line Moja - Wagiathi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 1499698.8 |  | C.G.N | [5 empty] | 1499698.8 |  |  | Complete | 100%
ROADS | 6598 | Assorted culverts- Charagita | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6599 | Mwisho wa Rami- Gordan Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1999880.8 |  | C.G.N | [5 empty] | 1999880.8 |  |  | Complete | 100%
ROADS | 6600 | Ruiru - St. Susan Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6601 | Gachuiri Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6602 | Junction-Kona Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3100000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6603 | Maimba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2499346 |  | C.G.N | [5 empty] | 2499346 |  |  | Complete | 100%
ROADS | 6604 | Kwa Lord Nyandundo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6605 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6606 | Other road works | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6607 | Kwa-biathi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6608 | Boiman centre roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 0 |  | C.G.N | [5 empty] | 0 |  |  | Complete | 100%
ROADS | 6609 | Gathanji Ward - Obed- Kimathi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6610 | Muthee road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6611 | Mahua road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 3998175.6 |  | C.G.N | [5 empty] | 3998175.6 |  |  | Complete | 100%
ROADS | 6612 | Mung'etho Njoro junction road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6613 | Bahati IDP road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6614 | Fetima Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1999776.3 |  | C.G.N | [5 empty] | 1999776.3 |  |  | Complete | 100%
ROADS | 6615 | Gituamba road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6616 | Kamugunda Smith road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1495810 |  | C.G.N | [5 empty] | 1495810 |  |  | Complete | 100%
ROADS | 6617 | Road 4 ACK | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6618 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6619 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 3984624.9 |  | C.G.N | [5 empty] | 3984624.9 |  |  | Complete | 100%
ROADS | 6620 | Gikingi - Ngomongo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4000000 | 2988447 |  | C.G.N | [5 empty] | 2988447 |  |  | Complete | 100%
ROADS | 6621 | Gatimu -Suera Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6622 | Madaraka road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6623 | Kanguo Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2500000 | 1988286 |  | C.G.N | [5 empty] | 1988286 |  |  | Complete | 100%
ROADS | 6624 | Gatimu primary road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6625 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6626 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2199658.59 |  | C.G.N | [5 empty] | 2199658.59 |  |  | Complete | 100%
ROADS | 6627 | Kiriita Ward - Mugiko -Kwa Dam Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 | 3498600 |  | C.G.N | [5 empty] | 3498600 |  |  | Complete | 100%
ROADS | 6628 | School - Tabby Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6629 | Blackie - Main Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 3499416 |  | C.G.N | [5 empty] | 3499416 |  |  | Complete | 100%
ROADS | 6630 | Yvonne Junction Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3500000 | 2999679.24 |  | C.G.N | [5 empty] | 2999679.24 |  |  | Complete | 100%
ROADS | 6631 | Kamau -Kanyutu Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6632 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6633 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 2999749 |  | C.G.N | [5 empty] | 2999749 |  |  | Complete | 100%
ROADS | 6634 | Kihingo PCEA road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 2999800 |  | C.G.N | [5 empty] | 2999800 |  |  | Complete | 100%
ROADS | 6635 | Kabuuri Kangeche road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 3000000 | 1999149 |  | C.G.N | [5 empty] | 1999149 |  |  | Complete | 100%
ROADS | 6636 | Shauri Itangi ini road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1299265.8 |  | C.G.N | [5 empty] | 1299265.8 |  |  | Complete | 100%
ROADS | 6637 | Huruma road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1300000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | Complete | 100%
ROADS | 6638 | Gatero road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 | 1399072.8 |  | C.G.N | [5 empty] | 1399072.8 |  |  | Complete | 100%
ROADS | 6639 | Kwa Ngurinu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6640 | Leshau pondo- Assorted culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6641 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 6000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6642 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6643 | Suguroi road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 1999996 |  | C.G.N | [5 empty] | 1999996 |  |  | Complete | 100%
ROADS | 6644 | Zaire road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 3999879 |  | C.G.N | [5 empty] | 3999879 |  |  | Complete | 100%
ROADS | 6645 | Kiriogo road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4000000 | 1999592 |  | C.G.N | [5 empty] | 1999592 |  |  | Complete | 100%
ROADS | 6646 | Murichu road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 | 1999546.8 |  | C.G.N | [5 empty] | 1999546.8 |  |  | Complete | 100%
ROADS | 6647 | Mwangaza road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6648 | Mugumoini Goodhope Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 1415300 |  | C.G.N | [5 empty] | 1415300 |  |  | Complete | 100%
ROADS | 6649 | Kahutha No. 13 Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6650 | Subego Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 1500000 | 6352600 |  | C.G.N | [5 empty] | 6352600 |  |  | Complete | 100%
ROADS | 6651 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 5400000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6652 | Road improvement and maintenance using county in-house roadwork machinery- supply of gravel | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6653 | Kianda Roads and culverts | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4500000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6654 | Karima-ini roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 5000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6655 | Junction Roads | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 5000000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6656 | Muhiriga village roads Shamata FY 2022-23 | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 4000000 | 0 |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6657 | Shamata ward- Rigathi Road | ROAD WORKS |  | ROAD WORKS | [5 empty] | 2023-07-01 | 2024-06-01 |  | 2200000 |  |  | C.G.N | [8 empty] | Complete | 100%
ROADS | 6658 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6659 | Road improvement and maintenance using hired machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 2250000 | 2250000 |  | C.G.N | [5 empty] | 2250000 |  |  | complete | 100
ROADS | 6660 | Supply of gravel | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 750000 | 112989 |  | C.G.N | [5 empty] | 112989 |  |  | ongoing | 15
ROADS | 6661 | Kinyanjui Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 1917182 | 1917182 |  | C.G.N | [5 empty] | 1917182 |  |  | complete | 100
ROADS | 6662 | Muthama Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 1950487 | 1950487 |  | C.G.N | [5 empty] | 1950487 |  |  | complete | 100
ROADS | 6663 | Johnson Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 1951921 | 1951921 |  | C.G.N | [5 empty] | 1951921 |  |  | complete | 100
ROADS | 6664 | Michael-Njane Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 2600000 | 2579357 |  | C.G.N | [5 empty] | 2579357 |  |  | complete | 100
ROADS | 6665 | Michael- Munoru Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 3600000 |  |  | C.G.N | [8 empty] | not done | -
ROADS | 6666 | Guest-inn and Church of God culvert installation | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 558535 | 558535 |  | C.G.N | [5 empty] | 558535 |  |  | complete | 100
ROADS | 6667 | Road improvement and maintenance using county in-house roadwork machinery/Hired machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6668 | Road improvement and maintenance using hired machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6669 | Supply of gravel | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 1200000 | 1199100 |  | C.G.N | [5 empty] | 1199100 |  |  | complete | 100
ROADS | 6670 | Assorted roadworks and gravel patching | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2559138 |  | C.G.N | [5 empty] | 2559138 |  |  | ongoing | 85
ROADS | 6671 | Nyakio ward - Rurii catholic road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 907960 |  | C.G.N | [5 empty] | 907960 |  |  | complete | 100
ROADS | 6672 | Assorted culverts | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 1896871 | 1896871 |  | C.G.N | [5 empty] | 1896871 |  |  | complete | 100
ROADS | 6673 | Additional assorted culverts- Nyakio | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | - |  | C.G.N | [5 empty] | - |  |  | not done | -
ROADS | 6674 | Assorted bush clearing/Drainage works | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 986055 |  | C.G.N | [5 empty] | 986055 |  |  | complete | 100
ROADS | 6675 | Rwanyambo Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 1857996 | 1857996 |  | C.G.N | [5 empty] | 1857996 |  |  | complete | 100
ROADS | 6676 | Yaang'a Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 1859107 | 1859107 |  | C.G.N | [5 empty] | 1859107 |  |  | complete | 100
ROADS | 6677 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2995700 |  | C.G.N | [5 empty] | 2995700 |  |  | complete | 100
ROADS | 6678 | Road improvement and maintenance using hired machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 4500000 | 4500000 |  | C.G.N | [5 empty] | 4500000 |  |  | complete | 100
ROADS | 6679 | Supply of gravel-Githabai | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100
ROADS | 6680 | Mwalimu Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 1500000 | - |  | C.G.N | [5 empty] | - |  |  | ongoing | 30
ROADS | 6681 | Gatinga Mukuru Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 3413292 | 3413292 |  | C.G.N | [5 empty] | 3413292 |  |  | complete | 100
ROADS | 6682 | Ngoyo- Wa Elijah Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 3896075 | 3896075 |  | C.G.N | [5 empty] | 3896075 |  |  | complete | 100
ROADS | 6683 | Kiyo Pry Sch Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 1292295 | 1292295 |  | C.G.N | [5 empty] | 1292295 |  |  | complete | 100
ROADS | 6684 | Mathu- Kwa Haraka Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 1295979 | 1295979 |  | C.G.N | [5 empty] | 1295979 |  |  | complete | 100
ROADS | 6685 | Central -Mijikenda Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 1883509 | 1883509 |  | C.G.N | [5 empty] | 1883509 |  |  | complete | 100
ROADS | 6686 | Ngarachu Kiyo Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 1394785 | 1394785 |  | C.G.N | [5 empty] | 1394785 |  |  | complete | 100
ROADS | 6687 | Supply and installation of assorted culverts | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Githabai |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 900480 |  | C.G.N | [5 empty] | 900480 |  |  | complete | 100
ROADS | 6688 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 3998437 |  | C.G.N | [5 empty] | 3998437 |  |  | complete | 100
ROADS | 6689 | Road improvement and maintenance using hired machinery - Njabini Ward | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2999310 |  | C.G.N | [5 empty] | 2999310 |  |  | complete | 100
ROADS | 6690 | Supply of gravel - Njabini ward | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100
ROADS | 6691 | Muigai- Gatina Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 827922 | 827922 |  | C.G.N | [5 empty] | 827922 |  |  | complete | 100
ROADS | 6692 | Kamwere Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 895688 | 895688 |  | C.G.N | [5 empty] | 895688 |  |  | complete | 100
ROADS | 6693 | Yaang'a Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1974651 | 1974651 |  | C.G.N | [5 empty] | 1974651 |  |  | complete | 100
ROADS | 6694 | Dr. Mathenge Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 901577 |  | C.G.N | [5 empty] | 901577 |  |  | complete | 100
ROADS | 6695 | Kiahiti- Githinjiro Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1840240 | 1840240 |  | C.G.N | [5 empty] | 1840240 |  |  | complete | 100
ROADS | 6696 | Assorted roadworks-Njabini | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 2985409 | 2985409 |  | C.G.N | [5 empty] | 2985409 |  |  | complete | 100
ROADS | 6697 | Assorted spot patching- Njabini | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 2976853 | 2976853 |  | C.G.N | [5 empty] | 2976853 |  |  | complete | 100
ROADS | 6698 | Assorted culverts -Njabini | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1704981 | 1704981 |  | C.G.N | [5 empty] | 1704981 |  |  | complete | 100
ROADS | 6699 | Construction of 1No. Boda boda shed | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 400000 | - |  | C.G.N | [5 empty] | - |  |  | ongoing | 10
ROADS | 6700 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Gathaara |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6701 | Road improvement and maintenance using hired Machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Gathaara |  |  | 2024-07-01 | 2025-07-01 |  | 7500000 |  |  | C.G.N | [8 empty] | ongoing | 10
ROADS | 6702 | Fuel to support road improvement and maintenance using county in-house roadwork machinery- Gathaara | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Gathaara |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100
ROADS | 6703 | Supply of Gravel | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Gathaara |  |  | 2024-07-01 | 2025-07-01 |  | 3500000 | 3500000 |  | C.G.N | [5 empty] | 3500000 |  |  | complete | 100
ROADS | 6704 | Kamau- Mwangi Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Gathaara |  |  | 2024-07-01 | 2025-07-01 |  | 3315684 | 3315683 |  | C.G.N | [5 empty] | 3315683 |  |  | complete | 100
ROADS | 6705 | Kihoto Maina Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Gathaara |  |  | 2024-07-01 | 2025-07-01 |  | 1788691 | 1788691 |  | C.G.N | [5 empty] | 1788691 |  |  | complete | 100
ROADS | 6706 | Assorted culverts and gabbions Gathaara Ward | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Gathaara |  |  | 2024-07-01 | 2025-07-01 |  | 1598433 | 1598433 |  | C.G.N | [5 empty] | 1598433 |  |  | complete | 100
ROADS | 6707 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2999400 |  | C.G.N | [5 empty] | 2999400 |  |  | complete | 100
ROADS | 6708 | Supply of gravel | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6709 | Road improvement and maintenance using hired Machinery- Mutiini- Ciondo area | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 11500000 | 11500000 |  | C.G.N | [5 empty] | 11500000 |  |  | complete | 100
ROADS | 6710 | Hire of Excavator/roller& grader- Mutiini, Ciondo and Chobe area | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 3400000 | 3400000 |  | C.G.N | [5 empty] | 3400000 |  |  | complete | 100
ROADS | 6711 | Supply of gravel- Mutiini, Ciondo and Chobe area | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 6000000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | complete | 100
ROADS | 6712 | Waikua- Manyatta-Kanyoi Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 1847896 | 1847896 |  | C.G.N | [5 empty] | 1847896 |  |  | complete | 100
ROADS | 6713 | Moses Bridge | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | - |  | C.G.N | [5 empty] | - |  |  | complete | -
ROADS | 6714 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | North Kinangop |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6715 | Road improvement and maintenance using hired machinery (Lorries and other machinery) | ROAD WORKS |  | ROAD WORKS |  | Kinangop | North Kinangop |  |  | 2024-07-01 | 2025-07-01 |  | 5900000 |  |  | C.G.N | [8 empty] | ongoing | 10
ROADS | 6716 | Supply of Gravel | ROAD WORKS |  | ROAD WORKS |  | Kinangop | North Kinangop |  |  | 2024-07-01 | 2025-07-01 |  | 2100000 | 2100000 |  | C.G.N | [5 empty] | 2100000 |  |  | complete | 100
ROADS | 6717 | Kiria Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | North Kinangop |  |  | 2024-07-01 | 2025-07-01 |  | 2577550 | 2577550 |  | C.G.N | [5 empty] | 2577550 |  |  | complete | 100
ROADS | 6718 | Kambi-Mbau Roads | ROAD WORKS |  | ROAD WORKS |  | Kinangop | North Kinangop |  |  | 2024-07-01 | 2025-07-01 |  | 1737764 | 1422425 |  | C.G.N | [5 empty] | 1422425 |  |  | complete | 82
ROADS | 6719 | Kiambariki Roads | ROAD WORKS |  | ROAD WORKS |  | Kinangop | North Kinangop |  |  | 2024-07-01 | 2025-07-01 |  | 1786933 | 1786933 |  | C.G.N | [5 empty] | 1786933 |  |  | complete | 100
ROADS | 6720 | Kiandege Roads | ROAD WORKS |  | ROAD WORKS |  | Kinangop | North Kinangop |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 1789114 |  | C.G.N | [5 empty] | 1789114 |  |  | complete | 89
ROADS | 6721 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 6000000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | complete | 100
ROADS | 6722 | Road improvement and maintenance under Hire Machinery | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6723 | Supply of Gravel | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100
ROADS | 6724 | AIC Mwihoti road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 |  |  | C.G.N | [8 empty] | complete | -
ROADS | 6725 | Kirathimo pry - Munene Kabaru road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 883144 | 883144 |  | C.G.N | [5 empty] | 883144 |  |  | complete | 100
ROADS | 6726 | Wanyiri Wambugu road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 |  |  | C.G.N | [8 empty] | not done | -
ROADS | 6727 | Kamirangi road concrete | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 859163 | 859163 |  | C.G.N | [5 empty] | 859163 |  |  | complete | 100
ROADS | 6728 | Mwalimu Gathumbi (Mkungi) road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 881912 | 881912 |  | C.G.N | [5 empty] | 881912 |  |  | complete | 100
ROADS | 6729 | Mwangi Chotora road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 803283 | 803283 |  | C.G.N | [5 empty] | 803283 |  |  | complete | 100
ROADS | 6730 | Murungaru ward - Shamata (Mikaro) road concrete | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 999677 |  | C.G.N | [5 empty] | 999677 |  |  | complete | 100
ROADS | 6731 | Assorted culverts | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 1454703 | 1454703 |  | C.G.N | [5 empty] | 1454703 |  |  | complete | 100
ROADS | 6732 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Geta |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6733 | Road improvement and maintenance using hired machinery | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Geta |  |  | 2024-07-01 | 2025-07-01 |  | 4750000 | 4750000 |  | C.G.N | [5 empty] | 4750000 |  |  | complete | 100
ROADS | 6734 | Supply of gravel- Geta Ward | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Geta |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100
ROADS | 6735 | Fuel to support road improvement and maintenance using county in-house roadwork machinery- Geta | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Geta |  |  | 2024-07-01 | 2025-07-01 |  | 1307007 | 1307007 |  | C.G.N | [5 empty] | 1307007 |  |  | complete | 100
ROADS | 6736 | Road No. 15 (lower) | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Geta |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 |  |  | C.G.N | [8 empty] | complete | -
ROADS | 6737 | Rewel- Waiyego-Kariithi Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Geta |  |  | 2024-07-01 | 2025-07-01 |  | 2342800 | 2342800 |  | C.G.N | [5 empty] | 2342800 |  |  | complete | 100
ROADS | 6738 | Kagongo Sec - Gichoya Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Geta |  |  | 2024-07-01 | 2025-07-01 |  | 2372530 | 2372530 |  | C.G.N | [5 empty] | 2372530 |  |  | complete | 100
ROADS | 6739 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6740 | Road improvement and maintenance under Hire Machinery | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2997125 |  | C.G.N | [5 empty] | 2997125 |  |  | complete | 100
ROADS | 6741 | Supply of Gravel | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100
ROADS | 6742 | Booster Road Turasha | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 1900000 | 1900000 |  | C.G.N | [5 empty] | 1900000 |  |  | complete | 100
ROADS | 6743 | Dry Mutamaiyu Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 2795971 | 2795971 |  | C.G.N | [5 empty] | 2795971 |  |  | complete | 100
ROADS | 6744 | Wa Mangu Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 2399244 | 2355497 |  | C.G.N | [5 empty] | 2355497 |  |  | complete | 98
ROADS | 6745 | Joe Kuria Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 1891119 | 1891119 |  | C.G.N | [5 empty] | 1891119 |  |  | complete | 100
ROADS | 6746 | Mumui Church Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 2997125 | 2997125 |  | C.G.N | [5 empty] | 2997125 |  |  | complete | 100
ROADS | 6747 | Kinja Road Mumui | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 1478361 | 1478361 |  | C.G.N | [5 empty] | 1478361 |  |  | complete | 100
ROADS | 6748 | Joseph Road Mumui | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 1388548 | 1388548 |  | C.G.N | [5 empty] | 1388548 |  |  | complete | 100
ROADS | 6749 | Bethiel Gakuru road Mumui | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2926283 |  | C.G.N | [5 empty] | 2926283 |  |  | complete | 98
ROADS | 6750 | Gachuha Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 2500000 |  |  | C.G.N | [8 empty] | complete
ROADS | 6751 | Assorted culverts | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Githioro |  |  | 2024-07-01 | 2025-07-01 |  | 1500000 | 1450531 |  | C.G.N | [5 empty] | 1450531 |  |  | complete | 97
ROADS | 6752 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Kipipiri |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6753 | Mzee Wanjema Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Kipipiri |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | - |  | C.G.N | [5 empty] | - |  |  | ongoing | -
ROADS | 6754 | Wa Beth Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Kipipiri |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 1930230 |  | C.G.N | [5 empty] | 1930230 |  |  | complete | 97
ROADS | 6755 | Lereshwa Secondary Sch Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Kipipiri |  |  | 2024-07-01 | 2025-07-01 |  | 1845674 | 1845674 |  | C.G.N | [5 empty] | 1845674 |  |  | complete | 100
ROADS | 6756 | Chief Mathenge Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Kipipiri |  |  | 2024-07-01 | 2025-07-01 |  | 2451215 | 2451215 |  | C.G.N | [5 empty] | 2451215 |  |  | complete | 100
ROADS | 6757 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Wanjohi ward |  |  | 2024-07-01 | 2025-07-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | complete | 100
ROADS | 6758 | Road improvement and maintenance using hire machinery | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Wanjohi ward |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100
ROADS | 6759 | Supply of gravel- Wanjohi | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Wanjohi ward |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | ongoing | 70
ROADS | 6760 | Njibiini Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Wanjohi ward |  |  | 2024-07-01 | 2025-07-01 |  | 1700000 | 1547100 |  | C.G.N | [5 empty] | 1547100 |  |  | complete | 91
ROADS | 6761 | Munyaga Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Wanjohi ward |  |  | 2024-07-01 | 2025-07-01 |  | 2993466 | 2993466 |  | C.G.N | [5 empty] | 2993466 |  |  | complete | 100
ROADS | 6762 | Cancer Centre-Ngarega Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Wanjohi ward |  |  | 2024-07-01 | 2025-07-01 |  | 2992245 | 2992246 |  | C.G.N | [5 empty] | 2992246 |  |  | complete | 100
ROADS | 6763 | Gichigirira Michore Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Wanjohi ward |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 625000 |  | C.G.N | [5 empty] | 625000 |  |  | ongoing | 31
ROADS | 6764 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 5700000 | 5700000 |  | C.G.N | [5 empty] | 5700000 |  |  | complete | 100
ROADS | 6765 | Road improvement and maintenance using hire machinery | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6766 | Supply of gravel-Kaimbaga | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100
ROADS | 6767 | Mwireri road - Ndemi road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 1890158 | 1890158 |  | C.G.N | [5 empty] | 1890158 |  |  | complete | 100
ROADS | 6768 | Mahinga road - Olkalou road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 1877300 | 1877300 |  | C.G.N | [5 empty] | 1877300 |  |  | complete | 100
ROADS | 6769 | Mwireri - Marubani road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 1893240 | 1893240 |  | C.G.N | [5 empty] | 1893240 |  |  | complete | 100
ROADS | 6770 | Kariamu road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 899483 |  | C.G.N | [5 empty] | 899483 |  |  | complete | 100
ROADS | 6771 | Rumathi road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 977660 |  | C.G.N | [5 empty] | 977660 |  |  | complete | 100
ROADS | 6772 | Kiganjo Dispensary PCEA Road - Culvert and Drainage | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 500000 | 381500 |  | C.G.N | [5 empty] | 381500 |  |  | no done | 76
ROADS | 6773 | Assorted culverts Kaimbaga ward | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 700000 | 700000 |  | C.G.N | [5 empty] | 700000 |  |  | complete | 100
ROADS | 6774 | Bishop Gathatwa-Kiganjo Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 1889147 | 1889147 |  | C.G.N | [5 empty] | 1889147 |  |  | complete | 100
ROADS | 6775 | Mama Tony-Nguku Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kaimbaga |  |  | 2024-07-01 | 2025-07-01 |  | 1529817 | 1529817 |  | C.G.N | [5 empty] | 1529817 |  |  | complete | 100
ROADS | 6776 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Karau |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6777 | Jawakwe Wamuhia Ngata road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Karau |  |  | 2024-07-01 | 2025-07-01 |  | 1407253 | 1407253 |  | C.G.N | [5 empty] | 1407253 |  |  | complete | 100
ROADS | 6778 | Baba Victor Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Karau |  |  | 2024-07-01 | 2025-07-01 |  | 500000 | 500000 |  | C.G.N | [5 empty] | 500000 |  |  | on going | 100
ROADS | 6779 | Assorted culverts | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Karau |  |  | 2024-07-01 | 2025-07-01 |  | 400000 | 400000 |  | C.G.N | [5 empty] | 400000 |  |  | complete | 100
ROADS | 6780 | Oleriondo assorted culverts | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Karau |  |  | 2024-07-01 | 2025-07-01 |  | 200000 | 99913 |  | C.G.N | [5 empty] | 99913 |  |  | ongoing | 50
ROADS | 6781 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Rurii |  |  | 2024-07-01 | 2025-07-01 |  | 8611893 | 8610034 |  | C.G.N | [5 empty] | 8610034 |  |  | complete | 100
ROADS | 6782 | Assorted culverts- Rurii | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Rurii |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 1879638 |  | C.G.N | [5 empty] | 1879638 |  |  | complete | 100
ROADS | 6783 | Wahome Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Rurii |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2944120 |  | C.G.N | [5 empty] | 2944120 |  |  | complete | 100
ROADS | 6784 | Mugathika-Sammy Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Rurii |  |  | 2024-07-01 | 2025-07-01 |  | 1500000 | 1396830 |  | C.G.N | [5 empty] | 1396830 |  |  | complete | 100
ROADS | 6785 | Mukindu- Lake Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Rurii |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 1617572 |  | C.G.N | [5 empty] | 1617572 |  |  | complete | 100
ROADS | 6786 | Kwa Iria SDA Road-Githunguri and Njenga Road kwa Iria | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Rurii |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 998258 |  | C.G.N | [5 empty] | 998258 |  |  | complete | 100
ROADS | 6787 | Senator Office- Benard Road-Culvert installation | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Rurii |  |  | 2024-07-01 | 2025-07-01 |  | 1173000 | 1173028 |  | C.G.N | [5 empty] | 1173028 |  |  | complete | 100
ROADS | 6788 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kanjuiri Range |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100
ROADS | 6789 | Tumaini Gichagi road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kanjuiri Range |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 1731900 |  | C.G.N | [5 empty] | 1731900 |  |  | complete | 100
ROADS | 6790 | Delight Road- Uhuru | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kanjuiri Range |  |  | 2024-07-01 | 2025-07-01 |  | 1784909 | 1784909 |  | C.G.N | [5 empty] | 1784909 |  |  | complete | 100
ROADS | 6791 | Kio-Shakora Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kanjuiri Range |  |  | 2024-07-01 | 2025-07-01 |  | 1801537 | 1801537 |  | C.G.N | [5 empty] | 1801537 |  |  | complete | 100
ROADS | 6792 | Jimarka Road-Uhuru | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kanjuiri Range |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 |  |  | C.G.N | [8 empty] | on going
ROADS | 6793 | Githabina Road -Tumaini | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Kanjuiri Range |  |  | 2024-07-01 | 2025-07-01 |  | 1817450 | 1817450 |  | C.G.N | [5 empty] | 1817450 |  |  | complete | 100
ROADS | 6794 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6795 | Road improvement and maintenance using hire machinery | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 |  |  | C.G.N | [8 empty] | ongoing | 10
ROADS | 6796 | Supply of gravel- Mirangine | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 1080576 | 1080576 |  | C.G.N | [5 empty] | 1080576 |  |  | complete | 100
ROADS | 6797 | Ndumaka Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 2889863 | 2889863 |  | C.G.N | [5 empty] | 2889863 |  |  | complete | 100
ROADS | 6798 | Miiri Roads | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 2120294 | 2120293 |  | C.G.N | [5 empty] | 2120293 |  |  | complete | 100
ROADS | 6799 | Kihoto Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 2265027 | 2265026 |  | C.G.N | [5 empty] | 2265026 |  |  | complete | 100
ROADS | 6800 | Kanja- Juma Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 4304525 |  |  | C.G.N | [8 empty] | not done | -
ROADS | 6801 | Makara Roads | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 2997276 | 2997276 |  | C.G.N | [5 empty] | 2997276 |  |  | complete | 100
ROADS | 6802 | Kirofi- Karung'o road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 |  |  | C.G.N | [8 empty] | Not done
ROADS | 6803 | Mbira- Miiri Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 2869487 | 2869487 |  | C.G.N | [5 empty] | 2869487 |  |  | complete | 100
ROADS | 6804 | Kibendera Roads | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 2467340 | 2467340 |  | C.G.N | [5 empty] | 2467340 |  |  | complete | 100
ROADS | 6805 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Weru ward |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6806 | Road improvement and maintenance using hired machinery - Weru Ward | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Weru ward |  |  | 2024-07-01 | 2025-07-01 |  | 6000000 |  |  | C.G.N | [8 empty] | not started | 0
ROADS | 6807 | Supply of gravel- Weru Ward | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Weru ward |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100
ROADS | 6808 | Ol'Joro-Orok KAG Church road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Weru ward |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 |  |  | C.G.N | [8 empty] | not done | -
ROADS | 6809 | Culvert installations | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Weru ward |  |  | 2024-07-01 | 2025-07-01 |  | 3892460 | 3892460 |  | C.G.N | [5 empty] | 3892460 |  |  | complete | 100
ROADS | 6810 | ACK Kahingo Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Weru ward |  |  | 2024-07-01 | 2025-07-01 |  | 3926431 | 3890297 |  | C.G.N | [5 empty] | 3890297 |  |  | complete | 99
ROADS | 6811 | Gacheru Dam Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Weru ward |  |  | 2024-07-01 | 2025-07-01 |  | 3891974 | 3891974 |  | C.G.N | [5 empty] | 3891974 |  |  | complete | 100
ROADS | 6812 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6813 | Road improvement and maintenance of Chaina Road using hired machinery | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 |  |  | C.G.N | [8 empty] | ongoing | 10
ROADS | 6814 | Supply of gravel for Chaina Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100
ROADS | 6815 | Kayu Ngatha Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2890014 |  | C.G.N | [5 empty] | 2890014 |  |  | complete | 96
ROADS | 6816 | Nguno Wachiuri Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1233836 | 1233836 |  | C.G.N | [5 empty] | 1233836 |  |  | complete | 100
ROADS | 6817 | Kihara Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 899304 | 899304 |  | C.G.N | [5 empty] | 899304 |  |  | complete | 100
ROADS | 6818 | Kwa Muchemi Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1844058 | 1844058 |  | C.G.N | [5 empty] | 1844058 |  |  | complete | 100
ROADS | 6819 | Kagema- Ngorongo Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1222353 | 1222353 |  | C.G.N | [5 empty] | 1222353 |  |  | complete | 100
ROADS | 6820 | Assorted culverts-Charagita | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1341072 | 1341072 |  | C.G.N | [5 empty] | 1341072 |  |  | complete | 100
ROADS | 6821 | Assorted grading and compacting | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 1989395 |  | C.G.N | [5 empty] | 1989395 |  |  | complete | 99
ROADS | 6822 | Kona Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 1997561 |  | C.G.N | [5 empty] | 1997561 |  |  | complete | 100
ROADS | 6823 | Busa road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 2400000 | 2375200 |  | C.G.N | [5 empty] | 2375200 |  |  | complete | 99
ROADS | 6824 | Hire of roadwork Machinery | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 7500000 |  |  | C.G.N | [8 empty] | ongoing | 10
ROADS | 6825 | Supply of gravel- Gathanji Ward | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100
ROADS | 6826 | Silibwet road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 1994470 |  | C.G.N | [5 empty] | 1994470 |  |  | complete | 100
ROADS | 6827 | Wamunene road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 2634088 | 2634088 |  | C.G.N | [5 empty] | 2634088 |  |  | complete | 100
ROADS | 6828 | Marphil Mikeu road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 1800000 | 1696143 |  | C.G.N | [5 empty] | 1696143 |  |  | complete | 94
ROADS | 6829 | Igwamiti road gravel patching | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 1500000 | 1495198 |  | C.G.N | [5 empty] | 1495198 |  |  | complete | 100
ROADS | 6830 | Kwa Mande road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 1325029 | 1325029 |  | C.G.N | [5 empty] | 1325029 |  |  | complete | 100
ROADS | 6831 | Kosovo road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 1852643 | 1852643 |  | C.G.N | [5 empty] | 1852643 |  |  | complete | 100
ROADS | 6832 | Mambo Yote Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 1284114 | 1284113 |  | C.G.N | [5 empty] | 1284113 |  |  | complete | 100
ROADS | 6833 | Bara Njeru | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 2000000 |  | C.G.N | [5 empty] | 2000000 |  |  | complete | 100
ROADS | 6834 | Assorted road works | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 |  |  | C.G.N | [8 empty] | complete
ROADS | 6835 | Gathabara Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gathanji ward |  |  | 2024-07-01 | 2025-07-01 |  | 2500000 | 2333007 |  | C.G.N | [5 empty] | 2333007 |  |  | complete | 100
ROADS | 6836 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gatimu ward |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6837 | Kisima road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gatimu ward |  |  | 2024-07-01 | 2025-07-01 |  | 3607889 | 3607889 |  | C.G.N | [5 empty] | 3607889 |  |  | complete | 100
ROADS | 6838 | Bishop road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gatimu ward |  |  | 2024-07-01 | 2025-07-01 |  | 1794810 | 1794810 |  | C.G.N | [5 empty] | 1794810 |  |  | complete | 100
ROADS | 6839 | Cucu Nyokabi road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gatimu ward |  |  | 2024-07-01 | 2025-07-01 |  | 2811179 | 2811179 |  | C.G.N | [5 empty] | 2811179 |  |  | complete | 100
ROADS | 6840 | Mbatia Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gatimu ward |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 |  |  | C.G.N | [8 empty] | not done | -
ROADS | 6841 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Kiriita |  |  | 2024-07-01 | 2025-07-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | complete | 100
ROADS | 6842 | Hire of roadwork machinery- Kiriita | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Kiriita |  |  | 2024-07-01 | 2025-07-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | complete | 100
ROADS | 6843 | Supply of gravel - Kiriita | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Kiriita |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100
ROADS | 6844 | Mwangi B Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Kiriita |  |  | 2024-07-01 | 2025-07-01 |  | 3837737 | 3837737 |  | C.G.N | [5 empty] | 3837737 |  |  | complete | 100
ROADS | 6845 | Mukuru Valley Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Kiriita |  |  | 2024-07-01 | 2025-07-01 |  | 1766622 | 1766622 |  | C.G.N | [5 empty] | 1766622 |  |  | complete | 100
ROADS | 6846 | Drainage structures- Kiriita | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Kiriita |  |  | 2024-07-01 | 2025-07-01 |  | 2766304 | 2766304 |  | C.G.N | [5 empty] | 2766304 |  |  | complete | 100
ROADS | 6847 | Kiriita- Additional drainage structures | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Kiriita |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 |  |  | C.G.N | [8 empty] | not done
ROADS | 6848 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Leshau Pondo |  |  | 2024-07-01 | 2025-07-01 |  | 6000000 | 6000000 |  | C.G.N | [5 empty] | 6000000 |  |  | complete | 100
ROADS | 6849 | Baba Ben road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Leshau Pondo |  |  | 2024-07-01 | 2025-07-01 |  | 1332897 | 1332897 |  | C.G.N | [5 empty] | 1332897 |  |  | complete | 100
ROADS | 6850 | Gachomo road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Leshau Pondo |  |  | 2024-07-01 | 2025-07-01 |  | 1349311 | 1349311 |  | C.G.N | [5 empty] | 1349311 |  |  | complete | 100
ROADS | 6851 | Wagithiga road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Leshau Pondo |  |  | 2024-07-01 | 2025-07-01 |  | 2500000 | 2500000 |  | C.G.N | [5 empty] | 2500000 |  |  | complete | 100
ROADS | 6852 | Mambo road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Leshau Pondo |  |  | 2024-07-01 | 2025-07-01 |  | 1256006 | 1256006 |  | C.G.N | [5 empty] | 1256006 |  |  | complete | 100
ROADS | 6853 | Mayuu forest road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Leshau Pondo |  |  | 2024-07-01 | 2025-07-01 |  | 1500000 | 1497314 |  | C.G.N | [5 empty] | 1497314 |  |  | complete | 100
ROADS | 6854 | Assorted culverts | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Leshau Pondo |  |  | 2024-07-01 | 2025-07-01 |  | 888548 | 888548 |  | C.G.N | [5 empty] | 888548 |  |  | complete | 100
ROADS | 6855 | Road improvement and maintenance under Hire of Machinery | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Ndaragwa Central |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 3000000 |  | C.G.N | [5 empty] | 3000000 |  |  | complete | 100
ROADS | 6856 | Supply of gravel | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Ndaragwa Central |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 1000000 |  | C.G.N | [5 empty] | 1000000 |  |  | complete | 100
ROADS | 6857 | John T-Mwaniki Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Ndaragwa Central |  |  | 2024-07-01 | 2025-07-01 |  | 1874914 | 1874914 |  | C.G.N | [5 empty] | 1874914 |  |  | complete | 100
ROADS | 6858 | Kangawa Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Ndaragwa Central |  |  | 2024-07-01 | 2025-07-01 |  | 2740534 | 2740534 |  | C.G.N | [5 empty] | 2740534 |  |  | complete | 100
ROADS | 6859 | Kariki Road- Ndaragwa Central | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Ndaragwa Central |  |  | 2024-07-01 | 2025-07-01 |  | 1500000 | 1409960 |  | C.G.N | [5 empty] | 1409960 |  |  | complete | 100
ROADS | 6860 | Gitare road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Ndaragwa Central |  |  | 2024-07-01 | 2025-07-01 |  | 1309657 | 1309657 |  | C.G.N | [5 empty] | 1309657 |  |  | complete | 100
ROADS | 6861 | Subuku Town Roads | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Ndaragwa Central |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 | 1934068 |  | C.G.N | [5 empty] | 1934068 |  |  | complete | 100
ROADS | 6862 | kienjeku road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Ndaragwa Central |  |  | 2024-07-01 | 2025-07-01 |  | 4561288 | 4561288 |  | C.G.N | [5 empty] | 4561288 |  |  | complete | 100
ROADS | 6863 | Road improvement and maintenance using county in-house roadwork machinery | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Shamata |  |  | 2024-07-01 | 2025-07-01 |  | 4000000 | 4000000 |  | C.G.N | [5 empty] | 4000000 |  |  | complete | 100
ROADS | 6864 | Kaheho Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Shamata |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 |  |  | C.G.N | [8 empty] | ongoing | -
ROADS | 6865 | Kaka Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Shamata |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 |  |  | C.G.N | [8 empty] | ongoing | -
ROADS | 6866 | Kirima Roads | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Shamata |  |  | 2024-07-01 | 2025-07-01 |  | 4627678 | 4627678 |  | C.G.N | [5 empty] | 4627678 |  |  | complete | 100
ROADS | 6867 | Metha Roads | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Shamata |  |  | 2024-07-01 | 2025-07-01 |  | 4797258 | 4797256 |  | C.G.N | [5 empty] | 4797256 |  |  | complete | 100
ROADS | 6868 | Kangocho Roads | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Shamata |  |  | 2024-07-01 | 2025-07-01 |  | 4534868 | 4534868 |  | C.G.N | [5 empty] | 4534868 |  |  | complete | 100
ROADS | 6869 | Richard Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Shamata |  |  | 2024-07-01 | 2025-07-01 |  | 5000000 | 5000000 |  | C.G.N | [5 empty] | 5000000 |  |  | complete | 100
ROADS | 6870 | Gakoe Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Shamata |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 | 906738 |  | C.G.N | [5 empty] | 906738 |  |  | complete | 100
ROADS | 6871 | Magumu ward- Forest- Mukera Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Magumu |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2779612 |  | C.G.N | [5 empty] | 2779612 |  |  | complete | 100
ROADS | 6872 | Assorted roads- Gathaara | ROAD WORKS |  | ROAD WORKS |  | Kinangop | gathara |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 785096 |  | C.G.N | [5 empty] | 785096 |  |  | ongoing | 26
ROADS | 6873 | Joice/Kaindo Road- Njabini | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 |  |  | C.G.N | [8 empty] | complete | -
ROADS | 6874 | Murungaru Ward- Saba-Munanda Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Murungaru |  |  | 2024-07-01 | 2025-07-01 |  | 2894357 | 2894355 |  | C.G.N | [5 empty] | 2894355 |  |  | complete | 100
ROADS | 6875 | Kipipiri Ward- Gituamba Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Kipipiri |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2928022 |  | C.G.N | [5 empty] | 2928022 |  |  | complete | 100
ROADS | 6876 | Gatimu Ward- PCEA Kianjata Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Gatimu ward |  |  | 2024-07-01 | 2025-07-01 |  | 2751684 | 2751684 |  | C.G.N | [5 empty] | 2751684 |  |  | complete | 100
ROADS | 6877 | Leshau Pondo Ward- Kihingo Ndivai road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Leshau Pondo |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2480269 |  | C.G.N | [5 empty] | 2480269 |  |  | complete | 100
ROADS | 6878 | Ndaragwa Central Ward- Tafalia-Suguroi- Kiriogo Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Ndaragwa Central |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2876846 |  | C.G.N | [5 empty] | 2876846 |  |  | complete | 100
ROADS | 6879 | Rurii Ward- Maran-Mwisho Road | ROAD WORKS |  | ROAD WORKS |  | Ol Kalou | rurii |  |  | 2024-07-01 | 2025-07-01 |  | 2786960 | 2786960 |  | C.G.N | [5 empty] | 2786960 |  |  | complete | 100
ROADS | 6880 | Weru Ward - Gikungu Wabari Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Weru ward |  |  | 2024-07-01 | 2025-07-01 |  | 2699369 | 2699369 |  | C.G.N | [5 empty] | 2699369 |  |  | complete | 100
ROADS | 6881 | Njabini Ward - Karuangi Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 2981227 | 2981226 |  | C.G.N | [5 empty] | 2981226 |  |  | complete | 100
ROADS | 6882 | Karamton- Mama Warima Road -Leshau Pondo | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Leshau Pondo |  |  | 2024-07-01 | 2025-07-01 |  | 2000000 |  |  | C.G.N | [8 empty] | not done | -
ROADS | 6883 | Ibrahim Road Njabini | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Njabini Ward |  |  | 2024-07-01 | 2025-07-01 |  | 1000000 |  |  | C.G.N | [8 empty] | not done | -
ROADS | 6884 | Shamata Ward- Quarry Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Shamata |  |  | 2024-07-01 | 2025-07-01 |  | 2697710 | 2697710 |  | C.G.N | [5 empty] | 2697710 |  |  | complete | 100
ROADS | 6885 | Wanjohi Ward- Gatare- Maitho Inya Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Wanjohi ward |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2893650 |  | C.G.N | [5 empty] | 2893650 |  |  | complete | 100
ROADS | 6886 | Kiriita Ward- Warukira Down Road | ROAD WORKS |  | ROAD WORKS |  | Ndaragwa | Kiriita |  |  | 2024-07-01 | 2025-07-01 |  | 2637926 | - |  | C.G.N | [5 empty] | - |  |  | ongoing | -
ROADS | 6887 | Karau Ward- Highlands- Kihoreri Road | ROAD WORKS |  | ROAD WORKS |  | Ol kalou | Karau |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2828295 |  | C.G.N | [5 empty] | 2828295 |  |  | complete | 100
ROADS | 6888 | Githioro Ward- Harambee Munoru Road | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | githioro |  |  | 2024-07-01 | 2025-07-01 |  | 2825057 | 2825057 |  | C.G.N | [5 empty] | 2825057 |  |  | complete | 100
ROADS | 6889 | Charagita Ward- Shifu Road | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 2740167 | 2598333 |  | C.G.N | [5 empty] | 2598333 |  |  | complete | 100
ROADS | 6890 | Matindiri-Karenju Road- Charagita | ROAD WORKS |  | ROAD WORKS |  | Ol joroorok | Charagita Ward |  |  | 2024-07-01 | 2025-07-01 |  | 2818405 | - |  | C.G.N | [5 empty] | - |  |  | complete | -
ROADS | 6891 | Mirangine-Forest road | ROAD WORKS |  | ROAD WORKS |  | Ol kalou | Mirangine |  |  | 2024-07-01 | 2025-07-01 |  | 1831552 | 1831552 |  | C.G.N | [5 empty] | 1831552 |  |  | complete | 100
ROADS | 6892 | Rironi Bridge Access Road - Wanjohi | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Wanjohi ward |  |  | 2024-07-01 | 2025-07-01 |  | 2634830 | - |  | C.G.N | [5 empty] | - |  |  | ongoing | -
ROADS | 6893 | Geta- Road No. 30 (Lower) | ROAD WORKS |  | ROAD WORKS |  | Kipipiri | Geta |  |  | 2024-07-01 | 2025-07-01 |  | 2975127 | 2975127 |  | C.G.N | [5 empty] | 2975127 |  |  | complete | 100
ROADS | 6894 | Lower Bongo Road Nyakio | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Nyakio |  |  | 2024-07-01 | 2025-07-01 |  | 3000000 | 2867188 |  | C.G.N | [5 empty] | 2867188 |  |  | complete | 100
ROADS | 6895 | Gichingiri - Wairi - Ngarachu Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 2785370 | 2785370 |  | C.G.N | [5 empty] | 2785370 |  |  | complete | 100
ROADS | 6896 | Kivuno- Mirofi Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 2734094 | 2734094 |  | C.G.N | [5 empty] | 2734094 |  |  | complete | 100
ROADS | 6897 | Waithaka-Utugi-Weshe-Ngure Road | ROAD WORKS |  | ROAD WORKS |  | Kinangop | Engineer |  |  | 2024-07-01 | 2025-07-01 |  | 2800000 | 2759724 |  | C.G.N | [5 empty] | 2759724 |  |  | complete | 99
ROADS | 6898 | Emergency road works | ROAD WORKS |  | ROAD WORKS |  |  | Countywide |  |  | 2024-07-01 | 2025-07-01 |  | 40000000 | 39948420 |  | C.G.N | [5 empty] | 39948420 |  |  | complete | 100%
ROADS | 6899 | Turasha - Mumui bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | KINANGOP | GITHIORO |  |  | 2016 | 2017 |  |  | 1 | [6 empty] | 0% | 0 |  | 1
ROADS | 6900 | Rirorni bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | KIPIPIRI | WANJOHI |  |  | 2019 | 2020
ROADS | 6901 | Rayeta bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | KIPIPIRI | WANJOHI |  |  | 2023 | 2024
ROADS | 6902 | Ciondo -Chobe bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | KINANGOP | EGINEER |  |  | 2024 | 2025
ROADS | 6903 | Njoguini bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | KINANGOP | NYAKIO |  |  | 2023 | 2025
ROADS | 6904 | Thaba bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | OL'KALOU | KARAU |  |  | 2024 | 2024 | 2024
ROADS | 6905 | Kidowa bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | OL'KALOU | RURII |  |  | 2024 | 2024 | 2024
ROADS | 6906 | Rumathi bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | OL'KALOU | KAIMBAGA |  |  | 2024 | 2024 | 2024
ROADS | 6907 | Kanduma bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | OL'KALOU | KARAU |  |  | 2024 | 2024 | 2024
ROADS | 6908 | Wangui bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | NDARAGUA | NDARAGUA CENTRAL |  |  | 2020 | 2021 | 2021
ROADS | 6909 | Kahutha bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | NDARAGUA | NDARAGUA CENTRAL |  |  | 2024 | 2024 | 2024
ROADS | 6910 | Mwaa bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | OL'KALOU | MIRANGINE |  |  | 2021 | 2022 | 2022
ROADS | 6911 | Njunu-Manyatta bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | OL'JORO-OROK | GATIMU |  |  | 2015 | 2015 | 2015
ROADS | 6912 | Prima rosa box culvert | BOX CULVERT CONSTRUCTION |  | 0NE BOX CULVERT CONSTRUCTED |  | OL'JORO-OROK | WERU |  |  | 2015 | 2015 | 2015
ROADS | 6913 | Gachuha bridge | BRIDGE CONSTRUCTION |  | 0NE BRIDGE CONSTRUCTED |  | KIPIPIRI | GITHIORO |  |  | 2025 | 2026 | ON-GOING
ROADS | 6914 | Gatimu air strip box culvert | BOX CULVERT CONSTRUCTION |  | 0NE BOX CULVERT CONSTRUCTED |  | OL'JORO-OROK | GATIMU |  |  | 2015 | 2015 | 2015
ROADS | 6915 | OLKALOU BUSPARK | CABRO LAYING |  | BUSPARK CONSTRUCTED |  | OL'KALOU | KARAU |  |  | 2015 | 2015 | 2015
ROADS | 6916 | MAIRO INYA BUSPARK | CABRO LAYING |  | BUSPARK CONSTRUCTED |  | NDARAGUA | KIRIITA |  |  | 2020 | 2020 | 2020
ROADS | 6917 | MIRANGINE BUSPARK | CABRO LAYING |  | BUSPARK CONSTRUCTED |  | OL'KALOU | MIRANGINE |  |  | 2021 | 2021 | 2021
ROADS | 6918 | COUNTY HEADQUATER OFFICES | OFFICE BLOCK CONSTRUCTION |  | OFFICE BLOCK CONSTRUCTION |  | OL'KALOU | KAIMBAGA |  |  | 2014 | 2016 | 2016
ROADS | 6919 | HEADQUARTER CARPARK | CAR PARK CONSTRUCTION |  | CARPARK CONSTRUCTED |  | OL'KALOU | KAIMBAGA |  |  | 2015 | 2015 | 2015
ROADS | 6920 | GOVERNOR'S RESIDENCE | COSTRUCTION OF GVN'S RESIDENCE |  | RESIDENCE CONSTRUCTED |  | OL'KALOU | KARAU |  |  | 2023 | 2025
ROADS | 6921 | GRADING & GRAVELING | GRADING AND GRAVELING OF ROADS |  | GRAVELING & GRADING DONE |  | ALL SUB-COUNTIES | ALL WARDS |  |  | 2013 | N/A | ON-GOING
ROADS | 6922 | CULVERT INSTALLATION | CULKVERT INSTALLATION |  | 5500 CULVERTS INSTALLED |  | ALL SUB-COUNTIES | ALL WARDS |  |  | 2013 | N/A | ON-GOING
ROADS | 6923 | BODA BODA SHEDS | BODA BODA SHEDS CONSTRUCTION |  | 600 NO. BODA BODA SHEDS CONSTRUCTED |  | ALL SUB-COUNTIES | ALL WARDS |  |  | 2013 | N/A | ON-GOING
TRADE | 6924 | Signage of Tourist attractions | Creation of Tourist sinages | To improve local tourism | Erected Tourist attractions signage | Signage of Tourist attractions | Olkalou | Kaimbaga |  | Productive Sector | Jul 2013 | 2014-06-01 | June 2014 | 700000 | 700000 | 700000 | CGN | N/A | 700000 | 0 | 700000 | 100% | 700000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6925 | Rehabilitation of Happy Valley Homes | Rehabilitation of Happy Valley Homes | To improve local tourism | Rehabilitated happy valley homes | Rehabilitation of Happy Valley Homes | Kinangop | Gathaara |  | Productive Sector | Jul 2013 | June 2014 | June 2014 | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6926 | Rehabilitation of Mau Mau Caves | Rehabilitation of Mau Mau Caves | To improve local tourism | Rehabilited Mau mau caves | Rehabilitation of Mau Mau Caves | Kipipiri | Wanjohi |  | Productive Sector | Jul 2013 | 2014-06-01 | June 2014 | 2300000 | 2300000 | 2300000 | CGN | N/A | 2300000 | 0 | 2300000 | 100% | 2300000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6927 | Survey and protection of Lake Olbollasat ecosystem | Survey of Lake Olbollosat | To protect the lake from encroachment | Surveyed Lake Olbollosat | Survey and protection of Lake Obollasat ecosystem | Olkalou | Rurii |  | Productive Sector | Jul 2013 | June 2014 | June 2014 | 14432960 | 14432960 | 14432960 | CGN | N/A | 14432960 | 0 | 14432960 | 100% | 14432960 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6928 | Milk Coolers - kipipiri | Provision of Milk Coolers | To Improve Trading Conditions | Provided Milk Coolers | Milk Coolers - kipipiri | Kipipiri | Kipipiri |  | Productive Sector | Jul 2014 | June 2015 | June 2015 | 4200000 | 4200000 | 4200000 | CGN | N/A | 4200000 | 0 | 4200000 | 100% | 4200000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6929 | Milk Coolers - kinangop | Provision of Milk Coolers | To Improve Trading Conditions | Provided Milk Coolers | Milk Coolers - kinangop | Kinangop | North Kinangop |  | Productive Sector | Jul 2014 | June 2015 | June 2015 | 4200000 | 4200000 | 4200000 | CGN | N/A | 4200000 | 0 | 4200000 | 100% | 4200000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6930 | Milk Cooler - Ol jororok | Provision of Milk Coolers | To Improve Trading Conditions | Provided Milk Coolers | Milk Cooler - Ol jororok | OL JOROROK | Gathanji |  | Productive Sector | Jul 2014 | June 2015 | June 2015 | 4600000 | 4600000 | 4600000 | CGN | N/A | 4600000 | 0 | 4600000 | 100% | 4600000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6931 | Chicken Incubator - ndaragwa | Provision of chicken incubators | To Improve livelihoods | Provided Chicken incubator | Chicken Incubator - ndaragwa | Ndaragwa | Ndaragwa Central |  | Productive Sector | Jul 2014 | June 2015 | June 2015 | 495000 | 495000 | 495000 | CGN | N/A | 495000 | 0 | 495000 | 100% | 495000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6932 | Honey Containers - kipipiri | Provision of honey containers | To Improve livelihoods | Provided honey containers | Honey Containers - kipipiri | Kipipiri | Kipipiri |  | Productive Sector | Jul 2014 | June 2015 | June 2015 | 500000 | 500000 | 500000 | CGN | N/A | 500000 | 0 | 500000 | 100% | 500000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6933 | Construction of Market Sheds | Construction of Market Sheds | To Improve Market Trading conditions | Constructed Market shed | Construction of Market Sheds |  |  |  | Productive Sector | Jul 2014 | June 2015 | June 2015 | 20880000 | 20880000 | 20880000 | CGN | N/A | 20880000 | 0 | 20880000 | 100% | 20880000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6934 | Purchase of Weights and Measures equipment | Purchase of Weights and Measures equipment | To Improve fair Trading | Procured weights and measures equipment | Purchase of Weights and Measures equipment | Olkalou | Karau |  | Productive Sector | Jul 2014 | June 2015 | June 2015 | 1095000 | 1095000 | 1095000 | CGN | N/A | 1095000 | 0 | 1095000 | 100% | 1095000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6935 | IMPROVEMENT OF MIHARATI MARKET SHED | Improvement of market sheds | To Improve Market Trading conditions | Constructed Market shed | IMPROVEMENT OF MIHARATI MARKET SHED | Kipipiri | Kipipiri |  | Productive Sector | Jul 2015 | June 2016 | June 2016 | 678919.35 | 678919.35 | 678919.35 | CGN | N/A | 678919.35 | 0 | 678919.35 | 100% | 678919.35 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6936 | CONSTRUCTION OF MARKET SHED AT MAWINGO. | Construction of Market Sheds | To Improve Market Trading conditions | Constructed Market shed | CONSTRUCTION OF MARKET SHED AT MAWINGO. | Kipipiri | Githioro |  | Productive Sector | Jul 2015 | June 2016 | June 2016 | 2800000 | 2800000 | 2800000 | CGN | N/A | 2800000 | 0 | 2800000 | 100% | 2800000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6937 | CONSTRUCTION OF JUA KALI SHED | Construction of Jua kali sheds | To Improve Market Trading conditions | Constructed jua kali shed | CONSTRUCTION OF JUA KALI SHED | Olkalou | Mirangine |  | Productive Sector | Jul 2015 | June 2016 | June 2016 | 1396535.6 | 1396535.6 | 1396535.6 | CGN | N/A | 1396535.6 | 0 | 1396535.6 | 100% | 1396535.6 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6938 | CONSTRUCTION OF A 4 DOOR PIT LATRINE | Construction of a latrine | To Improve hygiene and sanitation | Constructed pit latrine | CONSTRUCTION OF A 4 DOOR PIT LATRINE | Kipipiri | Kipipiri |  | Productive Sector | Jul 2015 | June 2016 | June 2016 | 598772 | 598772 | 598772 | CGN | N/A | 598772 | 0 | 598772 | 100% | 598772 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6939 | Infrastructure Development For Milk Coolers | Provision of infrastructure for Milk Coolers | To Improve Trading Conditions | Constructed infrastructure for milk coolers | Infrastructure Development For Milk Coolers | Olkalou | Mirangine |  | Productive Sector | Jul 2016 | June 2017 | June 2017 | 6000000 | 6000000 | 6000000 | CGN | N/A | 6000000 | 0 | 6000000 | 100% | 6000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6940 | Construction and Upgrade of Market Sheds | Construction of Market Sheds | To Improve Market Trading conditions | Constructed Market shed | Construction and Upgrade of Market Sheds | Kinangop | North Kinangop |  | Productive Sector | Jul 2016 | June 2017 | June 2017 | 8000000 | 8000000 | 8000000 | CGN | N/A | 8000000 | 0 | 8000000 | 100% | 8000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6941 | Construction of Jua Kali Sheds | Construction of Jua kali sheds | To Improve Market Trading conditions | Constructed jua kali shed | Construction of Jua Kali Sheds | OljoroOrok | Weru |  | Productive Sector | Jul 2016 | June 2017 | June 2017 | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6942 | Upgrading and equipping County Industrial Development Centers (CIDCs) | Upgrading and equipping County Industrial Development Centers (CIDCs) | To Improve Market Trading conditions | Equipped CIDCs | Upgrading and equipping County Industrial Development Centers (CIDCs) | OljoroOrok, Kipipiri, Kinangop, Olkalou | Weru, Geta, North Kinangop, Kaimbaga |  | Productive Sector | Jul 2016 | June 2017 | June 2017 | 3100000 | 3100000 | 3100000 | CGN | N/A | 3100000 | 0 | 3100000 | 100% | 3100000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6943 | Improvement of Miharati market shed | Construction of Market Sheds | To Improve Market Trading conditions | Improved market shed | Improvement of Miharati market shed | Kipipiri | Kipipiri |  | Productive Sector | Jul 2017 | June 2018 | June 2018 | 678917.35 | 678917.35 | 678917.35 | CGN | N/A | 678917.35 | 0 | 678917.35 | 100% | 678917.35 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6944 | Construction of market stalls | Construction of market stalls | To Improve Market Trading conditions | Constructed market stalls | Construction of market stalls | Kinangop | Gathaara |  | Productive Sector | Jul 2017 | June 2018 | June 2018 | 227619.9 | 227619.9 | 227619.9 | CGN | N/A | 227619.9 | 0 | 227619.9 | 100% | 227619.9 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6945 | Upgrade of Mawingu Market in Githioro | Construction of Market Sheds | To Improve Market Trading conditions | Upgraded Mawingu Market | Upgrade of Mawingu Market in Githioro | Kipipiri | Githioro |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 1424100 | 1424100 | 1424100 | CGN | N/A | 1424100 | 0 | 1424100 | 100% | 1424100 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6946 | Completion of Engineer mkt | Construction of Market Sheds | To Improve Market Trading conditions | Completed Engineer market | Completion of Engineer mkt | Kinangop | Gathaara |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 1996750 | 1996750 | 1996750 | CGN | N/A | 1996750 | 0 | 1996750 | 100% | 1996750 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6947 | Construction of Jua Kali sheds in Mirangine | Construction of Jua kali sheds | To Improve Market Trading conditions | Constructed jua kali shed | Construction of Jua Kali sheds in Mirangine | Olkalou | Mirangine |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 3950625 | 3950625 | 3950625 | CGN | N/A | 3950625 | 0 | 3950625 | 100% | 3950625 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6948 | Construction and upgrade of Ndaragwa market sheds/Toilets | Construction of Market Sheds/toilet | To Improve Market Trading conditions | Constructed Market shed/toilets | Construction and upgrade of Ndaragwa market sheds/Toilets | Ndaragwa | Ndaragwa Central |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 1398554 | 1398554 | 1398554 | CGN | N/A | 1398554 | 0 | 1398554 | 100% | 1398554 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6949 | Construction and upgrade of Wanjohi market sheds/Toilets | Construction of Market Sheds/toilet | To Improve Market Trading conditions | Constructed Market shed/toilets | Construction and upgrade of Wanjohi market sheds/Toilets | Kipipiri | Wanjohi |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 901227 | 901227 | 901227 | CGN | N/A | 901227 | 0 | 901227 | 100% | 901227 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6950 | Construction and upgrade of Karangatha market sheds/Toilets | Construction of Market Sheds/toilet | To Improve Market Trading conditions | Constructed Market shed/toilets | Construction and upgrade of Karangatha market sheds/Toilets | Kinangop | Nyakio |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 1388346 | 1388346 | 1388346 | CGN | N/A | 1388346 | 0 | 1388346 | 100% | 1388346 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6951 | fencing and leveling of Olkalou wholesale Mkt | fencing and leveling of Olkalou wholesale Mkt | To Improve Market Trading conditions | Fenced Olkalou wholesale market | fencing and leveling of Olkalou wholesale Mkt | Olkalou | Karau |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 1999000 | 1999000 | 1999000 | CGN | N/A | 1999000 | 0 | 1999000 | 100% | 1999000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6952 | Construction of Ndunyu Njeru mkt | Construction of Market Sheds/toilet | To Improve Market Trading conditions | Constructed market shed/toilet | Construction of Ndunyu Njeru mkt | Kinangop | North Kinangop |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 1072813 | 1072813 | 1072813 | CGN | N/A | 1072813 | 0 | 1072813 | 100% | 1072813 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6953 | construction of 6- door pit latrine in engineer mkt | construction of 6- door pit latrine in engineer mkt | To Improve hygiene and sanitation | Constructed pit latrine | construction of 6- door pit latrine in engineer mkt | Kinangop | Gathaara |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6954 | Market construction Kiboro phase II | Construction of Market Sheds/toilet | To Improve Market Trading conditions | Constructed market | Market construction Kiboro phase II | Kinangop | Njabini |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 3000000 | 3000000 | 3000000 | CGN | N/A | 3000000 | 0 | 3000000 | 100% | 3000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6955 | leveling of Miharati markets | leveling of Miharati markets | To Improve Market Trading conditions | Levelled Miharati Market | leveling of Miharati markets | Kipipiri | Kipipiri |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 897260 | 897260 | 897260 | CGN | N/A | 897260 | 0 | 897260 | 100% | 897260 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6956 | installation and commissioning of a floodmast in magumu ward | installation and commissioning of a floodmast in magumu ward | To Improve Market Trading conditions and security | Installed floodmast | installation and commissioning of a floodmast in magumu ward | Kinangop | Magumu |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 3298500 | 3298500 | 3298500 | CGN | N/A | 3298500 | 0 | 3298500 | 100% | 3298500 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6957 | Construction of Murungaru bus park (toilet) | Construction of Murungaru bus park (toilet) | To Improve hygiene and sanitation | Constructed toilet | Construction of Murungaru bus park (toilet) | Kinangop | Murungaru |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 92075 | 92075 | 92075 | CGN | N/A | 92075 | 0 | 92075 | 100% | 92075 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6958 | Construction and upgrade of Ol jororok market sheds/Toilets | Construction and upgrade of Ol jororok market sheds/Toilets | To Improve Market Trading conditions | Constructed market shade/toilets | Construction and upgrade of Ol jororok market sheds/Toilets | OljoroOrok | Weru |  | Productive Sector | Jul 2018 | June 2019 | June 2019 | 192672 | 192672 | 192672 | CGN | N/A | 192672 | 0 | 192672 | 100% | 192672 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6959 | Market development: laying of cabro at soko mpya | Laying of Cabro at Soko Mpya | To Improve Market Trading conditions | Layed cabro | Market development: laying of cabro at soko mpya | Kinangop | Magumu |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 10000000 | 10000000 | 10000000 | CGN | N/A | 10000000 | 0 | 10000000 | 100% | 10000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6960 | Construction of Njabini bus park- 4 door toilet | Construction of a toilet | To Improve hygiene and sanitation | Constructed toilet | Construction of Njabini bus park- 4 door toilet | Kinangop | Njabini |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1999970 | 1999970 | 1999970 | CGN | N/A | 1999970 | 0 | 1999970 | 100% | 1999970 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6961 | Construction of Charagita Market toilet | Construction of a toilet | To Improve hygiene and sanitation | Construsted Charagita Market Toilet | Construction of Charagita Market toilet | OljoroOrok | Charagita |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1199514 | 1199514 | 1199514 | CGN | N/A | 1199514 | 0 | 1199514 | 100% | 1199514 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6962 | Construction of Passenga market toilet | Construction of a toilet | To Improve hygiene and sanitation | Constructed toilet | Construction of Passenga market toilet | Olkalou | Rurii |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1198083 | 1198083 | 1198083 | CGN | N/A | 1198083 | 0 | 1198083 | 100% | 1198083 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6963 | Fencing of gwa kanyua market | Market Fencing | To Improve Market Trading conditions and security | Fenced Gwa kanyua market | Fencing of gwa kanyua market | Kinangop | Magumu |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1996012 | 1996012 | 1996012 | CGN | N/A | 1996012 | 0 | 1996012 | 100% | 1996012 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6964 | Construction of Kasuku market | Construction of a market shed | To Improve Market Trading conditions | Constructed Kasuku market | Construction of Kasuku market | OljoroOrok | Weru |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1200000 | 1200000 | 1200000 | CGN | N/A | 1200000 | 0 | 1200000 | 100% | 1200000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6965 | Construction of githabai market toilet | Construction of a market Toilet | To Improve Market Trading conditions | Constructed market Toilet | Construction of githabai market toilet | Kinangop | Githabai |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1198090 | 1198090 | 1198090 | CGN | N/A | 1198090 | 0 | 1198090 | 100% | 1198090 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6966 | Construction of Gwa Kung'u market Shed leshau | Construction of a market shed | To Improve Market Trading conditions | Constructed Market shed | Construction of Gwa Kung'u market Shed leshau | Ndaragwa | Leshau Pondo |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1499813 | 1499813 | 1499813 | CGN | N/A | 1499813 | 0 | 1499813 | 100% | 1499813 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6967 | Improvement of Boiman Market |  | To Improve Market Trading conditions | Improved Boiman Market | Improvement of Boiman Market | Ol-joro Orok | Gathanji |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 634568 | 634568 | 634568 | CGN | N/A | 634568 | 0 | 634568 | 100% | 634568 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6968 | Levelling of Kasuku market | Levelling of Kasuku market | To Improve Market Trading conditions | Levelled Kasuku Market | Levelling of Kasuku market | Ol-joro Orok | Weru |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6969 | levelling of Ol Joro Orok market | Levelling of a market | To Improve Market Trading conditions | Levelled Ol-joro-orok market | levelling of Ol Joro Orok market | Ol-joro Orok | Weru |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 997826 | 997826 | 997826 | CGN | N/A | 997826 | 0 | 997826 | 100% | 997826 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6970 | Improvement of Ngorika Market | Improving the state of Ngorika Market | To Improve Market Trading conditions | Improved Ngorika market | Improvement of Ngorika Market | Olkalou | Kanjuiri |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 798950 | 798950 | 798950 | CGN | N/A | 798950 | 0 | 798950 | 100% | 798950 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6971 | Improvement of Engineer Market | Improving the state of Engineer market | To Improve Market Trading conditions | Improved Engineer market | Improvement of Engineer Market | Kinangop | Gathaara |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6972 | Improvement of extension of Wanjohi market | Extension of Wanjohi Market | To Improve Market Trading conditions | Improved Wanjohi market | Improvement of extension of Wanjohi market | Kipipiri | Wanjohi |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1394598 | 1394598 | 1394598 | CGN | N/A | 1394598 | 0 | 1394598 | 100% | 1394598 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6973 | Construction of a refuse bin at Soko | Construction of a refuse bin | To Improve hygiene and sanitation | Constructed refuse bin | Construction of a refuse bin at Soko | Kinangop | Magumu |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1195984 | 1195984 | 1195984 | CGN | N/A | 1195984 | 0 | 1195984 | 100% | 1195984 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6974 | Construction of a toilet at Soko mpya | Construction of a toilet | To Improve hygiene and sanitation | Constructed toilet | Construction of a toilet at Soko mpya | Kinangop | Magumu |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1998297 | 1998297 | 1998297 | CGN | N/A | 1998297 | 0 | 1998297 | 100% | 1998297 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6975 | Construction of a horticultural shed at Soko mpya | Construction of a shed | To Improve Market Trading conditions | Constructed horticultural shed | Construction of a horticultural shed at Soko mpya | Kinangop | Magumu |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 1371717 | 1371717 | 1371717 | CGN | N/A | 1371717 | 0 | 1371717 | 100% | 1371717 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6976 | Support of cottage industries (icdc equipment for ndaragwa, ndunyu njeru, olkalou and geta icdc centres) | Provision of equipment to Cottage industries | To Improve livelihoods | Supported cottage industries | Support of cottage industries (icdc equipment for ndaragwa, ndunyu njeru, olkalou and geta icdc centres) | Ndaragwa, Kinangop, Olkalou, Kipipiri | Leshau Pondo, North Kinangop, Kaimbaga, Kipipiri |  | Productive Sector | Jul 2019 | June 2020 | June 2020 | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6977 | Mirangine Ward- Support to welfare groups | Provision of equipment | To Improve livelihoods | Supported welfare groups | Mirangine Ward- Support to welfare groups | Olkalou | Mirangine |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | 0 | 1500000 | 100% | 1500000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6978 | Charagita ward - Support to welfare Groups | Provision of equipment | To Improve livelihoods | Supported welfare groups | Charagita ward - Support to welfare Groups | OljoroOrok | Charagita |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 1300000 | 1300000 | 1300000 | CGN | N/A | 1300000 | 0 | 1300000 | 100% | 1300000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6979 | Charagita ward - Support to Groups | Provision of equipment | To Improve livelihoods | Supported welfare groups | Charagita ward - Support to Groups | OljoroOrok | Charagita |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6980 | Upgrade of mobile agency banking for viktas sacco - Kiriita Ward | Support of a sacco mobile agency banking | To Improve the cooperatives operations | Upgraded Vikta Sacco mobile agency | Upgrade of mobile agency banking for viktas sacco - Kiriita Ward | Ndaragwa | Kiriita |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | 0 | 1500000 | 100% | 1500000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6981 | Cooperative infrastructure support | Provision of various infrastructural support to Cooperatives | To Improve the cooperatives operations | Supported Cooperative infrastructure | Cooperative infrastructure support | ALL SUB COUNTIES | North Kinangop, Leshau Pondo ,shamata |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 7000000 | 7000000 | 7000000 | CGN | N/A | 7000000 | 0 | 7000000 | 100% | 7000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6982 | Njabini farmers society grant - milk value addition | Milk value addition | To Improve the cooperatives operations | Carried out milk value addition for Njabini farmers society | Njabini farmers society grant - milk value addition | Kinangop | Njabini |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 1998000 | 1998000 | 1998000 | CGN | N/A | 1998000 | 0 | 1998000 | 100% | 1998000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6983 | Ndaragwa central - infrastructure support | Provision of various infrastructural support to Cooperatives | To Improve the cooperatives operations | Supported infrastructure | Ndaragwa central - infrastructure support | Ndaragwa | Ndaragwa Central |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 1999940 | 1999940 | 1999940 | CGN | N/A | 1999940 | 0 | 1999940 | 100% | 1999940 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6984 | Leshau pondo Motor bikes for Juda SACCO | Provision of Motorbikes | To Improve the cooperatives operations | Procured motor bikes | Leshau pondo Motor bikes for Juda SACCO | Ndaragwa | Leshau Pondo |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 600000 | 600000 | 600000 | CGN | N/A | 600000 | 0 | 600000 | 100% | 600000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6985 | Kanjuiri- infrastructure support- Wiyumiririe Cooperative Society | Provision of various infrastructural support to Cooperatives | To Improve the cooperatives operations | Cooperative Society supported infrastructure | Kanjuiri- infrastructure support- Wiyumiririe Cooperative Society | Olkalou | Kanjuiri |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6986 | Renovations of Ndaragwa Cooperative Office | Office renovations | To Improve effiency in running of the office | Renovated Ndaragwa Office | Renovations of Ndaragwa Cooperative Office | Ndaragwa | Ndaragwa Central |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6987 | Purchase of Weights and Measures Equipment | Procurement of weights and measures equipment | To Improve fair trading | Procured weights and measures equipment | Purchase of Weights and Measures Equipment | Olkalou | Kaimbaga |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 150000 | 150000 | 150000 | CGN | N/A | 150000 | 0 | 150000 | 100% | 150000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6988 | Njabini bus park toilet | Construction of a bus park toilet | To Improve hygiene and sanitation | Constructed Toilet | Njabini bus park toilet | Kinangop | Njabini |  | Productive Sector | [6 empty] | CGN | N/A |  | 0 |  | #DIV/0! |  | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6989 | Geta- Market Stalls (Geta) | Construction of Market stalls | To Improve Market Trading conditions | Constructed Market stalls | Geta- Market Stalls (Geta) | Kipipiri | Geta |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 3999980 | 3999980 | 3999980 | CGN | N/A | 3999980 | 0 | 3999980 | 100% | 3999980 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6990 | Geta- Market shed (Geta) | Construction of Market Shed | To Improve Market Trading conditions | Constructed market shed | Geta- Market shed (Geta) | Kipipiri | Geta |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 3999815 | 3999815 | 3999815 | CGN | N/A | 3999815 | 0 | 3999815 | 100% | 3999815 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6991 | Improvement of Murungaru market | Improving the state of Murungaru market | To Improve Market Trading conditions | Improved Murungaru market | Improvement of Murungaru market | Kinangop | Murungaru |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 1999600 | 1999600 | 1999600 | CGN | N/A | 1999600 | 0 | 1999600 | 100% | 1999600 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6992 | Soko Mpya market shed phase 1 | Construction of a market shed | To Improve Market Trading conditions | Constructed market shed | Soko Mpya market shed phase 1 | Kinangop | Magumu |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 3999993 | 3999993 | 3999993 | CGN | N/A | 3999993 | 0 | 3999993 | 100% | 3999993 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6993 | Soko Mpya market shed phase 2 | Construction of a market shed | To Improve Market Trading conditions | Constructed market shed | Soko Mpya market shed phase 2 | Kinangop | Magumu |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 3900000 | 3900000 | 3900000 | CGN | N/A | 3900000 | 0 | 3900000 | 100% | 3900000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6994 | Improvement of Ndunyu Njeru Market | Improvement of Ndunyu Njeru Market | To Improve Market Trading conditions | Improved Ndunyu Njeru Market | Improvement of Ndunyu Njeru Market | Kinangop | North Kinangop |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 2900000 | 2900000 | 2900000 | CGN | N/A | 2900000 | 0 | 2900000 | 100% | 2900000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6995 | Improvement of miharati market | Improvement of miharati market | To Improve Market Trading conditions | Improved miharati market | Improvement of miharati market | Kipipiri | Kipipiri |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6996 | Construction of a Potato and Vegetable Processing Plant- Flagship Project | Construction of a Potato and Vegetable Processing Plant- Flagship Project | To Create farmers' market | Constructed vegetable processing plant | Construction of a Potato and Vegetable Processing Plant- Flagship Project | Olkalou | Kaimbaga |  | Productive Sector | Jul 2020 | June 2021 | June 2021 | 998500 | 998500 | 998500 | CGN | N/A | 998500 | 0 | 998500 | 100% | 998500 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6997 | Pre-Co-operative training - Charagita | Carrying out Training | To Improve the cooperatives operations | Conducted training | Pre-Co-operative training - Charagita | OljoroOrok | Charagita |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 1607000 | 1607000 | 1607000 | CGN | N/A | 1607000 | 0 | 1607000 | 100% | 1607000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6998 | Support to welfare groups- Njabini ward | Provision of Equipment | To Improve livelihoods | Supported welfare groups | Support to welfare groups- Njabini ward | Kinangop | Njabini |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 6999 | Support to NYANDAWAS cooperative with 3. No motorbikes | Provision of Motorbikes | To Improve the cooperatives operations | Supported Cooperative | Support to NYANDAWAS cooperative with 3. No motorbikes | Ndaragwa | Kiriita |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 500000 | 500000 | 500000 | CGN | N/A | 500000 | 0 | 500000 | 100% | 500000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7000 | Kiriita- Support to cooperative | Provision of equipment | To Improve the cooperatives operations | Supported Cooperative | Kiriita- Support to cooperative | Ndaragwa | Kiriita |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7001 | Cooperative infrastructure support in 5 sub counties at Kshs.1.6Million | Provision of various infrastructural support to Cooperatives | To Improve the cooperatives operations | Supported Cooperative infrastructure | Cooperative infrastructure support in 5 sub counties at Kshs.1.6Million | Ndaragwa | Ndaragwa Central,kiriita, Leshau pondo |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 5000000 | 5000000 | 5000000 | CGN | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7002 | Renovation of Ndaragwa cooperative office | Office renovations | To Improve effiency in running of the office | Renovated Ndaragwa Office | Renovation of Ndaragwa cooperative office | Ndaragwa | Ndaragwa Central |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 300000 | 300000 | 300000 | CGN | N/A | 300000 | 0 | 300000 | 100% | 300000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7003 | Upper Ndaragwa Central-Support to SMEs | Provision of Equipment | To Improve livelihoods | Supported SMEs | Upper Ndaragwa Central-Support to SMEs | Ndaragwa | Ndaragwa Central |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7004 | Lower Ndaragwa Central-Support to SMEs | Provision of Equipment | To Improve livelihoods | Supported SMEs | Lower Ndaragwa Central-Support to SMEs | Ndaragwa | Ndaragwa Central |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 2000000 | 2000000 | 2000000 | CGN | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7005 | Biodigester System for Njabini Market- Njabini | Construction of Biodigester | To Improve hygiene and sanitation | Constructed Biogester | Biodigester System for Njabini Market- Njabini | Kinangop | Njabini |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 1000000 | 1000000 | 1000000 | CGN | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7006 | Umbrellas for open air (vibanda) trader- Njabini | Provision of Open Air umbrellas | To Improve Market Trading conditions | Procured umbrellas | Umbrellas for open air (vibanda) trader- Njabini | Kinangop | Njabini |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | 0 | 1500000 | 100% | 1500000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7007 | Umbrellas for open air (vibanda) traders- Magumu | Provision of Open Air umbrellas | To Improve Market Trading conditions | Procured umbrellas | Umbrellas for open air (vibanda) traders- Magumu | Kinangop | Magumu |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | 0 | 1500000 | 100% | 1500000 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7008 | Completion of Boiman market | Completion of a market shade | To Improve Market Trading conditions | Completed Boiman Market | Completion of Boiman market | OljoroOrok | Gathanji |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 1999642 | 1999642 | 1999642 | CGN | N/A | 1999642 | 0 | 1999642 | 100% | 1999642 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7009 | Completion of ndunyu njeru market | Completion of a market shade | To Improve Market Trading conditions | Completed Ndunyu Njeru Market | Completion of ndunyu njeru market | Kinangop | North Kinangop |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 2499885 | 2499885 | 2499885 | CGN | N/A | 2499885 | 0 | 2499885 | 100% | 2499885 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7010 | Engineer wholesale market | Upgrade of Engineer wholesale market | To Improve Market Trading conditions | Completed Engineer wholasale market | Engineer wholesale market | Kinangop | Gathaara |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 4999698 | 4999698 | 4999698 | CGN | N/A | 4999698 | 0 | 4999698 | 100% | 4999698 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7011 | Completion of market structures at miharati market | Completion of a market shade | To Improve Market Trading conditions | Completed market structures | Completion of market structures at miharati market | Kipipiri | Kipipiri |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 2997948 | 2997948 | 2997948 | CGN | N/A | 2997948 | 0 | 2997948 | 100% | 2997948 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7012 | Market stalls njabini | Construction of market stalls | To Improve Market Trading conditions | Completed market stalls | Market stalls njabini | Kinangop | Njabini |  | Productive Sector | Jul 2021 | June 2022 | June 2022 | 2997948 | 2997948 | 2997948 | CGN | N/A | 2997948 | 0 | 2997948 | 100% | 2997948 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7013 | Cottage industry support for Magumu, ndunyu njeru and engineer(waste solar dryer, shredders and compactors) | Provision of Cottage industries equipment | To Improve livelihoods | Supported cottage industries | Cottage industry support for Magumu, ndunyu njeru and engineer(waste solar dryer, shredders and compactors) | Kinangop | Magumu, North Kinangop, Gathaara |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 2000000 | 1999500 | 1999500 | CGN | N/A | 1999500 | 0 | 1999500 | 100% | 1999500 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7014 | Repair of toilets- Njabini | Renovation of toilets | To Improve hygiene and sanitation | Repaired toilets | Repair of toilets- Njabini | Kinangop | Njabini |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 1000000 | 999200 | 999200 | CGN | N/A | 999200 | 0 | 999200 | 100% | 999200 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7015 | Leshau Pondo- Gwa Kungu market shed | Construction of a market shed | To Improve Market Trading conditions | Constructed market shed | Leshau Pondo- Gwa Kungu market shed | Ndaragwa | Leshau Pondo |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 3000000 | 0 | 0 | CGN | N/A | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7016 | Kaimbaga Ward Construction of Thitai Toilet | Construction of a toilet | To Improve hygiene and sanitation | Constructed Toilet | Kaimbaga Ward Construction of Thitai Toilet | Olkalou | Kaimbaga |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 1100000 | 1099582 | 1099582 | CGN | N/A | 1099582 | 0 | 1099582 | 100% | 1099582 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7017 | Proposed construction of perimeter wall phase 1 for the potato processing warehouse - Edmar enterprises limited | Construction of a perimeter wall | To Improve potato processing warehouse security | Constructed Perimeter wall | Proposed construction of perimeter wall phase 1 for the potato processing warehouse - Edmar enterprises limited | Olkalou | Kaimbaga |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 16112945 | 5206841 | 5206841 | CGN | N/A | 5206841 | 0 | 5206841 | 100% | 5206841 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7018 | Levelling of Wanjohi market | Levelling of a market | To Improve Market Trading conditions | Levelled Wanjohi market | Levelling of Wanjohi market | Kipipiri | Wanjohi |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 1561300 | 1561300 | 1561300 | CGN | N/A | 1561300 | 0 | 1561300 | 100% | 1561300 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7019 | Improvement and extension of market shed at Wanjohi market | Improvement of the state of Wanjohi market | To Improve Market Trading conditions | Improved and extended market shed | Improvement and extension of market shed at Wanjohi market | Kipipiri | Wanjohi |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 631699 | 631699 | 631699 | CGN | N/A | 631699 | 0 | 631699 | 100% | 631699 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7020 | Nyakio- Upgrade of Kwa Haraka Town | Upgrade of Kwa haraka Town | To Improve economic activity | Upgraded Haraka Town | Nyakio- Upgrade of Kwa Haraka Town | Kinangop | Nyakio |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 2000000 | 1999950 | 1999950 | CGN | N/A | 1999950 | 0 | 1999950 | 100% | 1999950 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7021 | Upgrade of Kasuku Town | Upgrade of Kasuku Town | To Improve economic activity | Upgraded Kasuku Town | Upgrade of Kasuku Town | OljoroOrok | Weru |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 3000000 | 2996312 | 2996312 | CGN | N/A | 2996312 | 0 | 2996312 | 100% | 2996312 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7022 | Upgrade of Ol'Joro-Orok town | Upgrade of OljoroOrok Town | To Improve economic activity | Upgraded Ol-joroOrok Town | Upgrade of Ol'Joro-Orok town | OljoroOrok | Weru |  | Productive Sector | Jul 2022 | June 2023 | June 2023 | 3000000 | 2999460 | 2999460 | CGN | N/A | 2999460 | 0 | 2999460 | 100% | 2999460 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7023 | Development of County Aggregation and Industrial Park (CAIP) -County contribution | Construction of a CAIP | To Improve farmer's market | Constructed CAIP | Development of County Aggregation and Industrial Park (CAIP) -County contribution | Kinangop | Njabini |  | Productive Sector | Jul 2023 | June 2024 | June 2024 | 500000000 | 464360410 | 75000000 | CGN/National Government | N/A | - | 0 | 75000000 | 15% | - | 0 | 389360410 | Ongoing | 17% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7024 | Upgrade of Soko Mpya (Cladding, Signage,Guttering, Cabro works,renovation of toilets) | Cladding, Signage, Guttering, Cabro works and renovation of toilets | To Improve Market Trading conditions | Upgraded Soko Mpya | Upgrade of Soko Mpya (Cladding, Signage,Guttering, Cabro works,renovation of toilets) | Kinangop | Magumu |  | Productive Sector | Jul 2023 | June 2024 | June 2024 | 10000000 | 0 | - | CGN | N/A | - | 0 | 0 | 0% | - | 0 | 0 | Ongoing | 75% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7025 | Upgrade of Soko Mpya (Phased financing - Cabro works,Market access road Drainage | Cabro works,Market access road Drainage | To Improve economic activity | Market with cabro works | Upgrade of Soko Mpya (Phased financing - Cabro works,Market access road Drainage | Kinangop | Magumu |  | Productive Sector | 2024-07-01 | 2025-06-01 | 2025-06-01 | 4597851 | 4597851 | 4597851 | CGN | N/A | 4597851 | 0 | 4597851 | 100% | 4597851 | 0 | 0 | Ongoing | 70% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7026 | Geta market stalls electricity installation and electrical works | Eletricity Installation | To Improve economic activity | Installed eletricity | Geta market stalls electricity installation and electrical works | Kipipiri | Geta |  | Productive Sector | 2024-07-01 | 2025-06-01 | 2025-06-01 | 1500000 | 1500000 | 1500000 | CGN | N/A | 1500000 | 0 | 1500000 | 100% | 1383599 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7027 | Installation of Solar for water distribution in the arboretum | Solar heating for water distribution | To promote Tourism | Installed Solar | Installation of Solar for water distribution in the arboretum | Olkalou | Kaimbaga |  | Productive Sector | 2024-07-01 | 2025-06-01 | 2025-06-01 | 2200000 | 2200000 | 2200000 | CGN | N/A | 2200000 | 0 | 2200000 | 100% | 2158122 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
TRADE | 7028 | Ol'kalou Arboretum-purchase and installation of swimming pool amenities and accessories | Provision of swimming pool amenties | To promote Tourism | Supplied swimming pool amenties | Ol'kalou Arboretum-purchase and installation of swimming pool amenities and accessories | Olkalou | Kaimbaga |  | Productive Sector | 2024-07-01 | 2025-06-01 | 2025-06-01 | 1999800 | 1999800 | 1999800 | CGN | N/A | 1999800 | 0 | 1999800 | 100% | 1999800 | 0 | 0 | Complete | 100% | N/A | N/A | N/A | N/A | N/A | No |  |  | No | There is no budget allocation | No | There is no budget allocation | No | There is no budget allocation
| 7029 | Crops Development | Potatoes value chain development, Procurement of potato seeds for bulking(1300 50kg bags) | procurement of high quality potato seed | high quality potato seed potato |  | Countywide | Countywide |  | Agriculture | 2013-07-01 | 30/6/2014 | 30/6/2014 | 3365590 | 3365590 | 3365590 | NGC | N/A | 3365590 | 0 | 3365590 | 1% | 3365590 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7030 | Horticultural cold storage facility (1) | Constuction of a Packhouse | Reduce Horticultural post-harvest losses | 1 pack house |  | Olkalou | Kaimbaga |  | Agriculture | 2013-07-01 | 30/6/2015 | On-going | 25000000 | 25000000 | 25000000 | NGC | N/A | 25000000 | 0 | 25000000 | 1% | 25000000 | N/A | 0 | Ongoing | 50 | _ | _ | _ | _ | _ | Yes | Provide moer funds for completion | No risks | Yes | No risks | Yes | project enviromentally friendly | Yes | Additional funding
| 7031 | Fruit trees value chain development | Fruit trees promotion | Increase farm incomes | increasd acreage under fruits production |  | All sub counties | All Wards |  | Agriculture | 2013-07-01 | 30/6/2014 | 30/6/2014 | 3293900 | 3293880 | 3293900 | NGC | N/A | 3293900 | 0 | 3293900 | 1% | 3293900 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7032 | Pyrethrum value chain & infrastructural development | Bulking of pyrethrum seedlings, Assorted inputs – fertilizers, herbicides,foliar | Increase farm incomes | increasd acreage under pyrethrum production |  | Olkalou | Karau- Mawingu pyrethrum farm |  | Agriculture | 2013-07-01 | 30/6/2014 | 30/6/2014 | 1500000 | 1500000 | 1500000 | NGC | N/A | 1500000 | 0 | 1500000 | 1% | 1500000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7033 | Irrigation development | Baraka Irrigation scheme | increase farm productivity | increasd acreage underirrigation by 2000 acres |  | Olkalou | Kaimbaga |  | Agriculture | 2013-07-01 | 30/6/2014 | 30/6/2014 | 4000000 | 4000000 | 4000000 | NGC | N/A | 4000000 | 0 | 4000000 | 1% | 4000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7034 |  | Thiririka irrigation scheme | increase farm productivity | increasd acreage underirrigation by 2000 acres |  | Kinangop | Magumu |  | Agriculture | 2013-07-01 | 30/6/2014 | 30/6/2014 | 3000000 | 3000000 | 3000000 | NGC | N/A | 3000000 | 0 | 3000000 | 1% | 3000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7035 |  | MwihokoGithima scheme irrigation | increase farm productivity | increasd acreage underirrigation by 2500 acres |  | Ndaragwa | Shamata |  | Agriculture | 2013-07-01 | 30/6/2014 | 30/6/2014 | 4000000 | 3000000 | 4000000 | NGC | N/A | 4000000 | 0 | 4000000 | 1% | 4000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7036 | Agricultural Institutions support | Purchase of Agricultural Equipment | Enable the AMS serve farmers better | 1 disc plough procured |  | AMS Nyahururu | AMS Nyahururu |  | Agriculture | 2013-07-01 | 30/6/2014 | 30/6/2014 | 625000 | 625000 | 625000 | NGC | N/A | 625000 | 0 | 625000 | 1% | 625000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7037 | Potato value chain development | Procure certified potato seed to give to potato farmers | increase productivity in potato farms | 1800 50kg bags potato seed d |  | Countywide | Countywide |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 8000000 | 6770000 | 6770000 | NGC | N/A | 6770000 | 0 | 6770000 | 1% | 6770000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7038 | Horticultural cold storage facility (1) | Constuction of a Packhouse | Reduce Horticultural post-harvest losses | 1 pack house constructed |  | Olkalou | Kaimbaga |  | Agriculture | 2014-07-01 | 30/6/2015 | On-going | 25000000 | 25000000 | 25000000 | NGC | N/A | 25000000 | 0 | 25000000 | 1% | 25000000 | N/A | 0 | Ongoing | 70 | _ | _ | _ | _ | _ | Yes | _ | No risks | Yes | No risks | Yes | project enviromentally friendly | Yes | Additional funding
| 7039 | Pyrethrum value chain & infrastructural development | Bulking of pyrethrum seedlings, Assorted inputs – fertilizers, herbicides,foliar | Increase farm incomes | increased acreage under pyrethrum production |  | Olkalou | Karau, Mawingu PBK farm |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 5000000 | 5000000 | 5000000 | NGC | N/A | 5000000 | 0 | 5000000 | 1% | 5000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7040 | Cut flower value chain development | Construction of flower grading shed | Reduce Horticultural post-harvest losses | 1 grading shed constructed |  | Kinangop | Njabini ATC |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 4500000 | 3094877 | 3094877 | NGC | N/A | 3094877 | 0 | 3094877 | 1% | 3094877 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7041 | Commercial peas value chain development -Procurement of lorry | Procure a lorry that would assit peas farmers in their transport needs eg bulk inputs buying | Make commercial peas farming more profitable | 1 lorry procured |  | Countywide | Countywide |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 5500000 | 4900000 | 4900000 | NGC | N/A | 4900000 | 0 | 4900000 | 1% | 4900000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7042 | Soil and Feeds testing Laboratory Equipment | procurement of lab equipment | Increase productivity in farm and animal production | Soil and Feeds testing Laboratory Equipmentprocured |  | Nyahururu | Nyahururu Vet Labs |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 10000000 | 8911840 | 8911840 | NGC | N/A | 8911840 | 0 | 8911840 | 1% | 8911840 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7043 | Agricultural Institutions Support And Infrastructure Development | Purchase of potato digger (2) | Make the institutions more efficient in service delivery | 1 potato digger procured |  | Nyahururu | AMS Station |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 4000000 | 4625000 | 4625000 | NGC | N/A | 4625000 | 0 | 4625000 | 1% | 4625000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7044 |  | Purchase of Potato planter (2) | Make the institutions more efficient in service delivery | 1 Potato planter procured |  | Nyahururu | AMS Station |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 600000 | 1387500 | 1387500 | NGC | N/A | 1387500 | 0 | 1387500 | 1% | 1387500 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7045 |  | Purchase of plant and Equipment (2 tractors) | Make the institutions more efficient in service delivery | 2 tractors) procured |  | Nyahururu | AMS Station |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 8350000 | 8350000 | 8350000 | NGC | N/A | 8350000 | 0 | 8350000 | 1% | 8350000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7046 |  | Completion of Oljoroorok office block | Make the institutions more efficient in service delivery | Oljoroorok ATC office block |  | Oljoroorok | Oljoroorok ATC |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 1440000 | 3086990 | 3086990 | NGC | N/A | 3086990 | 0 | 3086990 | 1% | 3086990 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7047 |  | Construction of Diffused Light store (1) | Make the institutions more efficient in service delivery | 1 Diffused Light store |  | Njabini | Njabini ATC |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 1800000 | 1761023 | 1761023 | NGC | N/A | 1761023 | 0 | 1761023 | 1% | 1761023 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7048 |  | Completion of hostel | Make the institutions more efficient in service delivery | 1 hostel constructed |  |  | Oljoroorok ATC |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 7360000 | 5958455 | 5958455 | NGC | N/A | 5958455 | 0 | 5958455 | 1% | 5958455 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7049 | Irrigation Development | Baraka Irrigation scheme | increase farm productivity | increasd acreage underirrigation |  | Olkalou | Kaimbaga |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 3000000 | 2023004 | 2023004 | NGC | N/A | 2023004 | 0 | 2023004 | 1% | 2023004 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7050 |  | Ndinda irrigation scheme | increase farm productivity | increasd acreage underirrigation |  | Kipipiri | Wanjohi |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 1440000 | 1388470 | 1388470 | NGC | N/A | 1388470 | 0 | 1388470 | 1% | 1388470 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7051 |  | Muthuri irrigation scheme | increase farm productivity | increasd acreage underirrigation |  | Ndaragwa | Central |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 2400000 | 1996710 | 1996710 | NGC | N/A | 1996710 | 0 | 1996710 | 1% | 1996710 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7052 |  | Thiririka irrigation scheme | increase farm productivity | increasd acreage underirrigation |  | Kinangop | Magumu |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 5356000 | 3000000 | 3000000 | NGC | N/A | 3000000 | 0 | 3000000 | 1% | 3000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7053 |  | MwihokoGithima | increase farm productivity | increasd acreage underirrigation |  | Ndaragwa- | Shamata |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 3000000 | 1817000 | 1817000 | NGC | N/A | 1817000 | 0 | 1817000 | 1% | 1817000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7054 | Water harvesting for food security and dam development | Rehabilitation of Kaimbaga and Gatumbiro Bore holes | increase farm productivity | increasd acreage underirrigation |  | Olkalou and Oljoroorok | Kaimbaga and Weru |  | Agriculture | 2014-07-01 | 30/6/2015 | 30/6/2015 | 7891600 | 6750000 | 6750000 | NGC | N/A | 6750000 | 0 | 6750000 | 1% | 6750000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7055 | Subsidized fertilizer | Procurement and distribution of fertilizer | Increase farm productivity | (DAP-3510bags23:23:0-1820 bags) |  | County wide | County wide |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 16248217 | 15008500 | 15008500 | NGC | N/A | 15008500 | 0 | 15008500 | 1% | 15008500 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7056 | Horticulture cold storage –Partial Completion | Partial completion of pack house | Reduse horticultural post harvest losses | 1 pack house/cold storage |  | Olkalou | Kaimbaga ward |  | Agriculture | 2015-01-07 | 30/6/2016 | Ongoing | 8328750 | 8328750 | 8328750 | NGC | N/A | 8328750 | 0 | 8328750 | 1% | 8328750 | N/A | 0 | Ongoing | 80 | _ | _ | _ | _ | _ | Yes | Provide moer funds for completion | No risks | Yes | No risks | Yes | project enviromentally friendly | Yes | Additional funding
| 7057 | Mobile soil and feeds testing laboratory | Rehabilitation of veterinary laboratory | Enable to to use specific fertilizers as per need | 1 soil testing laboratory |  | Ndaragwa | Kiriitaward |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 4000000 | 1859480 | 1859480 | NGC | N/A | 1859480 | 0 | 1859480 | 1% | 1859480 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7058 | ProsekiaSelf help group kiburu value chain | Procurement of farm inputs | Farmers empowerment | Various farm inputs |  | Kinangop | Njabini Ward |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1462094 | 1447600 | 1447600 | NGC | N/A | 1447600 | 0 | 1447600 | 1% | 1447600 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7059 | Institutions Support and Infrastructure Development | Completion of kitchen- Njabini ATC | Improve the ATCs service delivery | 1 complete kitchen |  | Kinangop | Njabini ATC |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1000000 | 998185 | 998185 | NGC | N/A | 998185 | 0 | 998185 | 1% | 998185 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7060 | Irrigation Development | Expansion of Silibwetwaterpan | Water provision | 1 water pan improved |  | Oljoroorok | Gathanji ward |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 2500000 | 1275368 | 1275368 | NGC | N/A | 1275368 | 0 | 1275368 | 1% | 1275368 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7061 |  | Kwanjora borehole and elevated tank platform | Increase farm productivity | 1 borehole |  | Ndaragwa | Kiirita ward |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 3400000 | 2336460 | 2336460 | NGC | N/A | 2336460 | 0 | 2336460 | 1% | 2336460 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7062 |  | Kiboya borehole & solar pump | Increase farm productivity | 1 borehole |  | Ndaragwa | LeshauPondo ward |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 5000000 | 6173340.5 | 6173340.5 | NGC | N/A | 6173340.5 | 0 | 6173340.5 | 1% | 6173340.5 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7063 |  | Genesis irrigation project | Increase farm productivity | 1 irrigation project |  | Ndaragwa | Central ward |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 2000000 | 1975720 | 1975720 | NGC | N/A | 1975720 | 0 | 1975720 | 1% | 1975720 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7064 | Institutions Support and Infrastructure Development | Purchase of plant and equipment- tractor | Improve the institutions service delivery | 1 tractor |  | Nyahururu | AMS Nyahururu |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 4600000 | 4482480 | 4482480 | NGC | N/A | 4482480 | 0 | 4482480 | 1% | 4482480 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7065 |  | Acquisition of plant and equipment-chisel plough | Improve the institutions service delivery | 1 chisel plough |  | Nyahururu | AMS Nyahururu |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1625000 | 1238000 | 1238000 | NGC | N/A | 1238000 | 0 | 1238000 | 1% | 1238000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7066 |  | Acquisition of plant and equipment-low bed trolley | Improve the institutions service delivery | 1 low bed trolley |  | Nyahururu | AMS Nyahururu |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 300000 | 299650 | 299650 | NGC | N/A | 299650 | 0 | 299650 | 1% | 299650 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7067 | Irrigation Development | Water tank and pump for gatumbiro&Kaimbaga irrigation project | Increase farm productivity | 1 complete irrigation project |  | Oljoroorok & Olkalou | Weru & Kaimbaga ward |  | Agriculture | 2015-01-07 | 30/6/2016 | 30/6/2016 | 4300000 | 4115988 | 4115988 | NGC | N/A | 4115988 | 0 | 4115988 | 1% | 4115988 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7068 | Pack house completion | Construction of a cold storage | Reduse horticultural post harvest lossses | 1Pack house |  | Olkalou | Karau |  | Agriculture | 2016-01-07 | 30/6/2017 | Ongoing | 3000000 | 3000000 | 3000000 | NGC | N/A | 3000000 | 0 | 3000000 | 1% | 3000000 | N/A | 0 | Ongoing | 85 | _ | _ | _ | _ | _ | Yes | Provide moer funds for completion | No risks | Yes | No risks | Yes | project enviromentally friendly | Yes | Additional funding
| 7069 | Pyrethrum development | provide farmers with seedlings | Provide enterprise diversification | pyrethrum seedlings |  | All sub counties | Countywide |  | Agriculture | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | NGC | N/A | 3000000 | 0 | 3000000 | 1% | 3000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7070 | Soil and feed testing laboratory | Renovation of soil and feeds lab | Improve Soil and feeds testing | 1 Soil and feed testing laboratory renovated |  | Ndaragwa | Shamata |  | Agriculture | 2016-01-07 | 30/6/2017 | 30/6/2017 | 5559480 | 1859480 | 1859480 | NGC | N/A | 1859480 | 0 | 1859480 | 1% | 1859480 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7071 | Shamata Green houses | Provide a green house to shamata group | Improve farm incomes | 2 Green houses |  | Olkalou | Kaimbaga |  | Agriculture | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1700000 | 1680000 | 1680000 | NGC | N/A | 1680000 | 0 | 1680000 | 1% | 1680000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7072 | Purchase of potatoes and related materials-Polseki | Make high quality potato seed avilable to potato famers | high quality seed potato | quality seed potato provided |  | Kinangop | Njabini |  | Agriculture | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2400000 | 2350000 | 2350000 | NGC | N/A | 2350000 | 0 | 2350000 | 1% | 2350000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7073 | Njabini ATC Kitchen | Construction of a kitchen | Improve the institutions service delivery | 1 kitchen |  | Kinangop | Njabini ATC |  | Agriculture | 2016-01-07 | 30/6/2017 | 30/6/2017 | 998185 | 998185 | 998185 | NGC | N/A | 998185 | 0 | 998185 | 1% | 998185 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7074 | Subsidized fertilizers (ward specific shs -200,000) | Procurement and distribution of fertilizer | Increase farm productivity | Subsidized fertilizer |  | Countywide | Countywide |  | Agriculture | 2016-01-07 | 30/6/2017 | 30/6/2017 | 10053795 | 9853795 | 9853795 | NGC | N/A | 9853795 | 0 | 9853795 | 1% | 9853795 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7075 | Giant Bamboo seedlings | Provide farmers with bamboo seedlings | Soil conservation | Supplied seedlings |  | Countywide | Countywide |  | Agriculture | 2017-01-07 | 30/6/2018 | 30/6/2018 | 900000 | 900000 | 900000 | NGC | N/A | 900000 | 0 | 900000 | 1% | 900000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7076 | Input subsidy- Fertilizer | Procurement and distribution of fertilizer | Increase farm productivity | Fertilizer delivered. |  | Countywide | Countywide |  | Agriculture | 2017-01-07 | 30/6/2018 | 30/6/2018 | 20000000 | 19599000 | 19599000 | NGC | N/A | 19599000 | 0 | 19599000 | 1% | 19599000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7077 | Purchase of Potato seeds ( Polsekia groups) | Potatoes value chain development, Procurement of potato seeds for bulking | Make high quality potato seed avilable to potato famers | high quality potato seed potato |  | Kinangop | Njabini |  | Agriculture | 2017-01-07 | 30/6/2018 | 30/6/2018 | 1400000 | 1398000 | 1398000 | NGC | N/A | 1398000 | 0 | 1398000 | 1% | 1398000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7078 | Subsidized AI | Provide subsidised fertilizer | Increase farm productivity | AI servings made |  | Countywide | Countywide |  | Agriculture | 2017-01-07 | 30/6/2018 | 30/6/2018 | 8600000 | 7908225 | 7908225 | NGC | N/A | 7908225 | 0 | 7908225 | 1% | 7908225 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7079 | Purchase of Pond liners, fish cages ,and seine nets- Oljoroork ATC | Provide Pond liners, fish cages ,and seine nets- Oljoroork ATC | provide institution with a fish training opportunity | Pond liners, fish cages ,and seine nets |  | Oljoroorok | Oljoroorok ATC |  | Agriculture | 2017-01-07 | 30/6/2018 | 30/6/2018 | 1500000 | 1366316 | 1366316 | NGC | N/A | 1366316 | 0 | 1366316 | 1% | 1366316 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7080 | Acaricides | Provide farmers with high quality acaricides | Reduse ticks prevalence in livestock | Acaricides procured |  | Countywide | Countywide |  | Agriculture | 2017-01-07 | 30/6/2018 | 30/6/2018 | 4200000 | 4000000 | 4000000 | NGC | N/A | 4000000 | 0 | 4000000 | 1% | 4000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7081 | Breeding stock (rabbits and feeds). | procure for the ATC Breeding stock | provide institution with a rabbit rearing training opportunity | Rabbits procured |  | Oljoroorok | Oljoroorok ATC |  | Agriculture | 2017-01-07 | 30/6/2018 | 30/6/2018 | 400000 | 390860 | 390860 | NGC | N/A | 390860 | 0 | 390860 | 1% | 390860 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7082 | Agric. Machinery &equipments | Purchase of Agric. Machinery &equipments- | Improve the institutions service delivery | 3no. of 4WD tractors-AMS Nyahururu |  | Nyahururu | AMS Nyahururu |  | Agriculture | 2017-01-07 | 30/6/2018 | 30/6/2018 | 10500000 | 10007800 | 10007800 | NGC | N/A | 10007800 | 0 | 10007800 | 1% | 10007800 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7083 | irrigation system in Oljoro-Orok ATC | Installation of irrigation system in Oljoro-Orok ATC | Increase ATC farm productivity | 1 irrigation system |  | Oljoroorok | Oljoro-Orok ATC |  | Agriculture | 2017-01-07 | 30/6/2018 | 30/6/2018 | 700000 | 505680 | 505680 | NGC | N/A | 505680 | 0 | 505680 | 1% | 505680 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7084 | Veterinary supplies and materials | procure Veterinary supplies and materials | strengthen the vet Department | supplies and materials |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 400000 | 398500 | 398500 | NGC | N/A | 398500 | 0 | 398500 | 1% | 398500 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7085 | vaccination equipments | Procure Vet vaccination equipments | supply vet vaccination equipments to the Department | vaccination equipments |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 500000 | 475600 | 475600 | NGC | N/A | 475600 | 0 | 475600 | 1% | 475600 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7086 | Supplies for Production- Acaricides and drugs | Procure Vet Acaricides and drugs | supply Acaricides and drugsto the Department | Acaricides and drugs |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 3000000 | 2980070 | 2980070 | NGC | N/A | 2980070 | 0 | 2980070 | 1% | 2980070 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7087 | Purchase of vaccines & sera | Procure Vet vaccines & sera | supply vaccines & sera to the Department | vaccines & sera |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 8000000 | 8000000 | 8000000 | NGC | N/A | 8000000 | 0 | 8000000 | 1% | 8000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7088 | Veterinary supplies and materials-liquid nitrogen | Procure liquid nitrogen | supply liquid nitrogen to the Department | liquid nitrogen |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 1000000 | 1000000 | 1000000 | NGC | N/A | 1000000 | 0 | 1000000 | 1% | 1000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7089 | Veterinary supplies and materials- Semen | Procure Semen | supply Semento the Department | Semen |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 3050000 | 3050000 | 3050000 | NGC | N/A | 3050000 | 0 | 3050000 | 1% | 3050000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7090 | Accessories (Haver sack, universal pistollets, socks) | Procure Accessories | supply Accessoriesto the Department | Accessories |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 700000 | 656600 | 656600 | NGC | N/A | 656600 | 0 | 656600 | 1% | 656600 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7091 | Emergency chemicals for pests control | Purchase of emergency chemicals for pests control | supply emergency chemicals to the Department | emergency chemicals |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 2000000 | 1925300 | 1925300 | NGC | N/A | 1925300 | 0 | 1925300 | 1% | 1925300 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7092 | Sunflower production | Procure sunflower seeds | Empower sunflower farmers | sunflower seeds |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 1000000 | 980000 | 980000 | NGC | N/A | 980000 | 0 | 980000 | 1% | 980000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7093 | Fruit seedlings | Procure Fruit seedlings | Empower Fruit farmers | Fruit seedlings |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 1000000 | 924000 | 924000 | NGC | N/A | 924000 | 0 | 924000 | 1% | 924000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7094 | Rehabilitation of cattle dips | Rehabilitation of cattle dips and recharge with Accaricides | Tick control | Rehabilitated of cattle dips |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 5000000 | 4895000 | 4895000 | NGC | N/A | 4895000 | 0 | 4895000 | 1% | 4895000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7095 | Purchase of spraying equipment | Purchase of spraying equipment | decease control | Purchase of spraying equipment |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 2000000 | 1745900 | 1745900 | NGC | N/A | 1745900 | 0 | 1745900 | 1% | 1745900 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7096 | Quality fodder production | procure assorted fodder seeds | Improve milk production | assorted fodder seeds |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 2000000 | 1800000 | 1800000 | NGC | N/A | 1800000 | 0 | 1800000 | 1% | 1800000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7097 | CAB hives starter kits for bee keeping groups | Procure KTBH | Empower bee keeping farmers | KTBH Hives |  |  | Kinangop |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 1250000 | 1246000 | 1246000 | NGC | N/A | 1246000 | 0 | 1246000 | 1% | 1246000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7098 | Development and supply of Piglets | ProcurePiglets | Empower pig keeping farmers | Piglet procured |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 2000000 | 1825000 | 1825000 | NGC | N/A | 1825000 | 0 | 1825000 | 1% | 1825000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7099 | Model zero grazing unit at Nyandarua school for the deaf | construct a Model zero grazing unit | EmpowerNyandarua school for the deaf | 1 Model zero grazing unit |  | Kinangop | Gathara |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 1250000 | 1030040 | 1030040 | NGC | N/A | 1030040 | 0 | 1030040 | 1% | 1030040 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7100 | model zero grazing unit at Kimaru school - kiriita ward | construct a Model zero grazing unit | Empower Kimaru school | 1 Model zero grazing unit |  | Ndaragwa | Kiriita |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 1250000 | 1250600 | 1250600 | NGC | N/A | 1250600 | 0 | 1250600 | 1% | 1250600 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7101 | Purchase of pedigree heifers | Purchase of pedigree heifers | iEnhance milk production | heifers purchsed |  | Countywide | Countywide |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 10000000 | 9000000 | 9000000 | NGC | N/A | 9000000 | 0 | 9000000 | 1% | 9000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7102 | Construction of grading shed - Gathaara | Construction of grading shed - Gathaara | reduce horticultural post harvet losses | 1 grading shed |  | Kinangop | Gathara |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 1000000 | 1000000 | 1000000 | NGC | N/A | 1000000 | 0 | 1000000 | 1% | 1000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7103 | Rehabilitation/Refurshbishment of ATC | Rehabilitation/Refurshbishment of ATC | Improve the ATC infrastructure | Improved ATC infrastructure |  | Oljoroorok | Oljoroorok ATC) |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 27000000 | 26857000 | 26857000 | NGC | N/A | 26857000 | 0 | 26857000 | 1% | 26857000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7104 | Purchase of potato seeds to vulnerable farmers | Purchase of potato seeds to vulnerable farmers | Improved potato yields | quality seed potato provided |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 2000000 | 1910000 | 1910000 | NGC | N/A | 1910000 | 0 | 1910000 | 1% | 1910000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7105 | Purchase of fingerlings and fish feeds | Purchase of fingerlings and fish feeds | Restocking dams with fingerings | procured fingerings |  | Countywide | All Wards |  | Agriculture | 2018-01-07 | 30/6/2019 | 30/6/2019 | 3200000 | 2890050 | 2890050 | NGC | N/A | 2890050 | 0 | 2890050 | 1% | 2890050 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7106 | Pyrethrum promotion | Procurement of pyrethrum seeds and seedlings | Farm diversification | pyrethrum seeds and seedlings |  | County wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1000000 | 927400 | 927400 | NGC | N/A | 927400 | 0 | 927400 | 1% | 927400 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7107 | Giant Bamboo promotion | Procurement of potted bamboo seedling varieties | Farm diversification | 4500 potted bamboo seedling |  | County wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1000000 | 900400 | 900400 | NGC | N/A | 900400 | 0 | 900400 | 1% | 900400 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7108 | Sun flower production | Purchase of sunflower seeds- Variety HB 8663 | Farm diversification | sunflower seeds- Variety HB 8663 |  | County wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1000000 | 854220 | 854220 | NGC | N/A | 854220 | 0 | 854220 | 1% | 854220 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7109 | Fruit trees promotion Avocado seedlings | Procurement of Hass Avocado seedling | Farm diversification | Hass Avocado seedling |  | County wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1000000 | 800000 | 800000 | NGC | N/A | 800000 | 0 | 800000 | 1% | 800000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7110 | Purchase of potato seeds for Mtongwe farmer group | Procurement of potatoes seeds – Shangi/ Unica | Increase productivity in potatoes | potato seeds |  | County Wide | County Wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 750000 | 720000 | 720000 | NGC | N/A | 720000 | 0 | 720000 | 1% | 720000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7111 | Mobile soil testing kit | Procurement of a soil testing kit | Soil analysis | 1 Mobile soil testing kit |  | County wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 700000 | 645000 | 645000 | NGC | N/A | 645000 | 0 | 645000 | 1% | 645000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7112 | Completion of grading shed - Gathaara | Construction works of the grading shed | Reduse horticultural post harvest losses | 1 grading shed |  | Kinangop | Gathaara |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1000000 | 1000000 | 1000000 | NGC | N/A | 1000000 | 0 | 1000000 | 1% | 1000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7113 | Input subsidy- fertilizer | Procurement of fertilizer seeds | Increase productivity | 5800 bags of 50kg |  | County wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 15000000 | 14500000 | 14500000 | NGC | N/A | 14500000 | 0 | 14500000 | 1% | 14500000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7114 | Green houses | Procurement of green houses for Youth and institutions. | improve farm incomes | 1 green house |  | Kinangop | North Kinangop |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1000000 | 970000 | 970000 | NGC | N/A | 970000 | 0 | 970000 | 1% | 970000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7115 | Purchase of vaccines & sera | Procure Vet vaccines & sera | supply vaccines & sera to the Department | vaccines & sera |  | County wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 4001600 | 4000000 | 4000000 | NGC | N/A | 4000000 | 0 | 4000000 | 1% | 4000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7116 | Veterinary supplies and materials-liquid nitrogen | Procure liquid nitrogen | supply liquid nitrogen to the Department | liquid nitrogen |  | County Wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 991000 | 843000 | 843000 | NGC | N/A | 843000 | 0 | 843000 | 1% | 843000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7117 | Veterinary supplies and materials- Semen | Procure Semen | supply Semento the Department | Semen |  | County wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1500000 | 1500000 | 1500000 | NGC | N/A | 1500000 | 0 | 1500000 | 1% | 1500000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7118 | Accessories (Haver sack, universal pistollets, socks) | Procure Accessories | supply Accessoriesto the Department | Accessories |  | County Wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 400000 | 398000 | 398000 | NGC | N/A | 398000 | 0 | 398000 | 1% | 398000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7119 | Purchase of 8 Motorcycles for A.I service providers | Purchase of 8 Motorcycles for A.I service providers | enhance AI sevices | 8 Motorcycles |  | County wide | County wide |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1000000 | 1000000 | 1000000 | NGC | N/A | 1000000 | 0 | 1000000 | 1% | 1000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7120 | Purchase of Agric. Machinery & equipment’s- 1-row ridge former | Purchase of Agric. Machinery & equipment’s- 1-row ridge former | Improve the institutions service delivery | 1-row ridge former |  | Kinangop | AMS - Kinangop |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 250000 | 235000 | 235000 | NGC | N/A | 235000 | 0 | 235000 | 1% | 235000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7121 | Purchase of Agric. Machinery & equipment- Flail mower | Purchase of Agric. Machinery & equipment’s- Flail mower | Improve the institutions service delivery | 1 Flail mower |  | Kinangop | AMS - Kinangop |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 350000 | 300000 | 300000 | NGC | N/A | 300000 | 0 | 300000 | 1% | 300000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7122 | Model zero grazing unit | Construct a Model zero grazing unit | Enhance the institutions training and production capacity | 1 Model zero grazing unit |  | Kinangop | AtcNjabini |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 2500000 | 2430000 | 2430000 | NGC | N/A | 2430000 | 0 | 2430000 | 1% | 2430000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7123 | Machinery and equipment shed | Construct aMachinery and equipment shed | Enhance the institutions machinery safe keeping | 1 Machinery and equipment shed |  | Kinangop | AtcNjabini |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1500000 | 1305800 | 1305800 | NGC | N/A | 1305800 | 0 | 1305800 | 1% | 1305800 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7124 | Completion of grading shed-Mirangine | Construct a grading shed | Reduse horticultural post harvest losses | 1 grading shed |  | Olkalou | Mirangine |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1000000 | 950000 | 950000 | NGC | N/A | 950000 | 0 | 950000 | 1% | 950000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7125 | Green Houses | procure a geen house for Kambi Mbao Youth Group | Youth empowermmment | 1 Green House |  |  |  |  | Agriculture | 2019-01-07 | 30/6/2020 | 30/6/2020 | 1000000 | 770000 | 770000 | NGC | N/A | 770000 | 0 | 770000 | 1% | 770000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7126 | Purchase of 5 motorized chaff cutters for youth groups | Procurement of 5 motorized chaff cutters | Youth empowermmment | 5 motorized chaff cutters |  | Countywide | County wide |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 500000 | 475000 | 475000 | NGC | N/A | 475000 | 0 | 475000 | 1% | 475000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7127 | Poultry & feeds for women, youth and vulnerable groups for Kiriita | purchse of Poultry & feeds for women, youth and vulnerable groups for Kiriita | Women and Youth empowermmment | Poultry & feeds |  | Ndaragwa | Kiirirta Ward |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 1000000 | 895280 | 895280 | NGC | N/A | 895280 | 0 | 895280 | 1% | 895280 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7128 | Supplies for Production- Acaricides and drugs | Procurement of Acaricides and drugs | Tick control | Acaricides and drugs |  | Countywide | Countywide |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 1000000 | 954000 | 954000 | NGC | N/A | 954000 | 0 | 954000 | 1% | 954000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7129 | Purchase of vaccines & sera (flagship project) | Procurement of vaccines & sera | supply vaccines & sera to the Department | vaccines & sera |  | Countywide | Countywide |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 5000000 | 5000000 | 5000000 | NGC | N/A | 5000000 | 0 | 5000000 | 1% | 5000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7130 | Veterinary supplies and materials- liquid nitrogen | Procurement of liquid nitrogen | supply liquid nitrogen to the Department | liquid nitrogen |  | Countywide | Countywide |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 800000 | 780000 | 780000 | NGC | N/A | 780000 | 0 | 780000 | 1% | 780000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7131 | Veterinary supplies and materials- Semen | Procurement of Semen | supply Semento the Department | Semen |  | Countywide | Countywide |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 1200000 | 1200000 | 1200000 | NGC | N/A | 1200000 | 0 | 1200000 | 1% | 1200000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7132 | Accessories (Haver sack, universal pistollets, socks) | Procurement of Accessories | supply Accessoriesto the Department | Accessories |  | Countywide | Countywide |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 400000 | 390000 | 390000 | NGC | N/A | 390000 | 0 | 390000 | 1% | 390000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7133 | Pyrethrum promotion | Procurement of Pyrethrum seedlings | Enterprises diverification | Pyrethrum seedlings |  | Countywide | Countywide |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 1000000 | 940500 | 940500 | NGC | N/A | 940500 | 0 | 940500 | 1% | 940500 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7134 | Input subsidy (fertilizer and seeds)(flagship project) | Procurement of fertilizer | Enhance farm productivity | fertilizer and seeds |  | Countywide | Countywide |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 15000000 | 14860000 | 14860000 | NGC | N/A | 14860000 | 0 | 14860000 | 1% | 14860000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7135 | Purchase of potato seeds -Njabini | Procurement of seed potato | Access to high quality seed potato | quality seed potato provided |  | Kinangop | Njabini-Kiburu Ward |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 1000000 | 960000 | 960000 | NGC | N/A | 960000 | 0 | 960000 | 1% | 960000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7136 | Purchase of certified seeds to farmers groups- Kanjuiri ward | Procurement of certified seeds | Enhance farm productivity | Seed Potato |  | Olkalou | Kanjuiri Ward |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 1000000 | 985000 | 985000 | NGC | N/A | 985000 | 0 | 985000 | 1% | 985000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7137 | Purchase of certified seeds to farmers groups-Gathanji | Procurement of certified seeds | Enhance farm productivity | Assorted certified seeds |  | Oljoroorok | Gathanji Ward |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 1500000 | 1464800 | 1464800 | NGC | N/A | 1464800 | 0 | 1464800 | 1% | 1464800 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7138 | purchase of potato seeds -Charagita | Procurement of seed potato | Enhance farm productivity | Seed Potato |  | Oljoroorok | Charagita Ward |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 1500000 | 1450000 | 1450000 | NGC | N/A | 1450000 | 0 | 1450000 | 1% | 1450000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7139 | Farm inputs to N. Kinangop horticultural farmers | Procurement of Farm inputs | Enhance farm productivity | Assorted certified seeds |  | Kinangop | N. Kinangop Ward |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 3000000 | 2983020 | 2983020 | NGC | N/A | 2983020 | 0 | 2983020 | 1% | 2983020 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7140 | Rehabilitation/Refurbishment of atcOl'Joro'Orok and other infrastructural | Rehabilitation of the ATC | Make the institutions more efficient in service delivery | Rehabilitated Oljoroorok ATC office block |  | Oljoroorok | Gatimu |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 1000000 | 980000 | 980000 | NGC | N/A | 980000 | 0 | 980000 | 1% | 980000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7141 | Specialized agricultural equipment (Boom sprayer) | Procurement of a Boom sprayer | Make the institutions more efficient in service delivery | 1 Boom sprayer |  | Kinangop | Njabini ATC |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 700000 | 670000 | 670000 | NGC | N/A | 670000 | 0 | 670000 | 1% | 670000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7142 | Purchase of Agric. Machinery &equipments- 1 no. three bottom disc plough | Procurement of a three bottom disc plough | Make the institutions more efficient in service delivery | 1 no. three bottom disc plough |  | Nyahururu | Nyahururu AMS |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 550000 | 505000 | 505000 | NGC | N/A | 505000 | 0 | 505000 | 1% | 505000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7143 | Purchase of Agric. Machinery &equipments - 1No. Three bottom disc plough | Procurement of a Three bottom disc plough | Make the institutions more efficient in service delivery | 1No. Three bottom disc plough |  | Kinangop | Njabini |  | Agriculture | 2020-01-07 | 30/6/2021 | 30/6/2021 | 550000 | 540000 | 540000 | NGC | N/A | 540000 | 0 | 540000 | 1% | 540000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7144 | Quality fodder production (planting materials and seeds) | Purchase Quality fodder production (planting materials and seeds) | Improve livestoc production | planting materials and seeds |  | Countywide | Countywide |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 1000000 | 946000 | 946000 | NGC | N/A | 946000 | 0 | 946000 | 1% | 946000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7145 | Supplies for Production- Acaricides and drugs (East Coast Fever Control Program) | Procurement of Acaricides and drugs | Tick control | Acaricides and drugs |  | Countywide | Countywide |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 2400000 | 2358200 | 2358200 | NGC | N/A | 2358200 | 0 | 2358200 | 1% | 2358200 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7146 | Purchase of vaccines & sera (vaccination program) | Procurement of vaccines & sera | supply vaccines & sera to the Department | vaccines & sera |  | Countywide | Countywide |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 4500000 | 4500000 | 4500000 | NGC | N/A | 4500000 | 0 | 4500000 | 1% | 4500000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7147 | Veterinary supplies and materials- liquid nitrogen (Free A.I Program) | Procurement of liquid nitrogen | supply liquid nitrogen to the Department | liquid nitrogen |  | Countywide | Countywide |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 1200000 | 1200000 | 1200000 | NGC | N/A | 1200000 | 0 | 1200000 | 1% | 1200000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7148 | Veterinary supplies and materials- Semen (Free A.I Program) | Procurement of Semen | supply Semento the Department | Semen |  | Countywide | Countywide |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 3000000 | 2900000 | 2900000 | NGC | N/A | 2900000 | 0 | 2900000 | 1% | 2900000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7149 | Supplies for Production-trout fish feeds and fish medicine | Procurement of trout fish feeds and fish medicine | supply trout fish feeds and fish medicine to Geta Trout farm | trout fish feeds and fish medicine |  | Countywide | Countywide |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 401000 | 398000 | 398000 | NGC | N/A | 398000 | 0 | 398000 | 1% | 398000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7150 | Stocking of dams and ponds with fingerlings | procure fish fingerings |  |  |  | Countywide | Countywide |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 500000 | 478200 | 478200 | NGC | N/A | 478200 | 0 | 478200 | 1% | 478200 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7151 | Supply of seedlings-Ndaragwa Central | Procurement of quality farm inputs | Enhanced farm productivity | farm inputs procured |  | Countywide | Countywide |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 2000000 | 1890400 | 1890400 | NGC | N/A | 1890400 | 0 | 1890400 | 1% | 1890400 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7152 | N. Kinangop Ward- Support to farmers groups with Farm inputs | Procurement of quality farm inputs | Enhanced farm productivity | farm inputs procured |  | Kinangop | N. Kinangop |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 2000000 | 1954000 | 1954000 | NGC | N/A | 1954000 | 0 | 1954000 | 1% | 1954000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7153 | Purchase of farm inputs to farmers groups - Njabini | Procurement of quality farm inputs | Enhanced farm productivity | farm inputs procured |  | Kinangop | Njabini |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 1000000 | 960280 | 960280 | NGC | N/A | 960280 | 0 | 960280 | 1% | 960280 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7154 | Purchase of farm inputs to farmers groups -Engineer | Procurement of quality farm inputs | Enhanced farm productivity | farm inputs procured |  | Kinangop | Engineer |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 700000 | 686450 | 686450 | NGC | N/A | 686450 | 0 | 686450 | 1% | 686450 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7155 | Purchase of farm inputs to farmers groups - Kanjuiri | Procurement of quality farm inputs | Enhanced farm productivity | farm inputs procured |  | Olkalou | Kanjuiri |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 800000 | 770000 | 770000 | NGC | N/A | 770000 | 0 | 770000 | 1% | 770000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7156 | Support to mushroom farming (Positive Vibration Youth Group | Procurement of quality farm inputs | Enhanced farm productivity | farm inputs procured |  | Kinangop | N. Kinangop |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 1000000 | 975000 | 975000 | NGC | N/A | 975000 | 0 | 975000 | 1% | 975000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7157 | Purchase of certified seeds to women groups and vulnerable groups(vegetables seeds) | Procurement of quality farm inputs | Enhanced farm productivity | farm inputs procured |  | Countywide | Countywide |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 1500000 | 1399645280 | 1399645280 | NGC | N/A | 1399645280 | 0 | 1399645280 | 1% | 1399645280 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7158 | Support to farmer groups with potato seeds-Charagita | Procurement of quality farm inputs | Enhanced farm productivity | farm inputs procured |  | Oljoroorok | Charagita |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 3500000 | 3400000 | 3400000 | NGC | N/A | 3400000 | 0 | 3400000 | 1% | 3400000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7159 | Supply and distribution of ovacado tree seedlings- Mirangine | Procurement of quality farm inputs | Enhanced farm productivity | farm inputs procured |  | Olkalou | Mirangine |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 2000000 | 1807000 | 1807000 | NGC | N/A | 1807000 | 0 | 1807000 | 1% | 1807000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7160 | Agricultural materials, supplies and small equipments -Lab equipment | Procurement of Lab equipment | Enhanced scientific investigation | Lab equipment procured |  | Oljoroorok | Gatimu |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 1200000 | 1132060 | 1132060 | NGC | N/A | 1132060 | 0 | 1132060 | 1% | 1132060 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7161 | Purchase of Motorized tractor mounted lawn mower | Procurement of a Motorized tractor mounted lawn mower | Make the institutions more efficient in service delivery | 1 Motorized tractor mounted lawn mower |  | Kinangop | Njabini |  | Agriculture | 2021-01-07 | 30/6/2022 | 30/6/2022 | 500000 | 495000 | 495000 | NGC | N/A | 495000 | 0 | 495000 | 1% | 495000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7162 | Sheep breed improvement Project- Move-on Women Group | Purchase of Sheep for breed improvement | Enhance sheep production | Rams procured |  | Kipipiri | Wanjohi ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 400000 | 400000 | 400000 | NGC | N/A | 400000 | 0 | 400000 | 1% | 400000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7163 | Dairy Goat promotion- breeding stock Simbara | Purchase of Dairy Goats | Enhance Dairy Goat production | Dairy Goats procured |  | Ndaragwea | Shamata ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 2000000 | 1430000 | 1430000 | NGC | N/A | 1430000 | 0 | 1430000 | 1% | 1430000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7164 | Dairy Goat promotion- breeding stock - Karandi | Purchase of Dairy Goats | Enhance Dairy Goat production | Dairy Goats procured |  | Ndaragwea | Shamata ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 2000000 | 2000000 | 2000000 | NGC | N/A | 2000000 | 0 | 2000000 | 1% | 2000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7165 | poultry promotion | Purchase of poultry | Enhance poultryproduction | poultry procured |  | Kipipiri | Kipipiri ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 1000000 | 1000000 | 1000000 | NGC | N/A | 1000000 | 0 | 1000000 | 1% | 1000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7166 | CAB hives starter kits for bee keeping groups | Purchase of CAB hives starter kits | Enhance honey production | CAB hives starter kits procured |  | Kipipiri | Githioro ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 350000 | 350000 | 350000 | NGC | N/A | 350000 | 0 | 350000 | 1% | 350000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7167 | Dairy and poultry farming promotion- Lower Shamata | Purchase of Dairy and poultry | Enhance Dairy and poultryproduction | Dairy animals and poultry procured |  | Ndaragwea | Shamata ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 3000000 | 3000000 | 3000000 | NGC | N/A | 3000000 | 0 | 3000000 | 1% | 3000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7168 | Dairy and poultry farming promotion- Shamata East | Purchase of Dairy and poultry | Enhance Dairy and poultryproduction | Dairy animals and poultry procured |  | Ndaragwea | Shamata ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 3000000 | 3000000 | 3000000 | NGC | N/A | 3000000 | 0 | 3000000 | 1% | 3000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7169 | Purchase and distribution of Heifers to farmer groups | Purchase of Heifers | Enhance Dairy production | Heifers procured |  | Kipipiri | Kipipiri |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 1000000 | 0 | 0 | NGC | N/A | 0 | 0 | 0 | 1% | 0 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7170 | Purchase and distribution of Heifers to farmer groups - Kawamaitha CBO | Purchase of Heifers | Enhance Dairy production | Heifers procured |  | Kinangop | North Kinangop |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 2998000 | 2998000 | 2998000 | NGC | N/A | 2998000 | 0 | 2998000 | 1% | 2998000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7171 | Purchase and distribution of Heifers to farmer groups - Ndunyu Njeru CBO | Purchase of Heifers | Enhance Dairy production | Heifers procured |  | Kinangop | N.Kinangop |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 3000000 | 3000000 | 3000000 | NGC | N/A | 3000000 | 0 | 3000000 | 1% | 3000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7172 | Purchase and distribution of Heifers to farmer groups - Kitiri CBO | Purchase of Heifers | Enhance Dairy production | Heifers procured |  | Kinangop | N.Kinangop |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 3000000 | 3000000 | 3000000 | NGC | N/A | 3000000 | 0 | 3000000 | 1% | 3000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7173 | Purchase and distribution of Heifers to farmer groups - Kiambariki CBO | Purchase of Heifers | Enhance Dairy production | Heifers procured |  | Kinangop | North Kinangop |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 2998000 | 2998000 | 2998000 | NGC | N/A | 2998000 | 0 | 2998000 | 1% | 2998000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7174 | Rehabilitation of Kamuyu Cattle dips | Rehabilitation of Kamuyu Cattle dips | Enhance Dairy production | ! Dip rehabilitated |  | Olkalou | Mirangine ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 1000000 | 1000000 | 1000000 | NGC | N/A | 1000000 | 0 | 1000000 | 1% | 1000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7175 | Veterinary supplies and materials- liquid nitrogen | Procurement of liquid nitrogen | supply liquid nitrogen to the Department | liquid nitrogen |  | Countywide | Countywide |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 900000 | 800000 | 800000 | NGC | N/A | 800000 | 0 | 800000 | 1% | 800000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7176 | Veterinary supplies and materials- Sexed Semen | Procurement of Semen | supply Semento the Department | Semen |  | Kipipiri | Geta ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 3900000 |  |  | NGC | N/A |  | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7177 | Input subsidy (fertilizer and seeds)(flagship project) | Procurement and distribution of fertilizer | Increase farm productivity | Fertilizer delivered. |  | Countywide | Countywide |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 19000000 | 19000000 | 19000000 | NGC | N/A | 19000000 | 0 | 19000000 | 1% | 19000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7178 | Purchase of certified seeds to women and youth groups | Procurement and distribution of certified seeds | Increase farm productivity | certified seeds delivered. |  | Ndaragwea | Shamata ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 700000 | 680000 | 680000 | NGC | N/A | 680000 | 0 | 680000 | 1% | 680000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7179 | Support to farmers with farm inputs (Including Hass Avocado certified seedlings) | Procurement and distribution of farm inputs (Including Hass Avocado certified seedlings) | Increase farm productivity | farm inputs (Including Hass Avocado certified seedlings) delivered. |  | Olkalou | Kaimbaga ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 1000000 | 975000 | 975000 | NGC | N/A | 975000 | 0 | 975000 | 1% | 975000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7180 | Farm inputs for various groups | Procurement and distribution of Farm inputs | Increase farm productivity | Farm inputs delivered. |  | Kipipiri | Kipipiri ward |  | Agriculture | 2022-01-07 | 30/6/2023 | 30/6/2023 | 2000000 | 2000000 | 2000000 | NGC | N/A | 2000000 | 0 | 2000000 | 1% | 2000000 | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7181 | proposed concstruction of soil lab in oljoroorok | Renovation of soil lab in oljoroorok | Improve Soil testing services in the county | 1 soil lab renovated |  | Oljoroorok | Gatimu |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1000000 | 999799 | 999799 | NGC | N/A | 999799 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7182 | Refurbishment of fish hatchery unit and trout fish in geta | Refurbishment of fish hatchery unit and trout fish in geta | Enhance trout fingerings production fro the fish farm | 1 fish hatchery unit refurbished |  | Kinangop | N. Kinangop |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1000000 | 999996.96 | 999996.96 | NGC | N/A | 999996.96 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7183 | Supply of Clean Certified seeds shamata ward | Supply of Clean Certified seeds shamata ward | Increase farm productivity | certified seeds delivered. |  | Ndaragwa | Shamata |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1000000 | 999600 | 999600 | NGC | N/A | 999600 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7184 | Installation of green houses in karau ward | Installation of green houses in karau ward | Youth empowerment | 1 green house |  | Olkalou | Karau |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 650000 | 599966 | 599966 | NGC | N/A | 599966 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7185 | Supply of breeding stock in kipipiri and north kinangop | Supply of breeding stock in kipipiri and north kinangop | Improve farm incomes | breeding stock supplied |  | Kipipiri, Kinangop | Kipipiri, N. Kinangop |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 4000000 | 3680000 | 3680000 | NGC | N/A | 3680000 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7186 | Supply of three bottom disc plough | Supply of three bottom disc plough | Make the institutions more efficient in service delivery | 1-three bottom disc plough |  | Nyahururu | AMS Nyahururu |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 700000 | 699800 | 699800 | NGC | N/A | 699800 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7187 | Renovation and repair of cattle dips and slaughter house | Renovation and repair of cattle dips and slaughter house | Tick control and enhance hygenic meat production systems | cattle dips and slaughter house repaired |  | Olkalou | Karau |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 2000000 | 1999916 | 1999916 | NGC | N/A | 1999916 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7188 | Supply and delivery of farm inputs in north kinangop | Supply and delivery of farm inputs in north kinangop | Increase farm productivity | certified seeds delivered. |  | Kinangop | N. Kinangop |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 2000000 | 1998500 | 1998500 | NGC | N/A | 1998500 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7189 | development of feeds centres in olkalou ward | development of feeds centres in olkalou ward | Livestock nutritionimprovement | feeds centre developed |  | Olkalou | Karau |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1000000 | 999500 | 999500 | NGC | N/A | 999500 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7190 | poultry farm promotion for kipipiri ward | poultry farm promotion for kipipiri ward | Poultry farmers empowerment | poultrys supplied |  | Kipipiri | Kipipiri |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1000000 | 999000 | 999000 | NGC | N/A | 999000 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7191 | Supply of assorted seeds in shamata ward. | Supply of assorted seeds in shamata ward. | Increase farm productivity | certified seeds delivered. |  | Ndaragwa | Shamata |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 4600000 | 4414210 | 4414210 | NGC | N/A | 4414210 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7192 | Supply of alphine goats and chicken for shamata ward | Supply of alphine goats and chicken for shamata ward | Diversification of the livestock sector | alphine goats and chicken supplied |  | Ndaragwa | Shamata |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 2500000 | 2499750 | 2499750 | NGC | N/A | 2499750 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7193 | Proposed and construction of sales yard in Gwa Kungu | Proposed and construction of sales yard in Gwa Kungu | Centralise and hence Improve livestock marketing | sales yard |  | Olkalou | Mirangine |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 3000000 | 2999831 | 2999831 | NGC | N/A | 2999831 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7194 | Supply and distribution of pyrethrum seedlings | Supply and distribution of pyrethrum seedlings | Farm enterprises diversification | pyrethrum seedlings |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 21000000 | 20160000 | 20160000 | NGC | N/A | 20160000 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7195 | Supply of cooler box,refrigretor | Supply of cooler box,refrigretor | Improve efficiency in Vet services offered to farmers | cooler box,refrigretor |  | Veterinary HQ | countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1000000 | 849000 | 849000 | NGC | N/A | 849000 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7196 | Supply of pigs in mirangine ward | Supply of pigs in mirangine ward | Expand pig farming in the ward | Pigs supplied |  | Olkalou | Mirangine |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 2000000 | 1997744 | 1997744 | NGC | N/A | 1997744 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7197 | Supply of corriedale rams in charagita | Supply of corriedale rams in charagita | Improve current gene pool in shep in Charagita | Rams supplied |  | Oljoroorok | Charagita |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1550000 | 1499556 | 1499556 | NGC | N/A | 1499556 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7198 | Supply of avocado seedlingsin mirangine | Supply of avocado seedlingsin mirangine | Farm enterprises diversification | avocado seedlings |  | Olkalou | Mirangine |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 2000000 | 1968750 | 1968750 | NGC | N/A | 1968750 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7199 | Supply of avocado seedlingsin KIRIITA WARD | Supply of avocado seedlingsin KIRIITA WARD | Farm enterprises diversification | avocado seedlings |  | Ndaragwa | Kiriita |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 500000 | 499840 | 499840 | NGC | N/A | 499840 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7200 | Supply of potatoes in githabai ward | Supply of potatoes in githabai ward | Enhance farm productivity | Seed Potato |  | Kinangop | githabai |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 500000 | 499960 | 499960 | NGC | N/A | 499960 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7201 | Supply of farm inputs | Supply of farm inputs | Increase farm productivity | certified seeds delivered. |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1250000 | 1049000 | 1049000 | NGC | N/A | 1049000 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7202 | Supply of farm inputs | Supply of farm inputs | Increase farm productivity | certified seeds delivered. |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1000000 | 999000 | 999000 | NGC | N/A | 999000 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7203 | Supply of incubators | Supply of incubators | Poultry farmers empowerment | incubators |  | Olkalou, Kipipiri | Karau, Githioro |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1100000 | 1047550 | 1047550 | NGC | N/A | 1047550 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7204 | Supply and delivery of improved kienyenji chickens | Supply and delivery of improved kienyenji chickens | Poultry farmers empowerment | improved kienyenji chickens supplied |  | Ndaragwa | Shamata |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1300000 | 1294308 | 1294308 | NGC | N/A | 1294308 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7205 | Supply of hand held tractor in geta ward | Supply of hand held tractor in geta ward | Introducing small scale mechanisation | hand held tractor |  | Kipipiri | Geta |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 300000 | 299804 | 299804 | NGC | N/A | 299804 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7206 | supply of fooder presarvation equipment | supply of fooder presarvation equipment | Ensure proper livestock nutrition even during times of scarcity | fooder presarvation equipment |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1000000 | 998700 | 998700 | NGC | N/A | 998700 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7207 | Supply and delivery of summer wood peas seeds in geta ward | Supply and delivery of summer wood peas seeds in geta ward | Increase farm productivity | certified seeds delivered. |  | Kipipiri | Geta |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1000000 | 999555 | 999555 | NGC | N/A | 999555 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7208 | Supplydelivey andinstallation of cooling tank in Shamata wad | Supplydelivey andinstallation of cooling tank in Shamata wad | Milk preservation | cooling tank |  | Ndaragwa | Shamata |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 5000000 | 4997717 | 4997717 | NGC | N/A | 4997717 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7209 | Supply and delivey of agricultural items | Supply and delivey of agricultural items | Increase farm productivity | certified seeds delivered. |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 1200000 | 1197456 | 1197456 | NGC | N/A | 1197456 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7210 | Supply and delivery of double cabin pick up | Supply and delivery of double cabin pick up | Improve service delivery | double cabin pick up |  | Department Headquarter | Department Headquarter |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 7000000 | 6.989,000 | 6.989,000 | NGC | N/A | 6.989,000 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7211 | Supply of Clean Certified seeds wanjohi ward | Supply of Clean Certified seeds wanjohi ward | Increase farm productivity | certified seeds delivered. |  | Kipipiri | Wanjohi |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 4600000 | 4500000 | 4500000 | NGC | N/A | 4500000 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7212 | Supply,delivery of assorted seeds in shamata ward | Supply,delivery of assorted seeds in shamata ward | Increase farm productivity | certified seeds delivered. |  | Ndaragwa | Shamata |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 4500000 | 4414210 | 4414210 | NGC | N/A | 4414210 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7213 | Supply and delivery of solar pyrethrum drier demo | Supply and delivery of solar pyrethrum drier demo | Reduse post harvest loses in Pyrethrum | solar pyrethrum drier |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 800000 | 799940 | 799940 | NGC | N/A | 799940 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7214 | supply and delivery of motor cycles | supply and delivery of motor cycles | Improve service delivery for subsidised AI | motor cycles |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 7000000 | 6856500 | 6856500 | NGC | N/A | 6856500 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7215 | Supply,delivery and distribution of fodder planting materials | Supply,delivery and distribution of fodder planting materials | Improved fodder production | fodder planting materials |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 8050020 | 7968300 | 7968300 | NGC | N/A | 7968300 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7216 | Supply delivery and distribution of fingerlings | Supply delivery and distribution of fingerlings | Strengthening the fish value chain | fingerlings procured and distributed |  | Ndaragwa | Central |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 500000 | 499970 | 499970 | NGC | N/A | 499970 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7217 | Supply of vaccines | Supply of vaccines | Disese control in livestock | vaccines supplied |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 800000 | 7875000 | 7875000 | NGC | N/A | 7875000 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| 7218 | Supply,delivery of assorted seeds. | Supply,delivery of assorted seeds. | Increase farm productivity | certified seeds maize delivered. |  | Countywide | Countywide |  | Agriculture | 2023-01-07 | 30/6/2024 | 30/6/2024 | 13060000 | 12939500 | 12939500 | NGC | N/A | 12939500 | 0 |  | 1% |  | N/A | 0 | Completed | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _